## Slide 1
01
Overall Progress
23 September – 21 October 2026
After several review rounds with SW, the positions of the key equipment are largely settled.
– Three modules; the front module pulls out for maintenance. BT01, BT04, the separator and the condenser sit forward; the separator is lowered.
– Reviews this period: 8, 15 and 20 October, on models issued by CFCT.
We are now going through the model at true positions: nozzle orientation, valve positions, pipe routing, and replacing instruments that take too much space.
Two decisions in this report: the re-estimated equipment cost against the approved budget, and DN65 for Reactor 1 (R24-CR01).
Action register (20 Oct): 63 closed, 47 pending, 28 open.
– Three items added: multipoint reactor temperature, metering-pump pulsation damper, and the position of the split control cabinets.
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Progress 2026-09-23 ~ 10-21 · 01 / 07

## Slide 2
02
Layout — Settled and Open Points
From the 8, 15 and 20 October reviews
TCU tie-in: the site TCU lines can shift about 150 mm to meet the skid nozzles (agreed 15 Oct).
– Flanged wall plate; the ten lines may stack in two layers after the wall. The Reactor 3 bottom HTF now turns toward the wall riser.
Split control cabinets: three cabinets / junction boxes are placed in the 3D at their current sizes (20 Oct).
– Main IS cabinet: 5 AI, 3 DI, 3 DO; minimum 530 × 450 × 230 mm, down from 950 × 450 × 350 mm.
– New IS cabinet on module 2: 3 RTD, 5 AI, 1 DI; minimum 470 × 450 × 230 mm.
Remote IS I/O panel: SW budget price about £20k, 10–12 weeks.
– Module list and Profinet / Profibus to be aligned first; then the quote is firmed up and the purchase route (UK or China) agreed.
Open: SE01 / CU01 — wall side or end face of module 3. Drain and CIP valves at the front.
– The end-face option clashes with the Reactor 3 HTF. Both points are in the 20 Oct model for SW review.
– Valves within 300–400 mm of the end stay manual; beyond that, compact actuated valves.
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Progress 2026-09-23 ~ 10-21 · 02 / 07

## Slide 3
03
Detailed Review — Pump and Instruments
Smaller, higher-specification items where space is tight
Metering pump: a three-head pump with inlet and outlet manifolds and no discharge damper replaces the single head with a pulsation damper.
– Addresses SW's concern: the damper is a dead leg, and a diaphragm failure could go undetected.
– Vendor drawing received 20 Oct and placed in the 3D; pulsation curves supplied. 20 L/h, 7.5 MPa discharge, GMP.
– CE marking is sufficient; no foreign motor brand is required (15 Oct).
– Vendor: flow can be calibrated on site for each material; a flowmeter is needed only for remote flow indication. To be confirmed by process.
Reactor temperatures: SW's multipoint RTD concept is feasible — no local transmitters or displays; readings on the HMI.
– E+H iTherm MultiSens Slim TMS21 on flexible conduit, wired direct to Siemens RTD module 6ES7134-7SD51-0AB0 in the ET200iSP panel.
– E+H has confirmed supply; Siemens has confirmed the RTD module. Parameter review with E+H this week.
Wider instrument selection: level gauges become guided-wave radar transmitters; on/off valves drop from 12 to 6; pressure control moves to electronic controllers and regulators.
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Progress 2026-09-23 ~ 10-21 · 03 / 07

## Slide 4
04
Decision 1 — Equipment Cost Re-estimate
Skid and auxiliary equipment, CFCT estimate, RMB thousand
Because of the skid space, components were re-selected for better performance and a smaller size. Fewer items in several categories; higher unit prices.
Category | Quantity | Previous | Current | Change
Main equipment | 10 → 10 (feed buffer tank removed, sampler added) | 946.0 | 1,049.4 | +103.4
Pumps | 3 → 1 (one three-head metering pump) | 260.0 | 250.0 | −10.0
Flowmeters and controllers | 5 → 5 | 315.0 | 400.0 | +85.0
Temperature transmitters | 19 → 11 | 136.8 | 147.6 | +10.8
Pressure transmitters | 16 → 13 | 112.0 | 169.0 | +57.0
Level instruments | 4 gauges → 3 transmitters | 80.0 | 68.5 | −11.5
Control valves | 5 → 5 pressure controllers / regulators | 100.0 | 240.0 | +140.0
On/off valves | 12 → 6 | 96.0 | 48.0 | −48.0
Subtotal, eight categories |  | 2,045.8 | 2,372.5 | +326.7
Skid and auxiliary equipment, total |  | ≈ 2,840.0 | 3,172.3 | ≈ +330
Modular assembly, CE certification and freight are not yet re-estimated and are carried at the previous figures.
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Progress 2026-09-23 ~ 10-21 · 04 / 07

## Slide 5
05
Decision 1 — Against the Approved Budget
Skid and auxiliary equipment + E&I and control cabinets
 | RMB thousand | GBP
Approved budget |  | 351,591
at approval rate, 1 GBP = 9.62 RMB | 3,382.3 | 
at today's rate, 1 GBP = 8.93 RMB | 3,139.7 | 
Current estimate — skid and auxiliary equipment | 3,172.3 | 
Current estimate — E&I and control cabinets | 540.8 | 
Current estimate — total | 3,713.1 | 415,803
Over budget at today's rate (18.3%) | 573.4 | 64,212
of which cost change (10.5 pts) | 330.8 | 
of which exchange rate (7.7 pts) | 242.6 | 
At today's rate the estimate is 18.3% over the approved budget. 7.7 points of that is the exchange rate. Had the rate stayed at 9.62, the estimate would be 9.8% over.
– Assembly, certification and freight are still to be re-estimated, so the total may move.
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Progress 2026-09-23 ~ 10-21 · 05 / 07

## Slide 6
06
Decision 2 — Reactor 1 (R24-CR01) at DN65
Preliminary decision, 15 October
R24-CR01 goes to DN65 — the same diameter as Reactors 2 and 3.
– Datasheet basis: 3.5 L and 0.23 m² heat-transfer area (DN80 was 5.1 L and 0.27 m²).
Catalyst charging decides it.
– DN50: the largest catalyst charge and discharge nozzle is 3/4"; the smallest bottom discharge valve is 3/4".
– SW view (8 Oct): 1/2" would not take the catalyst; 3/4" would be difficult.
– DN65 keeps the 1" charge and discharge nozzles already designed.
Temperature: R&D measured about 5–7 °C rise at DN40 and a 15–18 °C hot spot at DN65. There is no DN50 data.
– At DN65 the hot spot can be controlled by diluting the catalyst bed with inert material at loading.
Fits the skid height; DN50 would need a longer column for the same volume. PFD and mass balance are unchanged; the DN65 relief calculation already exists.
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Progress 2026-09-23 ~ 10-21 · 06 / 07

## Slide 7
07
Next Steps
Owners and open items
SW (Keith) — review the 20 Oct model: SE01 / CU01 position, drain and CIP valves, cabinet positions, three-head pump.
CFCT (Fan Shuangshuang) — freeze nozzle orientation and HTF routes, then release the main-equipment drawings for enquiry.
CIMT (Meng Dezhi) — align the Siemens IS I/O module list and Profinet / Profibus; agree UK or China purchase.
Instruments (Gao Yu) — E+H parameter review; apply the multipoint RTD concept to other temperature points where it suits.
Process (Hu Chaoqun) — confirm feed-flow measurement against the three-head pulsation curves.
R&D (Dr Feng) — catalyst loading and bed-dilution procedure for R24-CR01 at DN65.
CFCT — re-estimate assembly, certification and freight; update the budget comparison.
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Progress 2026-09-23 ~ 10-21 · 07 / 07