07-01 Hadoop分析准备与瓶颈讨论

发言人  00:00:00

就是说那个更新之后的这个进度表是吧更新之后的进度表嗯。嗯，是这样的，就是确实李博士刚才说的有一个紧急的项目的事，然后这个更新的稍微晚了一点，然后我把最近就是。我的文件都梳理了一下，黑屏还是还是只是啊黑屏吗？哦，稍等一下啊。嗯。嗯。想。嗯。呃，现在可以吗？

发言人  00:00:39

啊可以了嗯可以了是吧啊呃是这样的各位领导就是我把最近就是呃需要做hadoop之前的文件都梳理了一下就是几乎呃大部分都完成了出版有个别的在交审中然后这周的话。

发言人  00:00:57

或者是七月份的第一周一周内差不多都能完成你像这个控制说明啊这些然后呃这个P F D还有这个。P I D这是之前都完成的所以这个紫色的就是呃出版差不多完成了然后交审之后这周就能发出去所以在这个呃七月份的第一周大部分的工作都是。

发言人  00:01:22

可以完成的，所以就觉得排了一个激进的这个呃进度的话，后边可能就可以开展。还有就是从咱们国内常规的做法的话，这里面有一点那个。特殊的点就是有一个呃操作过程的讨论，之前有一点啊需要和这个三的负责人沟通一下，所以。

发言人  00:01:49

嗯初步那边有一个出版就我们觉得如果拿那个出版去开展这个讨论的话应该从这个激进的角度也是可行的所以做了这么一个方案看大家。领导们的意见啊，供讨论。李博士啊，这个意思。

发言人  00:02:09

Yeah, after the discussion from the two weeks ago, and we actually did some progress and

发言人  00:02:17

We are planning to finish the control description by the draft version or the version one by next week and the P I D, P F D, the P I D and the purple ones

发言人  00:02:33

Uh, uh, and also the process equipment list.

发言人  00:02:37

These purple ones are the one we have already won the version one or uh something that near to the finished version.

发言人  00:02:48

And we think the purple ones are other things we are good enough to support the hadoop.

发言人  00:02:56

So based on this progress, Xiao Peng is thinking if we make it. A little bit radical or radical

发言人  00:03:08

The we may can starting the hazard study from the second week of July and there is one bottleneck for the control description

发言人  00:03:22

This one we got an initial discussion with keys, and there may be some procedural need, operation procedures need to discuss further like the

发言人  00:03:37

呃，呃，那个，呃。

发言人  00:03:42

the startup and shutdown procedure and also the cleaning ones, and this may take some more time to do it, but we can make a rough or initial version, draft version of it

发言人  00:03:58

To see if it's good enough to support the hazard, like we don't need to a complete version of the this procedure, but we got a general idea of it and to see if it's good enough to

发言人  00:04:13

Suppose the hazard, what do you thinkWhat is your high level cleaning philosophyIs it spray? Is it soak?

发言人  00:04:28

And how do you determine whether it's clean at the endIs that going to be included in the operating instructions

发言人  00:04:36

I it will be, but that's the high level. I dont see the spray balls working at the moment.

发言人  00:04:42

Because they fill the vessels too quickly, the drain is not big enough to drain from the vesselsUM

发言人  00:04:50

I and so, so it's a very high level. Yes, because I dont know what the the color means. So the amber means what its.

发言人  00:04:57

Kind of do you don't know eitherWe don't know what the colors made on here

发言人  00:05:03

so so you know they they don't even know understand myself first i i did not join the meeting for quite a while so but i don't know what purple means green means blue amber

发言人  00:05:17

What does this

发言人  00:05:19

啊，那个and how come you have some some items actually purple and then blue and then purple again what what does that mean啊，那个the battery limit the tie in

发言人  00:05:32

本日。So the problem is, what the first draft completed or whatUh, uh, yeah, the milestone draft I think purple is。

发言人  00:05:43

那个高主管，这个各个颜色的，咱们那个各个颜色的块是呃都都代表什么来着？我记得紫色是这个里程碑的，这个是嗯这个是风。呃，前期的时候是蓝的，然后后来就是延期了，就是后来更新以后，因为我也是接手后来的哈，就是应该是标了黄色的，然后后期。

发言人  00:06:09

就是又有更新，咱这个进度表呢，更新的频次比较多。然后所以后期呢，你比如这个完成了，就是绿色的，就实际上又往后稍微延了一点嘛。嗯，然后这个紫色呢，就是表示计划到这个点完成的。

发言人  00:06:24

就是最后最后的节点是绿色的啊，比如说最后这个节点是绿色，都是已经完成了，最后是紫色的，呃，都是咱们计划完成，但是还没完成，绿色是完成了，这个是黄色，是相对蓝色是。有调整最开始应该是这个啊，对对对，主体就这个意思。对对对对对对，是吧？嗯嗯。

发言人  00:06:46

yeah so the the blue one is the very original version and then we adjust to the orange one

发言人  00:06:53

Uh, and then uh The green ones are the time we think we have uh completed the task and we got a mature version.

发言人  00:07:05

And the and the purple one is the like the current plan of the finish day

发言人  00:07:15

Okay, can I can I flag another potential issue with the house update is that I don't think I haveOh yeah, already

发言人  00:07:27

that's not a problem. were not ready. no, so there are only two people available who do house.

发言人  00:07:32

im not here and joes commissioning the gmp lab, so isnt available to do the house up for two weeks in that time frame. in august she might be available.

发言人  00:07:40

But certainly in July she won't be okay, uh understand? Let me transfer this to uh... Xiao Peng and other people.

发言人  00:07:50

呃，就是刚才说两个问题，一个是kiss提的，就是您记得我们之前那个技术讨论说这个就是清洗的这个呃呃这个哲学或者逻辑。

发言人  00:08:02

当时咱们的那个就是喷淋球，它太快把这个这个分离器就给充满了，然后所以它喷淋的效果很差，基本上就算浸泡了，然后所以他想问咱们的那个就是这种的那个清洗活剂到底是浸泡还是喷淋，然后怎么来确确认它到底。

发言人  00:08:22

洗没洗干净，然后呃那个，而且咱们的那个就是呃下水道当时设计比较小嘛，所以它这个如果就是一次次浸泡的话，它的时间会比较长。

发言人  00:08:34

这些事情是咱们在继续讨论，没有那个呃就是研究透的事，然后可能这个需要在这个哈萨布之前，我们需要有一个答案，然后那个有一个基础答案吧。

发言人  00:08:47

然后另外一个事是我们Hadoop的主席，就是得他们那个主持的人，呃，现在这个呃就是没人能做，他们这块都这个呃Claire这边有事，然后那个Joe在那块做那个GMP的开呃开始的工作。

发言人  00:09:06

然后可能到8月份才呃才有有人能做这个事情，所以基本上 Harvard 可能就是嗯他们那个主席我感觉也就就根据之前经验，也就他们能做。所以基本上得8月份。才能开展这个Hadoop的实践呃，的工作。

发言人  00:09:24

the other option we have will be to bring in an external chair, but the timelines are too short to be able to do that.

发言人  00:09:32

Its too short to notice to be able to bring in an external chair for those dates. 是外部雇一个工程师，这个时间段也来不及。嗯。嗯，好的。

发言人  00:09:46

那第一个问题的话，呃，我印象里是我们是说把那个放清洗之后的放料要加大呃。你能补充一下这个信息吗？有印象吗？就是这块的细节。

发言人  00:10:06

那现在的话，之前因为那个那个喷淋的那个流量，现在最小的就是那个之前说的两升每分钟，然后应该是当时说看看厂家有没有更小的。如果没有的话，可能的话他就是跟之前一样，进进很。定一会儿他那个罐就满了因为那罐比较小那个罐只有二十。

发言人  00:10:33

是个两百的吧，呃，对，反正就是是个20还是个210分钟内就进没了。然后出口的话，如果要排的话，出口准备整一个把管道放大点儿。然后弄个排金口。比。嗯，我是说这个管道加大P I D这个细节，咱们还没更新呢，是吧？上次更新P I D有这个有这一条的更新吗？

发言人  00:11:03

嗯，这个没有。哦那就那就我们及时再更新一下嗯我觉行这这个方案可能还得再深入深入的想想想然后看看这个正常怎么做的啊那我等会跟他下。好的。

发言人  00:11:21

呃，yeah，we uh高少锋和赵晨just mentioned the cleaning uh high level cleaning uh idea，and after the technology uh tech tech meeting，we actually explore uh several method and

发言人  00:11:36

We are looking for a smaller spray ball, but then the minimum limit is two liters per minute, so it is already the smallest one, so it is

发言人  00:11:51

It's hard to find a smaller one, and so we are turning to making the drain a little bit bigger, and so that it can like soak the

发言人  00:12:06

THE THE CHAMBER AND THEN WE DRAIN, DRAIN IT, DRAIN IT OUT, AND THEN DO DO IT SEVERAL TIMES TO DO THE CLEANING, AND WE ARE

发言人  00:12:20

Exploring on this direction and other possible directionsThis one may need some more work on it

发言人  00:12:37

Okay, just flagging if you're going to soak

发言人  00:12:41

Then you're going to exceed your high level switch, which is about a third of the way up the separator

发言人  00:12:49

And that is designated a safety interlockSo how is that safety in slotBeing suppressed or defeated while cleaning

发言人  00:13:03

That's a question up front

发言人  00:13:06

Yeah, you know, I'll ask that question because if you can defeat it during cleaning, then you can

发言人  00:13:12

Defeat it during processing. How robust is it? It's not safety interlocking.

发言人  00:13:18

People can turn it on and off. You got controls on how you turn it on and off, but.

发言人  00:13:23

Can you set different mode, uh, like operation mode and I don't know what it depends how the operator philosophy works out.

发言人  00:13:31

Yes, how you do it, but how is the China chain proposing to do it?

发言人  00:13:34

They got a key switch on the panel that defeats the interloper and cleaning only and.

发言人  00:13:39

The key secured or hmm, yeah, it's just, it's a hardwired interlock, so it's not through software they can do it

发言人  00:13:48

It's got to be something physicalTO DEFEAT ITit needs needs more thought.

发言人  00:13:54

yeah, we just need to understand. its not impossible to do. But how is it being done

发言人  00:14:00

Because the hazard should assess that and say it's, yeah, we agree with it嗯，也。嗯。

发言人  00:14:10

嗯那个did you get the point啊，yeah I got it。那个高主管就是那个这这个这个方案还是得就如果浸泡的话，这个方案还得就是去深深挖一些就。

发言人  00:14:23

因为它浸泡的话，它那个就是咱们上头的1/3处，就是就相当于是那个上口1/3处，就相当于是它有一个那个安全阀嘛，就安全开关那块，然后它如果咱们浸泡的话，等于是要没过这块，然后这样的话那就这个你就得，就是比如说把它给关了，在这个。

发言人  00:14:42

清洁的时候，那你这个它就会产生两个模式，那你这个呃就就会产生这种危险嘛。那个你在那个清洁的时候，你关，那你这个在反应时候它。

发言人  00:14:55

他误操作也可能会关，然后所以我们还得深挖一下到底具体怎么怎么来操作这个事，并且他这个是硬件控制的，不是软件控制的。这个模式的改变可能也得深挖一下。

发言人  00:15:08

然后那个整体的这个清洁模式，咱们还得那个就是想的稍微详细一点，然后这这都是hand up中间可能遇到的问题。好。

发言人  00:15:19

好的嗯然后这个我们下来再看一下细节然后排放的比如说快点能不能达到冲洗的效果然后呃第二个就是时间方面如果呃到八月份看是从八月初开始我改到这个如果是这样的话我们在这个期间呢就是会。

发言人  00:15:39

呃比如说咱侧重那个三D审查三D模型不出来了嘛那么就是他的主席那边时间紧张的话就是case啊他就我们还有咱们相关专业都一起可以进行这个三D模型的审查因为呃他。嗯，就是说有可能配置会有一些调整嘛。

发言人  00:15:59

就是那我们在中间可以做这个，如果确定了以后，对后续他的分析可能就更明确了一点。还有第二个就是。可以在这个期间，咱们准备一下认证需要的文件，再跟厂家沟通一下，就是看他针对我们的项目需要哪些文件。第三个就是跟那个自控那边像FDS啊那些文件就是。

发言人  00:16:21

啊，可以往前再做一些。所以到后期对对对，在这个认就是这个中间吧，我们也不会说呃，就是请就是能往前推进的还是。在这个八月份之前还会往前继续推进的嗯嗯，OK。

发言人  00:16:38

行，呃，yeah，I just get a answer from Xiao Hong and refer to the cleaning，yeah，we will consider that，and we understand the bottleneck and we will think more deep on to it，and Xiao Hong was also。

发言人  00:16:54

THINKING WE CAN EXPLORE THAT IF WE ARE ENLARGED THE DREAM, AND IF IT'S POSSIBLE TO MAKE IT DREAM FASTER AND MAKE IT DOING FROM SOAKING TO

发言人  00:17:07

Explain, uh, and make it, uh, but it's just exploring.

发言人  00:17:13

We havent, uh, got a, uh, uh, uh, determine and determined cleaning the physiology yet. And as we said, okay

发言人  00:17:27

can't just say on the cleaning as well.

发言人  00:17:30

We we have the separator which were looking at, but then bolted onto the side of the separator, theres the housing and the guided wave level transmitter.

发言人  00:17:39

Which is 100 diameter housingThat is going to give you equally as many problemsTrying to clean that

发言人  00:17:50

Because obviously that I imagine that will go above the high level switch.

发言人  00:17:55

You dont have a spray ball in that housing.

发言人  00:17:58

The philosophy needs to be integrated so it doesn't just look at the separator

发言人  00:18:06

But the design at the moment shows the hundred diameter housing for the guided wave bolted on the side that isn't cleanable

发言人  00:18:13

Apart from a potential soakBut it needs to be an integral, you don't just look atThe separator vessel

发言人  00:18:24

In that area, that level transmitter also has questions on how it's cleaned.

发言人  00:18:30

And if we got a good cleaning philosophy for the rest of the equipment, reactors and everything else, is that all?

发言人  00:18:35

All its kind of pumped through, so thats easy enough. Yeah.

发言人  00:18:39

Yeah, and the other vessels, the 200-liter vessels, you can get a spray ball in that again.

发言人  00:18:44

You got the problem that the spray ball will spray in far faster than. The outlet will let it drain

发言人  00:18:50

So you've got to fill it, but you got the 200 liters, you can run it for a couple of minutes and then drain

发言人  00:18:57

You run it for a couple of minutes to spray, and then it's going to take you forty minutes嗯，to drain that out。嗯，别的暂时。

发言人  00:19:07

Potentially a long cleaning cycle, which I don't think we're rushed for time, but it's a long cleaning cycle and it's multiple manual operations

发言人  00:19:18

And you probably have to do that film more than once, yeah

发言人  00:19:22

Because once you've sprayed, you're gonna start getting the old tide mark around the top, and then you probably lower the spread for a minute rather than two minutes

发言人  00:19:29

thisThere's lots of potential areas where you're going to leave the drivers that

发言人  00:19:38

you then have to either visually inspect

发言人  00:19:41

Which you can't do in the separator, cause there's no sight glass. You can in the main vessels.

发言人  00:19:46

It is just, or you have to get someone to say the amount of residual material on the walls

发言人  00:19:54

Size of vessels is going to be insignificant in the next batchAnd that's quite a brave sign off

发言人  00:20:00

To kind of what the politics of the material you're putting in is going to be, but if that's the you could always do a count on it, but if that's your philosophy then yeah, that's fine.

发言人  00:20:09

But somebody needs to make that call and get it approved and okay. Through keyway with the business, okay

发言人  00:20:16

But sounds like a little bit of work to do else on there. What else do we need to look at today?

发言人  00:20:21

Uh, is uh Shao Peng just mentioned if uh we are going to uh as the the limit of the uh has of chair uh uh chair's time and if we are going to start from the uh start uh start week of the August week uh during that period of time we can

发言人  00:20:42

We can just go through the 3D model, which is just finished by Shuangshuang, and also we can look into the FDS and also the documents needed by the vendor for the

发言人  00:21:01

certifications啊。Do you really think

发言人  00:21:08

How confident are you, Peter, that when we go through the model, everything is going to be great

发言人  00:21:13

Because I haven't seen it yetThat relied on free drink or my last

发言人  00:21:19

Understanding was it relied on free draining for cleaningAND THE SIZE OF THE SEPARATOR

发言人  00:21:25

On the reactor collection tanks look like that could be difficultUm

发言人  00:21:33

We need to make sure we can integrate in the catalyst charging, catalyst discharging

发言人  00:21:38

Now hopefully the nozzles poke out the side and it's not an issue, but that still needs to be agreed

发言人  00:21:45

And the control philosophy which we haven't seen yetWe've only got the draft we put forward last time for

发言人  00:21:52

To enable the has up to go forward

发言人  00:21:54

haven't seen that either, but do you think those are in good shape that if you sent them to us we could have a couple of weeks to review it

发言人  00:22:03

And then go into Hazop because there wouldn't be any comments嗯，Just ask it. Yeah, thanks.

发言人  00:22:11

呃，高主管就是咱们那个现在就是呃文件都有嘛，但是他呃他因为都还没跟他们这个就具体讨论过，就比如说3D模型啊，然后还有这个控制逻辑呀。

发言人  00:22:24

然后还有这些呃然后所以他会就是因为之前我们在讨论也提到了就是呃他这个就是我们得这这个这很多那个设计得基于这个他就是排空排净的这种的设计然后哦然后那个他咱们的那个就是比如说那个。

发言人  00:22:45

呃，那个呃各各种的那个当时呃就是各种的那个，比如说分分离器的大小啊，这些的。然后啊当时看可能会有些困难，然后包括他这个。呃那个那个呃那那叫什么那个啊那个那个催化剂的这个加料什么的这些的然后还有管嘴的朝向然后等等这些的，然后他们就是放在一起。

发言人  00:23:16

然后是否能在这个空间里头继承呃继承好，然后这个咱们有多大信心觉得就是啊这个东西，咱们比如说给给到他们，然后他们呃看完以后问题不会太多。这种的状态，还是说我们需要呃讨论的比较多，然后还要解决很多的问题。先报上去呃，这个也涉及到操作方面的。

发言人  00:23:41

呃比如说是空间和那个方位的这个就是通常拿着三D模型大家呃。一起看一下过一下嗯就是。就是各专业吧，站在不同的角度啊，从这个维护啊，包括操作就装填啊，啊为更换啊，这个不同的角度去一起过一下这个事，然后就把三D模型就确认下来了。

发言人  00:24:11

当然这些主要是呃和安全的还不太一样它就是便利和这个维护方面的操作所以说跟哈德分析呢也不太角度不太一样那哈德分析的时候像你刚提的就是涉及到逻辑的这些我们。

发言人  00:24:25

就那个呃连锁逻辑也都会提出来，就是嗯只不过它是一个表的形式嘛，就是这种关系都是有的配置的那些呃连锁逻辑值也都是有的，这是个安全。的方面所以这两个嗯就是刚才提的这个三D模型的这些消除呢是需要各专业去审查的。

发言人  00:24:47

呃那个三D模型现在我们是就是呃范光那发出来了对空间是那个呃是就比较比较富裕的状态还是说实际上还有打架的状态。这个范工有展示，就是可以再补充说一下，邮件里简单提了一下啊。呃，那个现在就是就是那个操作空间不太够，不太多。

发言人  00:25:13

我刚看我那个邮件里边写了一个就300~350嘛。嗯，呃，我还是希望能都能加宽一点更好。然后嗯，别的呃，别的就是有也是咱受咱们空间的限制吧。只能他们装了。然后就是还是可以希望各专业能看一下，就是操作呀维修的嗯。嗯，对，空间不是很富裕啊，嗯，比较拥挤。

发言人  00:25:43

您那方便展示一下吗？就需要吗？呃，李博士可以问一下嗯。嗯。我帮我看一下啊。然后。或者现在就那个呃大体的对对对对宏观的对宏观我们国内的讨论不应我们国内的讨论不应该在这个时间你知道吗？如果说你应该先把他们问题收集好之后，然后你那边。

发言人  00:26:15

把跨部门的讨论好之后来回答他，而不是说你今天才问这个问题，或者他提出问题当场在这边讨论。嗯你这样太花时间而且这这样这样效率太低了嗯所所以我我我另外提一个基本的问题，就以前我们类似的。那个就是说系统或者是这种啊整体的这个。

发言人  00:26:43

就是这个skid我们没有做过hazard吗没有类似他们问的这种问题吗。High level the cleaning procedure

发言人  00:26:51

控制逻辑从这个level transmitter一直到separate to the collector这个整套的这个以前我们应该也有啊不是没有吧。不会没有控制逻辑是吧？

发言人  00:27:03

有有的对啊，就是都在做，就是现在控制连锁逻辑关系的话，马上就会结束。呃，就是那个说明发出来给他们review呢，哦，这个是本来说你还还有一个什么激进的七月就要开始做黑照，那你都没review，你怎么怎么激进法呢？

发言人  00:27:23

对，先不要讲到你的个人的schedule。因为这周我觉得我们花这个时间讨论这个，这个其实真的都是应该我们内部觉得他这边的问题，然后peter你应该先organize。

发言人  00:27:36

I E P C F C T操作的，然后大家先讨论完之后，然后剩下的没办法解决才在这里讨论，而不是说你每一个问题都在这里公开。一句一句的这个翻译那这样这个。没有解决。我我就我就听了半个小时，感觉是这样。

发言人  00:27:59

而且其实他刚刚问的这个就是很typical的一个design那个邵峰你听得出来他刚刚讲的吗其实你也不一定要peter翻译啊。你那波transmitter你也听得懂啊separate你也听得懂啊collector你也听得懂不是呢。

发言人  00:28:14

他这个就整套的呀。我我我之前几个礼拜没参加我现在来听我也我也听得懂我知道他们在讲的这个。是的。

发言人  00:28:25

嗯是的呃是这样就是就是做hard work的话因为国内国外可能习惯不一样就咱们国内一般做hard work分析的话像P I D啊物流数据表这些设备数据单。

发言人  00:28:38

就是连锁因果表这些有了以后呃一般就可以做了然后而且这个一般通常在基础设计阶段开展所以啊我们站在这个角度说可以做然后像那种详细的。就是文件呃一个交付的文件出来，就是在他的分析的时候就定下来了。哎，我这个操作步骤要注意什么？

发言人  00:28:58

然后因为有了逻辑关系以后，它的安全方面配置是是是全了的，所以站在这个角度是说，哎，我基金我就后边就可以看展了。

发言人  00:29:07

如果说按照咱们那个不是嗯嗯邵峰我我觉得不是习惯不一样是你有没有办法在这个hands up里面因为语言的关系有没有办法当场回答我觉得他们是担心这个。

发言人  00:29:20

因为你你没有给他感觉说你已经有了那我们很多问的问题到了黑色一问大家又答不出来那不会又白开了吗他们担心那个不是我你你讲的不是说国内国外做黑茶不一样。而所以以前我们国内，我们因为语言很方便，大家讲讲讲就一解释都听得懂。

发言人  00:29:38

你现在有没有这个把握，说你有 PNID，你有逻辑图，你有这个这个这个所有的这些啊资料，可以在那个会里面，让他们知道，讲得很清楚。这个就他们，因为他们过去的经验感觉就是如果没有资料准备齐全一点。语言确实。是一个问题。

发言人  00:29:59

嗯对所以七月逻辑不一样嗯对所以七月呃第一个礼拜我们就把这些文件就都完成了就是我标紫色是说基本完成了就是快结束了是这个意思所以七月第一周就可以完成。可以交付出来啊。就用出来拿出来讨论。

发言人  00:30:21

嗯，就他刚才问的问题也是，就是咱们就完成是完成，但是他就是有多大信心能说服他这个东西能够支持has off，就可能咱们完成了，但是。

发言人  00:30:34

就像刚才说的，这个空间还很有，很局促，然后他这些的这个问题实际上还没有解决，啊，我们可能还得先把这些问题，就是弄成一个，呃，不只是 draft 然后可能就是我们在国内。团队先弄成一个。呃稍微这个更成熟一些的然后给到给到他们才能这个做hadoop

发言人  00:30:58

嗯，空间的话是便利方面，就是跟这个安全方面还。有有区别吧。嗯，少锋其实空间也是安全的一部分。咱们最近发生的事情都是因为空间不够，你不能说空间就不是安全。嗯嗯，当你空间不够的时候，安全就就有隐患。

发言人  00:31:22

嗯，我我觉得这样吧，我我那凯也可以讲讲他的看法，我觉得刚好现在8月还有点时间，我真的觉得你也不用再这么急，赶快把所有的问题收集好，然后好好地写出来，中间。

发言人  00:31:38

先沟通哦，然后我我是我是建议说他们的一些问题收集好之后，Peter 你应该先先在国内把他们先召集好之后，不是来这里就是一句一句，就是他问一句翻译听，然后再回来这样。

发言人  00:31:53

这样的话我觉得效率太低，应该百分之90、80的问题，应该是说前面啊都都已经你在那边沟通好，然后剩下的只是一些关键的东西在这边大家。这个讨论。嗯，我我我是比较建议这样，但是现在还有一个多月的时间啊，呃，这么一个月的时间啊。嗯，好的的。

发言人  00:32:14

嗯，郑博士原来是那样设想并执行的，就是我们每周二都有一个内部的会，包括跟踪的记录表都是这样，细节的话都会在那个会上讨论的。

发言人  00:32:26

就是今天议题也没有想着去问细节，只是说可能在三个位置正好想到了问题，然后有些感觉没落实的，所以就在会上提了，我们做了回应是这样的。嗯。然后我是建议我们国内的不，你们那礼拜二是跟kiss开会的吧，是吗？呃，对的，对的。

发言人  00:32:56

这周二取消，我讲的，我我讲的不是那个，我是觉得我们有很多问题啊，只要收起来了以后。咱们在国内可以不定期的，或者是这个密度高一点，你这 office 大家都很近的，就赶快讨论完之后，把把那个方案弄出来。

发言人  00:33:12

然后有答案了再来跟他们沟通，也不是利用礼拜二那个平台，像这种我看，因为我上次也参加过一次你们这种技术讨论的平台，我感觉那两个小时就类似这样。当场才提出问题，然后就是。

发言人  00:33:29

不同人回答完了以后，中文讲完之后翻译英文，英文讲完就再翻译中文，然后感觉这个就。那样你们的效率也其实也蛮低的呀。嗯，周二那个不是当场提问题的，就是我在群组里后续23号吧，我应该发过邮件，就是一个跟踪表。

发言人  00:33:50

我们提前都是把跟踪的事项，比如说本周讨论的议题就解决掉。就是设计文件更新了就要更新我这个解决掉了然后没解决掉了然后再剩下下一次跟踪讨论是有专门的那个议题跟踪的不是现象的这是一个然后。

发言人  00:34:09

呃，就是有那个需要讨论的，就提前就是标上去，然后就是每相当于上一次沟通的结果和新的议题都在上面了。呃，是有准备的。那现在听起来也还没具备条件可以做孩子不是吗你就算。他们下礼拜真的schedule可以的话你觉得。

发言人  00:34:47

Are you feel comfortable to do haze next week喂，你好。嗯，喂，你好。那问题就在他们也觉得。还不充分，所以你虽然说你说你每个礼拜有议题也也都是有规划的，但显然就是。有些关键的东西可能他。

发言人  00:35:10

就是从这边的角度，还是没没拿到，或者说一直不断的有生出新的问题来。嗯是的。So how do we need to change the Tuesday meeting to make it more effective赵光听得懂吧？

发言人  00:35:30

嗯，那快了就有有点差点。他就问，就是说你讲礼拜二那个他觉得有没有开的可以更效率高一点。周二的。呃主要是语言的事儿从关键点来说我个人觉得。是比较高的了，但是语言这是确实是缺点，就是这个没办法。

发言人  00:36:04

I don't think it's just a language barrier你看他都听得懂你的中文呃嗯对我之前一直想我之前一直有个想法就是你们为什么不能有translating的我也有translating的。

发言人  00:36:20

啊，我去法国我也得翻译成法文跟英文，我我有传神的，真的，我觉得你们应该自己多练点工具，我我。好的，好的。就是我之前也想尝试问他们，就是双向有没有可能他们懂一点简单的，我们说中文慢一点，或者他们说英文慢一点。可能。效果更好一点吧。

发言人  00:36:55

So if we speak more slowly, does your translation device work better呃。

发言人  00:37:04

Or is my translation device translating rubbish?

发言人  00:37:08

No, no, your translation is cash. Yes, seventy eighty percent of what this is, and thats why you can right away.

发言人  00:37:15

Response to what they, what they say, yeah就是刚才问那个他们售卖点是不是咱们的这个翻译器可能就翻的好一点，然后咱们就更能听懂，不用再翻来翻去这样的状态嗯。哎，邵峰，你在用翻译器吗？没有。

发言人  00:37:36

What he doesn't do is engineering terms very well at allSo anything that's technical, it doesn't translate.

发言人  00:37:44

It makes words up, but the technical term that you understand just like transmitter control valve vessel.

发言人  00:37:51

I think that shouldnt dont worry about the translation.

发言人  00:37:55

There may be just some words in between connecting the sentences that probably couldn't catch it

发言人  00:38:01

There must be a, there must be, there's a way to, there must be a way to do it on teams as well.

发言人  00:38:05

Yeah, yeah,没有啊，红姐不是都用的很好吗？对不对？我觉得你应该呃用这个。科大讯飞那个不是都很好吗？好的，我下来学习一下，就是郑博士可能习惯您说英文的时候，我能听大部分。就是还是口音可能习惯局限性，就是在那种外文的语境下少。

发言人  00:38:34

所以你那也可以就是翻译啊，对吧？哦，是吧。那我在我在那我的问题，我再补充学习学习确实是。But I don't think it's just language. I think its.

发言人  00:38:48

How we how we think about problems is quite different depending on our

发言人  00:38:53

backgrounds and I think that is the piece that takes a little bit of time is being able to understand

发言人  00:38:59

What the other team culturally thinkrather than

发言人  00:39:03

It isn't always about people's knowledge, it's just the approach is very different, and it's working through that approach that takes time, and what you would consider as part of the design is different

发言人  00:39:15

嗯。AND THAT WE NEED TO WORK ON就是刚刚他提出的问题我们清洗的时候呃这个液位超过三分之一泡过了安全阀这个我们有考虑过吗。我们清洗的时候，我就没有把这些细节问题都考虑到。有没有考虑呢？

发言人  00:39:36

如果考虑了之后，我我们当时怎么想的呢？如果没有考虑，就是我们这些细节怎么去解决呢？就我现在感觉做方法的问题。是的是的这个首先嗯还是得多说一句就是我现在我们这个团队整个接手这个项目是到了项目的后期然后原来聂博他们那个团队一个人都没留下。

发言人  00:39:58

所以有一些那个，包括初始的意图呢，也是逐步发现，啊，对，在补充。嗯。对，如果你现在接手了之后，你说你这个哈萨克，你说你具备条件了，但这个时候是应该是你就是把控整体的具备啊，明白明白。

发言人  00:40:15

是吧如果是说你刚才说已经具备条件的话那这个我们细节问题即使是转过来的那这些我们就是新的团队有没有考虑过呢？

发言人  00:40:23

嗯是的是的就是我们呃就像刚才说的可能会偶尔会发现没没注意到的点就是确实存在这个现象就是以前呃我们认为都是过来了包括数据单呀包括计算的呀碰到这种问题的话就是说你就快速的决定就是我们还没有考虑。

发言人  00:40:42

啊是的我再想一下就好了对吧是的是的，如果是太多这种解释性的事情，在这个会上去讲的话，确实影响效率。好吧嗯是的是的。嗯。So as it tends to, what will be decided嗯，那我们有一个什什么样的结果呢？就是。

发言人  00:41:17

呃感觉呃可以这个呃调整一下模式然后把这些东西做的更精细然后啊目标在八月初在这个考虑这个hadoop的问题。对的。可以，我就内部能不能就是国内的团队先自己做一个hard up，看看问题有在哪里，有没有问题。

发言人  00:41:42

如果现在没有时间的话，那我们国内先自己先做一个到底问题在哪里。仔细的每一个环节都梳理一遍呢。呃可以的就是花时间会比较长那个东那个哈德分析呢本身。

发言人  00:41:57

好多专业都要产的国内对，如果我们是国内我们自己做都做的很费劲的话，那跟赛德维一起去做的话不是更费劲吗？嗯，那个不是费劲，就是他本身所有的项目就是做Hadoop本身这个事就是时间比较长嗯。

发言人  00:42:16

假如我们国内先先国内的各个专业先先做一遍呢，我我不清楚这个这个逻辑问题啊，专业嗯可以的可以的，没问题。先做来把大部分问题都发现了我们自己哪些细节没有考虑到的，我们先自己先做一遍，先发现的问题，先自己再去想一下。

发言人  00:42:34

啊，然后不是说那跟Siri讨论，然后提出一个问题来咱们这边。就是商量半天，然后又又回他来，然后再提出一个问题来，又商量半天，又回答这个就确实很影响效率。

发言人  00:42:50

嗯您的建议也可以就是我我我需要就解释一句就是他的分析就是花时间比较长我们需要准备完美年以后就花一段时间把这个事做了然后。再去跟365人讨论，然后让他们主席再过一遍，在hub里面提出来一些关键的点。

发言人  00:43:10

如果我们说在国内的团队不能做决定的话，把这些做决定的这些这些item先列出来。哪些是我们发现的呀？他们需要啊，set the input，对吧？那那可以发邮件，他们可以邮件反馈，然后。

发言人  00:43:25

我们的国内觉得做的充分了，然后在八月份的时候再启动正式的哈，爸爸跟他的位置去讨论。嗯可以的内部先过一下如果说配置哪些。

发言人  00:43:39

呃欠缺的一般都会加那个建议措施建议措施出来以后针对这种重点的在呃沟通或者是在他们讨论的时候那效率就高了我们之前讨论过了回复就比较快。嗯，郑博士，你觉得。这个行吗？

发言人  00:43:58

对呀我不是我我一直就拿一个问题就是你把它当成说你这个就是要卖给客户客户不是都会要求hazop的report吗所以我们会没有吗。是不是类似的系统，咱们都在对外卖的不是吗？嗯，管一笔概念在是不是呃。

发言人  00:44:18

会就是这有很多的我觉得我们不是在讲求那个形式而是说你所有客户你你今天对外卖人家把你当成这个是产品的一部分。对不对？安全分析对不对？他们以后要长长久久使用这个，就等于说我们的卖的这个产品也包含这个，所以你也必须要有这方面的信息。对。

发言人  00:44:42

不是说你一定，我我的意思说不是在讲讲求那个形式，说谁当主席，什么问哪些，然后你你你都很花时间，就是好像得得那么那么争，但我觉得咱们以前应该也有模板的呀，我们也不是。这个连续化怎么做这么多年？哦，模板是有的。这模式要没有的话，那就更忙更慢了。

发言人  00:45:03

它是每个工艺不一样，它每一个工艺的每一步都要呃流量、温度啊，各个参数啊，它都要去问那些问题偏离，它是像过筛子一样，就是一个一个细节把它筛出来。所以就是花时间和人员有模板他那个东西就不会快我只是这样啊我我我我知道我知道这流程我非常清楚我的意思。

发言人  00:45:28

像这样的这种东西，本来就，你把它当成，就说这个就是要，我当然现在我们这是内部的技术转移，但你你你如果把它想成这个东西要外卖，不是所有东西都要有。资料所有的这些都要都要讨论清楚吗高流量。

发言人  00:45:45

低流量零流量高压力无压力对不对这个我知道一开始就是在做这些事情的。

发言人  00:45:53

那你有些东西也不必说一定要比较正式的是一定要这样问完然后记录下来我说我们既然都知道这个流程是这样我们也可以在国内做一个简约版的就是把关键你知道你都对系统一定也了解就哪些东西确实是。

发言人  00:46:10

有这方面的问题集中在讨论那一些就好，而不是说一定要把百分之六七十七八十的那种，就是主要常规性的问题也要这样子跑一次。

发言人  00:46:22

呃这个回答您这个呃常规是要考虑的就我们所以有一些典型的P I D对外配置的时候呃就您说的这些因素就提前考虑了然后包括在配置的时候嗯比如C四啊还有那种。

发言人  00:46:38

独立的那些C S和D C S系统啊，类似这样的呃包括监测呃报警，还有那些连锁啊，其实就是在提前做这些工作了。嗯，然后最后最后嗯您说您说嗯。

发言人  00:46:52

我的意思说常规的他们也不会有太多的这些问题啊我们不是说要你在大在在国内自己又再去跑一次然后再来跟他们不是要让你去浪费这个时间我的意思说。

发言人  00:47:05

你你你你你，我们过去有做过经验，我们也知道这个 hazard 出来大概大的问题风险在哪里，你应该着重在那个事先国内的人先跑一次，然后再来跟他们讨论。你那种单一的不不参与逻辑连锁的我认为那个问题都比较小，你看他们现在问题问的都比较属于是。

发言人  00:47:27

连锁逻辑的。然后是的是的，跟安全操作、安全阀或者操作空间有关的这种啊。那是不是都有想过。那你就知道大概问题就是都这一类型的单一的我觉得你不用跟他。做太多，他们的他他们这个肯定你们讨论这么多，他们都知道了。

发言人  00:47:55

是的就是我们嗯都会正常的也都会从重点的这个地方都会考虑然后社交审的话这是一个初步的然后。大家一起讨论就是一个形式上的孩子吧，然后呃对外也是嗯。都会走一遍的。那就赶快走一遍吧。

发言人  00:48:21

不要在八月那时候，我不晓得你们是 what what's the time you think

发言人  00:48:27

It's reasonable for you to, but has the middle of August or beginning of AugustLooks like

发言人  00:48:36

Middle two weeks in August is probably good from a time perspective, because it goes on holiday the end of August.

发言人  00:48:43

Check peoples availability, so its a big commitment to the site to get everybody in the room for.

发言人  00:48:48

House off as well, so we need to check we have the people available August from a being ready to do it.

发言人  00:48:53

I think is better.

发言人  00:48:54

Yeah, middle and middle two weeks is trying to run it in July impacts too many other pieces of equipment were commissioning at the moment, so Keith would have to stop commissioning the protea and Joe would have to stop commissioning the GMP lab. Protea is okay.

发言人  00:49:06

嗯。YEAHBut my gut feeling isthese guys won't be ready

发言人  00:49:17

into that in august still you don't you don't think they can i've not seen anything on the ur i've not seen the layout if it's perfect it's great

发言人  00:49:28

But got no controls strategy, I've got no cleaning strategy, I've got no layout

发言人  00:49:35

Where the tie ins are hasn't been communicated

发言人  00:49:39

you know we're guessing where some tie-ins are going to come through the wallBut that hasn't been sorted out yet.

发言人  00:49:46

It could just be a simple case of we move them, but theres some interactions there that we need to sort out.

发言人  00:49:52

I reckon there'sA good month's worth of turning and frothing just to get the layout

发言人  00:49:58

To a to a fixed position, so we have got a month from now. If theyre ready to start discussions now, we have got a month.

发言人  00:50:07

BUTWe've been talking about this for two or three months. Im just being honest here.

发言人  00:50:15

We talked about it for a long time, and were getting closer, but were not... Were not a week or two away. I wouldnt have said.

发言人  00:50:21

Did you mention all the questions

发言人  00:50:24

Along the way for the past two or three months, um Yeah, weve been working, weve been working through it, and we are making progress.

发言人  00:50:32

And the progress feels like it's speeding up, yeah, but it's Its things like the free draining.

发言人  00:50:38

I still cant see how we free drain. In the system with the height of the vessels we're talking about

发言人  00:50:44

I haven't seen the layout, maybe the guys have got it sorted so it works

发言人  00:50:49

Have we got a consolidated list of questions that so that the team can work through them?

发言人  00:50:55

I think the only question that came to me was the sampler.

发言人  00:50:58

Okay, what are the samplers? Can have any sample left in it when you do gas.

发言人  00:51:01

And that was driven. I was trying to think where all went wrong. Its driven around.

发言人  00:51:05

Nobody on the project team seems to know the liquid to gas ratios

发言人  00:51:12

Is that a process variable or is that a pressure variable?

发言人  00:51:15

Well, its... It goes back to the is it degassing or is it demisting for the separator design?

发言人  00:51:22

And we finally worked out, although originally it was shown as degassing. Now it's demisting

发言人  00:51:27

And I see what it's coming for. Im talking to Oliver. He would design a5 to one stockometric ratio hydrogen. 不知道。

发言人  00:51:36

So it looks like you've got excess gas and you're carrying the liquid through

发言人  00:51:42

The sampler is just changed, which tweaks the is the sampler okay?

发言人  00:51:47

Well, if youve got to get rid of all that gas from the sample system and youre dropping it in there at60 bar and then you drop it to zero.

发言人  00:51:55

Bar pressure before you put it in yourUM SEPTUM BOTTLE

发言人  00:52:01

As you drop in 60 bar, most of that liquid is going to vaporize and end up going out the vent with the gas

发言人  00:52:08

It was just get care, you know, it's things like that they just as you're doing the design, you think about

发言人  00:52:14

And you go, is that really going to happen? If it is, what are you doing to stop losing all your sample up the vent?

发言人  00:52:22

I know you've got another meeting at tenCan we build a consolidated list of outstanding questions? No, okay.

发言人  00:52:30

Cause I havent seen the drawings, I havent seen the control.

发言人  00:52:32

How can I make a list when I dont see the design documents?

发言人  00:52:35

Okay, can we make a list of what youve got now, and then when we see the drawings? We'll update it, does that work

发言人  00:52:42

Because there is enough one what we have been talking for months you are not paying ideas come back we've got a paying idea come back i'm not

发言人  00:52:51

That's probably the latest, but it doesn't show all the changes. Ive not seen the layout. I haven't seen

发言人  00:52:59

A data sheet for the guided wave to see whether that's cleanable

发言人  00:53:04

Yeah, we've just got the vessels through yesterday or the day before

发言人  00:53:10

I haven't been through the best of broins, I'll be honest there. Theyve just come in, but I still dont understand.

发言人  00:53:17

In terms of relief

发言人  00:53:20

Potentially we're really, you know, it's just simple things, and it's my lack of understanding here.

发言人  00:53:26

Our relief scenario is probably going to be around25300 degrees C.

发言人  00:53:31

I think we're still showing 150 degrees C as the design temperature on the vessels. I thought wed resolve that one.

发言人  00:53:40

I think we've got the temperature and the calculation for the releases

发言人  00:53:45

But in terms of the vessel, when you come up with a data sheet for the vessel, if you're leaving at 300, simplistically you'd expect the design temperature to be 300

发言人  00:53:54

I don't know whether there's something in the codethat says

发言人  00:53:58

For a relief scenario, a bit like overpressure, you can go twenty one percent over or ten percent over depending on which scenario you're looking at on relief over design pressure

发言人  00:54:07

I don't know whether something in the code that allows you to do that for temperature as well

发言人  00:54:11

I'm not aware of anythingBut this is the question for the mechanical guys that are designing to the code

发言人  00:54:19

I have the question, and it can be closed out by in the code.

发言人  00:54:22

It says thats allowed, or actually theres nothing in the code that says thats allowed.

发言人  00:54:27

Were going to up our design temperature to three hundred degrees.

发言人  00:54:31

And it might make the vessels a little bit thicker, it might not, but at least I could say the data sheet was correct

发言人  00:54:37

We've designed for our relief conditions

发言人  00:54:41

At the moment we could design for a one fifty, and when it gets to three hundred the wall thickness could be too thin and it could rupture

发言人  00:54:49

unlikelybut you know it'sIt's just notAll joined up.

发言人  00:54:56

Yeah, okay. And the hazard said its all joined up and it will be safe. As far as you can see

发言人  00:55:02

Yeah, and I think there's a point where we have to get to good enough for the house.

发言人  00:55:05

We wont be able to resolve every last little thing.

发言人  00:55:08

Design temperature and rupture of the natural during a relief event is not insignificant.

发言人  00:55:12

No, and that would just mean that were a lot of times stuck in a house up instead.

发言人  00:55:17

Yeah, because it will get or it will get put out as an action and it will sit there as an action for the next six months

发言人  00:55:23

visitors here safe by the phone。Yeah, yeah.

发言人  00:55:26

I understand the question, but uh, can you really put consolidate the the current situation and that that then can understand what most of them are on our list, arent they? Peter, we go through.

发言人  00:55:37

We go through on the weekly meet, I'll go and check them on the weekly meeting, let's put together and see what the completion of all this question.

发言人  00:55:44

If you still have a remaining issues, just highlight what still lacking, and then I think they. the schedule

发言人  00:55:54

I thought I'm being difficult

发言人  00:55:57

which doesn't feel good, but i think you know i just want to make sure it's safe for the guysThank youit

发言人  00:56:22

Anything else we want to talk about? Well, I think we already... I think I have a oneonone, onetoone with the. Martin呢？

发言人  00:56:32

Okay you've got some time this afternoon so if I always talk about it about thatDefinitely

发言人  00:56:41

Let let me see, I think I have a one to one with Martin at 10, yeah.

发言人  00:56:46

So, all right, yeah, then we can, yeah, we already set up two this, this, yeah, we can come. Yeah, thank you. Thank you. 对。

发言人  00:56:58

哎，李博士嗯，那您要不我们单独聊，还是说最后是有什么总结吗？

发言人  00:57:07

呃因为我这边确实没有用那个软件啊跟不上我回头再接一下以前有中文翻译现在没了啊哦是teams我看有字幕没有那个翻译啊孟工以前是有翻译吧还是说是因为我们用的版本不一样吗是要装一下那个我们没有装，就是I T说什么需要有那个。

发言人  00:57:28

权限登录啥的会给登录和不登录会有区别吗呃区别没有区别没有区别你网页版的登录的啥都没区别然后但是我这个里边那那也可能是我记我们上一个公司那个有。

发言人  00:57:42

呃，它里头有辅助功能，有花钱的那个翻译，但是它会卡，我我之前好像了解过，但是我，他们因为我不太用这个，嗯。哦，他们说那个，这。梦梦知道吗？就是说在线的装个软件是吗？他说的时候就可以翻译成中文了，是这样。

发言人  00:57:59

那个就是工程设备部是用的那个科大讯飞的耳机，然后他耳机是连着那个。这个这个手机的，然后你可以那个就是通过这个科大讯飞的耳机进会，然后然后在在在手机上直接就可以看一个延迟3到5秒左右的。

发言人  00:58:19

中文字幕翻译就出来了啊，然后然后然后那个，但是他们说还是我给他们翻，然后但是就是他们听就是等于少了一半，就至少啊对对对对，至少就。

发言人  00:58:31

前一半就不用那么麻烦，我觉得 Claire 说的对，就是实际上那个语言是个问题，但是现在逐渐在改善，我也尽量在那个学习各种的术语。

发言人  00:58:43

但还是核心的是那个，咱们实际上是以那个交付交付文档为那个核心目的，但人家是要你把所有的问题给解决清楚，就是你得想考，你在设计的时候，他希望你考虑到所有的。

发言人  00:58:58

所有的情况，就比如说这这块进气啊，这块低压啊，那块就高压了，然后这个他他那个需要那个就是排净，排净的话那个高度怎么影响，然后他等于是一个完整的方案，就不能是就你给我一个这个这个文档，然后你说按照这个就行，然后但是他提出一个问题，说我觉得这样不行，然后咱们发现没考虑他。

发言人  00:59:22

不希望是这样，他现在他觉得困境就是说他发现很多，就是按照我们给他们的文档的说法的话，他觉得危险性很大，他觉得不靠谱。这个直嗯直白的说就是他觉得嗯直接按他给咱们给他的设计，他觉得这这玩意儿做不了，嗯不靠谱。

发言人  00:59:44

嗯然后是这个困境然后所以他希望是说更多的是解决他各种的问题而不是说交付文档。嗯对所以现在就是嗯呃其实从一开始的感官就是交付的文件少深度嗯不不不探讨就会有这种感官的认识还有他们就是要求的多扣的细。

发言人  01:00:08

对呃就是花时间多就是好多可能跟这个也有关系吧他他的意思就是这个设计是一个系统性的东西然后而且就你得从头到尾一点点抠就是像kiss他自己就是。

发言人  01:00:23

他给我们的问题也是，他从头到尾一点点抠，想各种每一个步骤的每一个情况他想到嘛，然后他提出这些问题，然后给咱们嘛，就这种状态，他希望我们也就是在这个跟他做同样的工作，然后他只是查漏补缺，而不是就是。到哪块都有很多的问题，他当时提的这些问题。

发言人  01:00:45

对，就是我们其实习惯以前也都是这样的，就是就是比如说做哈兹福。你看我在会上提了一个做哈兹福，我想跟大家就是说。就是他确实是需要时间的，就是咱这两边儿，就是三个位置肯定是希望要精细的，就是各方面都考虑的讨论的。

发言人  01:01:04

嗯呃，但是往往咱们内部的可能就认为你需要这周就解决什么问题。比如说这两天就解决什么问题。嗯矛盾点可能在这儿吧孟工你有感觉吗还有赵工他们你们觉得呢就是我们俩想呃就在那边他们退场了然后有一些总结性的来咱。稍微耽误几分钟讨论一下。

发言人  01:01:30

孟工哎孟工还在吗孟工在啊在后面那后面咱们就呃抽个时间咱内部呃类似还是吧就或者是简版的咱们快速过一下。其实实际上就是他提了非常多的问题，咱们嗯主要就是咱们的时间，其实就是大家能分在这个项目的时间没有那么多，他提了很多问题，其实是。

发言人  01:01:55

遗留问题他提了很久了，咱们是一个一个解决的。就像他那个控制逻辑跟那个清洗，咱确实提了很久，但是我们在之前我们确实大家也在花力气去做这个 relief 计算啊，就那个这个卸放计算啊，然后再算那个。

发言人  01:02:14

这个这个这个分离那个的那个东西，对对对对对对对，这些的，然后他可能觉得我们本身，咱们等于是在卖这个产品，然后而且我们之前有经验，很多东西也很快就能解决，但确实没那么快。

发言人  01:02:29

不是的，嗯，现在现在就是从那个我们拿到手的东西来讲，就是以前的东西可能都不全呃，就是。

发言人  01:02:40

就有一些东西反正大家都能理解然后对那孟孟那边有感受吗就是以前那个敦化那吧就有个情况嘛不是这个东西参考那的嘛那边的文件全嘛因为我接手的就是就这些东西包括计算那些。呃，安全化计算那些都没有。

发言人  01:03:01

孟孟有印象吗我不大清那边我们也只是最终因为他接到了T C S上我们也啊也基本上没怎么参与这个东西对我们自控部分就是最终参与了一些你像正常其他其他其他的那些设备一样参与了调试其他的因为。

发言人  01:03:18

不涉及自控硬件啊什么的都都都然后那个呃最后最终的工艺方面的那些，最终的工艺逻辑和和调试我们参与，其他的没参与，对吧。啊呃。

发言人  01:03:29

就是我我因为那个聂婆当时给我，就是讲了他们很多的这个东西，然后还有他的一些文件，咱们做的没他们这么细，他，咱们已有的材料确实不足以支撑他们要这么细的东西。就是的，就就实话实说，是这样的。

发言人  01:03:46

嗯啊，咱们就都都是自己人的话，我就也不遮遮掩着了，就就是对实际情况是这样的啊。所以后面就是我们跟外头需要不能这么说啊。对，对。所以咱需要共同努力，就是这块看后边怎么做，你就是他的分析呢，然后咱也找一些问题，就把前面的捋一下，就是有一些东西吧。

发言人  01:04:09

呃，就很难就是支撑下去，就是就是他的介质也不定，然后包括溶剂啊，还有咱们操作压力那些，就是包括安全计算，现场计算也折腾好长时间，就是跟这个。非常特殊也有关系。

发言人  01:04:27

对，主要嗯就是呃因为你们不太清楚，但是聂博那时候就是我们其实有一部分的逻辑，就是这东西这么小，然后就是即使炸了什么的，也不会造成特别大的影响。

发言人  01:04:41

然后，但对人家不这么想，对，但他们不接受这个，啊，或者说对对，肯定的，分了也没啥事，啊，然后但实际上他们这个开车以后又没喷，然后就无所谓了，他们是啊对，这样这样的一个情况，但是就不太适用，我就我就感觉是这样，就是我们现在被动在这，就是以前呢，人家那个也没问题，然后就那么做的，然后。

发言人  01:05:04

但是到这里呢，他就要你证明你为什么这么做，为什么是合理的。嗯，呃就大的逻辑吧，我感觉是这样，所以后面咱就呃领导也提了，咱就其实我在会上提的意思就是想跟大家争取的时间。咱们就做一个哈，这个问题再再筛一下。

发言人  01:05:21

如果涉及到以前的问题，咱就往前扒，看谁能研发能配合呀，尽量提供一些充足的数据啊。作为人家来讲呢，咱不能把它当成一个小的撬块说小，咱就当成一个正式放大来对待。就是去抠它的原理抠文件的深度不够的就补嘛然后咱就把这些东西只能是这样去弥补了嗯那个。

发言人  01:05:44

就我这是我的理解，想留下多聊两句，然后赵工看看问问你们赵工，您您您有什么想法吗？就是今天开会。嗯他这个呃哈哈这不分析你说这个在国外的那些要求啊，和咱国内的是不是还是有差别的呀？就是我感觉这个大概率。嗯，有有可能有差别，大概率是相通的。

发言人  01:06:12

就比如说他那个偏离，那他偏离就是偏离，呃，他就问的东西是一样的，然后他有什么风险，那可能就是风险的定级。比如说我们认为财产损失啊。

发言人  01:06:25

或者那什么呀就很不严重啊举个例子啊他可能就认为我一个轻伤就很严重那在那个方向就有可能会有偏差但是逻辑上来说我这个少了它就温度就升高了我这个流量低了。

发言人  01:06:37

他那边就会就会缺料然后这个道理是相通的所以而且咱们国内的一些还在规范大概率有好多你像都是超国外的以前的道理我觉得应该是大体上应该是相通的。

发言人  01:06:53

但是咱说实话，就从我们这也是就李博士刚提的，关键的每个人投入的项目上的时间，其实充分的话，我想应该是做的更好。但是我们每个人就是我们湖光现在每这周也有紧急的事要交付，这都都背负的这种事。

发言人  01:07:10

就是说，呃，站在每一个项目呢，大家觉得唉，时间都过得很、很很多了。所以赵工我觉得大理上是相通的咱可以过一下行可以嗯是是这样就是那个呃高处贯通台说的也是一大部分就是他的那个。呃，就是要求会高一些，就是对那个，就是风险的控制的要求会高一些。

发言人  01:07:33

另外一个部分是他们的这个觉得的这个就是Hadoop的阶段是详细设计之后，相当于是完成了详细设计，它代表着详细设计就就就完成了这种状态。

发言人  01:07:48

咱们的Hadoop相当于是概念设计那种状态，他不这个不一样，就是说我们咱们他他理解的详细设计之后再做，所以我们就接受。不太能理解他要3D设计完了再做。

发言人  01:08:00

一般咱们这边都是那个初步设计阶段，对，基础设计阶段做概念设计，就就在就呃不是概念，就是在概念设计前面就危险性分析，就是供应风险分析就不是hazard。

发言人  01:08:12

然后逐步做的，到初步设计的时候，所有的3D不可能都完成的，就国内都国内的规范要求，初步设计阶段要做哈德勒分析，但是初步设计阶段你肯定不是把那个3D模型都做完了，肯定不是这样的。

发言人  01:08:26

但是我们也没有必要跟他矫情，这个就是这东西，这个东西是一个主观的，这个东西嗯没没，我们只能说站在我们的理解，那可以做了。然后我说这么多更多的可能也不一定。都愿意听，但是我们呃大家都明白这个他要求就是高。

发言人  01:08:46

但是呢你比如在意的，你这是设计阶段做的，他在意的时间他还要做他的文件。他那个理解就有点像那种在意的了啊，我这东西都定了是什么样的，我到底是怎么回事？其实咱建完了以后，如果你投入生产了，你过三年还是要做海德沃分析的。还是这样的嗯，李博能理解吧？

发言人  01:09:06

哦，我理解嗯啊，所以那这个事就这样吧，然后。其他的我想想啊。他。其他没啥了吧，嗯，我觉得孟总您那有什么建议吗？他们那没事，李涛你先说。

发言人  01:09:22

嗯，我觉得就是他们那个就是提的这些的就是之前一直以来提的这些的问题，咱们没解决的，主要其实就是这些那个就是清醒逻辑和控制逻辑。对对对，还有那个你的这个这个空间的大小，然后这些还有那个他特别特别注重的 free gene。

发言人  01:09:41

嗯，我们怎么实现？我们我们内部的对内部的。今天不又记了一下吗把那个清洗的这些咱再记记下来解决掉然后空间的问题我们呃我理解今天的会议是这意思，咱内部先讨论完，就是说不要告诉他不行了。

发言人  01:09:58

其实我们内部如果说不行，按道理来说我们内部解决，我理解这个意思，今天是吧？咱内部把那个模型再看一下，因为刚发完模型，大家还没时间看，但是我在会上我没我我没法说。嗯，就是咱抓紧时间看看完了以后再去给他发。

发言人  01:10:13

但是前期留下的习惯是这样，他参与的深度很深，就是说我们不给他发这个，不给他及时的发这个3D吧，呃就感觉好像我没做工作。所以养成的习惯是我们及时发给他了，及时发给他，他又想让你们讨论过以后再发给他，其实这是矛盾的。

发言人  01:10:30

所以问题在这儿了，那我们下边就把这个讨论一下，然后还有那些问题尽量的解决掉以后再去给他。这个整体的空间嗯提前不都是相当于咱们也提过好多轮了嘛对尺寸放不下呀有什么样的后边不同的尺寸你说。已经给咱们限定死了对对然后。

发言人  01:11:02

这些在会上没法说，就是相当于我们做的方案。呃就有一个宽松的方案也被否掉了。然后呃咱可以这样理解，就是换个说法，就是我们按照这种限制的位置做了一个我们认为的最优方案。

发言人  01:11:20

嗯然后他有什么弊端就是位置已经这样了但是已经实在呃想尽办法没办法解决了我我觉得领导的想让我们做到这个程度。赵哥，你看你我的理解对吗？嗯，是对他们这个他们也没法扩建，也没法拿出来更大空间了，主要是。

发言人  01:11:45

对对对对对对，那就只能是我们现在设计的这个样子，然后回头跟B端提一提呗。对，然后我理解赵总，咱这样就咱内部碰一下，过一下就确实比如说站在我们的角度，哎，觉得哎没有那个优化的空间了。

发言人  01:11:59

站在您的角度也没有再让高宇也看一下比如说那个仪表啊什么东西也没有优化的空间了就是就是我理解就是这个空间挤让对方也找不出办法来可能他们就接受了要么就接受要么就是这个方案。

发言人  01:12:14

就就相当于换方案吧，就是可能咱得做到这个极致的地步，咱大家都得努力一下。啊好对对对问我那边没啊对没事那个张总您说。没事儿那就咱们定个时间什么时间，咱们看一眼一个一个是看3D模型，然后剩下的就是呃那会儿说的哈道法内部的。对，咱们先先过一下。

发言人  01:12:38

对，但是这这个时间是不是要赶到下周二之前啊？呃，嗯，这个周周二的呃，之前尽量吧，我们这边那个那那这个主持就公益的，就我们这边主持了。对我看一下胡工那边工作，这周他是没时间。

发言人  01:12:58

下周二之前我们看看能不能开展然后他还得做一些准备工作就是我估计周二是比较麻烦的不一定行。我觉得这期间先看一下模型就是咱们先看一下模型然后呃下周有可能周二不行尽快吧。嗯，就是这个。这这有还有那个模模型跟主主设备的图，到时候一起看。

发言人  01:13:29

啊，对对对对对对，到时候都看一下，会审一下嗯，行。行。孟国，您看您那有什么需要补充的吗？哎，梦梦还在吗？