## 设备投资概算评估 (集团内部-Sandwich) (hidden)
连续生产设备清单 Flow Production Equipment List | [7 empty] | 投资明细 Investment details
序号 No. | 类别 Classification | 设备 Equipment | 规格型号 Specifications & Models | 数量 Number | 单位 Unit | 用途 Use | 备注 Notes | 设备单价 Unit price | 认证 Certification | 合计费用 Total cost | 备注 Notes | 说明
1 | 连续主设备 Continuous reaction main equipment | 原料缓冲罐 Buffer Supply Tank | 立式储罐，体积：220L，与物料接触材质：316L，工作压力：常压 Vertical storage tank, volume: 220L, material in contact with material: 316L, working pressure: atmospheric pressure | 1 | 台 | 原料缓冲 Raw material buffering | N/A | 36000 |  | 36000 |  | 供应商报价
2 |  | 原料缓冲罐 Buffer Supply Tank | 立式储罐，体积：220L，与物料接触材质：316L，工作压力：常压 Vertical storage tank, volume: 220L, material in contact with material: 316L, working pressure: atmospheric pressure | 1 | 台 | 原料缓冲 Raw material buffering | N/A | 36000 |  | 36000 |  | 供应商报价
3 |  | 氢气缓冲罐 H2 Buffer Tank | 立式储罐，体积：10L，与物料接触材质：316L，工作压力：6MPa Vertical storage tank, volume: 10L, material in contact with material: 316L, working pressure: 6MPa | 1 | 台 | 氢气缓冲 Hydrogen buffering | N/A | 35000 |  | 35000 |  | 供应商报价
4 |  | 反应柱01 Continuous Reactor Column 01 | 立式反应柱，体积5.1L，换热面积：0.27㎡，与物料接触材质：316L Vertical reaction column, volume 5.1L, heat exchange area: 0.27 ㎡, material in contact with material: 316L | 1 | 台 | 原料反应 Raw material reaction | N/A | 165000 |  | 165000 | DN80 | 供应商报价
5 |  | 反应柱02 Continuous Reactor Column 02 | 立式反应柱，体积3.5L，换热面积：0.23㎡，与物料接触材质：316L Vertical reaction column, volume 3.5L, heat exchange area: 0.23 ㎡, material in contact with material: 316L | 1 | 台 | 原料反应 Raw material reaction | N/A | 150000 |  | 150000 | DN65 | 供应商报价
6 |  | 反应柱03 Continuous Reactor Column 03 | 立式反应柱，体积3.5L，换热面积：0.23㎡，与物料接触材质：316L Vertical reaction column, volume 3.5L, heat exchange area: 0.23 ㎡, material in contact with material: 316L | 1 | 台 | 原料反应 Raw material reaction | N/A | 150000 |  | 150000 | DN65 | 供应商报价
7 |  | 预热器 Pre-heater | 换热器，换热面积：1.5㎡，与物料接触材质：316L Heat exchanger, heat exchange area: 1.5 ㎡, material in contact with material: 316L | 1 | 台 | 原料预热 Preheating of raw materials | N/A | 75000 |  | 75000 |  | 供应商报价
8 |  | 冷凝器 Condenser | 换热器，换热面积：1.2㎡，与物料接触材质：316L Heat exchanger, heat exchange area: 1.2 ㎡, material in contact with material: 316L | 1 | 台 | 反应后冷凝 Condensation after reaction | N/A | 68000 |  | 68000 |  | 供应商报价
9 |  | 气液分离器 Separator | 体积：20L，与物料接触材质：316L Volume: 20L, material in contact with material: 316L | 1 | 台 | 分液 Liquid separation | N/A | 25000 |  | 25000 |  | 供应商报价
10 |  | 产品缓冲罐 Product Buffer Tank | 立式储罐，体积：220L，与物料接触材质：316L，工作压力：常压 Vertical storage tank, volume: 220L, material in contact with material: 316L, working pressure: atmospheric pressure | 1 | 台 | 体系缓冲 System buffering | N/A | 36000 |  | 36000 |  | 供应商报价
11 |  | 设备CE 认证 Equipment CE certification |  | 1 | 项 | 10台主设备CE认证 Main equipment CE certification |  | 170000 |  | 170000 |  | 供应商报价
12 |  | 材料EN 认证 Material EN certification |  | 1 | 项 | 10台主设备EN认证 Main equipment EN certification |  | 50000 |  | 50000 |  | 供应商报价
13 |  | 单项合计： | [6 empty] | 0 | 996000
14 | 辅助设备 Continuous reaction auxiliary equipment | 计量泵 Metering Pump | 液压隔膜泵，量程：40L/h，与物料接触材质：316L，单泵头，排出压力：8.0MPa Hydraulic Diaphragm Pump, range: 40L/h, Material in contact with materials: 316L, Three pump heads, Discharge pressure：8.0MPa. | 2 | 台 | 进料，流速40L/h feeding pump,40L/h. | N/A | 80000 | 0 | 160000 | 进口品牌，自带IECE认证，英文资料 | 供应商报价
15 |  | 计量泵 Metering Pump | 液压隔膜泵，量程：0~1m3/h，与物料接触材质：316L，排出压力：0.6MPa，扬程：20m Hydraulic Diaphragm Pump, range: 0~1m3/h, material in contact with material: 316L, discharge pressure: 0.6MPa, head: 20m | 1 | 台 | 产品转移泵 Product transfer pump | N/A | 100000 | 0 | 100000 | 进口品牌，自带IECE认证，英文资料 | 供应商报价
16 |  | 单项合计： | [6 empty] | 0 | 260000
17 | 电气仪表和自控阀门 Electrical instruments and control valves | 质量流量计 Mass Flowmeter | 测量范围：0~50L/h，测量精度±0.5%，与物料接触材质：316L Measuring range: 0~50L/h, Measuring accuracy: 0.5%, Material in contact with materials: 316L | 2 | 台 | 流量计量 flow measure | Raw Material | 75000 | 0 | 150000 | 进口品牌，自带CE认证 | 供应商报价
18 |  | 质量流量计控制器 Mass Flow Controller | 测量范围：0-50L/min，测量精度±0.5%，与物料接触材质：316L Measuring range: 0-50L/min, Measuring accuracy: 0.5%, Material in contact with materials: 316L. | 1 | 台 | 流量计量 flow measure | H2 | 55000 | 0 | 55000 | 进口品牌，自带CE认证 | 供应商报价
19 |  | 质量流量计控制器 Mass Flow Controller | 测量范围：0~50L/h，测量精度±0.5%，与物料接触材质：316L Measuring range: 0~3L/h, Measuring accuracy: 0.5%, Material in contact with materials: 316L. | 1 | 台 | 流量计量 flow measure | Produce | 90000 | 0 | 90000 | 进口品牌，自带CE认证 | 供应商报价
20 |  | 金属转子流量计 metal rotor flowmeter | 测量范围：0~10L/min，测量精度： ±0.5%，与物料接触材质：316L，介质：N2气体 Measuring range: 1~10L/min, Measuring accuracy: 0.5%, Material in contact with materials: 316L.Medium: N2 gas | 1 | 台 | 流量计量 flow measure | N2 | 20000 | 0 | 20000 | 进口品牌，自带CE认证 | 供应商报价
21 |  | 温度变送器 Temperature Transmitter | 测量范围：0~150℃，测量精度±0.2%FS，6mm探头 Measuring range: 0~150℃, Measuring accuracy ±0.2%FS, 6mm probe. | 6 | 个 | 温度检测 temperature measure | H2、MTBE等 | 7200 | 0 | 43200 | 进口品牌，自带CE认证 | 供应商报价
22 |  | 温度变送器 Temperature Transmitter | 测量范围：-20~+120℃，测量精度±0.2%FS，6mm探头 Measuring range: -20~+120℃, Measuring accuracy ±0.2%FS, 6mm probe. | 13 | 个 | 温度检测 temperature measure | HTF等 | 7200 | 0 | 93600 | 进口品牌，自带CE认证 | 供应商报价
23 |  | 压力变送器 Pressure Transmitter | 测量范围：0~8.0MPa，测量精度±0.5%，与物料接触材质：316L Measuring range: 0~8.0MPa, Measuring accuracy: 0.5%, Material in contact with materials: 316L. | 16 | 个 | 压力检测 pressure measure | N/A | 7000 | 0 | 112000 | 进口品牌，自带CE认证 | 供应商报价
24 |  | 液位计 Liquid level measurment | 测量范围：0~1000mm（TBD），测量精度±1%，与物料接触材质：316L Measuring range: 0~1000mm, Measuring accuracy: ±1%, Material in contact with materials: 316L | 4 | 个 | 液位测量 level measurement | N/A | 20000 | 0 | 80000 | 进口品牌，自带CE认证 | 供应商报价
25 |  | 气动调节阀 Pneumatic control valve | 工作压力：0.4MPa，工作温度： 10~40℃，防爆 Working pressure: 0.4MPa, working temperature: 10~40 ℃,explosion-proof | 5 | 台 | 流量调节 flow regulation | N/A | 20000 | 0 | 100000 | 进口品牌，自带CE认证 | 供应商报价
26 |  | 气动开关阀 Pneumatic switching valve | 工作压力：0-8.0MPa，工作温度： -20~130 ℃，防爆 Working pressure: 0-8.0MPa, working temperature: -80~-70 ℃, explosion-proof | 12 | 台 | 开关控制 switch control | N/A | 8000 | 0 | 96000 | 进口品牌，自带CE认证 | 供应商报价
27 |  | 单项合计： | [6 empty] | 0 | 839800
28 | 控制系统 Control System | 控制系统（SCADA-现场防爆） Control System | 防爆变频柜：内置3个变频器（2.2kw），I/O模块若干，满足欧洲防爆要求（ATEX） Explosion proof frequency conversion cabinet: equipped with 2 frequency converters and several I/O modules, meeting European explosion-proof requirements (ATEX) | 1 | 台 | 泵控制系统 Pump control System | 西门子 | 340000 | 0 | 340000 | 变频柜、PLC柜 合并，另外配置防爆操作站
29 |  |  | 移动防爆操作站：内置工控机，PLC控制，显示器，WINCC客户端软件，UPS电源等，满足欧洲防爆要求（ATEX） Mobile explosion-proof operation station: built-in industrial computer, PLC control, display, WINCC client software, UPS power supply, etc., meeting European explosion-proof requirements (ATEX) | 1 | 台 | 控制系统 Control System | 西门子 |  | 0 |  | 变频柜、PLC柜 合并，另外配置防爆操作站
30 |  | 单项合计： | [6 empty] | 0 | 340000
31 | 模块化组装 Modular assembly | 模块化组装 Modular assembly | 设备手阀、单向阀、安全阀、管路及保温、模块化框架及外部连接管线、步梯 Equipment hand valves, one-way valves, safety valves, pipelines and insulation, modular frames, and electrical pipelines, external connection pipelines, steps，etc | 1 | 项 | N/A | N/A | 350000 | 0 | 350000 | 内部加工 | CFCT预估
32 |  | 仪表电气安装 E&I Installation | 自控仪表、自控阀门、变频器撬装内安装、接线、测试。含撬装内部电缆 Installation and locally test for control instruments、valves、VFD pumps，internal control cables included | 1 | 项 | N/A | N/A | 200818 | 0 | 200818 | 国内电气仪表组装部分。尽可能预制大部分电缆，减少Sandwich部分电缆工作量
33 |  | 单项合计： | [6 empty] | 0 | 550818
34 | CE认证 CE certification | MD认证 MDcertification | Asymchem整撬认证，机械指令MD2006/42/EC Asymchem whole pry certification, Machinery Directive MD2006/42/EC | 1 | 项 | N/A | N/A | 0 | 270000 | 270000 | 进口品牌，自带CE认证 | 供应商诚信报价
35 |  | ATEX认证 ATEX certification | 基于防爆区域为1区的前提下，器件都满足CE认证的情况下，防爆指令ATEX2014/34/EU检查评估（文件接收型认证） Based on the premise that the explosion-proof area is Zone 1 and all devices meet CE certification, the explosion-proof directive ATEX2014/34/EU inspection and evaluation (document receiving certification) | 1 | 项 | N/A | N/A | 0 | 60000 | 60000 |  | 供应商诚信报价
36 |  | 税费 taxation | 技术服务协议按照6%收税 The technical service agreement is taxed at 6% | 1 | 项 | N/A | N/A |  | 0 | 19800
37 | [8 empty] | 0 | 349800
38 | 设备出口安装 Equipment export and installation | 手续办理 Procedure handling | 设备出口相关手续的办理 Handling of equipment export related procedures | 1 | 项 | N/A | N/A | 0 | 0 | 0 |  | 请进出口部门协助评估？
39 |  | 货物运输 Freight transportation | 货物运输至海外工厂 Transport of goods to overseas factories | 1 | 项 | N/A | N/A | 100000 | 0 | 100000 |  | CFCT预估，请进出口部门协助核算
40 |  | 设备安装 Equipment installation | 海外工厂设备安装 Overseas factory equipment installation | 1 | 项 | N/A | N/A | 0 | 0 | 0
41 | [8 empty] | 0 | 100000
42 | 总费用合计： | [8 empty] | 3436418 | 321538.7331
[8 empty] | 折合美元： | 343.65 | 0.48 | 7.26
[8 empty] | 折合英镑： | 201.07 | 0.21 | 9.63

## 反馈认证费用 (hidden)
认证流程图
序号 | 设备名称 | 服务指令 | 报价万元
1 | ASYMCHEM整撬 | 机械指令MD2006/42/EC | 2
2 |  | 防爆指令ATEX2014/34/EU检查评估（文件接收型认证） | 3
note:
1.本报价基于防爆区域为2区的前提下，器件都满足CE认证的情况下。
认证资料
0 申请表：我司提供模板并指导填写；
1 产品功能描述：我司提供模板并指导填写；
2 机械规格表：我司提供模板并指导填写；
3 图纸：
3.1 机械外观尺寸图：
3.2 机械主要部件图：
3.3 机械安全装置及分布图：
3.4 设备铭牌图：
3.5 电气原理图：
3.6 气动原理图：
3.7 液压原理图：
3.8 机身标识及其分布图；
3.9 操作位置示意图；
3.10 搬运吊装示意图；
3.11 防爆分区图；
4 零部件CE证书或测试报告
4.1 机械部件CE证书或测试报告（并附上组件表）；
4.2 电气组件CE证书或测试报告（并附上组件表）；
4.3 气动组件CE证书或测试报告（并附上组件表）；
4.4 液压组件CE证书或测试报告（并附上组件表）；
4.5 防爆组件CE-ATEX证书（并附上组件表）；
5 安全设计计算
5.1 电气安全回路可靠性能等级计算
5.2 机械安全设计计算书；
5.3 防爆结构设计校核书（如有必要）；
6 材质证明、测试报告：第5.2条的计算中涉及到的数据文件；
7 安全相关部件数据表：第5.1条的计算中涉及到的数据文件；
8 设备说明书；
9 风险分析报告：我司提供模板并指导填写；
10 质量管理体系证书：ISO 9001
11 一致性声明：我司提供模板并指导填写；
备注：
- 以上所有资料均应提供英文（可以为中英文对照）
- 没有英文版本的测试报告或证书原件，可附上Word版本的英文翻译件（翻译件不需要签字盖章）；

## Timeline
| Sandwich Hydrogenation Implementation Schedule | [106 empty] | Resourse Note
时间 Time line |  | month | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9
工作事项 work item |  | 负责部门 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1
Design | HAZOP （support resource in grey） | UK | 1 4: hazop 下半部分 PID和泵的参数表、数据表 -- 提采购（仪表和自控阀门已经提交采购（采购收集需求信息与Keith确认，然后确定厂家和型号收集下，UK最终确认）；泵还没提，静设备还没提） layout初稿，共同讨论 设备数据表、设备图 、反应器设备数据表（1.19 聂博） -- 静设备结构（1.23更新好 赵工） 关键设备信息（难点在基于国外规范要求的需求，需要Keith他们提供或反复沟通） CEPS操作 输出：静设备最终结构设计确定 布局设计终稿 管路设计 -- PID的终稿、layout 终稿、泵和仪表静设备采购信息 -- 3D图 -- 采购 （采购信息确定之后 2周出3D） 结构设计 -- 强度计算（看SW需求？）CFCT无法，要找第三方 控制柜位置确定、采购
| Control Description | IEPE | bar: 6 2 to 7 1
| PFD and Mass Balance Data Sheet | SW | bar: 5 2
| HAZOP | SW | 7 2: HAZOP
| PI&D | IEPE | bar: 10 3 to 11 2; 1 2 to 1 3; 2 2; 4 2 to 5 4; 6 2
| Process Equipment List | IEPE | bar: 5 1 to 5 4; 6 3; 7 1
| Equipment datasheets | IEPE | bar: 10 3 to 11 2; 12 3 to 2 2; 5 1 to 5 4; 6 2
| Battery Limit Condition Sheet (Tie-in point sheet) | IEPE | bar: 5 1; 5 4 to 6 1; 6 3; 7 1
| Instrumentation Condition Table | IEPE | bar: 5 1; 5 4 to 6 1; 6 4
| Piping Material Class Specification | IEPE | bar: 3 4
| Process Piping List | IEPE | bar: 5 4 to 6 2; 6 4 to 7 1
| Special Piping Accessories Data Sheet | IEPE | bar: 5 4 to 6 2; 6 4
| Main Safety Relief Facilities Data Sheet | IEPE | bar: 4 4 to 5 2; 5 4 to 6 1; 6 3 to 6 4
| Instrument datasheets | IEPE | bar: 10 3 to 11 2; 1 3 to 2 2; 6 1 to 6 2; 7 1
| Interlock logic | IEPE/UK | bar: 10 3 to 11 2; 1 3; 2 2; 6 1 to 6 2; 7 1
| Pump specification sheet | IEPE/UK | bar: 1 2 to 1 3; 2 1 to 2 2; 5 1 to 5 2; 6 2
| Operating instructions | IEPE/UK | bar: 1 2 to 1 4; 2 2; 7 2 to 7 4
| Preliminary equipment layout | IEPE/CFCT | bar: 1 3 to 1 4; 4 2; 6 4
| structural design of static equipment（pink） | IEPE/CFCT/UK | bar: 1 4 to 2 2
| Reactor column specification sheet | IEPE/CFCT | bar: 1 4; 5 2; 5 4; 6 4
| Procurement information confirmation(pump\insturment\equipment schedule) | CFCT/IEPE/UK | bar: 1 4 to 3 4; 7 2 to 8 1
| FDS(CS in FDS)/SDS/HDS | IEPE/CFCT/CIMT | bar: 6 1 to 8 2
| URS | SW
| Instrument Schedule (including instrument ranges and set values) | SW
| I/O schedule (including I/O type, ranges and alarm settings) | SW
| trip and interlock schedules for PLC interlocks | SW
| PCS interlocks and hardwired interlocks | SW
| SIL assessments for safety/environmental interlocks and LOPA assessments for potential SIL rated SIFs | SW
| Alarm list | SW
| Hardware drawing of PLC | CIMT | bar: 6 3 to 8 2
| IOA of PLC | CIMT | bar: 8 1 to 8 4
| Cable schedule | CIMT | bar: 4 4 to 5 3
Skid | 3D modelling (procurement feedback; UK confirmation of equipment layout) | CFCT | bar: 2 4 to 3 3; 5 3 to 6 2; 6 4
| BOM | CFCT | bar: 3 4 to 4 1; 6 3 to 6 4
| Fabrication drawings | CFCT | bar: 4 2 to 4 3; 6 3
| Engineering procurement (valves & instruments, static equipment, pumps, piping and fittings; within the skid) | CFCT | bar: 3 3 to 12 1
| Control system procurement and configuration | CFCT/CIMT | bar: 2 4 to 6 4; 7 2 to 11 2
| Equipment fabrication, assembly and debugging | CFCT | bar: 7 3 to 9 1; 11 3 to 1 1
| Integrated factory acceptance (FAT) | UK/CFCT/IEPE | bar: 9 1 to 9 3; 1 2 to 2 1
| CE certification (individual equipment + whole-skid certification per Notified Body requirements); full documentation completed | CFCT | bar: 6 3 to 9 3; 12 1 to 3 1
| Export formalities, transport inspection/certification and packing | Import/Export | bar: 11 3 to 11 4; 3 2 to 3 3
| Export shipment (Europe) | Import/Export | bar: 12 1 to 2 4; 3 4 to 6 3; 8 1 to 8 3
On Site Engineering Design | PID | UK/IEPE | bar: 10 4 to 11 2
| Engineering design documents | UK/IEPE | bar: 10 4 to 1 3
| HAZOP | UK/IEPE | bar: 10 1; 11 3 to 11 4
| Detailed design | UK/IEPE | bar: 11 4 to 2 3
| Procurement | UK/IEPE | bar: 11 1 to 3 3
On Site Installing | Off-skid/peripheral installation | UK | bar: 3 4 to 5 3
| Skid installation | UK | bar: 3 1 to 3 2; 6 4 to 7 1
| Mechanical, electrical, instrumentation & piping (MEIP) installation | UK | bar: 5 4 to 6 1; 3 3 to 4 4; 7 2 to 8 3
| Qualification & acceptance testing (DQ / IQ / OQ) | UK/IEPE | bar: 5 1 to 5 3; 8 4 to 9 2
| Commissioning and start-up | UK/IEPE | bar: 5 4; 9 3
Note on AS12: Shaofeng Gao0169: update - 高少锋（Shaofeng Gao） - 高少锋（Shaofeng Gao）
Note on AR23: Shaofeng Gao0169: update - 高少锋（Shaofeng Gao） - 高少锋（Shaofeng Gao）
Note on AS11: Shaofeng Gao0169: update - 高少锋（Shaofeng Gao） - 高少锋（Shaofeng Gao）
Note on AR16: Shaofeng Gao0169: update - 高少锋（Shaofeng Gao） - 高少锋（Shaofeng Gao）
Note on AW39: Shaofeng Gao0169: update - 高少锋（Shaofeng Gao） - 高少锋（Shaofeng Gao）
Note on C24: Shaofeng Gao0169: 需要采购确定厂家前发Keith - 高少锋（Shaofeng Gao）
Note on AU9: Shaofeng Gao0169: 计划6.18发出 - 高少锋（Shaofeng Gao）
Note on D40: Shaofeng Gao0169: 需要工程部支持。 - 高少锋（Shaofeng Gao）
Note on AW25: Shaofeng Gao0169: update - 高少锋（Shaofeng Gao） - 高少锋（Shaofeng Gao）
Note on AU16: Shaofeng Gao0169: 计划6.18发出 - 高少锋（Shaofeng Gao）
Note on AT19: Shaofeng Gao0169: 6.11发出 - 高少锋（Shaofeng Gao）
Note on AS16: Shaofeng Gao0169: update - 高少锋（Shaofeng Gao） - 高少锋（Shaofeng Gao）
Note on AT36: Shaofeng Gao0169: update - 高少锋（Shaofeng Gao） - 高少锋（Shaofeng Gao）
Note on AU11: Shaofeng Gao0169: 计划6.18发出 - 高少锋（Shaofeng Gao）
Note on AT8: Shaofeng Gao0169: 6.11发出 - 高少锋（Shaofeng Gao）
Note on BA43: Shaofeng Gao0169: CE厂家介入点 - 高少锋（Shaofeng Gao）

## Timeline (old)
| sandwich连续氢化实施计划表 | [90 empty] | Resourse Note
时间 Time line |  | month | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5
工作事项 work item |  | 负责部门 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1
Design | HAZOP （support resource in grey） | UK | 1 4: hazop 下半部分 PID和泵的参数表、数据表 -- 提采购（仪表和自控阀门已经提交采购（采购收集需求信息与Keith确认，然后确定厂家和型号收集下，UK最终确认）；泵还没提，静设备还没提） layout初稿，共同讨论 设备数据表、设备图 、反应器设备数据表（1.19 聂博） -- 静设备结构（1.23更新好 赵工） 关键设备信息（难点在基于国外规范要求的需求，需要Keith他们提供或反复沟通） CEPS操作 输出：静设备最终结构设计确定 布局设计终稿 管路设计 -- PID的终稿、layout 终稿、泵和仪表静设备采购信息 -- 3D图 -- 采购 （采购信息确定之后 2周出3D） 结构设计 -- 强度计算（看SW需求？）CFCT无法，要找第三方 控制柜位置确定、采购
| PI&D | IEPE/UK | bar: 10 3 to 11 2; 1 2 to 1 3; 2 2
| Equipment datasheets | IEPE/UK | bar: 10 3 to 11 2; 12 3 to 2 2
| Instrument datasheets | IEPE/UK | bar: 10 3 to 11 2; 1 3 to 2 2
| Interlock logic | IEPE/UK | bar: 10 3 to 11 2; 1 3; 2 2
| Pump specification sheet | IEPE/UK | bar: 1 2 to 1 3; 2 1 to 2 2
| Operating instructions | IEPE/UK | bar: 1 2 to 1 4; 2 2
| Preliminary equipment layout | CFCT | bar: 1 3 to 1 4
| structural design of static equipment（pink） | IEPE/CFCT/UK | bar: 1 4 to 2 2
| Reactor column specification sheet | IEPE/CFCT | bar: 1 4
| Procurement information confirmation(pump\insturment\equipment schedule) | CFCT/UK | bar: 1 4 to 3 4
Skid | 3D modelling (procurement feedback; UK confirmation of equipment layout) | CFCT | bar: 2 4 to 3 3
| BOM | CFCT | bar: 3 4 to 4 1
| Fabrication drawings | CFCT | bar: 4 2 to 4 3
| Engineering procurement (valves & instruments, static equipment, pumps, piping and fittings; within the skid) | CFCT | bar: 3 3 to 7 4
| Control system procurement and configuration | CFCT/Dezhi | bar: 2 4 to 6 4; 7 3 to 8 3
| Equipment fabrication, assembly and debugging | CFCT | bar: 7 3 to 9 1
| Integrated factory acceptance (FAT) | UK/CFCT/IEPE | bar: 9 1 to 9 3
| CE certification (individual equipment + whole-skid certification per Notified Body requirements); full documentation completed | CFCT | bar: 9 3 to 11 2
| Export formalities, transport inspection/certification and packing | Import/Export | bar: 11 3 to 11 4
| Export shipment (Europe) | Import/Export | bar: 12 1 to 2 4
On Site Engineering Design | PID | UK/IEPE | bar: 10 4 to 11 2
| Engineering design documents | UK/IEPE | bar: 10 4 to 1 3
| HAZOP | UK/IEPE | bar: 10 1; 11 3 to 11 4
| Detailed design | UK/IEPE | bar: 11 4 to 2 3
| Procurement | UK/IEPE | bar: 11 1 to 3 3
On Site Installing | Off-skid/peripheral installation | UK | bar: 3 4 to 5 3
| Skid installation | UK | bar: 3 1 to 3 2
| Mechanical, electrical, instrumentation & piping (MEIP) installation | UK | bar: 5 4 to 6 1; 3 3 to 4 4
| Qualification & acceptance testing (DQ / IQ / OQ) | UK/IEPE | bar: 5 1 to 5 3
| Commissioning and start-up | UK/IEPE | bar: 5 4 to 5 1