## Visit Agenda
Agenda of the visit to Sandwich · 3D layout & HAZOP
On site: Keith, Clare, Lin Haogan, Fan Shuangshuang, Hu Chaoqun (Clare joins the site walkdown and the operability / safety sessions) Online: Gao Shaofeng, Meng Dezhi, Gao Yu, Zhao Ziliang Proposed dates: 12–16 Oct (layout / manuals / control), 20–22 Oct (HAZOP)
No. | Date | Time | Itinerary | On-site attendees | Online attendees | Topics | Objective | Remarks
Site walkdown & 3D model review
1 | 12 Oct (Mon) | 09:00–12:00 | 1. Site walkdown (0.5 day) | Keith, Clare Lin Haogan, Fan Shuangshuang, Hu Chaoqun | Gao Shaofeng, Meng Dezhi Gao Yu, Zhao Ziliang | 1. Skid boundary, stairwell clearance and usable operating faces 2. HTF wall penetration and equipment-room interface 3. Goods-lift and delivery-route dimensions | Site measurements taken as the fixed basis for every layout decision this week.
3 |  | 13:00–17:00 | 2.1 Equipment sequence (0.5 day) | Keith, Lin Haogan Fan Shuangshuang, Hu Chaoqun | Gao Shaofeng, Meng Dezhi Gao Yu, Zhao Ziliang | 1. Width released by the U-shape re-sequence 2. Positions of preheater / condenser / separator / product tank 3. Pipe length and crossings after re-sequencing | Equipment sequence frozen; model updated the same day.
3D model review
4 | 13 Oct (Tue) | 09:00–12:00 | 2.2 Maintenance access (0.5 day) | Keith, Clare Lin Haogan, Fan Shuangshuang, Hu Chaoqun | Gao Shaofeng, Meng Dezhi Gao Yu, Zhao Ziliang | 1. Design the centre aisle and front skid; pick one maintenance route 2. Flange-to-wall distance, reach-in depth and gasket-change space | Maintenance-access route decided; impact on site strip-out and SAT scope stated.
6 |  | 13:00–17:00 | 2.3 Control-cabinet layout (split) (Part 1) | Keith, Lin Haogan Fan Shuangshuang, Hu Chaoqun | Gao Shaofeng, Meng Dezhi Gao Yu, Zhao Ziliang | 1. Split-cabinet layout 2. IS and non-IS panels as separate enclosures 3. Position relative to the emergency shower / eyewash | Control-cabinet position confirmed.
3D model review
7 | 14 Oct (Wed) | 09:00–12:00 | 2.3 Control-cabinet layout (split) (Part 2) | Keith, Lin Haogan Fan Shuangshuang, Hu Chaoqun | Gao Shaofeng, Meng Dezhi Gao Yu, Zhao Ziliang | 1. Junction-box split; align cable count 2. Hinged cabinet — ship without disconnecting tested cables 3. Cabinet size from the instrument allocation agreed here | Cabinet quantity, size and mounting position frozen; cable count aligned.
9 |  | 13:00–17:00 | 2.4 Three-module split (0.5 day) | Keith, Lin Haogan Fan Shuangshuang, Hu Chaoqun | Gao Shaofeng, Meng Dezhi Gao Yu, Zhao Ziliang | 1. Split boundaries and I/O allocation per module 2. Lifting lugs, skate handling and on-site re-assembly sequence 3. Overall height to fit the goods lift | Split boundaries and per-module I/O frozen; goods-lift height solution confirmed feasible.
Operating manual
10 | 15 Oct (Thu) | 09:00–12:00 | 3.1 Operating manual (Part 1) | Keith, Clare Lin Haogan, Fan Shuangshuang, Hu Chaoqun | Gao Shaofeng, Meng Dezhi Gao Yu, Zhao Ziliang | 1. Walk the manual against this week's frozen layout 2. Catalyst charge / discharge (incl. water-wet sequence) 3. Cleaning: valve line-up and hose connections | Comments recorded and dispositioned in the session; revision scope of the manual agreed.
12 |  | 13:00–17:00 | 3.1 Operating manual (Part 2) | Keith, Clare Lin Haogan, Fan Shuangshuang, Hu Chaoqun | Gao Shaofeng, Meng Dezhi Gao Yu, Zhao Ziliang | 1. Start-up, normal operation, shutdown and emergency response 2. Valve and sample-point access, checked against the walkdown 3. Remaining comments closed one by one | Operating manual signed off, or every open comment has an agreed disposition and owner.
Control philosophy & sequence
13 | 16 Oct (Fri) | 09:00–12:00 | 3.2 Control philosophy (0.5 day) | Keith, Clare Lin Haogan, Fan Shuangshuang, Hu Chaoqun | Gao Shaofeng, Meng Dezhi Gao Yu, Zhao Ziliang | 1. Control loops, interlocks and fail positions 2. Split between hardwired interlocks and remote I/O 3. Confirm instrument signal types | Control philosophy agreed; instrument items closed so the I/O schedule can be issued.
15 |  | 13:00–17:00 | 3.3 Sequence control (0.5 day) | Keith, Clare Lin Haogan, Fan Shuangshuang, Hu Chaoqun | Gao Shaofeng, Meng Dezhi Gao Yu, Zhao Ziliang | 1. Sequence steps, permissives and hold points 2. Cleaning sequence and high-level interlock bypass in cleaning mode 3. Operator interface and alarm handling | Sequence agreed as HAZOP input; no open sequence question left going into the study.
HAZOP study
16 | 20 Oct (Tue) | 09:00–17:00 | 4. HAZOP study (Day 1) | SW team Lin Haogan, Fan Shuangshuang, Hu Chaoqun | Gao Shaofeng, Meng Dezhi Gao Yu, Zhao Ziliang |  | Nodes for the day completed.
17 | 21 Oct (Wed) | 09:00–17:00 | 4. HAZOP study (Day 2) | SW team Lin Haogan, Fan Shuangshuang, Hu Chaoqun | Gao Shaofeng, Meng Dezhi Gao Yu, Zhao Ziliang |  | Nodes for the day completed.
18 | 22 Oct (Thu) | 09:00–12:00 | 4. HAZOP study (Day 3, morning) | SW team Lin Haogan, Fan Shuangshuang, Hu Chaoqun | Gao Shaofeng, Meng Dezhi Gao Yu, Zhao Ziliang |  | All nodes completed; agreed action list and document-revision list issued.
Total 7.5 working days: site walkdown 0.5 + 3D model 2.5 + operating manual & control 2 + HAZOP 2.5