## Slide 1
Capacity Construction of the Sandwich Site
B902 Enhancement
B902 Expansion in east area
Construction of the High Potency Lab
Install multi-purpose continuous hydrogenation skids for Pilot Plant
Positioning：Upgrade capacities for reaction, hydrogenation, filtration and drying to support the medium and long-term production capacity demand in the Sandwich site
Positioning：Supplement the routine operation capacity of preparative HPLC, lyophilization and OEB5 within the existing plant
Progress：
HPLC + lyophilization：Technical feasibility study is completed; investment calculation is finished；
C1 module OEB5 upgrade：Scope definition and cost estimation have been completed; delivery shall be synchronized with the liquid chromatography renovation project
Future plans：
The revamped production line shall be prioritized to deliver capacity by 2027; it will be put into production in phases alongside the expansion line
Expansion scope: New 4-story main building plus equipment mezzanine on east side; 10 reactors, 2,500L hydrogenation reactor, 3 sets of filter dryers
Progress：
Investment calculation：finished
Feasibility study ：finished (May 2026); conceptual design & detailed design in next stage
Future plans：
planning permission→ construction→ The completion target by May 2030
Positioning：Add new high-potency lab and operational capacity, which shall be interfaced with OEB5 upgrade and preparative HPLC capacity expansion
Progress：
Investment calculation：in progress
Preliminary reasonable layout design and equipment count calculation completed; feasibility preliminarily verified, space determined and design preparation finished
Positioning：Build practical capabilities for UK/EU engineering standards, forming the capability infrastructure to support Asymchem’s CDMO market expansion in Europe
Progress：
Basic design documents fully available
CE certification scope & roadmap finalized
Sino-UK engineering collaboration framework finalized: IEPE overall design, CFCT skid manufacturing & CE certification, on-site integration at UK Sandwich
Future plans：
Target: commissioning in Sep 2027
Future plans：
Advance in coordination with the enhancement of B902

## Slide 2
Sandwich Site扩建进展
B902 既有厂房改造
B902 东侧扩建
高活实验室建设
Pilot Plant 加装多用途连续氢化撬块
定位：反应、加氢、过滤干燥能力提升，支撑英国中长期产能
定位：在现有厂房内补齐制备液相色谱HPLC、冻干及OEB5日常运行能力
Progress：
HPLC + 冻干：技术可行性研究已完成；投资测算已完成；
C1模块OEB5升级：范围与费用测算已完成；须与液相色谱改造同步交付
Future plans：
改造线优先兑现 2027 年可运行能力；与扩建线并行、分阶段投产
扩建范围：东侧新建四层主体及设备夹层，10 台反应釜、2,500L加氢釜、3 套过滤干燥机
Progress：
投资测算：已完成
可行性研究：已完成(2026年5月); 后续进入概念设计及详细设计
Future plans：
规划许可 → 施工建设 → 2030年5月竣工目标
定位：新增高活实验与运行能力，与OEB5升级及制备液相色谱能力衔接
Progress：
投资测算：进行中
已完成布局初步合理设计与设备数量测算，初步确认可行性，选定空间并完成设计准备
定位：系统建立UK/欧盟工程规范实操能力，支撑凯莱英欧洲 CDMO 市场拓展的能力基础设施
Progress：
基础设计文件已齐备
CE 认证范围与路径确定
中英团队双方工程协作机制成型：IEPE整体设计 + CFCT 撬块制造与CE 认证 + UK Sandwich 现场集成
Future plans：
于2027年9月实现Sandwich site现场开车目标
Future plans：
和B902既有厂房改造协同推进