## Slide 1
01
Overall Progress
整体推进
● 84 merged risks tracked one-by-one to closure
84 项风险清单合并统一跟踪，逐条闭环推进
● Key design deliverables — current status
关键设计文件更新 · 当前状态
– Cleaning plan in progress (Chaoqun; Xiantao ref.)
清洗方案编制中（Chaoqun 主责，Xiantao 提供参考）
– 3D Layout ready — pending joint review
3D 布置已完成，待综合讨论
– Control Philosophy draft ready — pending review
控制策略已有初版，待综合讨论
– Catalyst charging plan under CN discussion
催化剂加料方案 国内讨论中
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-07-01 ~ 07-15 · 01 / 04

## Slide 2
02
Key Technical Discussions
关键技术讨论
● SE01 separator — direction preliminarily set
SE01 气液分离器重点讨论，初步确定思路方向
– Remove side branch · enlarge the vessel
去旁路 · 加大分离器
– Use a flat plate to carry level transmitter / spray ball / relief
用 flat plate 承载液位计 / 喷淋球 / 泄放
● Design temperature / flange class discussed
设计温度 / 法兰等级讨论
● Leak-test strategy discussed
检漏策略讨论
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-07-01 ~ 07-15 · 02 / 04

## Slide 3
03
⚠ Decisions Needed from Leadership
需领导层决策
● Capacity — CR01 DN80→DN50 may fall below URS 30 kg/day. Keep capacity or revise URS?
产能：CR01 缩径（DN80→DN50）可能低于 URS 30 kg/day → 保产能 or 调整 URS？
● Transport — whole-unit lift vs modular skids (align with roof replacement?)
运输：整体吊装 vs 分撬模块化（是否配合屋顶更换）
● CE — on-site assembly needs a CE-mark rep in the UK for 3–4 weeks; certification boundary & cost
认证：现场组装需 CE-mark 人员赴英 3–4 周 → 边界与成本
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-07-01 ~ 07-15 · 03 / 04

## Slide 4
04
Next Steps
下一步
● Size up SE01 & consult Rosemount on the probe
SE01 做大方案测算 + 与 Rosemount 沟通探针
● Cleaning plan next week → align acceptance criteria
清洗方案下周出 → 对齐验收标准
● Control philosophy & interlock schedule next week
控制策略 / 联锁清单下周发出
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-07-01 ~ 07-15 · 04 / 04