## Slide 1
01
Overall Progress
整体推进
● Four key deliverables now issued to all parties
四份关键交付文件已同步发出（超群）
– 3D model · Cleaning plan
3D 模型 · 清洗方案
– Project interlock schedule · Control philosophy
项目联锁表 · 控制说明
● China team completing final internal review
China team 正在进行最后复核
● Joint review with Keith / SW starts next week
下周开始与 Keith 讨论
● 84 merged risk items managed under one tracker
84 项风险清单合并统一跟踪，逐条闭环推进
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-07-15 ~ 07-29 · 01 / 04

## Slide 2
02
Key Technical Progress
关键技术进展
● SE01 separator — design direction locked
SE01 气液分离器设计方向已确定
– Top-mounted level transmitter · flat-top vessel
液位计顶装内伸 · 平顶型式多布管口
– Set / design pressure 7.5 MPaG to keep CLASS 900
起跳/设计压力 7.5 MPaG 以保 CLASS 900
● Reactor CR01 sizing — tentatively DN65
反应器 CR01 暂定 DN65，9 月实验数据后定案
● Cleaning strategy & interlock bypass approach defined
清洗策略与联锁绕过方式已明确（增大排净管径 + 清洗模式）
● Cable schedule aligned against SW single-line diagram
电缆清单已按 SW 单线图核对更新
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-07-15 ~ 07-29 · 02 / 04

## Slide 3
03
⚠ Decisions Needed from Leadership
需领导层决策
● Capacity — CR01 final size DN65 or DN50, to be set on September R&D test data. URS 30 kg/day at stake.
产能：CR01 最终定 DN65 或 DN50，依据 9 月研发实验数据 → 关系 URS 30 kg/day
● Transport — four modular skids vs whole-unit lift through the roof (align with roof replacement?)
运输：4 撬块分体运输 vs 屋顶整体吊装（是否配合屋顶更换）
● CE — whether the Notified Body must verify on site in the UK before issuing the DoC; boundary & cost
认证：认证机构是否需赴英现场验证后才发证 → 边界与成本
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-07-15 ~ 07-29 · 03 / 04

## Slide 4
04
Next Steps
下一步
● Close out China-side review, then issue package to SW
完成国内复核后正式发出文件包
● Start joint review with Keith next week
下周启动与 Keith 的联合讨论
● HAZOP documents & preparation on plan for early September
HAZOP 文件与准备按计划推进，目标 9 月初开展
● O&M manual — the only deliverable still in preparation
操作维护手册为唯一在编交付文件
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-07-15 ~ 07-29 · 04 / 04