# AI润色

A: Okay, can you see my screen now?

B: Yeah.

A: Oh, great. So, for this part, we reevaluated the four phases. The first one is the skid design phase, the second one is procurement, then shipment, and finally installation.

In this version, after the evaluation, we think the third week of November 2027 would be a reasonable time for us to reach beneficial use of this skid.

For the first phase, we are still aiming for the middle of September to finish the HAZOP. The milestone is the HAZOP and also the decision on the size of the reactor. The size of the reactor will be based on Xian Tao's data, which will be available around early September. We think that after that, we can have the HAZOP.

We are now working on the documents, including the control description, the process and cleaning philosophy, the operation manual, and the 3D modeling. The progress on these documents is that the China team has discussed them internally and reached an agreement. We are sending them to the UK side for review.

I think Chao Qun has sent out most of the documents today. Hopefully, we can have a discussion in the technical meeting on Thursday, get some feedback, exchange ideas, and finalize the documents in early September. Then we can finish the HAZOP in the middle of September, maybe in the third week of September.

Regarding the control description, De Zhi may need some more time to complete it.

A: The Honggu side has already issued it, and we are reviewing it.

According to De Zhi, he and his colleague have already issued the draft version, and they are reviewing it internally. When can you send it to KISS?

B: According to De Zhi, they can send it to the UK side next week.

B: Okay. It does concern me that we haven't seen it, and we haven't done much on the layout, to be honest. We haven't looked at the operability of the layout from our side. We haven't sent you the proposed locations for the tie points, but there's still quite a bit of work to do on the layout, and we haven't looked at the controls.

I think September is tight. If everything's good, then September could happen, but my gut feeling is that there is going to be discussion.

A: Yeah.

B: And I'm not sure September will happen. The other issue in your program is that, until we know whether it's coming in as a single unit and being craned in, I think we're being a little optimistic with our timeline for the skid commissioning. We were envisaging just bringing a skid in in the lift originally, installing it in position, plugging it in, and testing what had already been tested.

If we have to rebuild it, repressurize it, test it, recheck all the cabling, and carry out the FAT again, or the SAT, as it will be called, then in full, that's a lot of work. That wasn't in our original program. It's not on the plan. SAT isn't on the plan at all.

A: You mean the testing part is not included here yet, right?

B: Yeah. We have to rebuild the skid because it comes in four modules, with the majority of the instrumentation disconnected from the panel, which is what I've got feelings about at the moment. We're basically rewiring the skid. We'll have to retest those 80-odd I/O points, and, yeah, it's a fair bit of time doing all of that.

So, the six weeks in there for mechanical, electrical, instrumentation, and piping: is that sufficient, or does that need to be longer, I guess?

A: Well, that was an original guess, but we were just taking some multicore cables across from the junction box. It wasn't rewiring through the skid or looking at trying to rerun it in the containment, assuming there is containment there.

B: So how much does that need to increase by?

A: Don't know yet. I don't know, so I don't know what it's coming in as.

B: Yeah, okay. But all I do know is that was for an easy install. That wasn't for a rebuild. So just temper your end date.

If you think we're going to rebuild that skid in that period, then yes, that's a bit optimistic on your end date.

A: So, Peter, have we decided whether the skid will come with four modules or as one piece?

A: Have we decided?

B: Not yet. But Ziliang has talked to the input and output department, and we are concerned about the head limit on the container on the ship. According to the reply he got, the container internal height is at most about 2.69, according to the department. Our current skid is around 3.6 or 3.7 meters, and it cannot ship upright. There are options where the flat rack can take the whole thing, but it's unsealed. There is also a risk of corrosion, and the road height also limits things. According to Ziliang, the road height is around 3.6 or 3.7, but there is still height from the route.

A: We will have some information on the route into site from some of the other projects we've done. I'll see if I can find that, Peter, and send it on to you, because that will tell you what the height is on the road in Sandwiches and the limitations.

A: Yeah, limitations based on size and weight.

B: Yeah.

A: That would be really helpful. Thanks.

B: My gut feeling is that it will be easier for shipment if we do the separate skid plan. But then we need to take into account, like Keith says, that the program needs to be expanded to include the additional work that will need to be done in standard Sandwich.

A: Yeah, Peter, that was the key point. If we come with the four pieces, or four modules, of the skid, then six weeks for the outside testing may be too optimistic. It needs more time for assembly. A lot of things need to make connections.

B: Yeah, I agree.

A: To give you some context, some of that work will be done by a third party. So we'll need to find their availability to come onto site during that window as well, which adds time.

B: Yeah, we can get that on. We just need to know what the scope is. A rough breakdown of how much I/O is on each module, where the panel is going to be located, and I know that is not fixed yet because you showed a panel where we have a safety shower, so on the 3D model that panel definitely needs to be moved.

A: Yeah, we talked last week. There could be a better location for some of the smaller panels where you don't have to disconnect as much. If you can get the panel on the module where most of the I/O is, that minimizes rework. But I don't even know where the splits are at the moment, so I can't comment on that.

A: So what information do we need to move this forward then? Where do we need to understand this?

B: Where the splits on the skid layout would be.

A: Yeah, it's a little bit difficult because we've got a STEP file from the end of June. So whatever's changed since the end of June, we're not aware of, which might be nothing. But we can't view STEP files, so we go through the CAT guys, and we've been through with the CAT guy looking at the tie points. We're waiting for a drawing to come back with some proposed tie-in locations, so then the pipework on the skid can be rerouted to those locations and make sure everything looks good. Then we start looking at what's on the skid and whether we can access it for operations and maintenance.

A: So is this on Peter? Peter, is this already on your work tracker? Is this a new item that needs to go on there?

B: I think it's already on the work tracker, and we are all working on that.

C: 双双，范工，在吗？

D: 啊，在那里。咱们的 3D 模型里头有那个，就是那个分号的计划吗？

C: 嗯，OK，就是已经表现出来了是吧，我记得。

D: 对，OK，对对对。然后就是那个发给那个 UK 的已经表现出来了，是吧。

A: Yes, the one sent last time already showed it. Okay, this is our current plan, right?

B: Yes. Okay. I just verified with Shuangshuang regarding the skid separation plan. We have it in the 3D model. The current plan is to separate the skid into four modules, and we showed in the 3D model where we are going to separate it.

Do you have an I/O count for each of the modules and the connection points? In effect, that is what we need to know. Do you have lifting lugs to lift it into position?

I am guessing we are going to need access to the rear of the skid to rebuild it, so we need to put it on skates. That way, we can access it before it is moved into its final position in the corner. We need to know how we are going to lift it onto the skates and secure it while we rebuild it in the room, and what connections we need to make.

Then we need to lower it, move it on the skates into the corner, take it off the skates, and locate it. That is the information we need. We need to know this so we can get some contractors to provide a price for the work.

C: Understood. Engineer Fan and Engineer Zhao, they may need more detailed information. For example, they need the I/O connection points, including exactly where the connections need to be made. They also need to know what kind of equipment is required, such as a transport vehicle or something like a skid or trolley, how it will be loaded onto the elevator, and how it will be removed after it reaches the destination.

They need relatively detailed installation information. Once they have this, they will need to involve a third party for the installation so that they can make a better assessment. We should prepare an on-site installation plan based on the elevator dimensions and see whether we can provide it to them soon.

Is the I/O referring to the wiring? Is it the piping connection or the electrical connection? I heard it as electrical I/O, but I am not very familiar with this part.

At present, our side may not have a sufficiently clear plan because we have done relatively little design work in this area. I will ask about it later. This is essentially about how they will install and lift the equipment on site, right?

Once we have a modularization plan, we also need to give them a plan for how the modules will be rebuilt into one complete unit. This should include the transport plan based on the elevator and how the equipment will be handled. I think they may understand the on-site implementation better, so I will ask about this again, because our side has done relatively little design work in this area.

D: I will transfer this to Ziliang and Shuangshuang, and they will double-check with the China team how we can reinstall the skid into one piece. They will gather the details and make a plan, and then we can get back to you.

B: Okay, that is great. If you can send the information in PDF or DWG format, we can view it on site. If you send it as a STEP file, it is easy to incorporate into the model, but we would then have to ask our CAD team to view it because we do not have software to view STEP files.

D: Okay. I will tell them to use DWG and PDF versions.

B: Thanks, Beta.

C: Thank you. Engineer Fan and Engineer Zhao, for the subsequent parts of this plan, it would be best to use PDF or DWG. The previous model or file format may require their CAD personnel to convert it first, so DWG and PDF will be more convenient.

B: So, Peter, are we going to update this plan and come back to it in two weeks, with the key information we need to understand about the back end of this project? I noticed that some of the UK elements are not included in the plan. We need to understand what is going on.

C: Yes, exactly.

B: We need to reach a decision so that we can understand when we should expect to have the equipment.

D: Yes, I agree. I think the main concerns are the design phase, and especially the installation and retesting. This part is still being evaluated, but it is highly dependent on the 3D modeling. We will try on our side to obtain a more detailed skid separation and reunion plan, as well as the 3D model. We can push this forward a little sooner, and after that we may be able to make an easier evaluation.

B: Do we have a clear list of what Keith needs to understand about the skid if we split it into modules? Keith, have you provided a list of the key information? Can we put that in an email?

C: It depends on where the splits are.

B: Okay. We just need to know the design intent for splitting it and rebuilding it. That is all.

C: Okay.

B: Then there is the matter of the I/O count. That should include the 60 I/O points on that unit. It is that level of detail. We need to make sure they understand the level of detail you need in order to make decisions. It is not difficult, is it, Peter? Whatever you disconnect to split it into four modules, we then have to reconnect to rebuild it and retest it. Just let us know what we need to do, or what you would need to do if you rebuilt it in China.

C: Okay, understood. We will prepare that.

B: Thanks.

C: Thank you.

B: Thanks. Are there any other comments on the timeline?

A: Um, modifications. Zheng Boshi, do you have any other ideas and plans? Are you doing the final discussion, or are you waiting for the data from Xian Tao to make a decision on the reactor size, the diameter?

A: For the key documents, we have only discussed internally in the China team, and we haven’t reached a discussion and agreement with Keith. So it takes time. I think it takes several rounds to reach a point where there is a perfect agreement between the China team and the UK team. I agree with Keith and Claire that it may be a little bit too optimistic. We can start it like the second week of September and finish it like the 3rd of September. It may be a little bit too optimistic, and we will try our best to make it happen sooner.

A: So you talk about the rounds of discussions. Is there a way of speeding those up?

B: Oh, sorry, I did.

A: Yeah, that’s also my question. Why do you need several rounds of discussion within the China team? Why not just send what you have, the conclusion within the China team, and have a review by Keith and Claire, not just at the end when you send a whole piece of your conclusion? But maybe that was not what they expected, so you may end up taking much longer than you thought.

C: Uh, this part, I am not very familiar with our design idea and principle. Right now, we normally finish internal review and discussion first, and then send it to Sandwich. Actually, if we are still in the process, the draft can also be sent directly to them, so the discussion will not end up reaching a point where we find the thing is not workable and then have to do major rework. Let me explain a little. First, in the workflow, there are some repeated reviews between upstream and downstream disciplines, for example the cleaning plan. So at the draft stage, there is a back-and-forth process. After the internal upstream and downstream review, sending it out is relatively more complete. If we send it out, then there will be opinions from multiple parties. Some issues can be handled internally, but in that case we may end up discussing the same thing repeatedly.

A: Why can’t you send them the big framework first? The detailed parts may not be able to reach a hundred percent conclusion internally right now, but there should at least be a broad process and logic. Can’t you send that first?

C: Previously, that is how it was executed. Files were sent out uniformly. But in the execution process, there were also some opinions from our side. Internal opinions can be divided into two types. If it is a major opinion, a major surgery, then that is troublesome. If it is a minor opinion, then you just need to change it. What we are worried about now is that if your structure, your overall big framework, is not accepted by them, then later it will not be solved by small modifications, and that will take a long time, maybe several more weeks.

A: So why not do it in parallel? You can keep optimizing internally. I have no objection to that, but you cannot show them a 70-point draft and let them see the framework. They will know it may still be different from the final version, but at least they can see the framework.

C: Yes, what you said is correct. We did run it that way before. I remember there was a meeting where it was said that we still need to eliminate some issues internally, so later we optimized it into a process where we try to communicate internally first, then send out the draft. The advantage, as you said, is that case may look at some issues and we also look at some issues, and the internal issues are actually eliminated. The downside is that both sides may end up exchanging emails on the same repeated issues. I remember we discussed this before, and later the idea was to digest it internally first and provide a more mature version.

A: Then why has internal digestion taken so long? We have already spent more than a month. And now you are saying it still has to wait until the beginning of September? It is only early August now.

C: It is not continuous in the sense that we are doing the same thing. Some work is being done, and some issues are discovered during the process. For example, venting temperature, increasing it to the design temperature, and so on. My point is that for some things, you can just write that we are calculating this item and it may take another five days or one week before it comes out. Then you leave it there and mark it, like a yellow note, saying that we are still waiting for some results. Then they will know that you are working on this, and it can already be discussed. It should not be that you wait until the result comes out a week or several days later before doing the next action. I think the way you are working now is too inefficient. Some results can still be pending, just like now Peter has already listed some decision points and we are waiting for certain results. For that kind of thing, I think it is acceptable. But now I feel your approach is open-ended. I am worried that by the second week, as Clear just said, this is too optimistic.

D: Right, Clear, yes, sorry, yes, it’s too optimistic. So I think you should discuss it again with Shao Feng, and quickly summarize some things first. Ask them whether there are any major issues. It is better to proceed in parallel on both sides, since there is still one month left.

C: Now most of the documents have come out, and more will be sent out today. At present, the green items we have sorted out are basically completed. As for the Control Description part, and also the latest draft of the 3D model, that may need to be sent out as well. In this state, forming that mechanism today is not a problem. I agree. I think both approaches are fine, and there is no issue on my side. My impression from the last meeting was also that the three of us felt some issues needed to be digested internally. For the initial draft, there may be more issues. At a glance, we hoped the internal side could digest them first, leave fewer problems, and provide a relatively mature version for the three of us to discuss again. Based on that principle, if we change the strategy today, I fully agree. No problem. We can share the files that are currently in progress as drafts while everyone is working on them, and do it in parallel.

D: Zheng Boshi, Shao Feng, my concern is the premise you just mentioned: that the thing you are digesting internally means you already fully understand the 3D curve’s idea. If that is the case, then I think what you just said makes sense. What I am afraid of is that you spend three more weeks digesting it internally, and in the end, after the file is completed, there will still be some individual issues left.

C: I am not talking about rework. I mean we will not let one problem stop the file for three weeks and then go through internal review. Instead, later we will share the initial draft, and there are also key items at the beginning. That has always been the way it was executed, including those more than one hundred issues that were sorted out. Basically, the big principle is that once they come out, they are shared in time.

D: Peter, I still think more interaction is needed, and you can be the bridge. Try to get more comments from Keith and Claire to make sure we do not have any major gap between the understanding of the two teams.

A: Yeah, we cannot afford any last-minute surprise. We have been working for so long. Supposedly we should be just working on very minor detail adjustment, but now I still worry that maybe at the end we still need a big surgery, and that will be unacceptable.

C: Yeah, I agree.

A: So, yeah.

C: AC, actually, I also think...

Sharing the draft and making sure the big directions are correct is important. And I think we can do it from now on, like the control description, also the speed dividends plan, and how we reinstated this kind of plan. We got a draft version first, and make sure the big direction is acceptable by both teams, both sides, and then we can revise them to get a final version.

Yeah, it's agreeing. Yeah, it's agreeing the high-level strategy and then putting in the detail to do it. I think a lot of the time we go straight to the detail, but we haven't agreed the key points, first of making sure that they're clearly explained.

Okay. So, Peter, this is my major comment. Make sure that up to this point, we don't have any major gap at a high-level understanding, or some information still lacking for the high-level structural or philosophical problem with the whole project or design or engineering, installation, whatever, that becomes a roadblock or on a critical path that will delay the project. So make sure we don't have such kind of an issue, yeah. If it's just detail, I think you just can highlight those points are still under calculation or still waiting for some results in China team. I think Keith and Claire can understand this is not the final results, but they can review all the method or the logic of what you are just drafting. So this, I think, is the key point.

Yeah, I will do so. Make sure no disagreement on the major framework and in the high-level structure of the report. For instance, you are talking about the control logic design, and there are some high-level information that needs to be agreed, that this really what we are aiming for, and then I think both teams can work on the details. So as long as the structures are agreed, I don't think the minor detail adjustment will be an issue.

Yeah, yes, I think so. Make sure that we don't further delay the project too much. I know we're still waiting for the results from Feng Xiantao, and I think his results should come out very soon, right by the end of August or early September.

Okay. Previously he said the time point of early September. And I think it's important at that point we then have a defined operating capability and understanding what process characteristics can go into the reactor, because we are designing the reactor to be able to remove a certain amount of heat. So we need to know what parameters we're going to be working to, so we can design prep teams can design processes to fit those parameters. But I haven't seen those written down anywhere since we've made the changes. Is that the PFD, or some other document? You were describing that part.

We'll probably summarize it on the PFD. Yeah, but as you make your reactor smaller, your surface area goes down, and it becomes harder to take away the same kilowatts of heat. So what does that translate into? A heat reaction? Or do you know how, how do we work out what the PFD describes, the kind of equipment capability?

It's the chemistry capability that you're designing the equipment to control. And it's not a big deal, I'm sure, because we can always put bypasses in. But the taste that was the large TCU was for reactor 1, so if you reduce the surface area on the reactor, that TCU is probably oversized and won't perform well because it's always trying to operate at 10% of its capability.

Oh, and that's on site, isn't it?

Yeah, we've got the TCUs because we've got the majors again.

Yeah, and so it's just understanding how that affects the overall design, not just a reactor's physical size change, but the heat balances that go with it.

Yeah.

And because we have to put a bypass in to try and lose some heat or create some heat somewhere, we need to include that in our design somehow.

Yeah, I understand.

A: Let me talk to Shao Feng and Zi Yang.

B: Yeah.

A: Oh, yeah. It does not need solving now. It is just a matter of making sure it is thought about and included. Essentially, we could get another, smaller TCU to do the duty, which would make it easier for us to fit within the available space. It would mean that we had a spare large TCU, but they were about, I think, thirty-eight thousand. The new TCU might be more beneficial than trying to install bypasses and something to remove some heat so that it can operate within its design range. We need to understand the downstream impacts of that change. The physical size is the important part for you guys.

B: Director Gao, Engineer Zhao, I just discussed this with you. If we change to a smaller unit, there is one issue: its heat-transfer surface area will also be smaller, so its heat exchange will definitely be reduced. The current TCU is a large TCU. There are two large TCUs supplying the reactor. If we change it this way, the large unit may no longer be suitable, and we may have excess capacity. We might need to install a bypass or find somewhere to dissipate that excess capacity.

This also needs to be considered. It is not especially urgent, but before we carry out the HAZOP, we need to have a plan or at least an assessment. For example, changing to a smaller TCU might be more favorable in terms of physical space. However, this also needs to be considered. Did we previously say that the TCU in the PFD was something we were considering when I took over, or was it equipment configured by the Sandwich team? I am not completely sure.

A: It has already been purchased?

B: Then the calculation needs to involve your research and development team, because the earlier stage has already passed. The difficulty is that R&D and the requirements team need to jointly confirm which basis to use for the calculation. Its volume and operating capacity are not fixed, so our calculation must use a defined basis. We need to determine which production rate the calculation should be based on.

Theoretically, if the original 80 is changed to 50, the scale will be reduced. If the dimensions are reduced to, for example, 65 or 50, then, theoretically, using the original calculation method with a smaller diameter is conservative and should not be a problem. However, if a detailed calculation is required, R&D needs to be brought in to determine which standard should be used.

That is the reactor issue. The second issue concerns the TCU. If it has already been purchased, we should check whether its pump is variable-frequency. If the circulation pump is variable-frequency, then it should not be a major problem. The TCU itself should also have a bypass, such as a return line. The TCU should have been designed with this situation in mind. Since its capacity is large, the configured heat-load requirement can be lower.

The disadvantage is that the temperature difference is difficult to determine at this stage. It may be slightly higher than it would be with a perfectly matched unit. That could be one drawback.

A: Okay. Then our side is okay. Regarding this GPU, was it purchased by the site? Is there anything we need to do? On our side, do we only need to connect the interfaces?

B: Are they asking for a bypass? If they want a bypass, then we can provide a bypass.

A: No, no. The second option is that they want a smaller TCU, right?

B: It would be better to replace it with a smaller one once the scale has been finalized.

A: No, but I think they are asking us to evaluate it. We need to calculate this, including the PFD and the heat exchanger, and then they can consider the options.

B: We cannot complete the PFD by ourselves. R&D needs to be involved to establish the relevant basis. I believe the previous PFD was being prepared together with R&D. Since the proposed arrangement requires Dr. Feng to be involved, he needs to determine which volume and composition parameters should be used for the calculation. We have always needed R&D to participate before we could transfer the results to our side. We cannot complete that part independently.

A: Regarding what we discussed last time, for the requirements from the process room and the site, what solvent or hydrogenation conditions are most likely? Which conditions should we use as the basis? Should we calculate using a relatively conservative operating condition? Please prepare the PFD material balance and confirm whether this belongs to the 33 team or to this side. We can check that later. Was the internal discussion also that Dr. Feng and Case should be involved in discussing the PFD?

B: Yes. By September, once the dimensions have been finalized, any change would require the scale to be changed. The PFD material balance would definitely need to change as well. After that changes, 365 is concerned about the heat-transfer issue.

A: The heat-transfer surface area is increased, not decreased. The processing capacity is reduced.

B: Yes, that is beneficial for the process. The purpose of reducing the size is to improve heat transfer and avoid high-temperature points at the center. The reason is to avoid that issue by increasing and strengthening the heat-transfer capability.

A: Okay, then I will discuss it with them again.

B: Yes. I will talk to Shao Feng and Zi Yang about this part of the heat calculation. We will involve Xian Tao from the research team. He may have a better understanding. According to Shao Feng and his experience, if the TCU is a frequency-conversion type, it should not cause much trouble. However, it also depends on the type of TCU. In fact, the heat-exchange efficiency should increase rather than decrease.

I think we can invite Jian Tao to discuss this at a technical meeting at some point, to confirm what calculation is actually needed and how we will resolve this problem. It is within our scope.

A: We just need to know whether the expected duty on that reactor decreases, or whether you simply need a smaller reactor while still requiring the same cooling capability. Can you actually achieve that with the heat-transfer area available? What is the limiting factor? I think your heat-transfer area is probably the limiting factor.

All of this should come out of the tracking you are doing on the impact of changing the reactor, surely.

B: Okay. Yes, understood.

A: I am not sure that tracking is that formal, but it should be at this point in the project.

B: I do not believe that tracking is that formal.

A: Yes, but I do not believe the change is being flagged as a change and that an impact assessment is being carried out on it at the moment. Whether that is right or wrong, it seems that the process is waiting until the change is decided.

B: Once the change is decided, that is a gap. We do need to understand and assess the impact of that change.

A: So let us make sure we capture everything at this point in time, rather than discovering it six or nine months later through the elements of the program.

B: Yes.

A: Okay.

B: Yes.

A: Uh, uh, I think this part, Xian Tao may know better, and this time we will invite Xian Tao to fully participate in this evaluation so that we won’t end up finding some problem a long time later and then finding issues that actually needed to be solved previously.

B: Yeah, because this time once we’ve done the hazard, we should then be tracking changes to make sure that they aren’t impacting the safety of the system design.

C: Yeah, I gotta say we would have normally done that post hazard, not pre hazard.

B: No, but yeah, this is a fairly big change though.

C: As big as the last one that was made with no tracking.

B: Yeah, true. Doesn’t make it right.

A: OK. I’ll keep that in my action tracker and make sure to talk to Qian Tao on that.

A: And so, is there any other comments on the... I guess my only concern is we haven’t actually got to a timeline that we’re comfortable we can then know that we’re gonna be able to deliver against. And I think we really need to start to get to that.

C: Yeah, because it’s difficult for everybody to plan work and resource and actually arrange to have processes to use the facility because we don’t know exactly when it’s going to be available. So I think it’s key over the next month, really, to get to a point where we have a timeline we think we can actually deliver. I’d rather have a realistic timeline that we know we can work to than one that constantly changes.

A: Yeah, understood.

A: So, for the other, the progress is mainly on the technical sessions, and we are closing the part. During the technical meeting, we are closing part of the trackers. We finished and resolved six tracker items in the last meeting, and now we are having discussion on the high pressure ceiling solution, but it’s not yet founded. And this part of the technical part is our bottleneck for now. For the next step, it’s mainly the...

A: As Claire just said, we need a reasonable and also realistic timeline evaluated in the near future. And about the technical ones, we just made the decision of sending out the draft and also the after-discussion internal discussion of the China team’s version of the key documents. In the next two weeks we will discuss on that and reach an agreement that no big concerns in these plans.

A: And for the import and export department confirmation, as I just said, Ziliang has got the information of the Shi shipment, and he will also contact them and get further information and find further plans, carrier plan options. And Claire, could you send us the limitation of the road transportation?

B: Yeah, that would be great.

A: And I think we will also work on the 3D modeling and also evaluating the FDT and also the retesting part in the UK.

A: And the China team will do the separation of the skid plan and also how we reinstall the skid, this kind of plan. I think that’s what I thought are the next steps.

D: Uh, Peter, can I suggest on the size of the skid?

E: Yeah, look carefully at why it doesn’t fit into a container, and see whether it’s a case of just taking one vessel off of the skid and shipping it separately, so that you have an easy way to install. Because if you’re planning on selling this skid to Europe, you want something that is easily shipped. So it’s a struggle where we’re getting the almost 4 meters high from just sitting here. There must be something that sticks out the top that maybe gets fitted as a separate vessel rather than a whole module at a later date when it’s on site.

D: Hmm.

E: Just looking at long term plans, if you want to try and sell the skid to other organizations, it needs to be easily shippable.

D: Yeah, and easy to put back together at the other end.

E: Yeah, yeah, yeah, yeah, I agree.

A: So, we will double-check that. I will talk to Zi Liang and Shuang Shuang. Zhao Gong and Fan Gong, as we just discussed, we need to look at where this four-meter figure came from. Is it actually 3.7 meters or 3.6 meters? It may only be caused by one particular section. For example, if it is one section of the reactor, or some part that protrudes, we can check whether it can be controlled or whether there is a better solution to make it a single unit for transportation.

In the long term, if we need to open this equipment and transport similar items again, it would be beneficial to have a better separation scheme, so that the equipment can be separated more safely and easily in the future. We can look at the specific situation. There are probably two issues: first, whether it really needs to be as high as 3.6 or 3.7 meters; and second, whether the separation process can be made simpler and faster, with reassembly also made easier and with less impact on the overall equipment. That is his suggestion.

A: The overall direction will follow the direction Case mentioned. We will work toward that. The 3D model has already been sent. If we have enough time tomorrow, we can look at the specific internal structure, which may give us a more intuitive impression. After that, we will continue working in the direction he suggested.

A: We will also evaluate what height we really need. Does it have to be four meters, or can we make it smaller? I think that, if we have enough time, we can discuss this at tomorrow's technical meeting using the 3D model. Zi Liang and Shuang Shuang will show the model version, and we can get a more intuitive understanding of why and how we are separating the sections and why we are doing it this way.

B: Yes, sure. Thanks. That is all from the China side. Does anyone have any other questions or comments?

C: No, not for me.

D: No, I think we are good for this one, Peter.

B: Yes, thank you.

A: And thank you.

C: Thank you.

B: We can talk more about this at tomorrow's technical meeting, please.

A: Brilliant. Thanks, Peter.

B: Thank you. We will speak to you soon.

A: Bye-bye.

B: Bye.

C: Bye.

A: Thanks. Bye.