## 0922
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. 05/12：Keith建议用气液两相计算安全阀尺寸，不提供模板 05/12：Keith suggests using gas-liquid two-phase calculations for determining the size of the safety valve, but no template is provided. 05/20：根据API520的气液两相泄放时计算安全阀尺寸，部分已完成 05/20：Calculate the size of the safety valve based on the API520 standard for the two-phase gas-liquid discharge situation.Partially completed. 06/02：安全阀计算初版已完成（包含临界流体和气液两相），校审中。 06/02：Preliminary calculation of safety relief valve (covering critical fluid & gas-liquid two-phase flow) completed, under review. 06/09: General 1. What was the source/reference for the Specific Volumes stated in column D/D 列中比容数据的来源及参考依据是什么？ The Specific Volumes stated in column D are derived from Aspen Plus simulation results.比容数据来自Aspen模拟 2. There is no backpressure considered in the calculation. The emergency vent relief will create some backpressure which needs to be considered in the calculation./本次计算未考虑背压。紧急放空泄放过程会产生一定背压，该因素需纳入计算。 Backpressure consists of static backpressure and built-up backpressure. Given the wide total pressure range, backpressure effects shall be incorporated into the calculation.背压分为静背压和积聚背压，总压力范围大，将背压包含在其中 3. At the assumed relief pressure Ethyl Acetate will be a supercritical fluid, therefore the required relief mass flowrate will not be dependent on the latent heat of vapourisation, and the calculated ‘required discharge area’ will not be valid. Do you agree with this statement, or have you found a reference in the standard that allows for this? 在设定的泄放压力下，乙酸乙酯将处于超临界流体状态，因此所需泄放质量流量不再依赖汽化潜热，本次算出的所需泄放流通面积也不再适用。你是否认同该观点？或是你是否在相关标准中查到可支持该计算的依据？ 详见06/16回复. Please refer to the reply dated 06/16 for details. Cooling Failure Calculations 4. For the cooling failure calculation, I would suggest using 550kJ/mol rather than 501.48. This is based on Sandwich PSL experience of heats of reaction. 针对冷却失效工况计算，建议将反应热取值由 501.48 kJ/mol 改为 550 kJ/mol。该取值参考了桑威奇工艺安全实验室（Sandwich PSL）过往反应热项目经验。 OK 5. Is the feed flowrate used in the calculation, based on the maximum metering pump capabilities? Do you assume a maximum concentration of reactant in the feed stream? 计算中采用的进料流量，是否按照计量泵最大额定流量取值？计算时是否假定进料流中反应物浓度为最大浓度？ The flow rate used in the calculation is set at the maximum rated capacity of the metering pump, and the maximum reactant concentration is adopted for the feed stream.计算时流量是按照计量泵最大额定流量取值，反应物浓度为最大浓度 06/16：根据文献“Relief Calculation for Supercritical Fluids”计算超临界流体的质量泄放流量，会后向Keith发计算书审核 06/16：Calculate the mass relief flow rate of supercritical fluids in accordance with the document Relief Calculation for Supercritical Fluids, and send the calculation sheet to Keith for review after the meeting. | YES | Chaoqun Hu
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun Hu
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. 06/16：06/11已收到审核完成的URS。 06/16：Received the reviewed URS on 06/11. | YES | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith确认CV08也是故障关，可以使用DS6080型，该型号没有5 bar 差压限制。 Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith confirmed that CV08 is also a faulty-close type, the DS6080 model can be used. This model does not have a 5-bar differential pressure limit. Keith offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. 06/02 进展：Habonim厂家反馈了样本资料，反馈可以满足工艺参数需求，货期大概16~20周。可以作为开关阀的备选品牌。 06/02 Progress: "Habonim" manufacturer has provided sample materials that can meet the process parameter requirements. The delivery time is approximately 16 to 20 weeks. It can be an alternative brand for on-off valves. | YES | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. 06/02：关于气液分离器液相出口减压，电子压力阀和自力式减压阀都可以满足使用，首选自力式减压阀。 06/02：For pressure reduction at the liquid outlet of the gas-liquid separator，both electronic pressure valves and self-operated pressure reducing valves can meet the requirements, with self-operated pressure reducing valves being the preferred choice. | YES | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. 05/20：SW已更新完URS并发出。The SW has been updated and the URS has been sent out. | YES | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表数据单。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. 06/23:仪表条件表已更新完成 06/23：The instrument conditions table has been updated and completed. 07/10：仪表数据单已更新完成 07/10：Instrument Data Sheet has been fully updated. | YES | Chaoqun Hu/Yu Gao
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. 05/20：SW已更新完PFD并发出。The SW has been updated and the PFD has been sent out. | YES | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ 4/30：Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? 0914：详见第72(0702)条。For Detail, please see item 72(0702). | YES | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted?05/12Decided not to make any adjustments. 05/12确定不做调整。 05/12：It is determined that the height of the catalyst bed in the main reactor will not be adjusted. | YES | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. 06/16：会议澄清：待布局完成后，SW主导完成爆炸危险区域的划分 09/06：Meeting Clarification: SW shall take the lead in completing the classification of hazardous areas for explosion after layout design is finalized. 0915:SW现场确定3D后1周时间SW方完成。 0915: After 1 week from the time the 3D model was determined on-site, the SW team will complete the task. | NO | All
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | YES | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements. | 05/20：与聂博沟通，小试使用的是进口是插底的分离器，生产使用的是侧进的分离器，按会议沟通的气体最大流量0.2Nm³/h，液体最大流量20L/h重新计算了分离器 05/20: Communicated with Nie Bo. The small-scale test used an imported bottom-insertion separator, while the production version used a side-inlet separator. Based on the maximum gas flow rate of 0.2 Nm³/h and the maximum liquid flow rate of 20 L/h for the communication at the meeting, the separator was recalculated.. | YES | Chaoqun Hu
06/02 | IEPE | 管道编号中的管线尺寸一般是指的公称直径，PID中尺寸为10mm的管道是Φ10mm，公称直径为6mm The line size in pipe line designations generally refers to the nominal diameter. In a P&ID, a pipe with a size of 10mm is specified as Φ10mm, corresponding to a nominal diameter of 6mm. | 06/02：会议澄清：DN15以下的管道，管道编号中的管径为外径，DN15及其以上的管道，管道编号中的管径为公称直径。 06/02：Clarification from meeting:For piping below DN15, the size specified in pipe tag number denotes outer diameter; for DN15 and above, the size in pipe tag refers to nominal diameter. | YES | Chaoqun Hu
06/02 | IEPE | 设备BT-01/03/04上的压力变送器不便于现场观察，是否可以考虑也选用WIKA的不带现场显示紧凑型的压力变送器？ The pressure transmitter on the equipment BT-01/03/04 is not convenient for on-site observation. Could it be considered to also choose WIKA's compact pressure transmitter without on-site display？ | 06/02：会上建议保留BT-01/04的现场显示，BT-03可不带现场显示。 06/02：It was suggested at the meeting that the on-site display of BT-01/04 be retained, while BT-03 may not have an on-site display. | YES | Yu Gao
06/02 | CFCT | 1-PID中V-9868，V-9965阀柄的含义？ What is the meaning of valve handles V-9868 and V-9965 in PID? 2-PID中压力变送器底部波纹含义是什么？ What does the corrugation at the bottom of the pressure transmitter signify? 3-与管道直径对应的保温厚度是多少？ What is the insulation thickness corresponding to the diameter of the pipeline? | 06/02： 1.PID中阀门V-9868，V-9965的阀柄为弹簧复位阀柄； In the PID,the valve handles of V-9868 and V-9965 are spring-reset handles； 2.PID中带底部波纹的压力变送器要求压力变送器带隔膜； The pressure transmitter with a bottom ripple in PID requires the pressure transmitter to be equipped with a diaphragm； 3.Keith分享了建议的管道直径与保温厚度表格，直径10到25mm的管路，保温厚度为30-35mm。 Keith shared the recommended pipe diameter and insulation thickness table, with insulation thickness ranging from 30-35mm for pipes with diameters of 10 to 25mm. | YES | ShuangshuangFan
06/16 | SW | 会议确认：气液分离器为侧进，尺寸为DN200*600mm，下次例会前CFCT向SW提供气液分离器的设备图纸 Confirmed at the meeting: The gas-liquid separator adopts side inlet configuration with dimensions DN200 × 600 mm. CFCT shall submit the equipment drawing of the gas-liquid separator to SW prior to the next regular meeting. | 06/22设备图纸已提供。06/23Keith回复意见，见06/23讨论内容。 Equipment drawings were provided on 06/22. Keith's feedback was received on 06/23 — please refer to the discussion notes from 06/23. | YES | Ziliang Zhao
06/17 | SW | 根据最新工作进展并结合HAZOP分析所需文件内容，更新“Sandwich Hydrogenation Implementation Schedule” Update the Sandwich Hydrogenation Implementation Schedule based on the latest progress and document requirements for HAZOP study. | 待SW现场3D讨论及HAZOP分析完成后更新相对准确的进度计划表。 | NO | All
06/17 | SW | 讨论操作规程：哪些部分需要顺控？开停车步骤等 Discuss operation procedures: identify sections requiring sequence control, including startup and shutdown steps, etc. | 06/23：开车步骤：公用工程确认/催化剂装填→氮气置换（R24-BT01、R24-BT04和剩余部分），氧含量<0.5vol%→氢气置换→原料系统备料→TCU系统调温→反应器进料（氢气先进料背压至反应压力，液相再进料）→气液分离→产品转移 停车步骤：停进料→产品缓冲罐物料转移→反应器卸压→R24-BT03卸压→反应系统降温→氮气置换→关闭氮气和TCU Startup Procedures： 1.Verification of utility systems & catalyst loading 2.Nitrogen purging (for R24-BT01, R24-BT04 and the rest of the system), oxygen content controlled below 0.5 vol% 3.Hydrogen purging 4.Raw material preparation for feed system 5.Temperature adjustment of TCU system 6.Reactor feeding: Introduce hydrogen first to build backpressure up to reaction pressure, then feed liquid phase material 7.Gas-liquid separation 8.Product transfer Shutdown Procedures： 1.Cut off feed supply 2.Transfer materials from product buffer tank 3.Depressurize reactor 4.Depressurize R24-BT03 5.Cool down reaction system 6.Nitrogen purging 7.Shut down nitrogen supply and TCU system Keith提供HAZOP时的开停车步骤，结合上述文件，整理开停车和清洗步骤 Compile the plant start-up, shutdown and cleaning procedures based on the above documents together with the start-up & shutdown sequences supplied by Keith for HAZOP assessment. 09/07：操作手册已于08/21发给SW 09/07：The operating manual was sent to SW on 08/21. | Pending | All
06/17 | SW | 会后确认：安全阀的泄放温度超过设备的设计温度，是否需要提高设备的设计温度？ To be confirmed after the meeting：If the relief temperature of the safety valve exceeds its design temperature, is it necessary to increase the design temperature rating? | 设备和管线材质为316L，结合设备和管道的壁厚，计算得出：在泄放温度下，材料的许用应力满足其强度要求，不需提高设备的设计温度 The equipment and piping are fabricated from 316L stainless steel. Wall thickness calculations for the equipment and piping demonstrate that the allowable stress of the material satisfies the strength requirements at relief temperature; therefore, no increase to the equipment design temperature is required. | YES | Ziliang Zhao/Chaoqun Hu
06/17 | SW | CFCT做撬块设计时，注意清洗过程中的低点排净 CFCT shall take full consideration of low-point draining during cleaning when designing the skid package. | 06/23：在撬块设计时，设置管道的低点排净阀 When designing the layout, install a drain valve at the low point of the pipeline 06/23会议方案：管道最低点设置排净阀，操作说明中明确排放时用容器收集排放液体。 Meeting Plant: Install drain valves at the lowest point of the pipeline, and specify in the operating instructions to collect the discharged liquid with a container during the drainage process. | YES | Shuangshuang Fan
06/17 | SW | CFCT提供放空缓冲罐T06是否放在撬内的方案 CFCT to provide a scheme on whether vent buffer tank T06 shall be installed inside the skid. | 06/23：按照现有空间的布置，T06放在撬块内的空间不足；撬块中间的操作维护通道宽度为300-350mm，能否将整体撬块宽度增加150-200mm？ According to the existing space arrangement, there is insufficient space for T06 to be placed inside the pry block; The width of the operation and maintenance channel in the middle of the pry block is 300-350mm. Can the overall pry block width be increased by 150-200mm? 06/23会议方案：T06不放在撬块内，放置在service area，同时反应柱/冷凝器的TCU出口管路上的温度变送器安装在近出口处，去掉手动球阀，安全阀可放到service area，并设置排净阀，进口管路手动球阀保持不变，温度变送器加套管，位置可前可后，低点设置排净阀，整体管路的高点设置排气阀。 Meeting Plant:: T06 is not placed inside the lever block but in the service area. The temperature transmitter on the TCU outlet pipeline of the reaction column/condenser is installed near the outlet. The manual ball valve is removed, and the safety valve can be placed in the service area. A drain valve is installed, while the manual ball valve on the inlet pipeline remains unchanged. The temperature transmitter is equipped with a protective sleeve, with its position adjustable forward or backward. A drain valve is set at the low point, and an air vent valve is installed at the high point of the entire pipeline. | YES | Shuangshuang Fan
06/23 | SW | Keith意见： 基本设计：我们是否有经批准的分离器设计方案？我上次看到的摘录中，计算出的容器直径为3毫米，这表明计算或输入数据可能存在错误。 Basic design 1. Do we have an approved design for the separator. The last extract I saw had a calculated vessel diameter of 3mm, which suggests an error in the calculations or input data. | 06/23讨论： 基本设计：按最新设备数据表进行气液分离器设计。气液分离器的计算书已复核过，数据无误。 06/23Discussion—Basic Design: The gas-liquid separator shall be designed in accordance with the latest equipment data sheet. The calculation sheet for the gas-liquid separator has been reviewed and the data are confirmed to be correct. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 分离器内件 1、本设计中是否已考虑分离器内件，例如入口导流装置或入口旋风分离器、气相除雾器、液体出口处的防涡流挡板？ 2、喷淋球能否采用焊接固定方式，而非通过管接头引入容器内部？ 3、喷淋球是否必须为旋转式喷淋球？这会增加设备复杂度，并在工厂运行寿命期内带来检查与维护方面的问题。 4、喷淋球实际能否起到喷淋清洗作用，还是仅仅将容器注满清洗液直至触发高位液位开关？根据此前讨论，从空罐到高位跳闸点的时间不足25秒，这无法为分离器气相侧提供足够的机械清洗作用时间。 Separator internals 1. Have separator internals been considered for this design e.g. inlet diverters or inlet cyclones, demisting of the vapour stream, vortex breakers on the liquid outlet. 2. Can the spray ball be welded in position rather than introducing a tube fitting into the vessel. 3. Does the spray ball need to be a rotary spray ball. This adds complexity and inspection/maintenance issues during the life of the plant. 4. Will the spray ball actually work as a spray ball, or will it simply fill the vessel with cleaning fluid until the high-level switch is activated. Based on previous discussions this would be less than 25 seconds from empty to high-level trip point, which doesn’t allow much time for mechanical cleaning action in the gas side of the separator. | 06/23讨论： 分离器内件： 1、气液分离器设计采用重力式分离，无需额外的内件。 2、喷淋球相关事宜，CN团队内部结合喷淋球供应商商议方案。 06/23 Discussion — Separator Internals: 1.The gas-liquid separator is designed as a gravity-type separator; no additional internals are required. 2.Regarding the spray ball matters, the CN team will internally discuss and determine the solution in coordination with the spray ball supplier. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 设计参数 1、“流体性能”是否应定为“非致命性”？我推测此概念类似于PED容器设计中的流体分组，在英国规范中应属于Group 1气体（即可燃/爆炸/有毒），而非“非致命性”。 2、工作压力应为0至6MPaG。 3、设计温度应至少为150°C，并且我假设在泄压事故工况下，容器温度可能达到约300°C。 4、设计压力应为全真空至9MPaG。 5、规范是否要求进行焊后热处理（PWHT）？ 6、水压试验压力应为设计压力的1.5倍，即13.5MPaG，而非12MPaG。 7、对于该容器，S4应为DN32 Cl900 WN法兰。喷淋球接口是否应作为单独细节在本图纸上表示，还是另页图纸表示更为合适？ 8、充装系数（Fulling Factor）是多少？ Design Parameters 1. Should the ‘Fluid Performance’ be Non-Lethal? I assume this is similar to the fluid group for PED vessel design, which for the UK would be Group 1 gas i.e. flammable/explosive/toxic and not Non-Lethal. 2. The working pressure should be 0 to 6MPaG. 3. The design temperature should be at least 150 °C and I assume the vessel has the potential to reach circa 300°C during a relief event. 4. The design pressure should be FV to 9MPaG 5. Is PWHT required by the code. 6. Hydro test pressure should be 1.5x design pressure i.e. 13.5MPaG not 12 MPaG. 7. For the vessel, S4 should be a DN32 Cl900 WN Flange. Should the spray ball fitting be shown as a separate detail on this drawing or possibly shown on a separate drawing. 8. What is the Fulling Factor. | 06/23讨论： 设计参数: 1、介质调整为易爆。 2、CN团队结合URS，修正工作压力，更新设备数据表。 3、可以将泄压事故工况，纳入到常规设计考虑中，即可提高设计温度到300℃。 4、修正设计压力，更新设备数据表。 5、规范可不进行焊后热处理（PWHT）。 6、水压试验压力为设计压力的1.3倍，故试验压力可不做调整。 7、S4为喷淋口，口径为Φ10，DN32法兰接口结构为保证喷淋球可抽出，后续根据喷淋球整体方案做调整，判定是否需要可抽式。 8、充装系数是指物料实际容积与容器全容积之比。 06/23 Discussion — Design Parameters: 1.The medium classification is revised to "explosive." 2.The CN team will revise the working pressure based on the URS and update the equipment data sheet accordingly. 3.The relief event scenario can be incorporated into the normal design considerations — i.e., the design temperature can be raised to 300°C. 4.The design pressure will be revised and the equipment data sheet updated accordingly. 5.PWHT (post-weld heat treatment) is not required per the applicable code. 6.The hydrostatic test pressure is 1.3 × design pressure, so the test pressure does not need to be adjusted. 7.S4 is the spray ball connection, with a bore size of Φ10. The DN32 flange connection is designed to allow the spray ball to be withdrawable. This will be reviewed and adjusted as part of the overall spray ball solution, and a decision will be made on whether a withdrawable type is necessary. 8.The filling factor is defined as the ratio of the actual liquid volume to the total vessel volume. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 通用事项 1、管口方位是否已考虑设备布置的最优化？ 2、在撬装高度限制范围内，容器能否通过重力自由排液至产品收集罐？ 3、在顶部法兰上开孔用于引出管，是否会损害其机械完整性并违反安全规范？是否已重新计算法兰厚度或进行有限元分析（FEA），以确保足够的金属厚度和结构完整性？ 4、液位变送器/液位开关的规格是否已确认？法兰尺寸及位置是否与仪表相匹配？ 5、请更新P&ID，以显示S4正确的管口尺寸。 6、是否有容器设计计算书？技术文件中需要包含设计计算书，并应在FAT（工厂验收测试）时进行核查。 General 1. Does the nozzle orientation allow for optimum equipment layout. 2. Can the vessel free drain into the product collection tank, within the skid height constraints. 3. Does boring a hole in the top flange for the outlet pipe compromise its mechanical integrity and violate safety codes. Have you recalculated the flange thickness/carried out FEA to ensure adequate metal thickness and structural integrity. 4. Has the level transmitter/level switches been agreed – does the flange size/position align with the instruments. 5. Update P&ID to show correct nozzle size for S4. 6. Do you have vessel design calculations. Design calculations will be required in the technical file and should be checked at FAT. | 06/23讨论： 通用事项: 1、管口方位已结合3D撬装布置给定。 2、3D撬装设计已考虑，待3D模型复核时，详细讨论。 3、重新计算法兰厚度，以满足结构强度要求。 4、仪表工程师已经确认复核。 5、P&ID，不需要更改S4管口尺寸。 6、设计计算书是设备完整技术文件中必不可少的一部分，后续会提供。 06/23 Discussion — General Items: 1.Nozzle orientation has been determined based on the 3D skid layout. 2.The 3D skid design has taken this into consideration; detailed discussion will be held during the 3D model review. 3.The flange thickness will be recalculated to meet structural strength requirements. 4.The instrumentation engineer has confirmed and verified this. 5.The P&ID does not require changes to the S4 nozzle size. 6.The design calculation sheet is an essential part of the complete technical documentation for the equipment and will be provided in due course. | YES | Ziliang Zhao/Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Overall cleaning philosophy per vessel 各容器整体清洗策略 Please confirm the intended cleaning philosophy for each vessel in the skid — spray-only, soak-only, spray-and-soak combined, or an alternative approach. Please also indicate whether a single philosophy applies across all vessels or whether the strategy varies by vessel. 请确认撬块内各台容器的清洗策略：单独喷淋、单独浸泡、喷淋+浸泡组合，或其它方式。请同时说明是否所有容器采用同一策略，或按容器区别设计。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：有喷淋球的设备R24-BT01、R24-BT04和R24-SE01采用喷淋循环清洗，其余设备采用浸没循环冲洗 09/07：Equipment R24-BT01, R24-BT04 and R24-SE01 equipped with spray balls shall adopt spray circulation cleaning. The remaining equipment shall use immersion circulation flushing. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleanliness verification method & acceptance criteria 清洁度验证方法与验收标准 Please advise the verification method(s) used to confirm cleaning completion (visual inspection, swab / rinse sample analysis, mass balance, calculated residue, etc.) and the numerical acceptance criteria applied (e.g. residue mass, ppm concentration threshold). 请说明用于确认清洗完成的验证方法（目视检查 / 拭子或冲洗样分析 / 物料衡算 / 残余物计算等），以及所采用的数值验收标准（如残余物质量、浓度阈值 ppm）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：与研发人员讨论后，由于国内外存在差异，建议由SW属地QA提供清洗验证 09/07：After discussion with the R&D team, considering regional differences between China and overseas sites, it is recommended that the local QA team of SW provide cleaning validation. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Sight glass availability for SE01 SE01 视镜配置 The reactor vessels are understood to be fitted with sight glasses to support visual verification of cleanliness. The gas–liquid separator SE01, however, does not include a sight glass. Please confirm the intended method for verifying cleanliness on SE01. 反应柱已配置视镜以支持目视清洁度检查，但气液分离器 SE01 未配置视镜。请确认 SE01 清洁度验证的具体手段（，以及是否考虑将新增视镜作为设计变更纳入）。 | 07/10：反应柱和分离器因为操作压力高，无法配置视镜，清洁度的验证无法依靠目测，需取样分析测量残留物的浓度 07/10：Due to the high operating pressure of the reaction column and separator, sight glasses cannot be installed. Visual inspection is therefore not feasible for cleanliness verification, and residue concentration shall be determined via sampling analysis instead. 08/13：不增加视镜，冯博士已提供国内清洁度验收限度的方法供SW参考。 08/13：Without adding a sight glass, Dr. Feng provided the domestic cleanliness acceptance criteria method for SW's reference. | YES | Xiantao feng/Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Spray ball flow rate vs. vessel fill time 喷淋球流量与容器充液时间的匹配 The lowest available spray ball flow rate (approximately 20 L/min) results in SE01 reaching the high-level trip point in under 25 seconds. This limits the time window in which mechanical spray action can achieve wetting coverage. Please advise the intended cleaning-time window on SE01 and the approach for ensuring adequate mechanical cleaning action within the design constraint. 现有最小可选喷淋球流量约 20 L/min，导致 SE01 容器在 25 秒内即达到高液位跳停，机械喷淋作用的有效时间窗口非常短。请说明 SE01 上预期的清洗时间窗口，以及在此设计约束下如何确保获得充分的机械清洗作用。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：R24-SE01清洗时采用喷淋循环清洗，及一边进液，一边排液，排液管的尺寸能匹配喷淋球的流量，保证清洗时不会达到高液位 09/07：R24-SE01 adopts spray circulation cleaning during cleaning operation, with continuous liquid feed and simultaneous liquid discharge. The drain line size is sized to match the flow rate of the spray balls, ensuring that a high liquid level will not be reached during cleaning. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Drain line sizing and fill–drain cycle 排放管径与充液-排空循环 Under the current drain line configuration, the drain rate is significantly slower than the spray inflow rate. Please advise the intended drain line diameter (whether upsizing is planned), the estimated single-cycle fill and drain durations, and the number of cycles anticipated per cleaning campaign. 当前排放管径下，排放速率显著慢于喷淋进料速率。请说明拟采用的排放管径（是否放大）、单次循环的充液和排空时间估算，以及每次清洗预期需要的循环次数。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：排放管径已放大，详见P&ID。不同物料，清洗循环的次数不同，可根据取样分析的结果确认 09/07：The drain line size has been increased; refer to the P&ID for details. The number of cleaning circulation cycles varies for different materials and can be confirmed based on sampling analysis results. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Soak cleaning vs. high-level interlock defeat mechanism 浸泡清洗与高液位联锁绕过机制 If soak cleaning is adopted on SE01, the liquid level during cleaning will exceed the high-level safety interlock (located at approximately one-third of vessel height). Please specify: (a) the physical mechanism intended for defeating this interlock during cleaning (key switch, procedural lockout, or other); (b) the authorisation and access controls surrounding the defeat mechanism; and (c) the safeguards against inadvertent defeat during normal processing operation. 若 SE01 采用浸泡清洗，清洗过程中的液位将超过位于容器约 1/3 高度的高液位安全联锁。请说明：(a) 清洗时用于绕过（defeat）该联锁的物理机制（钥匙开关 / 程序锁定 / 其它）；(b) 该绕过机制的授权与权限控制方式；(c) 防止正常运行时意外绕过的保护措施。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：R24-SE01清洗时采用喷淋循环清洗，及一边进液，一边排液，排液管的尺寸能匹配喷淋球的流量，保证清洗时不会达到高液位 09/07：R24-SE01 adopts spray circulation cleaning during cleaning operation, with continuous liquid feed and simultaneous liquid discharge. The drain line size is sized to match the flow rate of the spray balls, ensuring that a high liquid level will not be reached during cleaning. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleaning of the guided-wave level transmitter housing Guided wave 液位变送器外壳的清洁 The guided-wave level transmitter housing (approximately 100 mm diameter, side-mounted on SE01) sits above the high-level switch and lies outside the spray ball coverage envelope. Please advise the intended cleaning approach for this housing, and any mechanical or procedural provisions required to ensure it can be cleaned to the acceptance criteria in Q1.2. 液位变送器外壳（约 100 mm 直径，SE01 侧接管上）位于高液位开关之上，不在喷淋球覆盖范围内。请说明该外壳的清洁方案，以及为达到 Q1.2 中的验收标准所需的机械或程序性措施。 | 07/14：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用 07/14：Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. | YES | Chaoqun Hu/Yu Gao
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Reactor cleaning cycle time and manual interventions 反应器清洗循环时间与人工干预 For the 200-L reactor vessels, a single spray-and-drain cycle involves an extended drain phase relative to the spray phase. Multiple cycles are expected to achieve the required cleanliness. Please advise: the anticipated number of cycles, the total cleaning duration per campaign, and the specific manual interventions required at each step (drain valve operation, sample point access, lockout re-set, etc.). 200-L 反应器进行单次"喷淋-排空"循环时，排空阶段远长于喷淋阶段，需多次循环以达到清洁度要求。请说明：预期循环次数、每次清洗总时长，以及各步骤所需的具体人工干预（排放阀操作 / 取样口操作 / 联锁复位等）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：反应器采用浸没循环清洗，清洗进出口的管径为Ф10，可选用10L/min的泵循环冲洗，循环次数和清洗总时长需根据取样分析结果确认 09/07：The reactor adopts immersion circulation cleaning. The inlet and outlet nozzles for cleaning have an outer diameter of 10 mm. A pump with a flow rate of 10 L/min can be used for circulation flushing. The number of circulation cycles and total cleaning duration shall be confirmed based on sampling analysis results. | Pending | Chaoqun Hu
07/01 | SW 3D Layout 3D 布置与设备空间 | Operational access clearance 操作通道净空 The current 3D model shows approximately 300–350 mm clearance in certain operator access zones. Please confirm the target minimum clearance from a site operability and maintenance standpoint, and identify any specific zones where relaxation of the current clearance is acceptable, or where additional clearance is required. 当前 3D 模型显示部分操作人员通道净空约为 300–350 mm。请从现场操作与维护角度，确认目标最小净空要求，并识别可以放宽的具体区域，以及需要额外净空的区域。 | 07/10：建议增加反应柱撬块的宽度，审核模型后给出建议的空间区域。 It is recommended to increase the width of the reaction column skid and provide the suggested spatial area after reviewing the model. 09/08：根据SW最新建议的设备布置方案，减少设备中间通道，加大设备与墙体空间，具体尺寸待3D模型更新后确定。 According to SW's latest recommended equipment layout plan, reduce the middle channels of the equipment and increase the space between the equipment and the wall. The specific dimensions will be determined after the 3D model is updated. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Free-drain feasibility from each vessel 各容器的自重排放可行性 The cleaning strategy relies on free-drain of cleaning fluid from each vessel into downstream collection (BT04 or equivalent). Considering the skid height constraint and each vessel elevation, please confirm the free-drain path is mechanically feasible from each source vessel to its destination. Please identify any vessels where drainage cannot be achieved by gravity and would require pumping or an alternative arrangement. 清洗策略要求清洗液自重从各容器排入下游收集罐（BT04 或等效容器）。考虑撬块高度限制与各容器标高，请确认每台源容器至其目标容器的自重排放路径机械可行。请识别无法通过重力实现排放、需要泵抽或采用替代方案的容器。 | 07/10：根据目前容器的结构形式，反应柱可通过底部排放阀排放，缓冲罐可通过管路排放，预热器、冷凝器管路无排放口。具体排放方式参考清洗方案。 Based on the current structural design of the containers, the reaction column can be drained through the bottom discharge valve, the buffer tank can be discharged via piping, while the preheater and condenser have no discharge outlets in their pipelines.Refer to the cleaning plan for specific emission methods. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Nozzle orientation on pressure vessels 压力容器管嘴方位 Please review the nozzle orientation on all pressure vessels in the current 3D model. Confirm that nozzle positions provide adequate access for external piping tie-in, instrumentation installation, and maintenance (removal / reinstallation of internals, gasket replacement, catalyst service, etc.). 请审查当前 3D 模型中所有压力容器的管嘴方位。确认管嘴位置能够满足外部管路对接、仪表安装以及维护（内构件拆装 / 密封垫更换 / 催化剂检维修等）的空间要求。 | 07/10：由于空间尺寸限制，部分管口的维护可能存在不便。优化管口布置或能否增加设备空间。 Due to space size limitations, maintenance of some pipe openings may be inconvenient. Optimize pipe layout or increase equipment space 09/08：根据SW最新建议的设备布置方案，CIP及排放管口位于撬端面，并采用移动拉撬方案，满足中间设备及管路的维护空间要求。 According to SW's latest recommended equipment layout plan, the CIP and discharge ports are located on the pry end face, and a mobile pry scheme is adopted to meet the maintenance space requirements of intermediate equipment and pipelines. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Catalyst charging & discharging arrangement 催化剂加料与卸料布置 Please confirm that the catalyst charging (loading) and discharging (unloading) arrangement is compatible with the current nozzle layout on the reactor vessels, and that adequate space is provided for charge / discharge equipment and operator access during catalyst service. 请确认催化剂加料与卸料的操作方式与当前反应柱的管嘴布置兼容，且在催化剂检维修期间为加料/卸料设备与操作人员留有充足空间。 | 07/10：根据目前的布置方案，反应柱加料卸料口均在撬体端面，结合加料卸料方式看操作空间是否充足。 According to the current layout plan, the feeding and discharging ports of the reaction column are all located on the end face of the pry body. Considering the feeding and discharging methods, it is necessary to check whether the operating space is sufficient. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Tie-in points between skid and site utilities 撬块与现场公用工程接口 Please confirm the finalised location and specification of all tie-in points between the skid and the Sandwich site services, including process feed, product outlet, vent header, HTF supply and return, N₂ blanketing, instrument air, electrical supply, cable penetrations, and drain. Please advise the interfaces where design lock-down is still pending. 请确认撬块与 Sandwich 现场公用工程之间所有接口的最终位置与规格，包括工艺进料、产品出口、放空总管、导热油供回、氮气钝化、仪表空气、电气供应、电缆穿墙、排放。请说明尚未定稿的接口。 | 07/10：根据现有的布置方案，有部分公用工程的的接口，无仪表空气接口，电气供应、电缆穿墙，后续更新撬块与公用工程接口的位置与规格。 According to the existing layout plan, there are interfaces for some public works without instrument air interfaces, electrical supply, and cable penetration through walls. The location and specifications of the interface between the pry block and the public works will be updated in the future. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Cable wall penetration capacity and cable compatibility 穿墙电缆孔容量与电缆兼容性 The current design indicates 14 available cable wall penetration slots. Please confirm this final count, the internal diameter of each slot, and the compatibility of the slot with the largest cable type intended to pass through (multi-core, armoured, or shielded cables of relevant cross-section). 当前设计显示可用穿墙电缆孔 14 个。请确认该数量的最终定案、每个孔的内径规格，以及与拟穿过的最大电缆类型（相应截面的多芯 / 铠装 / 屏蔽电缆）的兼容性。 | 寻求工程部支持，和宋小旭主管约会讨论如何推进，7月10日反馈进展 | YES | Dezhi meng/Shaofeng gao
07/01 | SW Control Philosophy 控制策略 | Full Control Philosophy document issue date 完整《控制策略》文件发出日期 Please advise the target issue date for the complete Control Philosophy document, superseding the interim draft version previously circulated. 请说明完整版《控制策略》文件的目标发出日期（覆盖此前流转的过渡草稿版本）。 | 07/10：已完成初版，还在校核中，预计下周发出 07/10：The initial draft has been completed and is under review; it is expected to be issued next week. 09/07：控制说明已于08/21发给SW 09/07：The control description was sent to SW on 08/21. | Pending | Chaoqun Hu
07/01 | SW Control Philosophy 控制策略 | Interlock schedule — hardwired vs. software 联锁清单 —— 硬件联锁与软件联锁 Please provide a complete interlock schedule listing all safety interlocks, with clear delineation between hardwired (independent of the PLC) and software (PLC-implemented) interlocks. For each interlock, please include: initiating cause, sensing element, trip setpoint, action taken, and protective function fulfilled. 请提供完整的联锁清单，列出全部安全联锁，明确区分硬件联锁（独立于 PLC）与软件联锁（PLC 实现）。每一条联锁请包含：触发原因、检测元件、跳停设定值、联锁动作、承担的保护功能。 | 07/10：联锁条件已完成初版，还在校核中，预计下周发出 07/10：The initial draft of interlock conditions has been completed and is under review, which is expected to be issued next week. 09/07：联锁表已于08/21发给SW 09/07：The interlocks table was sent to SW on 08/21. | Pending | Chaoqun Hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Operational modes and mode-specific fail positions 操作模式与各模式下的故障位 Please define all operational modes of the skid (normal operation, start-up, shut-down, cleaning, catalyst change, emergency depressurisation, etc.), and for each mode specify: (a) the fail position of each control valve; (b) the state of each interlock (active / bypassed); and (c) the permissive conditions required to enter that mode. 请定义撬块的全部操作模式（正常运行 / 开车 / 停车 / 清洗 / 催化剂更换 / 紧急泄压等），并针对每一模式说明：(a) 每个控制阀的故障位；(b) 每个联锁的状态（激活 / 已绕过）；(c) 进入该模式所需的许可条件。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 分离器浸泡清洗时易触发液位高联锁，导致高液位以上清洗不彻底。增大分离器的排净管径可实现淋洗，同时系统处于清洗模式时，绕开液位高联锁。 High level interlock is prone to tripping during soaking cleaning of the separator, leading to inadequate cleaning of areas above the high liquid level. Increasing the drain pipe size of the separator allows shower rinsing. Meanwhile, the high level interlock can be bypassed when the system is under cleaning mode. 09/22：已于09/21在操作手册中补充，已反馈给CIMT 09/22: Added to the operation manual on 09/21, and feedback has been provided to CIMT | NO | Chaoqun Hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Mode-transition safeguards 操作模式切换的保护措施 Please advise the safeguards in place against inadvertent mode transitions, particularly from cleaning mode back to processing mode (e.g. an interlock bypass being left in place after cleaning is complete). Please describe both the technical safeguards (key switches, HMI confirmations) and the procedural safeguards (SOP requirements, dual sign-off). 请说明防止意外切换操作模式（尤其是从清洗模式返回处理模式时联锁绕过未复位）的保护措施。请分别描述技术性保护措施（钥匙开关 / HMI 确认）与程序性保护措施（SOP 要求 / 双签发）。 | 52条和Keith讨论后1周反馈。 周二上午组会专题讨论：超群+付工。 | NO | Dezhi meng
07/01 | SW Sampler System 取样系统 | Sample vaporisation during pressure reduction 取样过程中的样品闪蒸 The sampler transfers process fluid from a line operating at up to 60 barG to a sample container at approximately atmospheric pressure. Please advise the analysis of vaporisation during this pressure reduction (fraction vaporised, temperature drop) and its impact on the compositional representativeness of the collected sample. 取样器将最高 60 barG 工艺管路的介质转移至常压取样瓶。请说明此压降过程中的闪蒸分析（气化比例、温度降低）及其对所采样品成分代表性的影响。 | 07/10：冷凝器出口的温度为30℃，压力从60barG 泄至常压，此温度条件下不会发生闪蒸 07/10：The temperature at the condenser outlet is 30°C. The pressure is relieved from 60 barG to atmospheric pressure, and no flashing will occur under this temperature condition. | Pending | Chaoqun Hu
07/01 | SW Sampler System 取样系统 | Sample retention design 样品截留设计 Please advise the design of the sample bottle and sample-transfer system, including any vapour trap, septum, condenser, or other retention device intended to prevent loss of volatiles through the vent path and to ensure a representative liquid sample is captured. 请说明取样瓶及取样传输系统的设计，包括为防止挥发组分从放空路径流失、并确保获得代表性液样所采用的蒸汽阱、隔膜、冷凝器或其它截留装置。 | 07/10：取样器的流程：打开三通阀将缓冲罐充满，打开缓冲罐气相放空管线阀门，将缓冲罐中的气相排走并卸压，打开氮气手阀，将缓冲罐中的液体压至取样瓶 07/10：Sampling procedure: Open the three-way valve to fill the buffer drum. Open the valve on the vapor vent line of the buffer drum to vent the vapor inside and relieve pressure. Then open the nitrogen manual valve to pressurize and transfer the liquid from the buffer drum into the sampling bottle. | Pending | Chaoqun Hu
07/01 | SW Sampler System 取样系统 | Sampler behaviour under gas-rich flow regime 气相主导流态下取样器行为 With the intended process operating at a stoichiometric excess of hydrogen, the flow regime through the sampling point may be gas-rich with entrained liquid rather than liquid-continuous. Please advise how the sampler design accommodates this flow regime, and whether any sample point relocation, phase separator, or coalescer is being considered. 工艺预期在化学计量氢气过量条件下运行，取样点处流态可能为"气相夹带液体"而非液相连续。请说明取样器设计如何适应此流态，以及是否考虑取样点位置调整、加装相分离器或聚结器。 | 07/10：取样器的缓冲罐上有气体排放管线，取样罐充满后，打开气体排放管线，将气相排走并卸压，再用氮气将液相压至取样瓶 07/10：The buffer vessel of the sampler is equipped with a gas vent line. Once the sampling tank is full, open the gas vent line to vent the vapor phase and relieve pressure, then push the liquid phase into the sampling bottle with nitrogen. | Pending | Chaoqun Hu
07/01 | SW Instrumentation 仪表配置 | Guided-wave level transmitter — datasheet & cleanability Guided wave 液位变送器 —— 数据单与可清洁性 Please provide the guided-wave level transmitter datasheet and confirm: (a) the process compatibility of the probe assembly with the intended service (including any operating conditions in the supercritical or near-critical regime); and (b) the cleanability of the probe assembly under the adopted cleaning philosophy. 请提供 guided wave 液位变送器数据单，并确认：(a) 探头组件在拟定工况（含超临界或近临界工况）下的适用性；(b) 探头组件在拟采用清洗策略下的可清洁性。 | 7月10日反馈进展 (a) 导波雷达液位计工作原理是雷达波可以穿过介电常数较低的气相，遇到介电常数较大的液相返回，从而计算液位。适用蒸汽、粉尘、泡沫等工况。需了解超临界工况下的介质状态是否还存在液相，如果没有液相空间，则液位计无法识别。 The working principle of the guided-wave radar transmitter is that the radar wave can pass through the gas phase with a lower dielectric constant and return to the liquid phase with a larger dielectric constant, thereby calculating the liquid level. It is applicable to working conditions such as steam, dust and foam. It is necessary to understand whether there is still a liquid phase in the medium state under supercritical conditions. If there is no liquid phase space, the transmitter cannot identify it. 07/15进展：经内部评估，液位计所在容器操作工况下不存在超临界状态。 After internal assessment, it was determined that the liquid level gauge is not in a supercritical state under the operating conditions of the container it is located in. (b)BT01和BT04的导波雷达液位计为顶装内伸形式，可以利用设备内的喷淋头冲洗。SE-01的导波雷达液位计为侧装旁通式，可以选择在探头与旁通管的过程接口处增加配套冲洗环，并预留一路冲洗管线。 The guided-wave radar transmitters of BT01 and BT04 are top-mounted and iInsert type, and can be flushed by the spray heads inside the equipment. The guided-wave radar l transmitter of SE-01 is of side-mounted bypass type. A matching flushing ring can be added at the process interface between the probe and the bypass pipe, and a flushing pipeline can be reserved. 07/14进展：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用. Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. 07/17进展：气液分离器雷达液位计侧装改顶装，已完成图纸设计，筒体直径未变，邮件发出。 The radar level gauge for the gas-liquid separator has been redesigned from side-mounted to top-mounted. The drawing design has been completed, and the vessel diameter remains unchanged. The drawings have been sent out via email. | Pending | Yu gao/Chaoqun Hu/Zilaing Zhao
07/01 | SW Instrumentation 仪表配置 | Level switch position & interlock function 液位开关位置与联锁功能 Please confirm the finalised position (elevation, orientation, flange size and rating) and the interlock function of each level switch (LSL, LSLL, LSH, LSHH) on each vessel, together with the matching instrument selection. 请确认每台容器上各液位开关（低 LSL、低低 LSLL、高 LSH、高高 LSHH）的最终位置（标高、方位、法兰尺寸与压力等级）与联锁功能，以及对应的仪表选型。 | 7月10日反馈进展： 关于液位开关选型，之前寻价时只有VEGA的VEGASWING 63型号可以满足DN25 Class900 M的过程接口，其他厂家如E+H、Rosemount都不能满足。 About the selection of level switches, during the previous price search, only VEGA's VEGASWING 63 model could meet the DN25 Class 900 M process connection requirements. Other manufacturers such as E+H and Rosemount could not meet these requirements. 07/15：联锁值详见联锁条件表。 07/15：The interlock values can be found in the interlock condition table. | Pending | Chaoqun Hu/Yu gao
07/01 | SW Instrumentation 仪表配置 | Instrument datasheet next revision date 仪表数据单下一版本发出日期 Please advise the target issue date for the next revision of the Instrument Datasheet, reflecting the current SE01 design (post demister-configuration decision), the finalised interlock schedule, and the level switch position confirmation. 请说明反映当前 SE01 设计（demister 配置定稿后）、最终联锁清单以及液位开关位置确认的仪表数据单下一修订版本的目标发出日期。 | 7月10日反馈进展 仪表数据表已完成修订版，待意见讨论后看是否还需修改参数。 The instrument datasheet has been revised. After the discussion of opinions, we will see if the parameters still need to be modified. 08/05:根据最新设计温度和压力，更新仪表数据表，08/12发出 08/05:Update the instrument data sheet based on the latest design temperature and pressure, issued on 08/12 | YES | Chaoqun Hu/Yu gao
07/01 | SW Documentation Status 文档状态 | Current revision and next revision date of key deliverables 主要交付文件的当前版本与下一版本时间 Please confirm the current issued revision and the target date for the next revision of the following documents: • PFD • P&ID • URS • Equipment Datasheets • Control Philosophy • Instrument Datasheet • Operating Instructions • Cleaning Procedure • Vessel Design Calculation Package. 请确认以下文档的当前已发版本与下一修订版本的目标日期： · PFD · P&ID · URS · 设备数据单 · 控制策略 · 仪表数据单 · 操作说明 · 清洗程序 · 容器设计计算书。 | 7月10日反馈进展，操作手册还在编制中，其他设计文件已完成。On July 10th, we provided the progress update. The operation manual is still under preparation, while the other design documents have been completed. 08/21：工艺设计文件均已发出。 0821：The process design documents have been issued. | Pending | Shaofeng gao/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R1] Design Temperature — Vessel could fail during relief event. Equipment design temperature is specified for process requirements and does not consider elevated temperatures during relief events when short-term temperature increase has the potential to exceed the design temperature. 设计温度 —— 容器可能在泄放事件中失效。设备设计温度是按工艺需求设定的，未考虑泄放事件中的短时温升可能超过设计温度的情形。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：已更新数据表，提高设计温度，以满足工艺需求，图纸已升级。 07/10: Data sheet updated with elevated design temperature to meet process requirements; drawings revised accordingly. | YES | Chaoqun Hu/Ziliang zhao
07/02 | SW - Risk Register Engineering Design 工程设计 | [R2] Design Requirements — L:G ratio for plant is not clearly defined. Equipment design could result in very limited operating ranges and incorrect assumptions in plant capability and relief design. 设计条件 —— 装置的液气比（L:G ratio）未明确定义。可能导致设备设计的操作区间受限，以及在装置能力和泄放设计中做出错误假设。 | 7月10日反馈进展，根据最终确定的反应器尺寸核实气液比数据。On July 10th, the progress was reported. The gas-liquid ratio data was verified based on the final determined reactor size. 09/07: 根据08/25的会议确认PFD不更新，装置的气液比不改变 09/07: As confirmed in the meeting on 08/25, the PFD will not be updated, and the gas-to-liquid ratio of the unit will remain unchanged. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Engineering Design 工程设计 | [R3] Design Requirements — Catalyst specification is not available. Design may not be suitable for some catalysts. Dusty catalysts could cause blockages. 设计条件 —— 催化剂规格未明确。设计可能不适用于某些催化剂；含粉尘的催化剂可能导致堵塞。 | Keith / SW response: Design philosophy is based on catalyst beads/pellets which are dust-free, non-flammable and have exposure levels requiring OEB 3 or lower containment. Note: OEB 3 containment is a deviation from the URS and requires acceptance. Keith / SW 答复： 设计基于无粉尘、非燃、暴露等级 OEB 3 或更低的颗粒/粒状催化剂。注：OEB 3 的密闭要求相对 URS 存在偏离，需要接受确认。 | NO | SW
07/02 | SW - Risk Register Engineering Design 工程设计 | [R4] Access — Layouts are not available to assess whether access to equipment is acceptable for operations and maintenance. 通道 —— 布置图尚未提供，无法评估设备的操作与维护通道是否满足要求。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.1 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/YES | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R5] Maintenance — Lifting Aids (davit arms, lifting beams, etc.) have not been considered in design, with potential for injury to maintenance personnel removing heavy equipment for servicing / repair / replacement. 维护 —— 设计中尚未考虑起重辅助设施（吊臂、起吊梁等），维护人员在拆卸重型设备进行检修 / 修理 / 更换时可能存在人身伤害风险。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/YES | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R6] Lighting — Layouts are not available to assess whether lighting for routine operations and maintenance activities is acceptable. 照明 —— 布置图尚未提供，无法评估日常操作和维护活动的照明条件是否满足要求。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/YES | NO | UK/All
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R7] System leak detection — Pressure testing of high-pressure system will be hydraulically tested. Hydraulic testing demonstrates mechanical strength of the pressure system but does not demonstrate integrity for a hydrogen system. 系统检漏 —— 高压系统将进行水压试验。水压试验只能证明压力系统的机械强度，无法证明氢气系统的密封完整性。 | Keith / SW response: Helium testing is not routinely carried out in China. Keith / SW 答复： 国内通常不常规进行氦气检漏。 可以做气密性试验；国内整橇系统气密性试验后，分体运至英国，进入工厂房间后，再次组装，需重新进行泄漏试验，现场是否具备试验条件？现场可进行氦气检漏。 和CE认证机构确认一下具体方案。 A pneumatic test can be performed. After the complete skid system undergoes the pneumatic test in China, it will be shipped in split form to the UK. Upon arrival at the factory site and reassembly, a new leak test will be required. We need to confirm whether the site has the necessary conditions/facilities for this test. Helium leak detection is available on site. We will confirm the specific plan with the CE Notified Body. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R8] Line sizing / specification — Vents / headers incorrectly sized / specified, resulting in high back pressure and safety / operability issues, e.g. two-phase flow in emergency vent relief header. 管线规格 / 尺寸 —— 放空 / 泄放总管尺寸或规格不正确，导致背压过高及安全 / 可操作性问题，例如紧急泄放总管中出现两相流。 | 07/10：安全阀进出口尺寸详见P&ID 07/10：Refer to the P&ID for the inlet and outlet sizes of the safety valve. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R9] Insulation — Insulation requirements not specified, which could result in equipment / pipe layout not allowing space for insulation to be installed. 保温 —— 保温需求尚未明确，可能导致设备 / 管路布置未预留保温安装空间。 | Confirm the insulation material with Keith and determine the thickness. Once it's confirmed, provide a progress report on July 10th. 和Keith确认下保温材料，然后确定厚度。确定后，7月10日反馈进展 3D模型中管路的间距已按照保温厚度30-35mm预留了保温的安装空间。 The spacing between pipes in the 3D model has been designed to accommodate an insulation installation gap of 30-35mm, as per the insulation thickness requirements. | YES | Yinghui cheng/Chaoqun Hu/Shuangshuang fan/Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R10] Modular design — Modular design could introduce significant increase in site construction activities, e.g. mechanical and EC&I installation and subsequent testing. 模块化设计 —— 模块化设计可能大幅增加现场施工工作量，例如机械与电控仪表安装及后续测试。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 现有模块化设计的方案是根据进口电梯的尺寸，将整套设备拆分为4个撬块运输组装。 SW建议：需再考虑从屋顶直接吊装进去的方案，需要在后续周三会上进一步讨论。 The current modular design solution involves dividing the entire set of equipment into four skids for transportation and assembly based on the dimensions of imported elevators. SW Recommendation: Further consideration is needed for the direct hoisting-in-from-the-roof solution, which will be discussed in the upcoming Wednesday meeting. 07/29：会上澄清四撬块方案技术可行、屋顶吊装非必选；认证机构评估以 3D 定稿为前提，Keith 下周四返回后进一步确认。 07/29: Clarified that the four-module option is technically feasible and roof removal is not mandatory; the Notified Body assessment requires the finalised 3D layout, to be confirmed further with Keith after he returns next Thursday. 08/05:核实分撬是否与海运有关，和进出口部（公司内）请教下海运的最大尺寸事宜。 08/07：询问进出口部同事，集装箱内部高度有限，同时需要预留固定以及防撞等措施空间，所以橇块高度不要超过2.5m。整橇的话，有一种框架集装箱能放进去，但不密封，暴露在空气中，容易造成腐蚀，不建议采用。同时提醒，整橇运输也要考虑陆运高度限制。 09/08：根据SW最新建议的3撬块布置方案，框架高度不超过2.5m，超出部分管路采取预制加现场重新组装的安装方式。 09/08：According to the latest SW-recommended 3-pile block layout, the frame height shall not exceed 2.5m, with the excess portion of pipelines installed using a pre-fabrication and on-site reassembly method. | Pending | Chaoqun Hu/Shuangshuang fan
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R11] Skid assembled on site could result in CE / UKCA Responsible Person / Authorised Representative in China not being able to issue Declaration of Conformity for Skid Package. 撬块在现场组装可能导致中国境内的 CE / UKCA 负责人 / 授权代表无法为撬块整机签发符合性声明（Declaration of Conformity）。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 与CE认证方沟通确认好细节，特别是认证机构是否需要到UK现场验证，再发证。 We will communicate with the CE Notified Body to confirm all the details, in particular whether the certification body needs to attend the UK site for verification prior to issuing the certificate. 07/29：需以 3D 布置定稿版与 CE 认证机构沟通，评估现场组装后的验证方式、费用与工期。 07/29: The finalised 3D layout is required to engage the CE Notified Body and assess the post-assembly verification route, cost and duration. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R12] Wall penetrations — Layouts and cable schedules not available to confirm space is available for pipe / cable penetrations to / from R23 Module. 穿墙孔 —— 布置图和电缆清单尚未提供，无法确认与 R23 模块之间的管道 / 电缆穿墙位置有足够空间。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.6 | The initial cable schedule of CIMT is not fully aligned with the SW plan. SW has sent SLD, CIMT is verifying design discrepancies and will feed back comparison results, followed by discussions with SW CIMT初版线缆计划与SW计划没有完全匹配，SW已发出单线图，CIMT核对设计差异，返回对比结果，再与SW讨论。 7/23：CIMT根据SW提供的单线图，更新了电缆数量。部分流量控制器电缆待确认。硬联锁开关阀点位本安/隔爆待确认。 7/23：CIMT update the cable quantity based on the SLD provided by SW. some cables are still pending confirmed, 1. for flow controllers(modbus or 4-20mA). 2. for HW interlock on-off valve(I.S. or Ex d) 09/15：电缆数量已初步确认。因控制柜分撬，重新计算电缆数量。更新后电缆数量较多，待item135 确认后，继续确认此条目： The cable quantity has been preliminarily confirmed. Since the control cabinet is split across multiple skids, the cable quantity has been recalculated. The updated quantity is significantly larger; final confirmation of this item will proceed after item 135 is confirmed | NO | Dezhi meng
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R13] Catalyst charge point — Inlet pipe diameter is small and blockages may occur. 加料口 —— 加料管径较小，可能发生堵塞。 | Keith / SW response: Inlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking inlet pipe. Keith / SW 答复： 加料接口已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞加料管的风险。 | YES
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R14] Catalyst physical property requirements (size, shape, packing, etc.) are not defined, with the potential for incompatible catalyst to be charged to the reactors. 催化剂物性要求（粒径、形状、装填密度等）尚未定义，存在向反应器加入不兼容催化剂的风险。 | 07/10：催化剂直径0.5mm-5mm，形状不重要，球形，圆柱形，不规则颗粒状都可以，装填密度一般0.5g/mL来估算，但催化剂强度要高，不容易破碎起粉 07/10：The catalyst particle diameter ranges from 0.5 mm to 5 mm, with no specific shape requirement; spherical, cylindrical and irregular granular forms are all acceptable. The bulk density can be estimated at 0.5 g/mL in general. Meanwhile, the catalyst shall feature high mechanical strength to avoid fragmentation and dust generation. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R15] Packing of catalyst is not controlled, with the risk of reactants / gas channelling in the continuous reactor column, and the potential for incomplete reaction or impurities forming. 催化剂装填未受控，存在反应物 / 气体在连续反应柱内形成沟流的风险，可能导致反应不完全或杂质产生。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R16] Contained charge system design not available to assess risks and / or design limitation. 密闭加料系统的设计尚未提供，无法评估其风险与设计局限。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R17] Manual handling requirements for catalyst charging not assessed. 催化剂加料的人工搬运需求尚未评估。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R18] Access to charge point and support of charge container / bag not designed (access steps / integrated support shelf). 加料口的通道以及加料容器 / 料袋的支撑尚未设计（例如操作台阶、集成支撑架）。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R19] 20-micron catalyst retaining screen — Screen blockages prevent / limit flow of gas / reaction mix to continuous reactors. 20 微米催化剂拦截筛 —— 拦截筛堵塞会阻止 / 限制气体 / 反应液流入连续反应器。 | Keith / SW response: China Operations have reported blockages occur in local plant and screen has been removed and discarded. Keith / SW 答复： 国内运行反馈已在本地装置中发生堵塞，已将拦截筛拆除并弃用。 | YES
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R20] Polishing filter (FTR9832) — Filter blockages prevent / limit flow of gas / reaction mix through continuous reactors. Pressure increases in reactor system, with potential for undesirable reactions to occur, until reactor high-pressure trip is activated. 精滤器 (FTR9832) —— 滤芯堵塞会阻止 / 限制气体 / 反应液流经连续反应器；反应器压力升高，直到触发高压跳停前可能发生副反应。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 待定/To be determined 08/06:精滤器堵塞，加旁通，清洗时打开旁通，方便卸压 08/06: Fine filter clogged; bypass added. Open the bypass during cleaning to facilitate pressure release. | YES | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register CR01 – CR03 Reactors CR01 – CR03 反应器 | [R21] Temperature control — Jacket temperature control is configured to control jacket temperature only. Reactor internal temperatures are monitored, but no control, alarms or interlocks are configured for process control. 温度控制 —— 夹套温度仅控制夹套温度本身。反应器内部温度虽被监测，但未针对工艺过程配置控制、报警或联锁。 | Keith / SW response: Scale-up provides large operating envelopes for process temperature requirements and additional control, alarms and interlocks are not required. Keith / SW 答复： 由于放大试验提供了较大的工艺温度操作裕度，无需增加额外的控制、报警或联锁。 | YES
07/02 | SW - Risk Register System Pressure Monitoring 系统压力监测 | [R22] Differential pressure monitoring — Accuracy of static pressure measurements may not enable differential pressures to be calculated with any degree of accuracy or certainty. 差压监测 —— 静态压力测量精度可能不足以支持差压计算达到所需的精度或置信度。 | 通过反应柱上和反应器进出口管线上的的压力变送器精度估算，最大差压误差大约为40kPa。 Based on the accuracy estimation of the pressure transmitters on the reaction column and the inlet/outlet pipelines of the reactor, the maximum differential pressure error is approximately 40kPa. 07/14压力也增加了联锁。The pressure also increased the interlock. | YES | Chaoqun Hu/Yu gao
07/02 | SW - Risk Register Over Pressure Protection 过压保护 | [R23] Relief system design — Pressure systems not identified and relief studies not available. Identification of worst-case relief scenario not identified, and relief streams may be incorrectly categorised. Details of maximum reaction exotherm not fully documented. 泄放系统设计 —— 压力系统尚未识别、泄放研究尚未提供。最坏工况泄放情景未识别，泄放物流可能被错误归类。反应最大放热的详细信息尚未完整记录。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：详见安全阀计算书 07/10：See safety valve calculation sheet for details. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Separator 气液分离器 | [R24] Vessel design — Complete degassing of product stream not achieved, with the potential for hydrogen carry-over into BT04 and product transfer containers. 容器设计 —— 产品物流未实现完全脱气，H₂ 可能带入 BT04 及产品转运容器。 | 07/10：气液分离器满足气液分离的要求 07/10：The gas-liquid separator meets the requirements for gas-liquid separation. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Separator 气液分离器 | [R25] Cleaning of separator not fully understood but current concept relies on vessel free-draining to BT04. Current spray ball sizing is not consistent with this approach and may require significant rework to process piping. 分离器清洗方案尚未完全明确，当前概念依赖容器向 BT04 的自重排放。现有喷淋球规格与该思路不匹配，可能需要对工艺管路进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.4,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：R24-SE01采用喷淋循环冲洗，增加了DN15的排净口，不依赖R24-BT04的重力排放 09/07：R24-SE01 adopts spray circulation flushing. A DN15 drain port has been added so that gravity drainage from R24-BT04 is no longer required. | Pending | Chaoqun Hu/Ziliang zhao
07/02 | SW - Risk Register Separator 气液分离器 | [R26] Cleaning of LIT003 housing does not appear to be considered in design. LIT003 液位变送器外壳的清洗在设计中似乎尚未考虑。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.7 | 同上42行回复/Translation of the 42nd line above. | YES | Chaoqun Hu
07/02 | SW - Risk Register Separator 气液分离器 | [R27] P&ID does not clearly show nozzle locations and could lead to mal-ops / misunderstanding of the design intent by the Operations team. P&ID 上未清晰标注管嘴位置，可能导致运行团队误操作或误解设计意图。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.3 | 07/10：已标注，详见P&ID 07/10：Marked as indicated; refer to the P&ID for details. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Sampling 取样系统 | [R28] Sampler design — When depressurising the sample collection chamber, high gas or vapour vent rates could result in a bubbly or churn-turbulent flow regime, and sample will discharge to vent line as two-phase flow. 取样器设计 —— 对取样收集腔进行减压时，气体或蒸汽的高排放速率可能形成鼓泡或搅动湍流流态，样品将以两相流形式排入放空管。 Related Outstanding Questions ｜ 关联待澄清问题：Q5.1 | 07/10：缓冲罐静置一定时间，让气液分层，泄压时缓慢打开手阀 07/10：Allow the buffer tank to stand for a certain period for vapor-liquid stratification, then open the manual valve slowly during depressurization. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Sampling 取样系统 | [R29] With significantly more gas being present in the process stream, what will prevent overpressure of sample bottle and low-pressure nitrogen pipework? 由于工艺物流中气体明显较多，采用什么措施来防止取样瓶和低压氮气管路的超压？ | 07/10：取样瓶和氮气管线投用时，系统已泄压至常压 07/10：The system has been depressurized to atmospheric pressure prior to commissioning of sampling bottles and nitrogen pipelines. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R30] Catalyst Discharge Plug valve — Outlet pipe diameter is small and blockages may occur. 催化剂卸料闸阀 —— 出口管径较小，可能发生堵塞。 | Keith / SW response: Outlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking outlet pipe. Keith / SW 答复： 出口接管已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞出口管的风险。 | YES
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R31] Contained discharge system design not available. Layout design may not provide sufficient headroom for contained discharge system. 密闭卸料系统的设计尚未提供。当前布置可能无法为密闭卸料系统提供足够的顶部空间。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R32] Complete removal of catalyst during discharging operations is unlikely to remove 100% of the material, with the risk of cross contamination of catalyst material between campaigns. 卸料操作难以完全（100%）清除催化剂，存在批次间催化剂交叉污染的风险。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Cleaning 清洗 | [R33] CIP Design — CIP design incomplete. Initial spray ball sizing is inconsistent with process line sizing approach and may require significant rework to process piping and/or equipment layout. CIP 设计 —— 就地清洗设计不完整。初步喷淋球规格与工艺管路选型方式不匹配，可能需对工艺管路和 / 或设备布置进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.1,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：配置喷淋球的设备，喷淋球的流量与排放管径匹配，采用喷淋循环冲洗 09/07：Equipment fitted with spray balls shall have spray ball flow rate matched to the drain line size for spray circulation flushing. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Cleaning 清洗 | [R34] Cleaning carried out at nominally atmospheric pressure with the risk of material being trapped between flanges, which tend to separate slightly during high-pressure operation, and could lead to cross contamination between batches. 清洗在近常压下进行，高压运行时法兰会出现微量分开，可能将物料残留于法兰间隙中，进而导致批次间交叉污染。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 09/07：法兰密封面擦拭取样，定期开盖检查清洁状况 09/07：Swab sampling of flange sealing faces and periodic vessel opening inspection for cleanliness. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Cleaning 清洗 | [R35] Validation / Verification — Cleaning validation / verification philosophy not available. QA may not accept that the continuous reactor achieves minimum cleaning standards. 验证 / 确认 —— 清洗验证 / 确认策略尚未提供。质量保证部门可能不接受连续反应器满足最低清洗标准。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.2,Q1.9 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 更新清洗方案后讨论/Discuss after updating the cleaning procedure. 09/07：与研发人员讨论后，由于国内外存在差异，建议由SW属地QA提供清洗验证 09/07：After discussion with the R&D team, considering regional differences between China and overseas sites, it is recommended that the local QA team of SW provide cleaning validation. | Pending | Chaoqun Hu/Xiantao Feng
07/02 | SW - Risk Register Cleaning 清洗 | [R36] Layout — Layouts are not available to evaluate the impact of bypasses, dead legs, drains, vents, etc. 布置 —— 布置图尚未提供，无法评估旁路、死管、排放、放空等的影响。 | 09/08：3D模型确定后推进。 09/08：After the 3D model is finalized, proceed with the advancement. | NO | Shuangshuang fan
07/02 | SW - Risk Register Cleaning 清洗 | [R37] Layout — Layouts are not available to evaluate access to equipment for visual inspections, which may impact the effectiveness of critical inspections. 布置 —— 布置图尚未提供，无法评估设备的目视检查通道，可能影响关键检查的有效性。 | 09/08：3D模型确定后推进。 09/08：After the 3D model is finalized, proceed with the advancement. | NO | Shuangshuang fan
07/02 | SW - Risk Register Cleaning 清洗 | [R38] Layout — Equipment design / layout does not allow for routine disassembly and manual cleaning. Equipment turnaround times and operating costs would be adversely impacted if CIP system cannot be validated. 布置 —— 设备设计 / 布置未考虑日常拆装和人工清洗。如 CIP 系统无法通过验证，设备周转时间和运行成本都会受到不利影响。 | 09/08：3D模型确定后推进。 09/08：After the 3D model is finalized, proceed with the advancement. | NO | Ziliang zhao
07/02 | SW - Risk Register FT001 FT001 流量计 | [R39] Liquid Stream Flow Sensor for flow control loop FIC001. FT001 is a Coriolis mass flow meter installed downstream of the metering pump MP01. Pulsed flow from the pump will impact on the flow measurement and accurate flow control may not be possible. 液相流量传感器（用于 FIC001 流控回路）—— FT001 是安装在计量泵 MP01 下游的科里奥利质量流量计。泵的脉冲流会影响流量测量，可能无法实现精确流量控制。 | Keith / SW response: China Team have previously used this configuration and not experienced flow control issues. No further action required. Keith / SW 答复： 国内团队此前采用过该配置，未出现流控问题。无需进一步动作。 | YES
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R40] Maximum flow may exceed separator design limitations and carry hydrogen over into BT04 / product collection containers. 泵的最大流量可能超出分离器的设计上限，将 H₂ 带入 BT04 / 产品收集容器。 | 07/10：分离器的直径足够大，泵为最大流量时能满足分离要求 07/10：The separator has a sufficiently large diameter to meet separation requirements even when the pump operates at maximum flow rate. | Pending | Chaoqun Hu
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R41] Pump turndown does not meet URS minimum flow requirements. 泵的调节比无法满足 URS 中规定的最低流量要求。 | 07/10：机泵条件中规定了泵的最小流量要求，待泵厂家返回资料时审查是否满足最低流量要求 07/10：Minimum flow requirements for pumps are specified in pump data sheets. Compliance with the minimum flow criteria shall be verified upon receipt of vendor documentation. 08/05：根据最新机泵数据单走采购流程询问厂家资料 08/05：Proceed with the procurement process and request vendor documentation based on the latest pump data sheet. | NO | Chaoqun Hu
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R42] Hydrogen gas flow controller — Flow controller does not support tight shut-off and system pressure increase during hold periods. 氢气流量控制器 —— 控制器不支持严密关断，系统在保压期间压力会持续上升。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller to provide tight shut-off. Keith / SW 答复： 在控制器下游追加一台切断阀以提供严密关断。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R43] Maximum flow through controller may exceed separator design limitations and carry liquid into the vent line. 流经控制器的最大流量可能超出分离器设计上限，将液体带入放空管。 | Keith / SW response: High level interlock installed in the separator to stop gas supply and close PIC028 shut-off valve (CV08). Keith / SW 答复： 在分离器上设置高液位联锁，停 H₂ 供给并关闭 PIC028 的切断阀（CV08）。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R44] Time required for pressure testing the system and nitrogen inertion may be excessively high. 系统加压试验及氮气钝化所需时间可能过长。 | Keith / SW response: Pressure test / inertion times to be evaluated during FIC003 selection. Manual vent installed on BT03 to reduce depressurisation times via FIC003. Keith / SW 答复： 在 FIC003 选型时评估压力试验 / 惰化时间。在 BT03 上加装人工放空阀，缩短经 FIC003 的减压时间。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R45] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端的差压超出厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register LIC003 LIC003 分离器液位 | [R46] SE01 Separator Level Indicator — Cleaning / decontamination of housing is not possible. Residual product in housing could lead to cross contamination between campaigns. SE01 分离器液位指示 —— 变送器外壳无法进行清洗 / 净化。外壳内的残留物料可能导致批次间交叉污染。 | Keith / SW response: Design relies on dissolution of residual material. 100% flood-fill of housing is not possible, therefore any residual trace contamination in the housing is deemed to be small and will not significantly impact cleaning verification. Keith / SW 答复： 设计依赖残余物料的溶解。外壳无法 100% 灌满，因此外壳内任何残余痕量污染被视为很小，不会显著影响清洗验证。 | YES
07/02 | SW - Risk Register FIC004 FIC004 分离器液位控制 | [R47] Separator outlet flow / level control — Differential pressure across the controller exceeds manufacturer's recommendations and controller capability. 分离器出口流量 / 液位控制 —— 控制器两端差压超出厂家建议范围及控制器能力。 | 分离器出口先通过减压阀减到0.2MpaG左右，可以满足厂家建议的差压范围 The outlet of the separator is first reduced to approximately 0.2MpaG through a pressure reducing valve, which can meet the differential pressure range recommended by the manufacturer | Pending | Chaoqun Hu/Yu gao
07/02 | SW - Risk Register FIC005 FIC005 BT01 氮气吹扫 | [R48] BT01 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT01 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register FIC007 FIC007 BT04 氮气吹扫 | [R49] BT04 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R50] System back pressure controller — The back pressure controller does not support tight shut-off during hold periods and system pressure will not be maintained. 系统背压控制器 —— 该控制器在保压期间不支持严密关断，系统压力无法保持。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller. Keith / SW 答复： 在该控制器下游追加一台切断阀。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R51] Time required for depressurising the system following pressure testing and nitrogen inertion may be excessively high. 加压试验和氮气钝化之后系统减压所需时间可能过长。 | Keith / SW response: Manual bypass installed around PIC028 controller. Keith / SW 答复： 在 PIC028 控制器周围加装人工旁路。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R52] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端差压超出厂家建议范围，可能导致控制器无法正常工作。 | 07/10：关于背压阀028，之前Bronkhorst的电子压力阀厂家计算反馈的阀前背压范围最大为0.9~6MpaG，范围量程比不能过大。 07/10：About the back pressure valve 028, previously, the manufacturer of Bronkhorst’s electronic pressure valve calculated and reported that the maximum range of the back pressure before the valve was 0.9 to 6MpaG, and the range-to-range ratio cannot be too large. 09/07: 关于气液分离器设计温度改为270℃后，与Bronkhorst电子背压阀厂家进行沟通，厂家反馈270℃的温度可能会很快损坏电子元件导致无法使用，厂家推荐的工作温度最高是50℃，短时间能承受100~120℃左右。然后又咨询了一些耐高温的气动调节阀厂家，反馈背压的范围过大且流量偏小，选不出合适的阀门CV值。 会上确认还用该电子背压阀，270℃泄放工况很少出现，当270℃时背压阀不会外漏，电子元件损坏可以接收，将选择耐高温的密封材质。 09/07: After the design temperature of the gas-liquid separator was changed to 270℃, we communicated with the Bronkhorst electronic back pressure valve manufacturer. The manufacturer reported that a temperature of 270℃ might quickly damage the electronic components and make it unusable. The manufacturer recommended a maximum working temperature of 50℃, and it can withstand around 100 to 120℃ for a short period of time. Then, we consulted some manufacturers of high-temperature resistant pneumatic control valves. The feedback was that the range of back pressure was too large and the flow rate was too small, making it impossible to select a suitable CV value for the valve. It was confirmed at the meeting that the electronic back pressure valve would still be used. The 270℃ discharge condition rarely occurs. When the temperature is 270℃, the back pressure valve will not leak out. The damage of electronic components can be accepted. High-temperature resistant sealing materials will be selected. | YES | Chaoqun Hu/Yu gao
07/02 | SW - Risk Register PIC030 PIC030 分离器液相出口减压 | [R53] Separator liquid outlet pressure reducer — Is this confirmed as a Bronkhorst pressure controller, or is a mechanical regulator still an option? Does this provide the required independence assumed in the relevant SIL / risk assessments? 分离器液相出口减压器 —— 该阀是否确认为 Bronkhorst 电子压力控制器？还是仍可能选用机械式减压阀？该配置能否提供相关 SIL / 风险评估中假设所需的独立性？ | 目前选型机械式减压阀。机械阀不是电子设备，没有相关的SIL认证。 At present, mechanical pressure reducing valves are being selected. Mechanical valves are not electronic devices and do not have the relevant SIL certification. | Pending | Chaoqun Hu/Yu gao
07/02 | SW - Risk Register PIC049 PIC049 BT04 背压控制 | [R54] BT04 back pressure controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 背压控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register Automation 自动化 | [R55] Automation Build — Philosophy and Design documentation not available to assess risks and limitations. 自动化建设 —— 自动化策略与设计文档尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q3.1,Q3.2 | 专题沟通后确定反馈 09/07：控制说明和联锁表已于08/21发给SW 09/07：The control description and interlocks table were sent to SW on 08/21. | Pending | Chaoqun Hu/Dezhi meng/Ziliang zhao
07/02 | SW - Risk Register Documentation 文档 | [R56] Technical File — Technical File not available to assess risks and limitations. 技术文件 —— 技术文件尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.5,Q7.1 | SW现场3D等事项确定后陆续提供。 At the SW site, final design files will be provided sequentially after the 3D models and other topics have been confirmed. | NO | Shaofeng gao/All
07/02 | SW - Risk Register Documentation 文档 | [R57] O&M Manual — O&M manual not available to assess risks and limitations. 操作维护手册 —— O&M 手册尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q7.1 | 07/10：操作手册的编制还在进行中 07/10：Preparation of the operation manual is still in progress. 07/29：操作维护手册预计 8 月中完成。 07/29: The O&M manual is scheduled for completion in mid-August. 09/07：操作手册已于08/21发给SW 09/07：The operating manual was sent to SW on 08/21. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Documentation 文档 | [R58] Emissions Calculations — Calculations to demonstrate expected release of Class A and Class B VOCs to atmosphere are not available. These are required to demonstrate compliance with EA Permit limits. 排放量计算 —— 尚未提供证明 A 类和 B 类 VOC 向大气排放的预期计算。该计算是证明满足 EA 许可（英国环境署许可）限值要求所必需。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW负责排放量计算/SW is responsible for emissions calculation. | YES | Chaoqun Hu
07/02 | SW - Risk Register Regulatory Compliance 法规合规 | [R59] CE ¦ Functional Safety ¦ DSEAR / ATEX ¦ PSSR ¦ COSHH ¦ PUWER (Access, manual handling) ¦ Working at Height (Access Steps / Support Shelf) ¦ LOLER (Davit arms) ¦ Lighting ¦ Occupational Hygiene ¦ EA Permit — Regulatory non-conformance would prevent beneficial use of equipment in the UK. CE 认证 ¦ 功能安全 ¦ DSEAR / ATEX 防爆 ¦ PSSR 压力系统安全 ¦ COSHH 危害物质 ¦ PUWER 工作设备（含通道与人工搬运）¦ 高处作业（操作台阶 / 支撑架）¦ LOLER 起重设备（吊臂）¦ 照明 ¦ 职业卫生 ¦ EA 环境许可 —— 任何法规合规缺失都会导致设备无法在英国正常投入使用。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW内部的提醒事项。 CFCT核实加料步梯是否包含在内。 SW提供步梯平台尺寸。 Internal reminders for SW: CFCT to verify whether the feeding staircase is included. SW to provide dimensions of staircase and platform. 09/15 SW requires TJ to provide the following 3 heights: 1) flange height to the output 2) flang height to the catalyst charging valve 3) flang height to the top of cage 09/21 Keith发邮件，SW已将STEP格式转换成PDF，并已标注平台所需尺寸。 09/22 和SW确认：平台由SW设计，另外有无其他需要的尺寸。 | NO | Zilang zhao/All
07/14 |  | 根据生产经验，研发建议原R24-CR01的直径由DN80改为DN50，导致产能下降，可能无法满足URS中的产能30kg/day Based on production experience, the R&D team proposes reducing the diameter of the original R24-CR01 from DN80 to DN50. This modification will result in lower production capacity, which may fail to meet the 30 kg/day throughput specified in the URS. | 07/14：周三会上确定/To be confirmed at Wednesday's meeting. 07/15：暂定R24-CR01的直径修改为DN65，等9月份研发提供DN65的反应器实验数据后最终确认反应器的尺寸为DN65或DN50 07/15：It is tentatively agreed to revise the diameter of R24-CR01 to DN65. The reactor size (either DN65 or DN50) will be finalized after the R&D department provides DN65 reactor test data in September. 07/29：会上确定按 DN65 / DN50 两套方案并行准备，并建立变更影响日志；待 9 月研发 DN65 实验数据后最终定案。 07/29: Agreed to prepare the DN65 and DN50 cases in parallel and to set up a change-impact log; final decision after the September DN65 R&D test data. | NO | Xiantao Feng/All
07/23 | SW | 气液分离器SE01容器承受从常压到60 barg的压力循环次数？ How many pressure cycles does the gas-liquid separator SE01 vessel undergo from atmospheric pressure to 60 barg? | 07/23:会上讨论了加氢装置的操作周期，意见存在不一致，关于连续加氢的年运行周期，SW内部沟通后反馈循环次数需求。 气液分离器的设计温度调整到270℃，对应设计压力调整到7.5MPaG。垫片选用金属环垫片。 07/23：The operating cycle of the hydrogenation unit was discussed at the meeting, and divergent opinions remain. SW shall coordinate internally and provide feedback on the required number of cycles regarding the annual operating cycle for continuous hydrogenation. The design temperature of the gas-liquid separator shall be revised to 270°C, with the corresponding design pressure adjusted to 7.5 MPaG. Metallic ring gaskets shall be adopted . 08/06：垫片材质？原料酸性 PEEK，再寻找合适的垫片，讨论。 09/07：管法兰与金属环垫片均可选316L，但需要做技术要求：①金属环垫片硬度≤150HB，管法兰硬度≥160HB；②以上材料需有硬度检测报告；③到厂后复验；④组装前按硬度差≥10HB配对使用。 09/07：Both the pipe flanges and the metal ring gaskets may be made of 316L. However, the following technical requirements shall be complied with: ①The hardness of the metal ring gasket shall be ≤ 150 HB, and the hardness of the pipe flange shall be ≥ 160 HB. ②Hardness test reports shall be provided for all the above materials. ③The materials shall be re-inspected upon arrival at site. ④Prior to assembly, the flange and gasket shall be paired based on a hardness difference of ≥ 10 HB (i.e., the flange hardness shall be at least 10 HB higher than that of the gasket). | YES | Zilang zhao/Chaoqun Hu
07/23 | IEPE | P&ID中压力表无根部阀，是否需要增加根部阀？ Pressure gauges shown on the P&ID are not equipped with root valves. Is it necessary to add root valves? | 07/23:按照现有P&ID配置。 07/23：Configure in accordance with the existing P&ID. | YES | Chaoqun Hu/Yu gao
07/23 | IEPE | PCV028侯径小，反应系统卸压时，全开PCV028卸压速度也很慢，建议将PCV028的旁通手阀改为开关阀 PCV028 has a small orifice. When depressurizing the reaction system, the depressurization rate remains low even if PCV028 is fully open. It is recommended to change the bypass manual valve of PCV028 to an on-off valve. | 07/23:按照现有P&ID配置。 07/23：Configure in accordance with the existing P&ID. | YES | Chaoqun Hu
07/29 | SW | 针对 R24-CR01 直径变更（DN80→DN65/DN50），建立变更影响日志/清单，逐项列出受影响的设备、仪表、管线、安全阀及相关文件与参数，确保无遗漏。 Establish a change log / impact list for the R24-CR01 diameter change (DN80→DN65/DN50), itemising every affected item of equipment, instrumentation, piping, relief device and the related documents and parameters, so that nothing is missed. | 07/29：会上同意建立变更影响日志，由国内团队逐项梳理受影响范围并跟踪关闭。 07/29: Agreed at the meeting to create a change-impact log; the China team will work through the affected scope item by item and track it to closure. 09/07:变更清单已整理完成，根据08/25的会议确认PFD不更新，目前只有反应器的设备数据表需要变更 09/07: The change list has been finalized. Based on the meeting on 08/25, it was confirmed that PFD will not be updated; currently, only the equipment data sheet for the reactor has changed. | NO | Shaofeng Gao/Chaoqun Hu
07/29 | SW | 反应器 DN65 与 DN50 两种规格并行准备设计方案：先确定处理量，再分别出 PFD 与物料平衡；并核实仪表选型、安全阀/泄放组合是否需相应调整。待 9 月研发提供 DN65 实验数据后定案。 Prepare two parallel design cases for the DN65 and DN50 reactor: fix the throughput first, then issue a PFD and mass balance for each, and verify whether instrument selection and the relief-valve combination need to change accordingly. To be finalised once R&D provides the DN65 test data in September. | 07/29：会上确定按 DN65 / DN50 两套方案并行准备，使 9 月数据到位后可直接定案，不影响整体进度。 07/29: Agreed to progress both the DN65 and DN50 cases in parallel so that the decision can be taken as soon as the September data is available, without affecting the overall schedule. 0914：和研发沟通DN50反应器尺寸，更新设备数据单。 0914: Communicate with the R&D department regarding the size of the DN50 reactor and update the equipment data sheet. | NO | Shaofeng Gao/Chaoqun Hu/Xiantao Feng
07/29 | IEPE | 容器设计压力由 80 barg 调整为 75 barg，以保持法兰等级 CLASS 900、避免材料选型受限；需在设备数据表、图纸及相关计算书中同步更新落实。 Vessel design pressure revised from 80 barg to 75 barg in order to retain the CLASS 900 flange rating and avoid limitations on material selection; to be updated consistently in the equipment datasheets, drawings and supporting calculations. | 07/29：周二与 Keith 讨论已取得初步一致，继续推进并在各设计文件中落实。 07/29: Initial agreement reached with Keith on Tuesday; to be carried forward and reflected in the design documents. 08/12：设备数据单已更新完成 08/12：The equipment data sheet has been updated. | YES | Chaoqun Hu/Ziliang Zhao
07/29 | SW | 四撬块分体运输 vs 屋顶整体吊装的决策路径：国内先完成 3D 布置定稿，再以定稿版与 CE 认证机构评估现场组装后的验证方式、费用与工期；Keith 下周四返回后确认四撬块方案可行性；SW 侧评估屋顶更换的费用、工期及 R23 停用影响。 Decision path for four-module split shipment vs a whole-unit lift through the roof: the China team to finalise the 3D layout first, then use the finalised version to evaluate with the CE Notified Body the post-assembly verification route, cost and duration; confirm the four-module option with Keith after he returns next Thursday; SW to assess the roof-replacement cost, duration and the impact of taking R23 out of service. | 07/29：会上提议需要澄清四撬块方案技术上可行，屋顶吊装并非必选项；认证机构评估需以 3D 定稿为前提，国内加快 3D 定稿以尽早取得费用与工期结论。 07/29: Clarified at the meeting that the four-module option is technically feasible and roof removal is not mandatory. The Notified Body assessment depends on the finalised 3D layout, so the China team will accelerate finalisation to obtain the cost and schedule answer as early as possible. | NO | Ziliang Zhao/Shaofeng Gao/Keith
07/29 | SW | 明确下阶段（建造 / FAT）文件的编制与签发流程：由谁编制、由谁签发；SW 场地有自有的 FAT / 验证模板。CE 认证方参与文件评审但不参与签发。约定后续安排专题讨论。 Define the preparation and sign-off process for the next-stage (construction / FAT) documentation — who prepares and who signs off. The SW site has its own FAT / validation template. The CE Notified Body will take part in document review but not in sign-off. A dedicated follow-up discussion to be arranged. | 07/29：双方同意尽早对比两侧模板并识别差异；倾向直接采用 UK 模板以便英国侧验证与确认，国内按该模板提供资料，避免后期返工。 07/29: Both sides agreed to compare the two templates early and identify any gaps; the preference is to adopt the UK template so that verification and validation on the UK side is straightforward, with the China team supplying information to that template to avoid rework later. | NO | Shaofeng Gao/Ziliang Zhao
07/29 | IEPE | 请 SW / Keith 提供英国现场验证（validation）所需的信息清单与模板，国内据此提供资料并按该模板执行，以便尽早识别中英双方要求差异。 SW / Keith to provide the list of information required for the UK site verification / validation process, together with the template, so that the China team can supply the information and work to that template and any differences between the UK and China requirements are identified early. | 07/29：会上确定由 SW 提供模板与信息需求清单，国内提供文件 / 信息并按模板填写；下周与 Keith 沟通落实。 07/29: Agreed that SW will provide the template and the information requirement list; the China team will supply the documents / information and complete them to that template. To be taken forward with Keith next week. | NO | Keith/Shaofeng Gao
07/29 | SW | HAZOP 前须与 Keith 就 3D 布置与控制说明（含操作手册）达成一致 —— 该两项目前仅国内内部讨论过，是余下唯二可能引发重大设计变更的环节，须在 HAZOP 前关闭，以确保 HAZOP 只做一次、避免重做。 The 3D layout and the control philosophy (including the operating manual) must be agreed with Keith before HAZOP. These two items have so far only been reviewed internally by the China team and are the only remaining items that could still trigger a significant design change; they must be closed out beforehand so that HAZOP is run once only and does not have to be repeated. | 07/29：会上确认目标为「HAZOP 只做一次」；两项在 9 月初 HAZOP 前与 Keith 讨论定稿。 07/29: The meeting confirmed the objective of running HAZOP only once; both items to be discussed and finalised with Keith ahead of the early September HAZOP. | NO | All
08/25 | IEPE | 反应柱 R24-CR01 直径变更（DN80→DN65/DN50），产能改变，进料量可能会调整，是否需要修改PFD？ The diameter of the reaction column R24-CR01 has been changed (from DN80 to DN65/DN50), resulting in a change in production capacity. The feed volume may need to be adjusted. Is it necessary to modify the PFD? | 08/25：反应柱 R24-CR01 直径变更（DN80→DN65/DN50），跟研发和Keith沟通后确认：流速不变工况下后续反应器可承担部分转化率，故产能不一定改变，PFD不做调整；对应的TCU功率匹配事宜可通过调整出口温度实现，方案由SW自行调整。 08/25: Diameter of reaction column R24-CR01 was changed (from DN80 to DN65/DN50). After communicating with R&D and Keith, it was confirmed that under the condition of unchanged flow rate, the subsequent reactor can handle a portion of the conversion rate. Therefore, the production capacity is not necessarily changed, and the PFD will not be adjusted. The power matching of the corresponding TCU can be achieved by adjusting the outlet temperature. The plan will be adjusted by SW on its own. | YES | Keith/Xiantao Feng
08/25 | SW | CFCT向SW提供R24-BT03的尺寸和3D模型，方便Keith优化3D方案 CFCT provides SW with the dimensions and 3D model of R24-BT03 to facilitate Keith's optimization of the 3D design. | 08/25：会后提供R24-BT03的尺寸和3D模型 08/25: Dimensions and 3D model of R24-BT03 will be provided after the meeting. | YES | Shuangshuang Fan
09/07 | CFCT | 根据SW建议的3撬的设备布置的3D模型，主要讨论气液分离器的安装高度、HTF管路的高度及撬外管路的安装。 Based on the three-skid equipment layout 3D model proposed by SW, the main focus is on the installation height of the gas-liquid separator, the height of the HTF pipeline, and the installation of external pipelines. | 09/08：①分离器的安装高度：会上确定分离器安装高度可以降低，不必自流到 BT04。新的高度反馈给胡工，用来确定减压阀后压力； ②HTF的10 根管穿墙：穿墙高度先维持原高度，撬内和现场的高度差通过弯头转接； ③撬外管路的安装：对于安装高度高于运输高度2.5m的管路，撬体组装时预制好，运输时拆下，现场再次安装； ④按照BT01 / BT04 / 分离器 / 冷凝器尽量前移，缩减中间通道，以及CIP 和排放接口在撬装前端操作的方案更新3D模型； ⑤对于拉撬方案可能存在的操作维修不便的问题，后续邮件沟通。 09/08：①Separator Installation Height: It will be confirmed that the separator installation height can be reduced and does not necessarily need to flow by gravity to BT04. The new height will be reported to Engineer Hu to determine the pressure after the pressure reducing valve; ②The 10 pipes of HTF penetrate the wall: the height of the penetration is initially maintained at the original level, while the height difference between the inside and the site is adjusted through elbows; ③Installation of external pipelines: For pipelines with an installation height exceeding the transportation height by 2.5m, the skid assembly is prefabricated, then disassembled during transportation and reinstalled on-site; ④Update the 3D model according to the plan of moving BT01/BT04/separator/condenser forward as much as possible, reducing the intermediate channel, and operating CIP and discharge interfaces at the front end of the assembly; ⑤Regarding the potential inconvenience in operation and maintenance of the pull and pry scheme, we will communicate via email . 09/15：21日完成3D模型更新。 09/15: The 3D model update was completed on the 21st. 09/16：CFCT21日已完成3D并邮件发出。 09/16: CFCT completed the 3D version on the 21st and sent it via email. 09/22: 21日3D模型待讨论问题：①TCU管路进出口可否分成上下两层？ ②SE01/CU01建议靠墙布置，这样能预留出阀门检修和液位计的抽取空间。 ③CIP和排放管路在撬前操作，管路死区会增加。 | NO | Shuangshuang Fan
09/15 | SW | 3D模型确定后，讨论关闭Pending项内容。 After the 3D model is determined, the discussion will focus on closing the "Pending" items. |  | NO | ALL
09/15 | CIMT | 因为分撬原因，SW要求现场本安接线箱尺寸缩小，小尺寸接线箱可考虑SW采购方案，CIMT提供所需接线箱最小尺寸。 Due to skid split, SW requires the on-site IS junction box to be reduced in size. For the smaller junction box, CIMT will provide the minimum size required for the junction box. SW will assess if the size is feasible and get the box in UK if possible | 09/15：CIMT 提供接线箱最小尺寸 09/15：CIMT provided the minimum size needed: 09/16：CIMT通过邮件已 提供接线箱最小尺寸。 09/16: CIMT has already provided the minimum size of the junction box via email. | NO | ALL
09/22 | CFCT | 1、最新主设备图纸08/18邮件发出，各专业是否有异议？均确认后，着手提报采购流程。 The latest main equipment drawings were issued by email on 08/18. Do any disciplines have objections/comments? Once all disciplines have confirmed, we will proceed with the procurement submission process. 2、各专业按CE认证公司要求准备文件： ①PID完整文件-IEPE； ②所有设备、机泵、阀门、仪表等明细表-IEPE； ③3D橇块图纸-CFCT； ④主电柜介绍-CIMT； Each discipline shall prepare documents in accordance with CE Notified Body requirements: ① Complete P&ID documentation – IEPE ② Detailed lists of all equipment, pumps, valves, instruments, etc. – IEPE ③ 3D skid drawings – CFCT ④ Main electrical cabinet introduction – CIMT |  | NO | ALL

## 0915
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. 05/12：Keith建议用气液两相计算安全阀尺寸，不提供模板 05/12：Keith suggests using gas-liquid two-phase calculations for determining the size of the safety valve, but no template is provided. 05/20：根据API520的气液两相泄放时计算安全阀尺寸，部分已完成 05/20：Calculate the size of the safety valve based on the API520 standard for the two-phase gas-liquid discharge situation.Partially completed. 06/02：安全阀计算初版已完成（包含临界流体和气液两相），校审中。 06/02：Preliminary calculation of safety relief valve (covering critical fluid & gas-liquid two-phase flow) completed, under review. 06/09: General 1. What was the source/reference for the Specific Volumes stated in column D/D 列中比容数据的来源及参考依据是什么？ The Specific Volumes stated in column D are derived from Aspen Plus simulation results.比容数据来自Aspen模拟 2. There is no backpressure considered in the calculation. The emergency vent relief will create some backpressure which needs to be considered in the calculation./本次计算未考虑背压。紧急放空泄放过程会产生一定背压，该因素需纳入计算。 Backpressure consists of static backpressure and built-up backpressure. Given the wide total pressure range, backpressure effects shall be incorporated into the calculation.背压分为静背压和积聚背压，总压力范围大，将背压包含在其中 3. At the assumed relief pressure Ethyl Acetate will be a supercritical fluid, therefore the required relief mass flowrate will not be dependent on the latent heat of vapourisation, and the calculated ‘required discharge area’ will not be valid. Do you agree with this statement, or have you found a reference in the standard that allows for this? 在设定的泄放压力下，乙酸乙酯将处于超临界流体状态，因此所需泄放质量流量不再依赖汽化潜热，本次算出的所需泄放流通面积也不再适用。你是否认同该观点？或是你是否在相关标准中查到可支持该计算的依据？ 详见06/16回复. Please refer to the reply dated 06/16 for details. Cooling Failure Calculations 4. For the cooling failure calculation, I would suggest using 550kJ/mol rather than 501.48. This is based on Sandwich PSL experience of heats of reaction. 针对冷却失效工况计算，建议将反应热取值由 501.48 kJ/mol 改为 550 kJ/mol。该取值参考了桑威奇工艺安全实验室（Sandwich PSL）过往反应热项目经验。 OK 5. Is the feed flowrate used in the calculation, based on the maximum metering pump capabilities? Do you assume a maximum concentration of reactant in the feed stream? 计算中采用的进料流量，是否按照计量泵最大额定流量取值？计算时是否假定进料流中反应物浓度为最大浓度？ The flow rate used in the calculation is set at the maximum rated capacity of the metering pump, and the maximum reactant concentration is adopted for the feed stream.计算时流量是按照计量泵最大额定流量取值，反应物浓度为最大浓度 06/16：根据文献“Relief Calculation for Supercritical Fluids”计算超临界流体的质量泄放流量，会后向Keith发计算书审核 06/16：Calculate the mass relief flow rate of supercritical fluids in accordance with the document Relief Calculation for Supercritical Fluids, and send the calculation sheet to Keith for review after the meeting. | YES | Chaoqun Hu
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun Hu
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. 06/16：06/11已收到审核完成的URS。 06/16：Received the reviewed URS on 06/11. | YES | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith确认CV08也是故障关，可以使用DS6080型，该型号没有5 bar 差压限制。 Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith confirmed that CV08 is also a faulty-close type, the DS6080 model can be used. This model does not have a 5-bar differential pressure limit. Keith offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. 06/02 进展：Habonim厂家反馈了样本资料，反馈可以满足工艺参数需求，货期大概16~20周。可以作为开关阀的备选品牌。 06/02 Progress: "Habonim" manufacturer has provided sample materials that can meet the process parameter requirements. The delivery time is approximately 16 to 20 weeks. It can be an alternative brand for on-off valves. | YES | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. 06/02：关于气液分离器液相出口减压，电子压力阀和自力式减压阀都可以满足使用，首选自力式减压阀。 06/02：For pressure reduction at the liquid outlet of the gas-liquid separator，both electronic pressure valves and self-operated pressure reducing valves can meet the requirements, with self-operated pressure reducing valves being the preferred choice. | YES | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. 05/20：SW已更新完URS并发出。The SW has been updated and the URS has been sent out. | YES | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表数据单。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. 06/23:仪表条件表已更新完成 06/23：The instrument conditions table has been updated and completed. 07/10：仪表数据单已更新完成 07/10：Instrument Data Sheet has been fully updated. | YES | Chaoqun Hu/Yu Gao
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. 05/20：SW已更新完PFD并发出。The SW has been updated and the PFD has been sent out. | YES | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ 4/30：Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? 0914：详见第72(0702)条。For Detail, please see item 72(0702). | YES | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted?05/12Decided not to make any adjustments. 05/12确定不做调整。 05/12：It is determined that the height of the catalyst bed in the main reactor will not be adjusted. | YES | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. 06/16：会议澄清：待布局完成后，SW主导完成爆炸危险区域的划分 09/06：Meeting Clarification: SW shall take the lead in completing the classification of hazardous areas for explosion after layout design is finalized. 0915:SW现场确定3D后1周时间SW方完成。 0915: After 1 week from the time the 3D model was determined on-site, the SW team will complete the task. | NO | All
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | YES | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements. | 05/20：与聂博沟通，小试使用的是进口是插底的分离器，生产使用的是侧进的分离器，按会议沟通的气体最大流量0.2Nm³/h，液体最大流量20L/h重新计算了分离器 05/20: Communicated with Nie Bo. The small-scale test used an imported bottom-insertion separator, while the production version used a side-inlet separator. Based on the maximum gas flow rate of 0.2 Nm³/h and the maximum liquid flow rate of 20 L/h for the communication at the meeting, the separator was recalculated.. | YES | Chaoqun Hu
06/02 | IEPE | 管道编号中的管线尺寸一般是指的公称直径，PID中尺寸为10mm的管道是Φ10mm，公称直径为6mm The line size in pipe line designations generally refers to the nominal diameter. In a P&ID, a pipe with a size of 10mm is specified as Φ10mm, corresponding to a nominal diameter of 6mm. | 06/02：会议澄清：DN15以下的管道，管道编号中的管径为外径，DN15及其以上的管道，管道编号中的管径为公称直径。 06/02：Clarification from meeting:For piping below DN15, the size specified in pipe tag number denotes outer diameter; for DN15 and above, the size in pipe tag refers to nominal diameter. | YES | Chaoqun Hu
06/02 | IEPE | 设备BT-01/03/04上的压力变送器不便于现场观察，是否可以考虑也选用WIKA的不带现场显示紧凑型的压力变送器？ The pressure transmitter on the equipment BT-01/03/04 is not convenient for on-site observation. Could it be considered to also choose WIKA's compact pressure transmitter without on-site display？ | 06/02：会上建议保留BT-01/04的现场显示，BT-03可不带现场显示。 06/02：It was suggested at the meeting that the on-site display of BT-01/04 be retained, while BT-03 may not have an on-site display. | YES | Yu Gao
06/02 | CFCT | 1-PID中V-9868，V-9965阀柄的含义？ What is the meaning of valve handles V-9868 and V-9965 in PID? 2-PID中压力变送器底部波纹含义是什么？ What does the corrugation at the bottom of the pressure transmitter signify? 3-与管道直径对应的保温厚度是多少？ What is the insulation thickness corresponding to the diameter of the pipeline? | 06/02： 1.PID中阀门V-9868，V-9965的阀柄为弹簧复位阀柄； In the PID,the valve handles of V-9868 and V-9965 are spring-reset handles； 2.PID中带底部波纹的压力变送器要求压力变送器带隔膜； The pressure transmitter with a bottom ripple in PID requires the pressure transmitter to be equipped with a diaphragm； 3.Keith分享了建议的管道直径与保温厚度表格，直径10到25mm的管路，保温厚度为30-35mm。 Keith shared the recommended pipe diameter and insulation thickness table, with insulation thickness ranging from 30-35mm for pipes with diameters of 10 to 25mm. | YES | ShuangshuangFan
06/16 | SW | 会议确认：气液分离器为侧进，尺寸为DN200*600mm，下次例会前CFCT向SW提供气液分离器的设备图纸 Confirmed at the meeting: The gas-liquid separator adopts side inlet configuration with dimensions DN200 × 600 mm. CFCT shall submit the equipment drawing of the gas-liquid separator to SW prior to the next regular meeting. | 06/22设备图纸已提供。06/23Keith回复意见，见06/23讨论内容。 Equipment drawings were provided on 06/22. Keith's feedback was received on 06/23 — please refer to the discussion notes from 06/23. | YES | Ziliang Zhao
06/17 | SW | 根据最新工作进展并结合HAZOP分析所需文件内容，更新“Sandwich Hydrogenation Implementation Schedule” Update the Sandwich Hydrogenation Implementation Schedule based on the latest progress and document requirements for HAZOP study. | 待SW现场3D讨论及HAZOP分析完成后更新相对准确的进度计划表。 | NO | All
06/17 | SW | 讨论操作规程：哪些部分需要顺控？开停车步骤等 Discuss operation procedures: identify sections requiring sequence control, including startup and shutdown steps, etc. | 06/23：开车步骤：公用工程确认/催化剂装填→氮气置换（R24-BT01、R24-BT04和剩余部分），氧含量<0.5vol%→氢气置换→原料系统备料→TCU系统调温→反应器进料（氢气先进料背压至反应压力，液相再进料）→气液分离→产品转移 停车步骤：停进料→产品缓冲罐物料转移→反应器卸压→R24-BT03卸压→反应系统降温→氮气置换→关闭氮气和TCU Startup Procedures： 1.Verification of utility systems & catalyst loading 2.Nitrogen purging (for R24-BT01, R24-BT04 and the rest of the system), oxygen content controlled below 0.5 vol% 3.Hydrogen purging 4.Raw material preparation for feed system 5.Temperature adjustment of TCU system 6.Reactor feeding: Introduce hydrogen first to build backpressure up to reaction pressure, then feed liquid phase material 7.Gas-liquid separation 8.Product transfer Shutdown Procedures： 1.Cut off feed supply 2.Transfer materials from product buffer tank 3.Depressurize reactor 4.Depressurize R24-BT03 5.Cool down reaction system 6.Nitrogen purging 7.Shut down nitrogen supply and TCU system Keith提供HAZOP时的开停车步骤，结合上述文件，整理开停车和清洗步骤 Compile the plant start-up, shutdown and cleaning procedures based on the above documents together with the start-up & shutdown sequences supplied by Keith for HAZOP assessment. 09/07：操作手册已于08/21发给SW 09/07：The operating manual was sent to SW on 08/21. | Pending | All
06/17 | SW | 会后确认：安全阀的泄放温度超过设备的设计温度，是否需要提高设备的设计温度？ To be confirmed after the meeting：If the relief temperature of the safety valve exceeds its design temperature, is it necessary to increase the design temperature rating? | 设备和管线材质为316L，结合设备和管道的壁厚，计算得出：在泄放温度下，材料的许用应力满足其强度要求，不需提高设备的设计温度 The equipment and piping are fabricated from 316L stainless steel. Wall thickness calculations for the equipment and piping demonstrate that the allowable stress of the material satisfies the strength requirements at relief temperature; therefore, no increase to the equipment design temperature is required. | YES | Ziliang Zhao/Chaoqun Hu
06/17 | SW | CFCT做撬块设计时，注意清洗过程中的低点排净 CFCT shall take full consideration of low-point draining during cleaning when designing the skid package. | 06/23：在撬块设计时，设置管道的低点排净阀 When designing the layout, install a drain valve at the low point of the pipeline 06/23会议方案：管道最低点设置排净阀，操作说明中明确排放时用容器收集排放液体。 Meeting Plant: Install drain valves at the lowest point of the pipeline, and specify in the operating instructions to collect the discharged liquid with a container during the drainage process. | YES | Shuangshuang Fan
06/17 | SW | CFCT提供放空缓冲罐T06是否放在撬内的方案 CFCT to provide a scheme on whether vent buffer tank T06 shall be installed inside the skid. | 06/23：按照现有空间的布置，T06放在撬块内的空间不足；撬块中间的操作维护通道宽度为300-350mm，能否将整体撬块宽度增加150-200mm？ According to the existing space arrangement, there is insufficient space for T06 to be placed inside the pry block; The width of the operation and maintenance channel in the middle of the pry block is 300-350mm. Can the overall pry block width be increased by 150-200mm? 06/23会议方案：T06不放在撬块内，放置在service area，同时反应柱/冷凝器的TCU出口管路上的温度变送器安装在近出口处，去掉手动球阀，安全阀可放到service area，并设置排净阀，进口管路手动球阀保持不变，温度变送器加套管，位置可前可后，低点设置排净阀，整体管路的高点设置排气阀。 Meeting Plant:: T06 is not placed inside the lever block but in the service area. The temperature transmitter on the TCU outlet pipeline of the reaction column/condenser is installed near the outlet. The manual ball valve is removed, and the safety valve can be placed in the service area. A drain valve is installed, while the manual ball valve on the inlet pipeline remains unchanged. The temperature transmitter is equipped with a protective sleeve, with its position adjustable forward or backward. A drain valve is set at the low point, and an air vent valve is installed at the high point of the entire pipeline. | YES | Shuangshuang Fan
06/23 | SW | Keith意见： 基本设计：我们是否有经批准的分离器设计方案？我上次看到的摘录中，计算出的容器直径为3毫米，这表明计算或输入数据可能存在错误。 Basic design 1. Do we have an approved design for the separator. The last extract I saw had a calculated vessel diameter of 3mm, which suggests an error in the calculations or input data. | 06/23讨论： 基本设计：按最新设备数据表进行气液分离器设计。气液分离器的计算书已复核过，数据无误。 06/23Discussion—Basic Design: The gas-liquid separator shall be designed in accordance with the latest equipment data sheet. The calculation sheet for the gas-liquid separator has been reviewed and the data are confirmed to be correct. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 分离器内件 1、本设计中是否已考虑分离器内件，例如入口导流装置或入口旋风分离器、气相除雾器、液体出口处的防涡流挡板？ 2、喷淋球能否采用焊接固定方式，而非通过管接头引入容器内部？ 3、喷淋球是否必须为旋转式喷淋球？这会增加设备复杂度，并在工厂运行寿命期内带来检查与维护方面的问题。 4、喷淋球实际能否起到喷淋清洗作用，还是仅仅将容器注满清洗液直至触发高位液位开关？根据此前讨论，从空罐到高位跳闸点的时间不足25秒，这无法为分离器气相侧提供足够的机械清洗作用时间。 Separator internals 1. Have separator internals been considered for this design e.g. inlet diverters or inlet cyclones, demisting of the vapour stream, vortex breakers on the liquid outlet. 2. Can the spray ball be welded in position rather than introducing a tube fitting into the vessel. 3. Does the spray ball need to be a rotary spray ball. This adds complexity and inspection/maintenance issues during the life of the plant. 4. Will the spray ball actually work as a spray ball, or will it simply fill the vessel with cleaning fluid until the high-level switch is activated. Based on previous discussions this would be less than 25 seconds from empty to high-level trip point, which doesn’t allow much time for mechanical cleaning action in the gas side of the separator. | 06/23讨论： 分离器内件： 1、气液分离器设计采用重力式分离，无需额外的内件。 2、喷淋球相关事宜，CN团队内部结合喷淋球供应商商议方案。 06/23 Discussion — Separator Internals: 1.The gas-liquid separator is designed as a gravity-type separator; no additional internals are required. 2.Regarding the spray ball matters, the CN team will internally discuss and determine the solution in coordination with the spray ball supplier. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 设计参数 1、“流体性能”是否应定为“非致命性”？我推测此概念类似于PED容器设计中的流体分组，在英国规范中应属于Group 1气体（即可燃/爆炸/有毒），而非“非致命性”。 2、工作压力应为0至6MPaG。 3、设计温度应至少为150°C，并且我假设在泄压事故工况下，容器温度可能达到约300°C。 4、设计压力应为全真空至9MPaG。 5、规范是否要求进行焊后热处理（PWHT）？ 6、水压试验压力应为设计压力的1.5倍，即13.5MPaG，而非12MPaG。 7、对于该容器，S4应为DN32 Cl900 WN法兰。喷淋球接口是否应作为单独细节在本图纸上表示，还是另页图纸表示更为合适？ 8、充装系数（Fulling Factor）是多少？ Design Parameters 1. Should the ‘Fluid Performance’ be Non-Lethal? I assume this is similar to the fluid group for PED vessel design, which for the UK would be Group 1 gas i.e. flammable/explosive/toxic and not Non-Lethal. 2. The working pressure should be 0 to 6MPaG. 3. The design temperature should be at least 150 °C and I assume the vessel has the potential to reach circa 300°C during a relief event. 4. The design pressure should be FV to 9MPaG 5. Is PWHT required by the code. 6. Hydro test pressure should be 1.5x design pressure i.e. 13.5MPaG not 12 MPaG. 7. For the vessel, S4 should be a DN32 Cl900 WN Flange. Should the spray ball fitting be shown as a separate detail on this drawing or possibly shown on a separate drawing. 8. What is the Fulling Factor. | 06/23讨论： 设计参数: 1、介质调整为易爆。 2、CN团队结合URS，修正工作压力，更新设备数据表。 3、可以将泄压事故工况，纳入到常规设计考虑中，即可提高设计温度到300℃。 4、修正设计压力，更新设备数据表。 5、规范可不进行焊后热处理（PWHT）。 6、水压试验压力为设计压力的1.3倍，故试验压力可不做调整。 7、S4为喷淋口，口径为Φ10，DN32法兰接口结构为保证喷淋球可抽出，后续根据喷淋球整体方案做调整，判定是否需要可抽式。 8、充装系数是指物料实际容积与容器全容积之比。 06/23 Discussion — Design Parameters: 1.The medium classification is revised to "explosive." 2.The CN team will revise the working pressure based on the URS and update the equipment data sheet accordingly. 3.The relief event scenario can be incorporated into the normal design considerations — i.e., the design temperature can be raised to 300°C. 4.The design pressure will be revised and the equipment data sheet updated accordingly. 5.PWHT (post-weld heat treatment) is not required per the applicable code. 6.The hydrostatic test pressure is 1.3 × design pressure, so the test pressure does not need to be adjusted. 7.S4 is the spray ball connection, with a bore size of Φ10. The DN32 flange connection is designed to allow the spray ball to be withdrawable. This will be reviewed and adjusted as part of the overall spray ball solution, and a decision will be made on whether a withdrawable type is necessary. 8.The filling factor is defined as the ratio of the actual liquid volume to the total vessel volume. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 通用事项 1、管口方位是否已考虑设备布置的最优化？ 2、在撬装高度限制范围内，容器能否通过重力自由排液至产品收集罐？ 3、在顶部法兰上开孔用于引出管，是否会损害其机械完整性并违反安全规范？是否已重新计算法兰厚度或进行有限元分析（FEA），以确保足够的金属厚度和结构完整性？ 4、液位变送器/液位开关的规格是否已确认？法兰尺寸及位置是否与仪表相匹配？ 5、请更新P&ID，以显示S4正确的管口尺寸。 6、是否有容器设计计算书？技术文件中需要包含设计计算书，并应在FAT（工厂验收测试）时进行核查。 General 1. Does the nozzle orientation allow for optimum equipment layout. 2. Can the vessel free drain into the product collection tank, within the skid height constraints. 3. Does boring a hole in the top flange for the outlet pipe compromise its mechanical integrity and violate safety codes. Have you recalculated the flange thickness/carried out FEA to ensure adequate metal thickness and structural integrity. 4. Has the level transmitter/level switches been agreed – does the flange size/position align with the instruments. 5. Update P&ID to show correct nozzle size for S4. 6. Do you have vessel design calculations. Design calculations will be required in the technical file and should be checked at FAT. | 06/23讨论： 通用事项: 1、管口方位已结合3D撬装布置给定。 2、3D撬装设计已考虑，待3D模型复核时，详细讨论。 3、重新计算法兰厚度，以满足结构强度要求。 4、仪表工程师已经确认复核。 5、P&ID，不需要更改S4管口尺寸。 6、设计计算书是设备完整技术文件中必不可少的一部分，后续会提供。 06/23 Discussion — General Items: 1.Nozzle orientation has been determined based on the 3D skid layout. 2.The 3D skid design has taken this into consideration; detailed discussion will be held during the 3D model review. 3.The flange thickness will be recalculated to meet structural strength requirements. 4.The instrumentation engineer has confirmed and verified this. 5.The P&ID does not require changes to the S4 nozzle size. 6.The design calculation sheet is an essential part of the complete technical documentation for the equipment and will be provided in due course. | YES | Ziliang Zhao/Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Overall cleaning philosophy per vessel 各容器整体清洗策略 Please confirm the intended cleaning philosophy for each vessel in the skid — spray-only, soak-only, spray-and-soak combined, or an alternative approach. Please also indicate whether a single philosophy applies across all vessels or whether the strategy varies by vessel. 请确认撬块内各台容器的清洗策略：单独喷淋、单独浸泡、喷淋+浸泡组合，或其它方式。请同时说明是否所有容器采用同一策略，或按容器区别设计。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：有喷淋球的设备R24-BT01、R24-BT04和R24-SE01采用喷淋循环清洗，其余设备采用浸没循环冲洗 09/07：Equipment R24-BT01, R24-BT04 and R24-SE01 equipped with spray balls shall adopt spray circulation cleaning. The remaining equipment shall use immersion circulation flushing. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleanliness verification method & acceptance criteria 清洁度验证方法与验收标准 Please advise the verification method(s) used to confirm cleaning completion (visual inspection, swab / rinse sample analysis, mass balance, calculated residue, etc.) and the numerical acceptance criteria applied (e.g. residue mass, ppm concentration threshold). 请说明用于确认清洗完成的验证方法（目视检查 / 拭子或冲洗样分析 / 物料衡算 / 残余物计算等），以及所采用的数值验收标准（如残余物质量、浓度阈值 ppm）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：与研发人员讨论后，由于国内外存在差异，建议由SW属地QA提供清洗验证 09/07：After discussion with the R&D team, considering regional differences between China and overseas sites, it is recommended that the local QA team of SW provide cleaning validation. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Sight glass availability for SE01 SE01 视镜配置 The reactor vessels are understood to be fitted with sight glasses to support visual verification of cleanliness. The gas–liquid separator SE01, however, does not include a sight glass. Please confirm the intended method for verifying cleanliness on SE01. 反应柱已配置视镜以支持目视清洁度检查，但气液分离器 SE01 未配置视镜。请确认 SE01 清洁度验证的具体手段（，以及是否考虑将新增视镜作为设计变更纳入）。 | 07/10：反应柱和分离器因为操作压力高，无法配置视镜，清洁度的验证无法依靠目测，需取样分析测量残留物的浓度 07/10：Due to the high operating pressure of the reaction column and separator, sight glasses cannot be installed. Visual inspection is therefore not feasible for cleanliness verification, and residue concentration shall be determined via sampling analysis instead. 08/13：不增加视镜，冯博士已提供国内清洁度验收限度的方法供SW参考。 08/13：Without adding a sight glass, Dr. Feng provided the domestic cleanliness acceptance criteria method for SW's reference. | YES | Xiantao feng/Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Spray ball flow rate vs. vessel fill time 喷淋球流量与容器充液时间的匹配 The lowest available spray ball flow rate (approximately 20 L/min) results in SE01 reaching the high-level trip point in under 25 seconds. This limits the time window in which mechanical spray action can achieve wetting coverage. Please advise the intended cleaning-time window on SE01 and the approach for ensuring adequate mechanical cleaning action within the design constraint. 现有最小可选喷淋球流量约 20 L/min，导致 SE01 容器在 25 秒内即达到高液位跳停，机械喷淋作用的有效时间窗口非常短。请说明 SE01 上预期的清洗时间窗口，以及在此设计约束下如何确保获得充分的机械清洗作用。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：R24-SE01清洗时采用喷淋循环清洗，及一边进液，一边排液，排液管的尺寸能匹配喷淋球的流量，保证清洗时不会达到高液位 09/07：R24-SE01 adopts spray circulation cleaning during cleaning operation, with continuous liquid feed and simultaneous liquid discharge. The drain line size is sized to match the flow rate of the spray balls, ensuring that a high liquid level will not be reached during cleaning. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Drain line sizing and fill–drain cycle 排放管径与充液-排空循环 Under the current drain line configuration, the drain rate is significantly slower than the spray inflow rate. Please advise the intended drain line diameter (whether upsizing is planned), the estimated single-cycle fill and drain durations, and the number of cycles anticipated per cleaning campaign. 当前排放管径下，排放速率显著慢于喷淋进料速率。请说明拟采用的排放管径（是否放大）、单次循环的充液和排空时间估算，以及每次清洗预期需要的循环次数。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：排放管径已放大，详见P&ID。不同物料，清洗循环的次数不同，可根据取样分析的结果确认 09/07：The drain line size has been increased; refer to the P&ID for details. The number of cleaning circulation cycles varies for different materials and can be confirmed based on sampling analysis results. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Soak cleaning vs. high-level interlock defeat mechanism 浸泡清洗与高液位联锁绕过机制 If soak cleaning is adopted on SE01, the liquid level during cleaning will exceed the high-level safety interlock (located at approximately one-third of vessel height). Please specify: (a) the physical mechanism intended for defeating this interlock during cleaning (key switch, procedural lockout, or other); (b) the authorisation and access controls surrounding the defeat mechanism; and (c) the safeguards against inadvertent defeat during normal processing operation. 若 SE01 采用浸泡清洗，清洗过程中的液位将超过位于容器约 1/3 高度的高液位安全联锁。请说明：(a) 清洗时用于绕过（defeat）该联锁的物理机制（钥匙开关 / 程序锁定 / 其它）；(b) 该绕过机制的授权与权限控制方式；(c) 防止正常运行时意外绕过的保护措施。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：R24-SE01清洗时采用喷淋循环清洗，及一边进液，一边排液，排液管的尺寸能匹配喷淋球的流量，保证清洗时不会达到高液位 09/07：R24-SE01 adopts spray circulation cleaning during cleaning operation, with continuous liquid feed and simultaneous liquid discharge. The drain line size is sized to match the flow rate of the spray balls, ensuring that a high liquid level will not be reached during cleaning. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleaning of the guided-wave level transmitter housing Guided wave 液位变送器外壳的清洁 The guided-wave level transmitter housing (approximately 100 mm diameter, side-mounted on SE01) sits above the high-level switch and lies outside the spray ball coverage envelope. Please advise the intended cleaning approach for this housing, and any mechanical or procedural provisions required to ensure it can be cleaned to the acceptance criteria in Q1.2. 液位变送器外壳（约 100 mm 直径，SE01 侧接管上）位于高液位开关之上，不在喷淋球覆盖范围内。请说明该外壳的清洁方案，以及为达到 Q1.2 中的验收标准所需的机械或程序性措施。 | 07/14：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用 07/14：Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. | YES | Chaoqun Hu/Yu Gao
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Reactor cleaning cycle time and manual interventions 反应器清洗循环时间与人工干预 For the 200-L reactor vessels, a single spray-and-drain cycle involves an extended drain phase relative to the spray phase. Multiple cycles are expected to achieve the required cleanliness. Please advise: the anticipated number of cycles, the total cleaning duration per campaign, and the specific manual interventions required at each step (drain valve operation, sample point access, lockout re-set, etc.). 200-L 反应器进行单次"喷淋-排空"循环时，排空阶段远长于喷淋阶段，需多次循环以达到清洁度要求。请说明：预期循环次数、每次清洗总时长，以及各步骤所需的具体人工干预（排放阀操作 / 取样口操作 / 联锁复位等）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：反应器采用浸没循环清洗，清洗进出口的管径为Ф10，可选用10L/min的泵循环冲洗，循环次数和清洗总时长需根据取样分析结果确认 09/07：The reactor adopts immersion circulation cleaning. The inlet and outlet nozzles for cleaning have an outer diameter of 10 mm. A pump with a flow rate of 10 L/min can be used for circulation flushing. The number of circulation cycles and total cleaning duration shall be confirmed based on sampling analysis results. | Pending | Chaoqun Hu
07/01 | SW 3D Layout 3D 布置与设备空间 | Operational access clearance 操作通道净空 The current 3D model shows approximately 300–350 mm clearance in certain operator access zones. Please confirm the target minimum clearance from a site operability and maintenance standpoint, and identify any specific zones where relaxation of the current clearance is acceptable, or where additional clearance is required. 当前 3D 模型显示部分操作人员通道净空约为 300–350 mm。请从现场操作与维护角度，确认目标最小净空要求，并识别可以放宽的具体区域，以及需要额外净空的区域。 | 07/10：建议增加反应柱撬块的宽度，审核模型后给出建议的空间区域。 It is recommended to increase the width of the reaction column skid and provide the suggested spatial area after reviewing the model. 09/08：根据SW最新建议的设备布置方案，减少设备中间通道，加大设备与墙体空间，具体尺寸待3D模型更新后确定。 According to SW's latest recommended equipment layout plan, reduce the middle channels of the equipment and increase the space between the equipment and the wall. The specific dimensions will be determined after the 3D model is updated. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Free-drain feasibility from each vessel 各容器的自重排放可行性 The cleaning strategy relies on free-drain of cleaning fluid from each vessel into downstream collection (BT04 or equivalent). Considering the skid height constraint and each vessel elevation, please confirm the free-drain path is mechanically feasible from each source vessel to its destination. Please identify any vessels where drainage cannot be achieved by gravity and would require pumping or an alternative arrangement. 清洗策略要求清洗液自重从各容器排入下游收集罐（BT04 或等效容器）。考虑撬块高度限制与各容器标高，请确认每台源容器至其目标容器的自重排放路径机械可行。请识别无法通过重力实现排放、需要泵抽或采用替代方案的容器。 | 07/10：根据目前容器的结构形式，反应柱可通过底部排放阀排放，缓冲罐可通过管路排放，预热器、冷凝器管路无排放口。具体排放方式参考清洗方案。 Based on the current structural design of the containers, the reaction column can be drained through the bottom discharge valve, the buffer tank can be discharged via piping, while the preheater and condenser have no discharge outlets in their pipelines.Refer to the cleaning plan for specific emission methods. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Nozzle orientation on pressure vessels 压力容器管嘴方位 Please review the nozzle orientation on all pressure vessels in the current 3D model. Confirm that nozzle positions provide adequate access for external piping tie-in, instrumentation installation, and maintenance (removal / reinstallation of internals, gasket replacement, catalyst service, etc.). 请审查当前 3D 模型中所有压力容器的管嘴方位。确认管嘴位置能够满足外部管路对接、仪表安装以及维护（内构件拆装 / 密封垫更换 / 催化剂检维修等）的空间要求。 | 07/10：由于空间尺寸限制，部分管口的维护可能存在不便。优化管口布置或能否增加设备空间。 Due to space size limitations, maintenance of some pipe openings may be inconvenient. Optimize pipe layout or increase equipment space 09/08：根据SW最新建议的设备布置方案，CIP及排放管口位于撬端面，并采用移动拉撬方案，满足中间设备及管路的维护空间要求。 According to SW's latest recommended equipment layout plan, the CIP and discharge ports are located on the pry end face, and a mobile pry scheme is adopted to meet the maintenance space requirements of intermediate equipment and pipelines. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Catalyst charging & discharging arrangement 催化剂加料与卸料布置 Please confirm that the catalyst charging (loading) and discharging (unloading) arrangement is compatible with the current nozzle layout on the reactor vessels, and that adequate space is provided for charge / discharge equipment and operator access during catalyst service. 请确认催化剂加料与卸料的操作方式与当前反应柱的管嘴布置兼容，且在催化剂检维修期间为加料/卸料设备与操作人员留有充足空间。 | 07/10：根据目前的布置方案，反应柱加料卸料口均在撬体端面，结合加料卸料方式看操作空间是否充足。 According to the current layout plan, the feeding and discharging ports of the reaction column are all located on the end face of the pry body. Considering the feeding and discharging methods, it is necessary to check whether the operating space is sufficient. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Tie-in points between skid and site utilities 撬块与现场公用工程接口 Please confirm the finalised location and specification of all tie-in points between the skid and the Sandwich site services, including process feed, product outlet, vent header, HTF supply and return, N₂ blanketing, instrument air, electrical supply, cable penetrations, and drain. Please advise the interfaces where design lock-down is still pending. 请确认撬块与 Sandwich 现场公用工程之间所有接口的最终位置与规格，包括工艺进料、产品出口、放空总管、导热油供回、氮气钝化、仪表空气、电气供应、电缆穿墙、排放。请说明尚未定稿的接口。 | 07/10：根据现有的布置方案，有部分公用工程的的接口，无仪表空气接口，电气供应、电缆穿墙，后续更新撬块与公用工程接口的位置与规格。 According to the existing layout plan, there are interfaces for some public works without instrument air interfaces, electrical supply, and cable penetration through walls. The location and specifications of the interface between the pry block and the public works will be updated in the future. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Cable wall penetration capacity and cable compatibility 穿墙电缆孔容量与电缆兼容性 The current design indicates 14 available cable wall penetration slots. Please confirm this final count, the internal diameter of each slot, and the compatibility of the slot with the largest cable type intended to pass through (multi-core, armoured, or shielded cables of relevant cross-section). 当前设计显示可用穿墙电缆孔 14 个。请确认该数量的最终定案、每个孔的内径规格，以及与拟穿过的最大电缆类型（相应截面的多芯 / 铠装 / 屏蔽电缆）的兼容性。 | 寻求工程部支持，和宋小旭主管约会讨论如何推进，7月10日反馈进展 | YES | Dezhi meng/Shaofeng gao
07/01 | SW Control Philosophy 控制策略 | Full Control Philosophy document issue date 完整《控制策略》文件发出日期 Please advise the target issue date for the complete Control Philosophy document, superseding the interim draft version previously circulated. 请说明完整版《控制策略》文件的目标发出日期（覆盖此前流转的过渡草稿版本）。 | 07/10：已完成初版，还在校核中，预计下周发出 07/10：The initial draft has been completed and is under review; it is expected to be issued next week. 09/07：控制说明已于08/21发给SW 09/07：The control description was sent to SW on 08/21. | Pending | Chaoqun Hu
07/01 | SW Control Philosophy 控制策略 | Interlock schedule — hardwired vs. software 联锁清单 —— 硬件联锁与软件联锁 Please provide a complete interlock schedule listing all safety interlocks, with clear delineation between hardwired (independent of the PLC) and software (PLC-implemented) interlocks. For each interlock, please include: initiating cause, sensing element, trip setpoint, action taken, and protective function fulfilled. 请提供完整的联锁清单，列出全部安全联锁，明确区分硬件联锁（独立于 PLC）与软件联锁（PLC 实现）。每一条联锁请包含：触发原因、检测元件、跳停设定值、联锁动作、承担的保护功能。 | 07/10：联锁条件已完成初版，还在校核中，预计下周发出 07/10：The initial draft of interlock conditions has been completed and is under review, which is expected to be issued next week. 09/07：联锁表已于08/21发给SW 09/07：The interlocks table was sent to SW on 08/21. | Pending | Chaoqun Hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Operational modes and mode-specific fail positions 操作模式与各模式下的故障位 Please define all operational modes of the skid (normal operation, start-up, shut-down, cleaning, catalyst change, emergency depressurisation, etc.), and for each mode specify: (a) the fail position of each control valve; (b) the state of each interlock (active / bypassed); and (c) the permissive conditions required to enter that mode. 请定义撬块的全部操作模式（正常运行 / 开车 / 停车 / 清洗 / 催化剂更换 / 紧急泄压等），并针对每一模式说明：(a) 每个控制阀的故障位；(b) 每个联锁的状态（激活 / 已绕过）；(c) 进入该模式所需的许可条件。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 分离器浸泡清洗时易触发液位高联锁，导致高液位以上清洗不彻底。增大分离器的排净管径可实现淋洗，同时系统处于清洗模式时，绕开液位高联锁。 High level interlock is prone to tripping during soaking cleaning of the separator, leading to inadequate cleaning of areas above the high liquid level. Increasing the drain pipe size of the separator allows shower rinsing. Meanwhile, the high level interlock can be bypassed when the system is under cleaning mode. | NO | Chaoqun Hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Mode-transition safeguards 操作模式切换的保护措施 Please advise the safeguards in place against inadvertent mode transitions, particularly from cleaning mode back to processing mode (e.g. an interlock bypass being left in place after cleaning is complete). Please describe both the technical safeguards (key switches, HMI confirmations) and the procedural safeguards (SOP requirements, dual sign-off). 请说明防止意外切换操作模式（尤其是从清洗模式返回处理模式时联锁绕过未复位）的保护措施。请分别描述技术性保护措施（钥匙开关 / HMI 确认）与程序性保护措施（SOP 要求 / 双签发）。 | 52条和Keith讨论后1周反馈。 周二上午组会专题讨论：超群+付工。 | NO | Dezhi meng
07/01 | SW Sampler System 取样系统 | Sample vaporisation during pressure reduction 取样过程中的样品闪蒸 The sampler transfers process fluid from a line operating at up to 60 barG to a sample container at approximately atmospheric pressure. Please advise the analysis of vaporisation during this pressure reduction (fraction vaporised, temperature drop) and its impact on the compositional representativeness of the collected sample. 取样器将最高 60 barG 工艺管路的介质转移至常压取样瓶。请说明此压降过程中的闪蒸分析（气化比例、温度降低）及其对所采样品成分代表性的影响。 | 07/10：冷凝器出口的温度为30℃，压力从60barG 泄至常压，此温度条件下不会发生闪蒸 07/10：The temperature at the condenser outlet is 30°C. The pressure is relieved from 60 barG to atmospheric pressure, and no flashing will occur under this temperature condition. | Pending | Chaoqun Hu
07/01 | SW Sampler System 取样系统 | Sample retention design 样品截留设计 Please advise the design of the sample bottle and sample-transfer system, including any vapour trap, septum, condenser, or other retention device intended to prevent loss of volatiles through the vent path and to ensure a representative liquid sample is captured. 请说明取样瓶及取样传输系统的设计，包括为防止挥发组分从放空路径流失、并确保获得代表性液样所采用的蒸汽阱、隔膜、冷凝器或其它截留装置。 | 07/10：取样器的流程：打开三通阀将缓冲罐充满，打开缓冲罐气相放空管线阀门，将缓冲罐中的气相排走并卸压，打开氮气手阀，将缓冲罐中的液体压至取样瓶 07/10：Sampling procedure: Open the three-way valve to fill the buffer drum. Open the valve on the vapor vent line of the buffer drum to vent the vapor inside and relieve pressure. Then open the nitrogen manual valve to pressurize and transfer the liquid from the buffer drum into the sampling bottle. | Pending | Chaoqun Hu
07/01 | SW Sampler System 取样系统 | Sampler behaviour under gas-rich flow regime 气相主导流态下取样器行为 With the intended process operating at a stoichiometric excess of hydrogen, the flow regime through the sampling point may be gas-rich with entrained liquid rather than liquid-continuous. Please advise how the sampler design accommodates this flow regime, and whether any sample point relocation, phase separator, or coalescer is being considered. 工艺预期在化学计量氢气过量条件下运行，取样点处流态可能为"气相夹带液体"而非液相连续。请说明取样器设计如何适应此流态，以及是否考虑取样点位置调整、加装相分离器或聚结器。 | 07/10：取样器的缓冲罐上有气体排放管线，取样罐充满后，打开气体排放管线，将气相排走并卸压，再用氮气将液相压至取样瓶 07/10：The buffer vessel of the sampler is equipped with a gas vent line. Once the sampling tank is full, open the gas vent line to vent the vapor phase and relieve pressure, then push the liquid phase into the sampling bottle with nitrogen. | Pending | Chaoqun Hu
07/01 | SW Instrumentation 仪表配置 | Guided-wave level transmitter — datasheet & cleanability Guided wave 液位变送器 —— 数据单与可清洁性 Please provide the guided-wave level transmitter datasheet and confirm: (a) the process compatibility of the probe assembly with the intended service (including any operating conditions in the supercritical or near-critical regime); and (b) the cleanability of the probe assembly under the adopted cleaning philosophy. 请提供 guided wave 液位变送器数据单，并确认：(a) 探头组件在拟定工况（含超临界或近临界工况）下的适用性；(b) 探头组件在拟采用清洗策略下的可清洁性。 | 7月10日反馈进展 (a) 导波雷达液位计工作原理是雷达波可以穿过介电常数较低的气相，遇到介电常数较大的液相返回，从而计算液位。适用蒸汽、粉尘、泡沫等工况。需了解超临界工况下的介质状态是否还存在液相，如果没有液相空间，则液位计无法识别。 The working principle of the guided-wave radar transmitter is that the radar wave can pass through the gas phase with a lower dielectric constant and return to the liquid phase with a larger dielectric constant, thereby calculating the liquid level. It is applicable to working conditions such as steam, dust and foam. It is necessary to understand whether there is still a liquid phase in the medium state under supercritical conditions. If there is no liquid phase space, the transmitter cannot identify it. 07/15进展：经内部评估，液位计所在容器操作工况下不存在超临界状态。 After internal assessment, it was determined that the liquid level gauge is not in a supercritical state under the operating conditions of the container it is located in. (b)BT01和BT04的导波雷达液位计为顶装内伸形式，可以利用设备内的喷淋头冲洗。SE-01的导波雷达液位计为侧装旁通式，可以选择在探头与旁通管的过程接口处增加配套冲洗环，并预留一路冲洗管线。 The guided-wave radar transmitters of BT01 and BT04 are top-mounted and iInsert type, and can be flushed by the spray heads inside the equipment. The guided-wave radar l transmitter of SE-01 is of side-mounted bypass type. A matching flushing ring can be added at the process interface between the probe and the bypass pipe, and a flushing pipeline can be reserved. 07/14进展：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用. Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. 07/17进展：气液分离器雷达液位计侧装改顶装，已完成图纸设计，筒体直径未变，邮件发出。 The radar level gauge for the gas-liquid separator has been redesigned from side-mounted to top-mounted. The drawing design has been completed, and the vessel diameter remains unchanged. The drawings have been sent out via email. | Pending | Yu gao/Chaoqun Hu/Zilaing Zhao
07/01 | SW Instrumentation 仪表配置 | Level switch position & interlock function 液位开关位置与联锁功能 Please confirm the finalised position (elevation, orientation, flange size and rating) and the interlock function of each level switch (LSL, LSLL, LSH, LSHH) on each vessel, together with the matching instrument selection. 请确认每台容器上各液位开关（低 LSL、低低 LSLL、高 LSH、高高 LSHH）的最终位置（标高、方位、法兰尺寸与压力等级）与联锁功能，以及对应的仪表选型。 | 7月10日反馈进展： 关于液位开关选型，之前寻价时只有VEGA的VEGASWING 63型号可以满足DN25 Class900 M的过程接口，其他厂家如E+H、Rosemount都不能满足。 About the selection of level switches, during the previous price search, only VEGA's VEGASWING 63 model could meet the DN25 Class 900 M process connection requirements. Other manufacturers such as E+H and Rosemount could not meet these requirements. 07/15：联锁值详见联锁条件表。 07/15：The interlock values can be found in the interlock condition table. | Pending | Chaoqun Hu/Yu gao
07/01 | SW Instrumentation 仪表配置 | Instrument datasheet next revision date 仪表数据单下一版本发出日期 Please advise the target issue date for the next revision of the Instrument Datasheet, reflecting the current SE01 design (post demister-configuration decision), the finalised interlock schedule, and the level switch position confirmation. 请说明反映当前 SE01 设计（demister 配置定稿后）、最终联锁清单以及液位开关位置确认的仪表数据单下一修订版本的目标发出日期。 | 7月10日反馈进展 仪表数据表已完成修订版，待意见讨论后看是否还需修改参数。 The instrument datasheet has been revised. After the discussion of opinions, we will see if the parameters still need to be modified. 08/05:根据最新设计温度和压力，更新仪表数据表，08/12发出 08/05:Update the instrument data sheet based on the latest design temperature and pressure, issued on 08/12 | YES | Chaoqun Hu/Yu gao
07/01 | SW Documentation Status 文档状态 | Current revision and next revision date of key deliverables 主要交付文件的当前版本与下一版本时间 Please confirm the current issued revision and the target date for the next revision of the following documents: • PFD • P&ID • URS • Equipment Datasheets • Control Philosophy • Instrument Datasheet • Operating Instructions • Cleaning Procedure • Vessel Design Calculation Package. 请确认以下文档的当前已发版本与下一修订版本的目标日期： · PFD · P&ID · URS · 设备数据单 · 控制策略 · 仪表数据单 · 操作说明 · 清洗程序 · 容器设计计算书。 | 7月10日反馈进展，操作手册还在编制中，其他设计文件已完成。On July 10th, we provided the progress update. The operation manual is still under preparation, while the other design documents have been completed. 08/21：工艺设计文件均已发出。 0821：The process design documents have been issued. | Pending | Shaofeng gao/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R1] Design Temperature — Vessel could fail during relief event. Equipment design temperature is specified for process requirements and does not consider elevated temperatures during relief events when short-term temperature increase has the potential to exceed the design temperature. 设计温度 —— 容器可能在泄放事件中失效。设备设计温度是按工艺需求设定的，未考虑泄放事件中的短时温升可能超过设计温度的情形。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：已更新数据表，提高设计温度，以满足工艺需求，图纸已升级。 07/10: Data sheet updated with elevated design temperature to meet process requirements; drawings revised accordingly. | YES | Chaoqun Hu/Ziliang zhao
07/02 | SW - Risk Register Engineering Design 工程设计 | [R2] Design Requirements — L:G ratio for plant is not clearly defined. Equipment design could result in very limited operating ranges and incorrect assumptions in plant capability and relief design. 设计条件 —— 装置的液气比（L:G ratio）未明确定义。可能导致设备设计的操作区间受限，以及在装置能力和泄放设计中做出错误假设。 | 7月10日反馈进展，根据最终确定的反应器尺寸核实气液比数据。On July 10th, the progress was reported. The gas-liquid ratio data was verified based on the final determined reactor size. 09/07: 根据08/25的会议确认PFD不更新，装置的气液比不改变 09/07: As confirmed in the meeting on 08/25, the PFD will not be updated, and the gas-to-liquid ratio of the unit will remain unchanged. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Engineering Design 工程设计 | [R3] Design Requirements — Catalyst specification is not available. Design may not be suitable for some catalysts. Dusty catalysts could cause blockages. 设计条件 —— 催化剂规格未明确。设计可能不适用于某些催化剂；含粉尘的催化剂可能导致堵塞。 | Keith / SW response: Design philosophy is based on catalyst beads/pellets which are dust-free, non-flammable and have exposure levels requiring OEB 3 or lower containment. Note: OEB 3 containment is a deviation from the URS and requires acceptance. Keith / SW 答复： 设计基于无粉尘、非燃、暴露等级 OEB 3 或更低的颗粒/粒状催化剂。注：OEB 3 的密闭要求相对 URS 存在偏离，需要接受确认。 | NO | SW
07/02 | SW - Risk Register Engineering Design 工程设计 | [R4] Access — Layouts are not available to assess whether access to equipment is acceptable for operations and maintenance. 通道 —— 布置图尚未提供，无法评估设备的操作与维护通道是否满足要求。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.1 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/YES | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R5] Maintenance — Lifting Aids (davit arms, lifting beams, etc.) have not been considered in design, with potential for injury to maintenance personnel removing heavy equipment for servicing / repair / replacement. 维护 —— 设计中尚未考虑起重辅助设施（吊臂、起吊梁等），维护人员在拆卸重型设备进行检修 / 修理 / 更换时可能存在人身伤害风险。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/YES | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R6] Lighting — Layouts are not available to assess whether lighting for routine operations and maintenance activities is acceptable. 照明 —— 布置图尚未提供，无法评估日常操作和维护活动的照明条件是否满足要求。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/YES | NO | UK/All
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R7] System leak detection — Pressure testing of high-pressure system will be hydraulically tested. Hydraulic testing demonstrates mechanical strength of the pressure system but does not demonstrate integrity for a hydrogen system. 系统检漏 —— 高压系统将进行水压试验。水压试验只能证明压力系统的机械强度，无法证明氢气系统的密封完整性。 | Keith / SW response: Helium testing is not routinely carried out in China. Keith / SW 答复： 国内通常不常规进行氦气检漏。 可以做气密性试验；国内整橇系统气密性试验后，分体运至英国，进入工厂房间后，再次组装，需重新进行泄漏试验，现场是否具备试验条件？现场可进行氦气检漏。 和CE认证机构确认一下具体方案。 A pneumatic test can be performed. After the complete skid system undergoes the pneumatic test in China, it will be shipped in split form to the UK. Upon arrival at the factory site and reassembly, a new leak test will be required. We need to confirm whether the site has the necessary conditions/facilities for this test. Helium leak detection is available on site. We will confirm the specific plan with the CE Notified Body. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R8] Line sizing / specification — Vents / headers incorrectly sized / specified, resulting in high back pressure and safety / operability issues, e.g. two-phase flow in emergency vent relief header. 管线规格 / 尺寸 —— 放空 / 泄放总管尺寸或规格不正确，导致背压过高及安全 / 可操作性问题，例如紧急泄放总管中出现两相流。 | 07/10：安全阀进出口尺寸详见P&ID 07/10：Refer to the P&ID for the inlet and outlet sizes of the safety valve. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R9] Insulation — Insulation requirements not specified, which could result in equipment / pipe layout not allowing space for insulation to be installed. 保温 —— 保温需求尚未明确，可能导致设备 / 管路布置未预留保温安装空间。 | Confirm the insulation material with Keith and determine the thickness. Once it's confirmed, provide a progress report on July 10th. 和Keith确认下保温材料，然后确定厚度。确定后，7月10日反馈进展 3D模型中管路的间距已按照保温厚度30-35mm预留了保温的安装空间。 The spacing between pipes in the 3D model has been designed to accommodate an insulation installation gap of 30-35mm, as per the insulation thickness requirements. | YES | Yinghui cheng/Chaoqun Hu/Shuangshuang fan/Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R10] Modular design — Modular design could introduce significant increase in site construction activities, e.g. mechanical and EC&I installation and subsequent testing. 模块化设计 —— 模块化设计可能大幅增加现场施工工作量，例如机械与电控仪表安装及后续测试。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 现有模块化设计的方案是根据进口电梯的尺寸，将整套设备拆分为4个撬块运输组装。 SW建议：需再考虑从屋顶直接吊装进去的方案，需要在后续周三会上进一步讨论。 The current modular design solution involves dividing the entire set of equipment into four skids for transportation and assembly based on the dimensions of imported elevators. SW Recommendation: Further consideration is needed for the direct hoisting-in-from-the-roof solution, which will be discussed in the upcoming Wednesday meeting. 07/29：会上澄清四撬块方案技术可行、屋顶吊装非必选；认证机构评估以 3D 定稿为前提，Keith 下周四返回后进一步确认。 07/29: Clarified that the four-module option is technically feasible and roof removal is not mandatory; the Notified Body assessment requires the finalised 3D layout, to be confirmed further with Keith after he returns next Thursday. 08/05:核实分撬是否与海运有关，和进出口部（公司内）请教下海运的最大尺寸事宜。 08/07：询问进出口部同事，集装箱内部高度有限，同时需要预留固定以及防撞等措施空间，所以橇块高度不要超过2.5m。整橇的话，有一种框架集装箱能放进去，但不密封，暴露在空气中，容易造成腐蚀，不建议采用。同时提醒，整橇运输也要考虑陆运高度限制。 09/08：根据SW最新建议的3撬块布置方案，框架高度不超过2.5m，超出部分管路采取预制加现场重新组装的安装方式。 09/08：According to the latest SW-recommended 3-pile block layout, the frame height shall not exceed 2.5m, with the excess portion of pipelines installed using a pre-fabrication and on-site reassembly method. | Pending | Chaoqun Hu/Shuangshuang fan
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R11] Skid assembled on site could result in CE / UKCA Responsible Person / Authorised Representative in China not being able to issue Declaration of Conformity for Skid Package. 撬块在现场组装可能导致中国境内的 CE / UKCA 负责人 / 授权代表无法为撬块整机签发符合性声明（Declaration of Conformity）。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 与CE认证方沟通确认好细节，特别是认证机构是否需要到UK现场验证，再发证。 We will communicate with the CE Notified Body to confirm all the details, in particular whether the certification body needs to attend the UK site for verification prior to issuing the certificate. 07/29：需以 3D 布置定稿版与 CE 认证机构沟通，评估现场组装后的验证方式、费用与工期。 07/29: The finalised 3D layout is required to engage the CE Notified Body and assess the post-assembly verification route, cost and duration. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R12] Wall penetrations — Layouts and cable schedules not available to confirm space is available for pipe / cable penetrations to / from R23 Module. 穿墙孔 —— 布置图和电缆清单尚未提供，无法确认与 R23 模块之间的管道 / 电缆穿墙位置有足够空间。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.6 | The initial cable schedule of CIMT is not fully aligned with the SW plan. SW has sent SLD, CIMT is verifying design discrepancies and will feed back comparison results, followed by discussions with SW CIMT初版线缆计划与SW计划没有完全匹配，SW已发出单线图，CIMT核对设计差异，返回对比结果，再与SW讨论。 7/23：CIMT根据SW提供的单线图，更新了电缆数量。部分流量控制器电缆待确认。硬联锁开关阀点位本安/隔爆待确认。 7/23：CIMT update the cable quantity based on the SLD provided by SW. some cables are still pending confirmed, 1. for flow controllers(modbus or 4-20mA). 2. for HW interlock on-off valve(I.S. or Ex d) 09/15：电缆数量已初步确认。因控制柜分撬，重新计算电缆数量。更新后电缆数量较多，待item135 确认后，继续确认此条目： The cable quantity has been preliminarily confirmed. Since the control cabinet is split across multiple skids, the cable quantity has been recalculated. The updated quantity is significantly larger; final confirmation of this item will proceed after item 135 is confirmed | NO | Dezhi meng
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R13] Catalyst charge point — Inlet pipe diameter is small and blockages may occur. 加料口 —— 加料管径较小，可能发生堵塞。 | Keith / SW response: Inlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking inlet pipe. Keith / SW 答复： 加料接口已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞加料管的风险。 | YES
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R14] Catalyst physical property requirements (size, shape, packing, etc.) are not defined, with the potential for incompatible catalyst to be charged to the reactors. 催化剂物性要求（粒径、形状、装填密度等）尚未定义，存在向反应器加入不兼容催化剂的风险。 | 07/10：催化剂直径0.5mm-5mm，形状不重要，球形，圆柱形，不规则颗粒状都可以，装填密度一般0.5g/mL来估算，但催化剂强度要高，不容易破碎起粉 07/10：The catalyst particle diameter ranges from 0.5 mm to 5 mm, with no specific shape requirement; spherical, cylindrical and irregular granular forms are all acceptable. The bulk density can be estimated at 0.5 g/mL in general. Meanwhile, the catalyst shall feature high mechanical strength to avoid fragmentation and dust generation. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R15] Packing of catalyst is not controlled, with the risk of reactants / gas channelling in the continuous reactor column, and the potential for incomplete reaction or impurities forming. 催化剂装填未受控，存在反应物 / 气体在连续反应柱内形成沟流的风险，可能导致反应不完全或杂质产生。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R16] Contained charge system design not available to assess risks and / or design limitation. 密闭加料系统的设计尚未提供，无法评估其风险与设计局限。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R17] Manual handling requirements for catalyst charging not assessed. 催化剂加料的人工搬运需求尚未评估。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R18] Access to charge point and support of charge container / bag not designed (access steps / integrated support shelf). 加料口的通道以及加料容器 / 料袋的支撑尚未设计（例如操作台阶、集成支撑架）。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R19] 20-micron catalyst retaining screen — Screen blockages prevent / limit flow of gas / reaction mix to continuous reactors. 20 微米催化剂拦截筛 —— 拦截筛堵塞会阻止 / 限制气体 / 反应液流入连续反应器。 | Keith / SW response: China Operations have reported blockages occur in local plant and screen has been removed and discarded. Keith / SW 答复： 国内运行反馈已在本地装置中发生堵塞，已将拦截筛拆除并弃用。 | YES
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R20] Polishing filter (FTR9832) — Filter blockages prevent / limit flow of gas / reaction mix through continuous reactors. Pressure increases in reactor system, with potential for undesirable reactions to occur, until reactor high-pressure trip is activated. 精滤器 (FTR9832) —— 滤芯堵塞会阻止 / 限制气体 / 反应液流经连续反应器；反应器压力升高，直到触发高压跳停前可能发生副反应。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 待定/To be determined 08/06:精滤器堵塞，加旁通，清洗时打开旁通，方便卸压 08/06: Fine filter clogged; bypass added. Open the bypass during cleaning to facilitate pressure release. | YES | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register CR01 – CR03 Reactors CR01 – CR03 反应器 | [R21] Temperature control — Jacket temperature control is configured to control jacket temperature only. Reactor internal temperatures are monitored, but no control, alarms or interlocks are configured for process control. 温度控制 —— 夹套温度仅控制夹套温度本身。反应器内部温度虽被监测，但未针对工艺过程配置控制、报警或联锁。 | Keith / SW response: Scale-up provides large operating envelopes for process temperature requirements and additional control, alarms and interlocks are not required. Keith / SW 答复： 由于放大试验提供了较大的工艺温度操作裕度，无需增加额外的控制、报警或联锁。 | YES
07/02 | SW - Risk Register System Pressure Monitoring 系统压力监测 | [R22] Differential pressure monitoring — Accuracy of static pressure measurements may not enable differential pressures to be calculated with any degree of accuracy or certainty. 差压监测 —— 静态压力测量精度可能不足以支持差压计算达到所需的精度或置信度。 | 通过反应柱上和反应器进出口管线上的的压力变送器精度估算，最大差压误差大约为40kPa。 Based on the accuracy estimation of the pressure transmitters on the reaction column and the inlet/outlet pipelines of the reactor, the maximum differential pressure error is approximately 40kPa. 07/14压力也增加了联锁。The pressure also increased the interlock. | YES | Chaoqun Hu/Yu gao
07/02 | SW - Risk Register Over Pressure Protection 过压保护 | [R23] Relief system design — Pressure systems not identified and relief studies not available. Identification of worst-case relief scenario not identified, and relief streams may be incorrectly categorised. Details of maximum reaction exotherm not fully documented. 泄放系统设计 —— 压力系统尚未识别、泄放研究尚未提供。最坏工况泄放情景未识别，泄放物流可能被错误归类。反应最大放热的详细信息尚未完整记录。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：详见安全阀计算书 07/10：See safety valve calculation sheet for details. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Separator 气液分离器 | [R24] Vessel design — Complete degassing of product stream not achieved, with the potential for hydrogen carry-over into BT04 and product transfer containers. 容器设计 —— 产品物流未实现完全脱气，H₂ 可能带入 BT04 及产品转运容器。 | 07/10：气液分离器满足气液分离的要求 07/10：The gas-liquid separator meets the requirements for gas-liquid separation. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Separator 气液分离器 | [R25] Cleaning of separator not fully understood but current concept relies on vessel free-draining to BT04. Current spray ball sizing is not consistent with this approach and may require significant rework to process piping. 分离器清洗方案尚未完全明确，当前概念依赖容器向 BT04 的自重排放。现有喷淋球规格与该思路不匹配，可能需要对工艺管路进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.4,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：R24-SE01采用喷淋循环冲洗，增加了DN15的排净口，不依赖R24-BT04的重力排放 09/07：R24-SE01 adopts spray circulation flushing. A DN15 drain port has been added so that gravity drainage from R24-BT04 is no longer required. | Pending | Chaoqun Hu/Ziliang zhao
07/02 | SW - Risk Register Separator 气液分离器 | [R26] Cleaning of LIT003 housing does not appear to be considered in design. LIT003 液位变送器外壳的清洗在设计中似乎尚未考虑。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.7 | 同上42行回复/Translation of the 42nd line above. | YES | Chaoqun Hu
07/02 | SW - Risk Register Separator 气液分离器 | [R27] P&ID does not clearly show nozzle locations and could lead to mal-ops / misunderstanding of the design intent by the Operations team. P&ID 上未清晰标注管嘴位置，可能导致运行团队误操作或误解设计意图。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.3 | 07/10：已标注，详见P&ID 07/10：Marked as indicated; refer to the P&ID for details. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Sampling 取样系统 | [R28] Sampler design — When depressurising the sample collection chamber, high gas or vapour vent rates could result in a bubbly or churn-turbulent flow regime, and sample will discharge to vent line as two-phase flow. 取样器设计 —— 对取样收集腔进行减压时，气体或蒸汽的高排放速率可能形成鼓泡或搅动湍流流态，样品将以两相流形式排入放空管。 Related Outstanding Questions ｜ 关联待澄清问题：Q5.1 | 07/10：缓冲罐静置一定时间，让气液分层，泄压时缓慢打开手阀 07/10：Allow the buffer tank to stand for a certain period for vapor-liquid stratification, then open the manual valve slowly during depressurization. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Sampling 取样系统 | [R29] With significantly more gas being present in the process stream, what will prevent overpressure of sample bottle and low-pressure nitrogen pipework? 由于工艺物流中气体明显较多，采用什么措施来防止取样瓶和低压氮气管路的超压？ | 07/10：取样瓶和氮气管线投用时，系统已泄压至常压 07/10：The system has been depressurized to atmospheric pressure prior to commissioning of sampling bottles and nitrogen pipelines. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R30] Catalyst Discharge Plug valve — Outlet pipe diameter is small and blockages may occur. 催化剂卸料闸阀 —— 出口管径较小，可能发生堵塞。 | Keith / SW response: Outlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking outlet pipe. Keith / SW 答复： 出口接管已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞出口管的风险。 | YES
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R31] Contained discharge system design not available. Layout design may not provide sufficient headroom for contained discharge system. 密闭卸料系统的设计尚未提供。当前布置可能无法为密闭卸料系统提供足够的顶部空间。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R32] Complete removal of catalyst during discharging operations is unlikely to remove 100% of the material, with the risk of cross contamination of catalyst material between campaigns. 卸料操作难以完全（100%）清除催化剂，存在批次间催化剂交叉污染的风险。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Cleaning 清洗 | [R33] CIP Design — CIP design incomplete. Initial spray ball sizing is inconsistent with process line sizing approach and may require significant rework to process piping and/or equipment layout. CIP 设计 —— 就地清洗设计不完整。初步喷淋球规格与工艺管路选型方式不匹配，可能需对工艺管路和 / 或设备布置进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.1,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：配置喷淋球的设备，喷淋球的流量与排放管径匹配，采用喷淋循环冲洗 09/07：Equipment fitted with spray balls shall have spray ball flow rate matched to the drain line size for spray circulation flushing. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Cleaning 清洗 | [R34] Cleaning carried out at nominally atmospheric pressure with the risk of material being trapped between flanges, which tend to separate slightly during high-pressure operation, and could lead to cross contamination between batches. 清洗在近常压下进行，高压运行时法兰会出现微量分开，可能将物料残留于法兰间隙中，进而导致批次间交叉污染。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 09/07：法兰密封面擦拭取样，定期开盖检查清洁状况 09/07：Swab sampling of flange sealing faces and periodic vessel opening inspection for cleanliness. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Cleaning 清洗 | [R35] Validation / Verification — Cleaning validation / verification philosophy not available. QA may not accept that the continuous reactor achieves minimum cleaning standards. 验证 / 确认 —— 清洗验证 / 确认策略尚未提供。质量保证部门可能不接受连续反应器满足最低清洗标准。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.2,Q1.9 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 更新清洗方案后讨论/Discuss after updating the cleaning procedure. 09/07：与研发人员讨论后，由于国内外存在差异，建议由SW属地QA提供清洗验证 09/07：After discussion with the R&D team, considering regional differences between China and overseas sites, it is recommended that the local QA team of SW provide cleaning validation. | Pending | Chaoqun Hu/Xiantao Feng
07/02 | SW - Risk Register Cleaning 清洗 | [R36] Layout — Layouts are not available to evaluate the impact of bypasses, dead legs, drains, vents, etc. 布置 —— 布置图尚未提供，无法评估旁路、死管、排放、放空等的影响。 | 09/08：3D模型确定后推进。 09/08：After the 3D model is finalized, proceed with the advancement. | NO | Shuangshuang fan
07/02 | SW - Risk Register Cleaning 清洗 | [R37] Layout — Layouts are not available to evaluate access to equipment for visual inspections, which may impact the effectiveness of critical inspections. 布置 —— 布置图尚未提供，无法评估设备的目视检查通道，可能影响关键检查的有效性。 | 09/08：3D模型确定后推进。 09/08：After the 3D model is finalized, proceed with the advancement. | NO | Shuangshuang fan
07/02 | SW - Risk Register Cleaning 清洗 | [R38] Layout — Equipment design / layout does not allow for routine disassembly and manual cleaning. Equipment turnaround times and operating costs would be adversely impacted if CIP system cannot be validated. 布置 —— 设备设计 / 布置未考虑日常拆装和人工清洗。如 CIP 系统无法通过验证，设备周转时间和运行成本都会受到不利影响。 | 09/08：3D模型确定后推进。 09/08：After the 3D model is finalized, proceed with the advancement. | NO | Ziliang zhao
07/02 | SW - Risk Register FT001 FT001 流量计 | [R39] Liquid Stream Flow Sensor for flow control loop FIC001. FT001 is a Coriolis mass flow meter installed downstream of the metering pump MP01. Pulsed flow from the pump will impact on the flow measurement and accurate flow control may not be possible. 液相流量传感器（用于 FIC001 流控回路）—— FT001 是安装在计量泵 MP01 下游的科里奥利质量流量计。泵的脉冲流会影响流量测量，可能无法实现精确流量控制。 | Keith / SW response: China Team have previously used this configuration and not experienced flow control issues. No further action required. Keith / SW 答复： 国内团队此前采用过该配置，未出现流控问题。无需进一步动作。 | YES
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R40] Maximum flow may exceed separator design limitations and carry hydrogen over into BT04 / product collection containers. 泵的最大流量可能超出分离器的设计上限，将 H₂ 带入 BT04 / 产品收集容器。 | 07/10：分离器的直径足够大，泵为最大流量时能满足分离要求 07/10：The separator has a sufficiently large diameter to meet separation requirements even when the pump operates at maximum flow rate. | Pending | Chaoqun Hu
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R41] Pump turndown does not meet URS minimum flow requirements. 泵的调节比无法满足 URS 中规定的最低流量要求。 | 07/10：机泵条件中规定了泵的最小流量要求，待泵厂家返回资料时审查是否满足最低流量要求 07/10：Minimum flow requirements for pumps are specified in pump data sheets. Compliance with the minimum flow criteria shall be verified upon receipt of vendor documentation. 08/05：根据最新机泵数据单走采购流程询问厂家资料 08/05：Proceed with the procurement process and request vendor documentation based on the latest pump data sheet. | NO | Chaoqun Hu
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R42] Hydrogen gas flow controller — Flow controller does not support tight shut-off and system pressure increase during hold periods. 氢气流量控制器 —— 控制器不支持严密关断，系统在保压期间压力会持续上升。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller to provide tight shut-off. Keith / SW 答复： 在控制器下游追加一台切断阀以提供严密关断。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R43] Maximum flow through controller may exceed separator design limitations and carry liquid into the vent line. 流经控制器的最大流量可能超出分离器设计上限，将液体带入放空管。 | Keith / SW response: High level interlock installed in the separator to stop gas supply and close PIC028 shut-off valve (CV08). Keith / SW 答复： 在分离器上设置高液位联锁，停 H₂ 供给并关闭 PIC028 的切断阀（CV08）。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R44] Time required for pressure testing the system and nitrogen inertion may be excessively high. 系统加压试验及氮气钝化所需时间可能过长。 | Keith / SW response: Pressure test / inertion times to be evaluated during FIC003 selection. Manual vent installed on BT03 to reduce depressurisation times via FIC003. Keith / SW 答复： 在 FIC003 选型时评估压力试验 / 惰化时间。在 BT03 上加装人工放空阀，缩短经 FIC003 的减压时间。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R45] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端的差压超出厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register LIC003 LIC003 分离器液位 | [R46] SE01 Separator Level Indicator — Cleaning / decontamination of housing is not possible. Residual product in housing could lead to cross contamination between campaigns. SE01 分离器液位指示 —— 变送器外壳无法进行清洗 / 净化。外壳内的残留物料可能导致批次间交叉污染。 | Keith / SW response: Design relies on dissolution of residual material. 100% flood-fill of housing is not possible, therefore any residual trace contamination in the housing is deemed to be small and will not significantly impact cleaning verification. Keith / SW 答复： 设计依赖残余物料的溶解。外壳无法 100% 灌满，因此外壳内任何残余痕量污染被视为很小，不会显著影响清洗验证。 | YES
07/02 | SW - Risk Register FIC004 FIC004 分离器液位控制 | [R47] Separator outlet flow / level control — Differential pressure across the controller exceeds manufacturer's recommendations and controller capability. 分离器出口流量 / 液位控制 —— 控制器两端差压超出厂家建议范围及控制器能力。 | 分离器出口先通过减压阀减到0.2MpaG左右，可以满足厂家建议的差压范围 The outlet of the separator is first reduced to approximately 0.2MpaG through a pressure reducing valve, which can meet the differential pressure range recommended by the manufacturer | Pending | Chaoqun Hu/Yu gao
07/02 | SW - Risk Register FIC005 FIC005 BT01 氮气吹扫 | [R48] BT01 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT01 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register FIC007 FIC007 BT04 氮气吹扫 | [R49] BT04 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R50] System back pressure controller — The back pressure controller does not support tight shut-off during hold periods and system pressure will not be maintained. 系统背压控制器 —— 该控制器在保压期间不支持严密关断，系统压力无法保持。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller. Keith / SW 答复： 在该控制器下游追加一台切断阀。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R51] Time required for depressurising the system following pressure testing and nitrogen inertion may be excessively high. 加压试验和氮气钝化之后系统减压所需时间可能过长。 | Keith / SW response: Manual bypass installed around PIC028 controller. Keith / SW 答复： 在 PIC028 控制器周围加装人工旁路。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R52] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端差压超出厂家建议范围，可能导致控制器无法正常工作。 | 07/10：关于背压阀028，之前Bronkhorst的电子压力阀厂家计算反馈的阀前背压范围最大为0.9~6MpaG，范围量程比不能过大。 07/10：About the back pressure valve 028, previously, the manufacturer of Bronkhorst’s electronic pressure valve calculated and reported that the maximum range of the back pressure before the valve was 0.9 to 6MpaG, and the range-to-range ratio cannot be too large. 09/07: 关于气液分离器设计温度改为270℃后，与Bronkhorst电子背压阀厂家进行沟通，厂家反馈270℃的温度可能会很快损坏电子元件导致无法使用，厂家推荐的工作温度最高是50℃，短时间能承受100~120℃左右。然后又咨询了一些耐高温的气动调节阀厂家，反馈背压的范围过大且流量偏小，选不出合适的阀门CV值。 会上确认还用该电子背压阀，270℃泄放工况很少出现，当270℃时背压阀不会外漏，电子元件损坏可以接收，将选择耐高温的密封材质。 09/07: After the design temperature of the gas-liquid separator was changed to 270℃, we communicated with the Bronkhorst electronic back pressure valve manufacturer. The manufacturer reported that a temperature of 270℃ might quickly damage the electronic components and make it unusable. The manufacturer recommended a maximum working temperature of 50℃, and it can withstand around 100 to 120℃ for a short period of time. Then, we consulted some manufacturers of high-temperature resistant pneumatic control valves. The feedback was that the range of back pressure was too large and the flow rate was too small, making it impossible to select a suitable CV value for the valve. It was confirmed at the meeting that the electronic back pressure valve would still be used. The 270℃ discharge condition rarely occurs. When the temperature is 270℃, the back pressure valve will not leak out. The damage of electronic components can be accepted. High-temperature resistant sealing materials will be selected. | YES | Chaoqun Hu/Yu gao
07/02 | SW - Risk Register PIC030 PIC030 分离器液相出口减压 | [R53] Separator liquid outlet pressure reducer — Is this confirmed as a Bronkhorst pressure controller, or is a mechanical regulator still an option? Does this provide the required independence assumed in the relevant SIL / risk assessments? 分离器液相出口减压器 —— 该阀是否确认为 Bronkhorst 电子压力控制器？还是仍可能选用机械式减压阀？该配置能否提供相关 SIL / 风险评估中假设所需的独立性？ | 目前选型机械式减压阀。机械阀不是电子设备，没有相关的SIL认证。 At present, mechanical pressure reducing valves are being selected. Mechanical valves are not electronic devices and do not have the relevant SIL certification. | Pending | Chaoqun Hu/Yu gao
07/02 | SW - Risk Register PIC049 PIC049 BT04 背压控制 | [R54] BT04 back pressure controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 背压控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register Automation 自动化 | [R55] Automation Build — Philosophy and Design documentation not available to assess risks and limitations. 自动化建设 —— 自动化策略与设计文档尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q3.1,Q3.2 | 专题沟通后确定反馈 09/07：控制说明和联锁表已于08/21发给SW 09/07：The control description and interlocks table were sent to SW on 08/21. | Pending | Chaoqun Hu/Dezhi meng/Ziliang zhao
07/02 | SW - Risk Register Documentation 文档 | [R56] Technical File — Technical File not available to assess risks and limitations. 技术文件 —— 技术文件尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.5,Q7.1 | SW现场3D等事项确定后陆续提供。 At the SW site, final design files will be provided sequentially after the 3D models and other topics have been confirmed. | NO | Shaofeng gao/All
07/02 | SW - Risk Register Documentation 文档 | [R57] O&M Manual — O&M manual not available to assess risks and limitations. 操作维护手册 —— O&M 手册尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q7.1 | 07/10：操作手册的编制还在进行中 07/10：Preparation of the operation manual is still in progress. 07/29：操作维护手册预计 8 月中完成。 07/29: The O&M manual is scheduled for completion in mid-August. 09/07：操作手册已于08/21发给SW 09/07：The operating manual was sent to SW on 08/21. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Documentation 文档 | [R58] Emissions Calculations — Calculations to demonstrate expected release of Class A and Class B VOCs to atmosphere are not available. These are required to demonstrate compliance with EA Permit limits. 排放量计算 —— 尚未提供证明 A 类和 B 类 VOC 向大气排放的预期计算。该计算是证明满足 EA 许可（英国环境署许可）限值要求所必需。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW负责排放量计算/SW is responsible for emissions calculation. | YES | Chaoqun Hu
07/02 | SW - Risk Register Regulatory Compliance 法规合规 | [R59] CE ¦ Functional Safety ¦ DSEAR / ATEX ¦ PSSR ¦ COSHH ¦ PUWER (Access, manual handling) ¦ Working at Height (Access Steps / Support Shelf) ¦ LOLER (Davit arms) ¦ Lighting ¦ Occupational Hygiene ¦ EA Permit — Regulatory non-conformance would prevent beneficial use of equipment in the UK. CE 认证 ¦ 功能安全 ¦ DSEAR / ATEX 防爆 ¦ PSSR 压力系统安全 ¦ COSHH 危害物质 ¦ PUWER 工作设备（含通道与人工搬运）¦ 高处作业（操作台阶 / 支撑架）¦ LOLER 起重设备（吊臂）¦ 照明 ¦ 职业卫生 ¦ EA 环境许可 —— 任何法规合规缺失都会导致设备无法在英国正常投入使用。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW内部的提醒事项。 CFCT核实加料步梯是否包含在内。 SW提供步梯平台尺寸。 Internal reminders for SW: CFCT to verify whether the feeding staircase is included. SW to provide dimensions of staircase and platform. 09/15 SW requires TJ to provide the following 3 heights: 1) flange height to the output 2) flang height to the catalyst charging valve 3) flang height to the top of cage 09/21 Keith发邮件，SW已将STEP格式转换成PDF，并已标注平台所需尺寸。 | NO | Zilang zhao/All
07/14 |  | 根据生产经验，研发建议原R24-CR01的直径由DN80改为DN50，导致产能下降，可能无法满足URS中的产能30kg/day Based on production experience, the R&D team proposes reducing the diameter of the original R24-CR01 from DN80 to DN50. This modification will result in lower production capacity, which may fail to meet the 30 kg/day throughput specified in the URS. | 07/14：周三会上确定/To be confirmed at Wednesday's meeting. 07/15：暂定R24-CR01的直径修改为DN65，等9月份研发提供DN65的反应器实验数据后最终确认反应器的尺寸为DN65或DN50 07/15：It is tentatively agreed to revise the diameter of R24-CR01 to DN65. The reactor size (either DN65 or DN50) will be finalized after the R&D department provides DN65 reactor test data in September. 07/29：会上确定按 DN65 / DN50 两套方案并行准备，并建立变更影响日志；待 9 月研发 DN65 实验数据后最终定案。 07/29: Agreed to prepare the DN65 and DN50 cases in parallel and to set up a change-impact log; final decision after the September DN65 R&D test data. | NO | Xiantao Feng/All
07/23 | SW | 气液分离器SE01容器承受从常压到60 barg的压力循环次数？ How many pressure cycles does the gas-liquid separator SE01 vessel undergo from atmospheric pressure to 60 barg? | 07/23:会上讨论了加氢装置的操作周期，意见存在不一致，关于连续加氢的年运行周期，SW内部沟通后反馈循环次数需求。 气液分离器的设计温度调整到270℃，对应设计压力调整到7.5MPaG。垫片选用金属环垫片。 07/23：The operating cycle of the hydrogenation unit was discussed at the meeting, and divergent opinions remain. SW shall coordinate internally and provide feedback on the required number of cycles regarding the annual operating cycle for continuous hydrogenation. The design temperature of the gas-liquid separator shall be revised to 270°C, with the corresponding design pressure adjusted to 7.5 MPaG. Metallic ring gaskets shall be adopted . 08/06：垫片材质？原料酸性 PEEK，再寻找合适的垫片，讨论。 09/07：管法兰与金属环垫片均可选316L，但需要做技术要求：①金属环垫片硬度≤150HB，管法兰硬度≥160HB；②以上材料需有硬度检测报告；③到厂后复验；④组装前按硬度差≥10HB配对使用。 09/07：Both the pipe flanges and the metal ring gaskets may be made of 316L. However, the following technical requirements shall be complied with: ①The hardness of the metal ring gasket shall be ≤ 150 HB, and the hardness of the pipe flange shall be ≥ 160 HB. ②Hardness test reports shall be provided for all the above materials. ③The materials shall be re-inspected upon arrival at site. ④Prior to assembly, the flange and gasket shall be paired based on a hardness difference of ≥ 10 HB (i.e., the flange hardness shall be at least 10 HB higher than that of the gasket). | YES | Zilang zhao/Chaoqun Hu
07/23 | IEPE | P&ID中压力表无根部阀，是否需要增加根部阀？ Pressure gauges shown on the P&ID are not equipped with root valves. Is it necessary to add root valves? | 07/23:按照现有P&ID配置。 07/23：Configure in accordance with the existing P&ID. | YES | Chaoqun Hu/Yu gao
07/23 | IEPE | PCV028侯径小，反应系统卸压时，全开PCV028卸压速度也很慢，建议将PCV028的旁通手阀改为开关阀 PCV028 has a small orifice. When depressurizing the reaction system, the depressurization rate remains low even if PCV028 is fully open. It is recommended to change the bypass manual valve of PCV028 to an on-off valve. | 07/23:按照现有P&ID配置。 07/23：Configure in accordance with the existing P&ID. | YES | Chaoqun Hu
07/29 | SW | 针对 R24-CR01 直径变更（DN80→DN65/DN50），建立变更影响日志/清单，逐项列出受影响的设备、仪表、管线、安全阀及相关文件与参数，确保无遗漏。 Establish a change log / impact list for the R24-CR01 diameter change (DN80→DN65/DN50), itemising every affected item of equipment, instrumentation, piping, relief device and the related documents and parameters, so that nothing is missed. | 07/29：会上同意建立变更影响日志，由国内团队逐项梳理受影响范围并跟踪关闭。 07/29: Agreed at the meeting to create a change-impact log; the China team will work through the affected scope item by item and track it to closure. 09/07:变更清单已整理完成，根据08/25的会议确认PFD不更新，目前只有反应器的设备数据表需要变更 09/07: The change list has been finalized. Based on the meeting on 08/25, it was confirmed that PFD will not be updated; currently, only the equipment data sheet for the reactor has changed. | NO | Shaofeng Gao/Chaoqun Hu
07/29 | SW | 反应器 DN65 与 DN50 两种规格并行准备设计方案：先确定处理量，再分别出 PFD 与物料平衡；并核实仪表选型、安全阀/泄放组合是否需相应调整。待 9 月研发提供 DN65 实验数据后定案。 Prepare two parallel design cases for the DN65 and DN50 reactor: fix the throughput first, then issue a PFD and mass balance for each, and verify whether instrument selection and the relief-valve combination need to change accordingly. To be finalised once R&D provides the DN65 test data in September. | 07/29：会上确定按 DN65 / DN50 两套方案并行准备，使 9 月数据到位后可直接定案，不影响整体进度。 07/29: Agreed to progress both the DN65 and DN50 cases in parallel so that the decision can be taken as soon as the September data is available, without affecting the overall schedule. 0914：和研发沟通DN50反应器尺寸，更新设备数据单。 0914: Communicate with the R&D department regarding the size of the DN50 reactor and update the equipment data sheet. | NO | Shaofeng Gao/Chaoqun Hu/Xiantao Feng
07/29 | IEPE | 容器设计压力由 80 barg 调整为 75 barg，以保持法兰等级 CLASS 900、避免材料选型受限；需在设备数据表、图纸及相关计算书中同步更新落实。 Vessel design pressure revised from 80 barg to 75 barg in order to retain the CLASS 900 flange rating and avoid limitations on material selection; to be updated consistently in the equipment datasheets, drawings and supporting calculations. | 07/29：周二与 Keith 讨论已取得初步一致，继续推进并在各设计文件中落实。 07/29: Initial agreement reached with Keith on Tuesday; to be carried forward and reflected in the design documents. 08/12：设备数据单已更新完成 08/12：The equipment data sheet has been updated. | YES | Chaoqun Hu/Ziliang Zhao
07/29 | SW | 四撬块分体运输 vs 屋顶整体吊装的决策路径：国内先完成 3D 布置定稿，再以定稿版与 CE 认证机构评估现场组装后的验证方式、费用与工期；Keith 下周四返回后确认四撬块方案可行性；SW 侧评估屋顶更换的费用、工期及 R23 停用影响。 Decision path for four-module split shipment vs a whole-unit lift through the roof: the China team to finalise the 3D layout first, then use the finalised version to evaluate with the CE Notified Body the post-assembly verification route, cost and duration; confirm the four-module option with Keith after he returns next Thursday; SW to assess the roof-replacement cost, duration and the impact of taking R23 out of service. | 07/29：会上提议需要澄清四撬块方案技术上可行，屋顶吊装并非必选项；认证机构评估需以 3D 定稿为前提，国内加快 3D 定稿以尽早取得费用与工期结论。 07/29: Clarified at the meeting that the four-module option is technically feasible and roof removal is not mandatory. The Notified Body assessment depends on the finalised 3D layout, so the China team will accelerate finalisation to obtain the cost and schedule answer as early as possible. | NO | Ziliang Zhao/Shaofeng Gao/Keith
07/29 | SW | 明确下阶段（建造 / FAT）文件的编制与签发流程：由谁编制、由谁签发；SW 场地有自有的 FAT / 验证模板。CE 认证方参与文件评审但不参与签发。约定后续安排专题讨论。 Define the preparation and sign-off process for the next-stage (construction / FAT) documentation — who prepares and who signs off. The SW site has its own FAT / validation template. The CE Notified Body will take part in document review but not in sign-off. A dedicated follow-up discussion to be arranged. | 07/29：双方同意尽早对比两侧模板并识别差异；倾向直接采用 UK 模板以便英国侧验证与确认，国内按该模板提供资料，避免后期返工。 07/29: Both sides agreed to compare the two templates early and identify any gaps; the preference is to adopt the UK template so that verification and validation on the UK side is straightforward, with the China team supplying information to that template to avoid rework later. | NO | Shaofeng Gao/Ziliang Zhao
07/29 | IEPE | 请 SW / Keith 提供英国现场验证（validation）所需的信息清单与模板，国内据此提供资料并按该模板执行，以便尽早识别中英双方要求差异。 SW / Keith to provide the list of information required for the UK site verification / validation process, together with the template, so that the China team can supply the information and work to that template and any differences between the UK and China requirements are identified early. | 07/29：会上确定由 SW 提供模板与信息需求清单，国内提供文件 / 信息并按模板填写；下周与 Keith 沟通落实。 07/29: Agreed that SW will provide the template and the information requirement list; the China team will supply the documents / information and complete them to that template. To be taken forward with Keith next week. | NO | Keith/Shaofeng Gao
07/29 | SW | HAZOP 前须与 Keith 就 3D 布置与控制说明（含操作手册）达成一致 —— 该两项目前仅国内内部讨论过，是余下唯二可能引发重大设计变更的环节，须在 HAZOP 前关闭，以确保 HAZOP 只做一次、避免重做。 The 3D layout and the control philosophy (including the operating manual) must be agreed with Keith before HAZOP. These two items have so far only been reviewed internally by the China team and are the only remaining items that could still trigger a significant design change; they must be closed out beforehand so that HAZOP is run once only and does not have to be repeated. | 07/29：会上确认目标为「HAZOP 只做一次」；两项在 9 月初 HAZOP 前与 Keith 讨论定稿。 07/29: The meeting confirmed the objective of running HAZOP only once; both items to be discussed and finalised with Keith ahead of the early September HAZOP. | NO | All
08/25 | IEPE | 反应柱 R24-CR01 直径变更（DN80→DN65/DN50），产能改变，进料量可能会调整，是否需要修改PFD？ The diameter of the reaction column R24-CR01 has been changed (from DN80 to DN65/DN50), resulting in a change in production capacity. The feed volume may need to be adjusted. Is it necessary to modify the PFD? | 08/25：反应柱 R24-CR01 直径变更（DN80→DN65/DN50），跟研发和Keith沟通后确认：流速不变工况下后续反应器可承担部分转化率，故产能不一定改变，PFD不做调整；对应的TCU功率匹配事宜可通过调整出口温度实现，方案由SW自行调整。 08/25: Diameter of reaction column R24-CR01 was changed (from DN80 to DN65/DN50). After communicating with R&D and Keith, it was confirmed that under the condition of unchanged flow rate, the subsequent reactor can handle a portion of the conversion rate. Therefore, the production capacity is not necessarily changed, and the PFD will not be adjusted. The power matching of the corresponding TCU can be achieved by adjusting the outlet temperature. The plan will be adjusted by SW on its own. | YES | Keith/Xiantao Feng
08/25 | SW | CFCT向SW提供R24-BT03的尺寸和3D模型，方便Keith优化3D方案 CFCT provides SW with the dimensions and 3D model of R24-BT03 to facilitate Keith's optimization of the 3D design. | 08/25：会后提供R24-BT03的尺寸和3D模型 08/25: Dimensions and 3D model of R24-BT03 will be provided after the meeting. | YES | Shuangshuang Fan
09/07 | CFCT | 根据SW建议的3撬的设备布置的3D模型，主要讨论气液分离器的安装高度、HTF管路的高度及撬外管路的安装。 Based on the three-skid equipment layout 3D model proposed by SW, the main focus is on the installation height of the gas-liquid separator, the height of the HTF pipeline, and the installation of external pipelines. | 09/08：①分离器的安装高度：会上确定分离器安装高度可以降低，不必自流到 BT04。新的高度反馈给胡工，用来确定减压阀后压力； ②HTF的10 根管穿墙：穿墙高度先维持原高度，撬内和现场的高度差通过弯头转接； ③撬外管路的安装：对于安装高度高于运输高度2.5m的管路，撬体组装时预制好，运输时拆下，现场再次安装； ④按照BT01 / BT04 / 分离器 / 冷凝器尽量前移，缩减中间通道，以及CIP 和排放接口在撬装前端操作的方案更新3D模型； ⑤对于拉撬方案可能存在的操作维修不便的问题，后续邮件沟通。 09/08：①Separator Installation Height: It will be confirmed that the separator installation height can be reduced and does not necessarily need to flow by gravity to BT04. The new height will be reported to Engineer Hu to determine the pressure after the pressure reducing valve; ②The 10 pipes of HTF penetrate the wall: the height of the penetration is initially maintained at the original level, while the height difference between the inside and the site is adjusted through elbows; ③Installation of external pipelines: For pipelines with an installation height exceeding the transportation height by 2.5m, the skid assembly is prefabricated, then disassembled during transportation and reinstalled on-site; ④Update the 3D model according to the plan of moving BT01/BT04/separator/condenser forward as much as possible, reducing the intermediate channel, and operating CIP and discharge interfaces at the front end of the assembly; ⑤Regarding the potential inconvenience in operation and maintenance of the pull and pry scheme, we will communicate via email . 09/15：21日完成3D模型更新。 09/15: The 3D model update was completed on the 21st. | NO | Shuangshuang Fan
09/15 | SW | 3D模型确定后，讨论关闭Pending项内容。 After the 3D model is determined, the discussion will focus on closing the "Pending" items. |  | NO | ALL
09/15 | CIMT | 因为分撬原因，SW要求现场本安接线箱尺寸缩小，小尺寸接线箱可考虑SW采购方案，CIMT提供所需接线箱最小尺寸。 Due to skid split, SW requires the on-site IS junction box to be reduced in size. For the smaller junction box, CIMT will provide the minimum size required for the junction box. SW will assess if the size is feasible and get the box in UK if possible | 09/15：CIMT 提供接线箱最小尺寸 09/15：CIMT provided the minimum size needed | NO | ALL

## 0907
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. 05/12：Keith建议用气液两相计算安全阀尺寸，不提供模板 05/12：Keith suggests using gas-liquid two-phase calculations for determining the size of the safety valve, but no template is provided. 05/20：根据API520的气液两相泄放时计算安全阀尺寸，部分已完成 05/20：Calculate the size of the safety valve based on the API520 standard for the two-phase gas-liquid discharge situation.Partially completed. 06/02：安全阀计算初版已完成（包含临界流体和气液两相），校审中。 06/02：Preliminary calculation of safety relief valve (covering critical fluid & gas-liquid two-phase flow) completed, under review. 06/09: General 1. What was the source/reference for the Specific Volumes stated in column D/D 列中比容数据的来源及参考依据是什么？ The Specific Volumes stated in column D are derived from Aspen Plus simulation results.比容数据来自Aspen模拟 2. There is no backpressure considered in the calculation. The emergency vent relief will create some backpressure which needs to be considered in the calculation./本次计算未考虑背压。紧急放空泄放过程会产生一定背压，该因素需纳入计算。 Backpressure consists of static backpressure and built-up backpressure. Given the wide total pressure range, backpressure effects shall be incorporated into the calculation.背压分为静背压和积聚背压，总压力范围大，将背压包含在其中 3. At the assumed relief pressure Ethyl Acetate will be a supercritical fluid, therefore the required relief mass flowrate will not be dependent on the latent heat of vapourisation, and the calculated ‘required discharge area’ will not be valid. Do you agree with this statement, or have you found a reference in the standard that allows for this? 在设定的泄放压力下，乙酸乙酯将处于超临界流体状态，因此所需泄放质量流量不再依赖汽化潜热，本次算出的所需泄放流通面积也不再适用。你是否认同该观点？或是你是否在相关标准中查到可支持该计算的依据？ 详见06/16回复. Please refer to the reply dated 06/16 for details. Cooling Failure Calculations 4. For the cooling failure calculation, I would suggest using 550kJ/mol rather than 501.48. This is based on Sandwich PSL experience of heats of reaction. 针对冷却失效工况计算，建议将反应热取值由 501.48 kJ/mol 改为 550 kJ/mol。该取值参考了桑威奇工艺安全实验室（Sandwich PSL）过往反应热项目经验。 OK 5. Is the feed flowrate used in the calculation, based on the maximum metering pump capabilities? Do you assume a maximum concentration of reactant in the feed stream? 计算中采用的进料流量，是否按照计量泵最大额定流量取值？计算时是否假定进料流中反应物浓度为最大浓度？ The flow rate used in the calculation is set at the maximum rated capacity of the metering pump, and the maximum reactant concentration is adopted for the feed stream.计算时流量是按照计量泵最大额定流量取值，反应物浓度为最大浓度 06/16：根据文献“Relief Calculation for Supercritical Fluids”计算超临界流体的质量泄放流量，会后向Keith发计算书审核 06/16：Calculate the mass relief flow rate of supercritical fluids in accordance with the document Relief Calculation for Supercritical Fluids, and send the calculation sheet to Keith for review after the meeting. | YES | Chaoqun Hu
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun Hu
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. 06/16：06/11已收到审核完成的URS。 06/16：Received the reviewed URS on 06/11. | YES | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith确认CV08也是故障关，可以使用DS6080型，该型号没有5 bar 差压限制。 Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith confirmed that CV08 is also a faulty-close type, the DS6080 model can be used. This model does not have a 5-bar differential pressure limit. Keith offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. 06/02 进展：Habonim厂家反馈了样本资料，反馈可以满足工艺参数需求，货期大概16~20周。可以作为开关阀的备选品牌。 06/02 Progress: "Habonim" manufacturer has provided sample materials that can meet the process parameter requirements. The delivery time is approximately 16 to 20 weeks. It can be an alternative brand for on-off valves. | YES | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. 06/02：关于气液分离器液相出口减压，电子压力阀和自力式减压阀都可以满足使用，首选自力式减压阀。 06/02：For pressure reduction at the liquid outlet of the gas-liquid separator，both electronic pressure valves and self-operated pressure reducing valves can meet the requirements, with self-operated pressure reducing valves being the preferred choice. | YES | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. 05/20：SW已更新完URS并发出。The SW has been updated and the URS has been sent out. | YES | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表数据单。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. 06/23:仪表条件表已更新完成 06/23：The instrument conditions table has been updated and completed. 07/10：仪表数据单已更新完成 07/10：Instrument Data Sheet has been fully updated. | YES | Chaoqun Hu/Yu Gao
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. 05/20：SW已更新完PFD并发出。The SW has been updated and the PFD has been sent out. | YES | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ 4/30：Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? 0914：详见第72(0702)条。For Detail, please see item 72(0702). | YES | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted?05/12Decided not to make any adjustments. 05/12确定不做调整。 05/12：It is determined that the height of the catalyst bed in the main reactor will not be adjusted. | YES | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. 06/16：会议澄清：待布局完成后，SW主导完成爆炸危险区域的划分 09/06：Meeting Clarification: SW shall take the lead in completing the classification of hazardous areas for explosion after layout design is finalized. 0915:SW现场确定3D后1周时间SW方完成。 0915: After 1 week from the time the 3D model was determined on-site, the SW team will complete the task. | NO | All
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | YES | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements. | 05/20：与聂博沟通，小试使用的是进口是插底的分离器，生产使用的是侧进的分离器，按会议沟通的气体最大流量0.2Nm³/h，液体最大流量20L/h重新计算了分离器 05/20: Communicated with Nie Bo. The small-scale test used an imported bottom-insertion separator, while the production version used a side-inlet separator. Based on the maximum gas flow rate of 0.2 Nm³/h and the maximum liquid flow rate of 20 L/h for the communication at the meeting, the separator was recalculated.. | YES | Chaoqun Hu
06/02 | IEPE | 管道编号中的管线尺寸一般是指的公称直径，PID中尺寸为10mm的管道是Φ10mm，公称直径为6mm The line size in pipe line designations generally refers to the nominal diameter. In a P&ID, a pipe with a size of 10mm is specified as Φ10mm, corresponding to a nominal diameter of 6mm. | 06/02：会议澄清：DN15以下的管道，管道编号中的管径为外径，DN15及其以上的管道，管道编号中的管径为公称直径。 06/02：Clarification from meeting:For piping below DN15, the size specified in pipe tag number denotes outer diameter; for DN15 and above, the size in pipe tag refers to nominal diameter. | YES | Chaoqun Hu
06/02 | IEPE | 设备BT-01/03/04上的压力变送器不便于现场观察，是否可以考虑也选用WIKA的不带现场显示紧凑型的压力变送器？ The pressure transmitter on the equipment BT-01/03/04 is not convenient for on-site observation. Could it be considered to also choose WIKA's compact pressure transmitter without on-site display？ | 06/02：会上建议保留BT-01/04的现场显示，BT-03可不带现场显示。 06/02：It was suggested at the meeting that the on-site display of BT-01/04 be retained, while BT-03 may not have an on-site display. | YES | Yu Gao
06/02 | CFCT | 1-PID中V-9868，V-9965阀柄的含义？ What is the meaning of valve handles V-9868 and V-9965 in PID? 2-PID中压力变送器底部波纹含义是什么？ What does the corrugation at the bottom of the pressure transmitter signify? 3-与管道直径对应的保温厚度是多少？ What is the insulation thickness corresponding to the diameter of the pipeline? | 06/02： 1.PID中阀门V-9868，V-9965的阀柄为弹簧复位阀柄； In the PID,the valve handles of V-9868 and V-9965 are spring-reset handles； 2.PID中带底部波纹的压力变送器要求压力变送器带隔膜； The pressure transmitter with a bottom ripple in PID requires the pressure transmitter to be equipped with a diaphragm； 3.Keith分享了建议的管道直径与保温厚度表格，直径10到25mm的管路，保温厚度为30-35mm。 Keith shared the recommended pipe diameter and insulation thickness table, with insulation thickness ranging from 30-35mm for pipes with diameters of 10 to 25mm. | YES | ShuangshuangFan
06/16 | SW | 会议确认：气液分离器为侧进，尺寸为DN200*600mm，下次例会前CFCT向SW提供气液分离器的设备图纸 Confirmed at the meeting: The gas-liquid separator adopts side inlet configuration with dimensions DN200 × 600 mm. CFCT shall submit the equipment drawing of the gas-liquid separator to SW prior to the next regular meeting. | 06/22设备图纸已提供。06/23Keith回复意见，见06/23讨论内容。 Equipment drawings were provided on 06/22. Keith's feedback was received on 06/23 — please refer to the discussion notes from 06/23. | YES | Ziliang Zhao
06/17 | SW | 根据最新工作进展并结合HAZOP分析所需文件内容，更新“Sandwich Hydrogenation Implementation Schedule” Update the Sandwich Hydrogenation Implementation Schedule based on the latest progress and document requirements for HAZOP study. | 待SW现场3D讨论及HAZOP分析完成后更新相对准确的进度计划表。 | NO | All
06/17 | SW | 讨论操作规程：哪些部分需要顺控？开停车步骤等 Discuss operation procedures: identify sections requiring sequence control, including startup and shutdown steps, etc. | 06/23：开车步骤：公用工程确认/催化剂装填→氮气置换（R24-BT01、R24-BT04和剩余部分），氧含量<0.5vol%→氢气置换→原料系统备料→TCU系统调温→反应器进料（氢气先进料背压至反应压力，液相再进料）→气液分离→产品转移 停车步骤：停进料→产品缓冲罐物料转移→反应器卸压→R24-BT03卸压→反应系统降温→氮气置换→关闭氮气和TCU Startup Procedures： 1.Verification of utility systems & catalyst loading 2.Nitrogen purging (for R24-BT01, R24-BT04 and the rest of the system), oxygen content controlled below 0.5 vol% 3.Hydrogen purging 4.Raw material preparation for feed system 5.Temperature adjustment of TCU system 6.Reactor feeding: Introduce hydrogen first to build backpressure up to reaction pressure, then feed liquid phase material 7.Gas-liquid separation 8.Product transfer Shutdown Procedures： 1.Cut off feed supply 2.Transfer materials from product buffer tank 3.Depressurize reactor 4.Depressurize R24-BT03 5.Cool down reaction system 6.Nitrogen purging 7.Shut down nitrogen supply and TCU system Keith提供HAZOP时的开停车步骤，结合上述文件，整理开停车和清洗步骤 Compile the plant start-up, shutdown and cleaning procedures based on the above documents together with the start-up & shutdown sequences supplied by Keith for HAZOP assessment. 09/07：操作手册已于08/21发给SW 09/07：The operating manual was sent to SW on 08/21. | Pending | All
06/17 | SW | 会后确认：安全阀的泄放温度超过设备的设计温度，是否需要提高设备的设计温度？ To be confirmed after the meeting：If the relief temperature of the safety valve exceeds its design temperature, is it necessary to increase the design temperature rating? | 设备和管线材质为316L，结合设备和管道的壁厚，计算得出：在泄放温度下，材料的许用应力满足其强度要求，不需提高设备的设计温度 The equipment and piping are fabricated from 316L stainless steel. Wall thickness calculations for the equipment and piping demonstrate that the allowable stress of the material satisfies the strength requirements at relief temperature; therefore, no increase to the equipment design temperature is required. | YES | Ziliang Zhao/Chaoqun Hu
06/17 | SW | CFCT做撬块设计时，注意清洗过程中的低点排净 CFCT shall take full consideration of low-point draining during cleaning when designing the skid package. | 06/23：在撬块设计时，设置管道的低点排净阀 When designing the layout, install a drain valve at the low point of the pipeline 06/23会议方案：管道最低点设置排净阀，操作说明中明确排放时用容器收集排放液体。 Meeting Plant: Install drain valves at the lowest point of the pipeline, and specify in the operating instructions to collect the discharged liquid with a container during the drainage process. | YES | Shuangshuang Fan
06/17 | SW | CFCT提供放空缓冲罐T06是否放在撬内的方案 CFCT to provide a scheme on whether vent buffer tank T06 shall be installed inside the skid. | 06/23：按照现有空间的布置，T06放在撬块内的空间不足；撬块中间的操作维护通道宽度为300-350mm，能否将整体撬块宽度增加150-200mm？ According to the existing space arrangement, there is insufficient space for T06 to be placed inside the pry block; The width of the operation and maintenance channel in the middle of the pry block is 300-350mm. Can the overall pry block width be increased by 150-200mm? 06/23会议方案：T06不放在撬块内，放置在service area，同时反应柱/冷凝器的TCU出口管路上的温度变送器安装在近出口处，去掉手动球阀，安全阀可放到service area，并设置排净阀，进口管路手动球阀保持不变，温度变送器加套管，位置可前可后，低点设置排净阀，整体管路的高点设置排气阀。 Meeting Plant:: T06 is not placed inside the lever block but in the service area. The temperature transmitter on the TCU outlet pipeline of the reaction column/condenser is installed near the outlet. The manual ball valve is removed, and the safety valve can be placed in the service area. A drain valve is installed, while the manual ball valve on the inlet pipeline remains unchanged. The temperature transmitter is equipped with a protective sleeve, with its position adjustable forward or backward. A drain valve is set at the low point, and an air vent valve is installed at the high point of the entire pipeline. | YES | Shuangshuang Fan
06/23 | SW | Keith意见： 基本设计：我们是否有经批准的分离器设计方案？我上次看到的摘录中，计算出的容器直径为3毫米，这表明计算或输入数据可能存在错误。 Basic design 1. Do we have an approved design for the separator. The last extract I saw had a calculated vessel diameter of 3mm, which suggests an error in the calculations or input data. | 06/23讨论： 基本设计：按最新设备数据表进行气液分离器设计。气液分离器的计算书已复核过，数据无误。 06/23Discussion—Basic Design: The gas-liquid separator shall be designed in accordance with the latest equipment data sheet. The calculation sheet for the gas-liquid separator has been reviewed and the data are confirmed to be correct. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 分离器内件 1、本设计中是否已考虑分离器内件，例如入口导流装置或入口旋风分离器、气相除雾器、液体出口处的防涡流挡板？ 2、喷淋球能否采用焊接固定方式，而非通过管接头引入容器内部？ 3、喷淋球是否必须为旋转式喷淋球？这会增加设备复杂度，并在工厂运行寿命期内带来检查与维护方面的问题。 4、喷淋球实际能否起到喷淋清洗作用，还是仅仅将容器注满清洗液直至触发高位液位开关？根据此前讨论，从空罐到高位跳闸点的时间不足25秒，这无法为分离器气相侧提供足够的机械清洗作用时间。 Separator internals 1. Have separator internals been considered for this design e.g. inlet diverters or inlet cyclones, demisting of the vapour stream, vortex breakers on the liquid outlet. 2. Can the spray ball be welded in position rather than introducing a tube fitting into the vessel. 3. Does the spray ball need to be a rotary spray ball. This adds complexity and inspection/maintenance issues during the life of the plant. 4. Will the spray ball actually work as a spray ball, or will it simply fill the vessel with cleaning fluid until the high-level switch is activated. Based on previous discussions this would be less than 25 seconds from empty to high-level trip point, which doesn’t allow much time for mechanical cleaning action in the gas side of the separator. | 06/23讨论： 分离器内件： 1、气液分离器设计采用重力式分离，无需额外的内件。 2、喷淋球相关事宜，CN团队内部结合喷淋球供应商商议方案。 06/23 Discussion — Separator Internals: 1.The gas-liquid separator is designed as a gravity-type separator; no additional internals are required. 2.Regarding the spray ball matters, the CN team will internally discuss and determine the solution in coordination with the spray ball supplier. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 设计参数 1、“流体性能”是否应定为“非致命性”？我推测此概念类似于PED容器设计中的流体分组，在英国规范中应属于Group 1气体（即可燃/爆炸/有毒），而非“非致命性”。 2、工作压力应为0至6MPaG。 3、设计温度应至少为150°C，并且我假设在泄压事故工况下，容器温度可能达到约300°C。 4、设计压力应为全真空至9MPaG。 5、规范是否要求进行焊后热处理（PWHT）？ 6、水压试验压力应为设计压力的1.5倍，即13.5MPaG，而非12MPaG。 7、对于该容器，S4应为DN32 Cl900 WN法兰。喷淋球接口是否应作为单独细节在本图纸上表示，还是另页图纸表示更为合适？ 8、充装系数（Fulling Factor）是多少？ Design Parameters 1. Should the ‘Fluid Performance’ be Non-Lethal? I assume this is similar to the fluid group for PED vessel design, which for the UK would be Group 1 gas i.e. flammable/explosive/toxic and not Non-Lethal. 2. The working pressure should be 0 to 6MPaG. 3. The design temperature should be at least 150 °C and I assume the vessel has the potential to reach circa 300°C during a relief event. 4. The design pressure should be FV to 9MPaG 5. Is PWHT required by the code. 6. Hydro test pressure should be 1.5x design pressure i.e. 13.5MPaG not 12 MPaG. 7. For the vessel, S4 should be a DN32 Cl900 WN Flange. Should the spray ball fitting be shown as a separate detail on this drawing or possibly shown on a separate drawing. 8. What is the Fulling Factor. | 06/23讨论： 设计参数: 1、介质调整为易爆。 2、CN团队结合URS，修正工作压力，更新设备数据表。 3、可以将泄压事故工况，纳入到常规设计考虑中，即可提高设计温度到300℃。 4、修正设计压力，更新设备数据表。 5、规范可不进行焊后热处理（PWHT）。 6、水压试验压力为设计压力的1.3倍，故试验压力可不做调整。 7、S4为喷淋口，口径为Φ10，DN32法兰接口结构为保证喷淋球可抽出，后续根据喷淋球整体方案做调整，判定是否需要可抽式。 8、充装系数是指物料实际容积与容器全容积之比。 06/23 Discussion — Design Parameters: 1.The medium classification is revised to "explosive." 2.The CN team will revise the working pressure based on the URS and update the equipment data sheet accordingly. 3.The relief event scenario can be incorporated into the normal design considerations — i.e., the design temperature can be raised to 300°C. 4.The design pressure will be revised and the equipment data sheet updated accordingly. 5.PWHT (post-weld heat treatment) is not required per the applicable code. 6.The hydrostatic test pressure is 1.3 × design pressure, so the test pressure does not need to be adjusted. 7.S4 is the spray ball connection, with a bore size of Φ10. The DN32 flange connection is designed to allow the spray ball to be withdrawable. This will be reviewed and adjusted as part of the overall spray ball solution, and a decision will be made on whether a withdrawable type is necessary. 8.The filling factor is defined as the ratio of the actual liquid volume to the total vessel volume. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 通用事项 1、管口方位是否已考虑设备布置的最优化？ 2、在撬装高度限制范围内，容器能否通过重力自由排液至产品收集罐？ 3、在顶部法兰上开孔用于引出管，是否会损害其机械完整性并违反安全规范？是否已重新计算法兰厚度或进行有限元分析（FEA），以确保足够的金属厚度和结构完整性？ 4、液位变送器/液位开关的规格是否已确认？法兰尺寸及位置是否与仪表相匹配？ 5、请更新P&ID，以显示S4正确的管口尺寸。 6、是否有容器设计计算书？技术文件中需要包含设计计算书，并应在FAT（工厂验收测试）时进行核查。 General 1. Does the nozzle orientation allow for optimum equipment layout. 2. Can the vessel free drain into the product collection tank, within the skid height constraints. 3. Does boring a hole in the top flange for the outlet pipe compromise its mechanical integrity and violate safety codes. Have you recalculated the flange thickness/carried out FEA to ensure adequate metal thickness and structural integrity. 4. Has the level transmitter/level switches been agreed – does the flange size/position align with the instruments. 5. Update P&ID to show correct nozzle size for S4. 6. Do you have vessel design calculations. Design calculations will be required in the technical file and should be checked at FAT. | 06/23讨论： 通用事项: 1、管口方位已结合3D撬装布置给定。 2、3D撬装设计已考虑，待3D模型复核时，详细讨论。 3、重新计算法兰厚度，以满足结构强度要求。 4、仪表工程师已经确认复核。 5、P&ID，不需要更改S4管口尺寸。 6、设计计算书是设备完整技术文件中必不可少的一部分，后续会提供。 06/23 Discussion — General Items: 1.Nozzle orientation has been determined based on the 3D skid layout. 2.The 3D skid design has taken this into consideration; detailed discussion will be held during the 3D model review. 3.The flange thickness will be recalculated to meet structural strength requirements. 4.The instrumentation engineer has confirmed and verified this. 5.The P&ID does not require changes to the S4 nozzle size. 6.The design calculation sheet is an essential part of the complete technical documentation for the equipment and will be provided in due course. | YES | Ziliang Zhao/Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Overall cleaning philosophy per vessel 各容器整体清洗策略 Please confirm the intended cleaning philosophy for each vessel in the skid — spray-only, soak-only, spray-and-soak combined, or an alternative approach. Please also indicate whether a single philosophy applies across all vessels or whether the strategy varies by vessel. 请确认撬块内各台容器的清洗策略：单独喷淋、单独浸泡、喷淋+浸泡组合，或其它方式。请同时说明是否所有容器采用同一策略，或按容器区别设计。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：有喷淋球的设备R24-BT01、R24-BT04和R24-SE01采用喷淋循环清洗，其余设备采用浸没循环冲洗 09/07：Equipment R24-BT01, R24-BT04 and R24-SE01 equipped with spray balls shall adopt spray circulation cleaning. The remaining equipment shall use immersion circulation flushing. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleanliness verification method & acceptance criteria 清洁度验证方法与验收标准 Please advise the verification method(s) used to confirm cleaning completion (visual inspection, swab / rinse sample analysis, mass balance, calculated residue, etc.) and the numerical acceptance criteria applied (e.g. residue mass, ppm concentration threshold). 请说明用于确认清洗完成的验证方法（目视检查 / 拭子或冲洗样分析 / 物料衡算 / 残余物计算等），以及所采用的数值验收标准（如残余物质量、浓度阈值 ppm）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：与研发人员讨论后，由于国内外存在差异，建议由SW属地QA提供清洗验证 09/07：After discussion with the R&D team, considering regional differences between China and overseas sites, it is recommended that the local QA team of SW provide cleaning validation. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Sight glass availability for SE01 SE01 视镜配置 The reactor vessels are understood to be fitted with sight glasses to support visual verification of cleanliness. The gas–liquid separator SE01, however, does not include a sight glass. Please confirm the intended method for verifying cleanliness on SE01. 反应柱已配置视镜以支持目视清洁度检查，但气液分离器 SE01 未配置视镜。请确认 SE01 清洁度验证的具体手段（，以及是否考虑将新增视镜作为设计变更纳入）。 | 07/10：反应柱和分离器因为操作压力高，无法配置视镜，清洁度的验证无法依靠目测，需取样分析测量残留物的浓度 07/10：Due to the high operating pressure of the reaction column and separator, sight glasses cannot be installed. Visual inspection is therefore not feasible for cleanliness verification, and residue concentration shall be determined via sampling analysis instead. 08/13：不增加视镜，冯博士已提供国内清洁度验收限度的方法供SW参考。 08/13：Without adding a sight glass, Dr. Feng provided the domestic cleanliness acceptance criteria method for SW's reference. | YES | Xiantao feng/Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Spray ball flow rate vs. vessel fill time 喷淋球流量与容器充液时间的匹配 The lowest available spray ball flow rate (approximately 20 L/min) results in SE01 reaching the high-level trip point in under 25 seconds. This limits the time window in which mechanical spray action can achieve wetting coverage. Please advise the intended cleaning-time window on SE01 and the approach for ensuring adequate mechanical cleaning action within the design constraint. 现有最小可选喷淋球流量约 20 L/min，导致 SE01 容器在 25 秒内即达到高液位跳停，机械喷淋作用的有效时间窗口非常短。请说明 SE01 上预期的清洗时间窗口，以及在此设计约束下如何确保获得充分的机械清洗作用。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：R24-SE01清洗时采用喷淋循环清洗，及一边进液，一边排液，排液管的尺寸能匹配喷淋球的流量，保证清洗时不会达到高液位 09/07：R24-SE01 adopts spray circulation cleaning during cleaning operation, with continuous liquid feed and simultaneous liquid discharge. The drain line size is sized to match the flow rate of the spray balls, ensuring that a high liquid level will not be reached during cleaning. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Drain line sizing and fill–drain cycle 排放管径与充液-排空循环 Under the current drain line configuration, the drain rate is significantly slower than the spray inflow rate. Please advise the intended drain line diameter (whether upsizing is planned), the estimated single-cycle fill and drain durations, and the number of cycles anticipated per cleaning campaign. 当前排放管径下，排放速率显著慢于喷淋进料速率。请说明拟采用的排放管径（是否放大）、单次循环的充液和排空时间估算，以及每次清洗预期需要的循环次数。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：排放管径已放大，详见P&ID。不同物料，清洗循环的次数不同，可根据取样分析的结果确认 09/07：The drain line size has been increased; refer to the P&ID for details. The number of cleaning circulation cycles varies for different materials and can be confirmed based on sampling analysis results. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Soak cleaning vs. high-level interlock defeat mechanism 浸泡清洗与高液位联锁绕过机制 If soak cleaning is adopted on SE01, the liquid level during cleaning will exceed the high-level safety interlock (located at approximately one-third of vessel height). Please specify: (a) the physical mechanism intended for defeating this interlock during cleaning (key switch, procedural lockout, or other); (b) the authorisation and access controls surrounding the defeat mechanism; and (c) the safeguards against inadvertent defeat during normal processing operation. 若 SE01 采用浸泡清洗，清洗过程中的液位将超过位于容器约 1/3 高度的高液位安全联锁。请说明：(a) 清洗时用于绕过（defeat）该联锁的物理机制（钥匙开关 / 程序锁定 / 其它）；(b) 该绕过机制的授权与权限控制方式；(c) 防止正常运行时意外绕过的保护措施。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：R24-SE01清洗时采用喷淋循环清洗，及一边进液，一边排液，排液管的尺寸能匹配喷淋球的流量，保证清洗时不会达到高液位 09/07：R24-SE01 adopts spray circulation cleaning during cleaning operation, with continuous liquid feed and simultaneous liquid discharge. The drain line size is sized to match the flow rate of the spray balls, ensuring that a high liquid level will not be reached during cleaning. | Pending | Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleaning of the guided-wave level transmitter housing Guided wave 液位变送器外壳的清洁 The guided-wave level transmitter housing (approximately 100 mm diameter, side-mounted on SE01) sits above the high-level switch and lies outside the spray ball coverage envelope. Please advise the intended cleaning approach for this housing, and any mechanical or procedural provisions required to ensure it can be cleaned to the acceptance criteria in Q1.2. 液位变送器外壳（约 100 mm 直径，SE01 侧接管上）位于高液位开关之上，不在喷淋球覆盖范围内。请说明该外壳的清洁方案，以及为达到 Q1.2 中的验收标准所需的机械或程序性措施。 | 07/14：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用 07/14：Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. | YES | Chaoqun Hu/Yu Gao
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Reactor cleaning cycle time and manual interventions 反应器清洗循环时间与人工干预 For the 200-L reactor vessels, a single spray-and-drain cycle involves an extended drain phase relative to the spray phase. Multiple cycles are expected to achieve the required cleanliness. Please advise: the anticipated number of cycles, the total cleaning duration per campaign, and the specific manual interventions required at each step (drain valve operation, sample point access, lockout re-set, etc.). 200-L 反应器进行单次"喷淋-排空"循环时，排空阶段远长于喷淋阶段，需多次循环以达到清洁度要求。请说明：预期循环次数、每次清洗总时长，以及各步骤所需的具体人工干预（排放阀操作 / 取样口操作 / 联锁复位等）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：反应器采用浸没循环清洗，清洗进出口的管径为Ф10，可选用10L/min的泵循环冲洗，循环次数和清洗总时长需根据取样分析结果确认 09/07：The reactor adopts immersion circulation cleaning. The inlet and outlet nozzles for cleaning have an outer diameter of 10 mm. A pump with a flow rate of 10 L/min can be used for circulation flushing. The number of circulation cycles and total cleaning duration shall be confirmed based on sampling analysis results. | Pending | Chaoqun Hu
07/01 | SW 3D Layout 3D 布置与设备空间 | Operational access clearance 操作通道净空 The current 3D model shows approximately 300–350 mm clearance in certain operator access zones. Please confirm the target minimum clearance from a site operability and maintenance standpoint, and identify any specific zones where relaxation of the current clearance is acceptable, or where additional clearance is required. 当前 3D 模型显示部分操作人员通道净空约为 300–350 mm。请从现场操作与维护角度，确认目标最小净空要求，并识别可以放宽的具体区域，以及需要额外净空的区域。 | 07/10：建议增加反应柱撬块的宽度，审核模型后给出建议的空间区域。 It is recommended to increase the width of the reaction column skid and provide the suggested spatial area after reviewing the model. 09/08：根据SW最新建议的设备布置方案，减少设备中间通道，加大设备与墙体空间，具体尺寸待3D模型更新后确定。 According to SW's latest recommended equipment layout plan, reduce the middle channels of the equipment and increase the space between the equipment and the wall. The specific dimensions will be determined after the 3D model is updated. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Free-drain feasibility from each vessel 各容器的自重排放可行性 The cleaning strategy relies on free-drain of cleaning fluid from each vessel into downstream collection (BT04 or equivalent). Considering the skid height constraint and each vessel elevation, please confirm the free-drain path is mechanically feasible from each source vessel to its destination. Please identify any vessels where drainage cannot be achieved by gravity and would require pumping or an alternative arrangement. 清洗策略要求清洗液自重从各容器排入下游收集罐（BT04 或等效容器）。考虑撬块高度限制与各容器标高，请确认每台源容器至其目标容器的自重排放路径机械可行。请识别无法通过重力实现排放、需要泵抽或采用替代方案的容器。 | 07/10：根据目前容器的结构形式，反应柱可通过底部排放阀排放，缓冲罐可通过管路排放，预热器、冷凝器管路无排放口。具体排放方式参考清洗方案。 Based on the current structural design of the containers, the reaction column can be drained through the bottom discharge valve, the buffer tank can be discharged via piping, while the preheater and condenser have no discharge outlets in their pipelines.Refer to the cleaning plan for specific emission methods. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Nozzle orientation on pressure vessels 压力容器管嘴方位 Please review the nozzle orientation on all pressure vessels in the current 3D model. Confirm that nozzle positions provide adequate access for external piping tie-in, instrumentation installation, and maintenance (removal / reinstallation of internals, gasket replacement, catalyst service, etc.). 请审查当前 3D 模型中所有压力容器的管嘴方位。确认管嘴位置能够满足外部管路对接、仪表安装以及维护（内构件拆装 / 密封垫更换 / 催化剂检维修等）的空间要求。 | 07/10：由于空间尺寸限制，部分管口的维护可能存在不便。优化管口布置或能否增加设备空间。 Due to space size limitations, maintenance of some pipe openings may be inconvenient. Optimize pipe layout or increase equipment space 09/08：根据SW最新建议的设备布置方案，CIP及排放管口位于撬端面，并采用移动拉撬方案，满足中间设备及管路的维护空间要求。 According to SW's latest recommended equipment layout plan, the CIP and discharge ports are located on the pry end face, and a mobile pry scheme is adopted to meet the maintenance space requirements of intermediate equipment and pipelines. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Catalyst charging & discharging arrangement 催化剂加料与卸料布置 Please confirm that the catalyst charging (loading) and discharging (unloading) arrangement is compatible with the current nozzle layout on the reactor vessels, and that adequate space is provided for charge / discharge equipment and operator access during catalyst service. 请确认催化剂加料与卸料的操作方式与当前反应柱的管嘴布置兼容，且在催化剂检维修期间为加料/卸料设备与操作人员留有充足空间。 | 07/10：根据目前的布置方案，反应柱加料卸料口均在撬体端面，结合加料卸料方式看操作空间是否充足。 According to the current layout plan, the feeding and discharging ports of the reaction column are all located on the end face of the pry body. Considering the feeding and discharging methods, it is necessary to check whether the operating space is sufficient. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Tie-in points between skid and site utilities 撬块与现场公用工程接口 Please confirm the finalised location and specification of all tie-in points between the skid and the Sandwich site services, including process feed, product outlet, vent header, HTF supply and return, N₂ blanketing, instrument air, electrical supply, cable penetrations, and drain. Please advise the interfaces where design lock-down is still pending. 请确认撬块与 Sandwich 现场公用工程之间所有接口的最终位置与规格，包括工艺进料、产品出口、放空总管、导热油供回、氮气钝化、仪表空气、电气供应、电缆穿墙、排放。请说明尚未定稿的接口。 | 07/10：根据现有的布置方案，有部分公用工程的的接口，无仪表空气接口，电气供应、电缆穿墙，后续更新撬块与公用工程接口的位置与规格。 According to the existing layout plan, there are interfaces for some public works without instrument air interfaces, electrical supply, and cable penetration through walls. The location and specifications of the interface between the pry block and the public works will be updated in the future. | Pending | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Cable wall penetration capacity and cable compatibility 穿墙电缆孔容量与电缆兼容性 The current design indicates 14 available cable wall penetration slots. Please confirm this final count, the internal diameter of each slot, and the compatibility of the slot with the largest cable type intended to pass through (multi-core, armoured, or shielded cables of relevant cross-section). 当前设计显示可用穿墙电缆孔 14 个。请确认该数量的最终定案、每个孔的内径规格，以及与拟穿过的最大电缆类型（相应截面的多芯 / 铠装 / 屏蔽电缆）的兼容性。 | 寻求工程部支持，和宋小旭主管约会讨论如何推进，7月10日反馈进展 | YES | Dezhi meng/Shaofeng gao
07/01 | SW Control Philosophy 控制策略 | Full Control Philosophy document issue date 完整《控制策略》文件发出日期 Please advise the target issue date for the complete Control Philosophy document, superseding the interim draft version previously circulated. 请说明完整版《控制策略》文件的目标发出日期（覆盖此前流转的过渡草稿版本）。 | 07/10：已完成初版，还在校核中，预计下周发出 07/10：The initial draft has been completed and is under review; it is expected to be issued next week. 09/07：控制说明已于08/21发给SW 09/07：The control description was sent to SW on 08/21. | Pending | Chaoqun Hu
07/01 | SW Control Philosophy 控制策略 | Interlock schedule — hardwired vs. software 联锁清单 —— 硬件联锁与软件联锁 Please provide a complete interlock schedule listing all safety interlocks, with clear delineation between hardwired (independent of the PLC) and software (PLC-implemented) interlocks. For each interlock, please include: initiating cause, sensing element, trip setpoint, action taken, and protective function fulfilled. 请提供完整的联锁清单，列出全部安全联锁，明确区分硬件联锁（独立于 PLC）与软件联锁（PLC 实现）。每一条联锁请包含：触发原因、检测元件、跳停设定值、联锁动作、承担的保护功能。 | 07/10：联锁条件已完成初版，还在校核中，预计下周发出 07/10：The initial draft of interlock conditions has been completed and is under review, which is expected to be issued next week. 09/07：联锁表已于08/21发给SW 09/07：The interlocks table was sent to SW on 08/21. | Pending | Chaoqun Hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Operational modes and mode-specific fail positions 操作模式与各模式下的故障位 Please define all operational modes of the skid (normal operation, start-up, shut-down, cleaning, catalyst change, emergency depressurisation, etc.), and for each mode specify: (a) the fail position of each control valve; (b) the state of each interlock (active / bypassed); and (c) the permissive conditions required to enter that mode. 请定义撬块的全部操作模式（正常运行 / 开车 / 停车 / 清洗 / 催化剂更换 / 紧急泄压等），并针对每一模式说明：(a) 每个控制阀的故障位；(b) 每个联锁的状态（激活 / 已绕过）；(c) 进入该模式所需的许可条件。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 分离器浸泡清洗时易触发液位高联锁，导致高液位以上清洗不彻底。增大分离器的排净管径可实现淋洗，同时系统处于清洗模式时，绕开液位高联锁。 High level interlock is prone to tripping during soaking cleaning of the separator, leading to inadequate cleaning of areas above the high liquid level. Increasing the drain pipe size of the separator allows shower rinsing. Meanwhile, the high level interlock can be bypassed when the system is under cleaning mode. | NO | Chaoqun Hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Mode-transition safeguards 操作模式切换的保护措施 Please advise the safeguards in place against inadvertent mode transitions, particularly from cleaning mode back to processing mode (e.g. an interlock bypass being left in place after cleaning is complete). Please describe both the technical safeguards (key switches, HMI confirmations) and the procedural safeguards (SOP requirements, dual sign-off). 请说明防止意外切换操作模式（尤其是从清洗模式返回处理模式时联锁绕过未复位）的保护措施。请分别描述技术性保护措施（钥匙开关 / HMI 确认）与程序性保护措施（SOP 要求 / 双签发）。 | 52条和Keith讨论后1周反馈。 周二上午组会专题讨论：超群+付工。 | NO | Dezhi meng
07/01 | SW Sampler System 取样系统 | Sample vaporisation during pressure reduction 取样过程中的样品闪蒸 The sampler transfers process fluid from a line operating at up to 60 barG to a sample container at approximately atmospheric pressure. Please advise the analysis of vaporisation during this pressure reduction (fraction vaporised, temperature drop) and its impact on the compositional representativeness of the collected sample. 取样器将最高 60 barG 工艺管路的介质转移至常压取样瓶。请说明此压降过程中的闪蒸分析（气化比例、温度降低）及其对所采样品成分代表性的影响。 | 07/10：冷凝器出口的温度为30℃，压力从60barG 泄至常压，此温度条件下不会发生闪蒸 07/10：The temperature at the condenser outlet is 30°C. The pressure is relieved from 60 barG to atmospheric pressure, and no flashing will occur under this temperature condition. | Pending | Chaoqun Hu
07/01 | SW Sampler System 取样系统 | Sample retention design 样品截留设计 Please advise the design of the sample bottle and sample-transfer system, including any vapour trap, septum, condenser, or other retention device intended to prevent loss of volatiles through the vent path and to ensure a representative liquid sample is captured. 请说明取样瓶及取样传输系统的设计，包括为防止挥发组分从放空路径流失、并确保获得代表性液样所采用的蒸汽阱、隔膜、冷凝器或其它截留装置。 | 07/10：取样器的流程：打开三通阀将缓冲罐充满，打开缓冲罐气相放空管线阀门，将缓冲罐中的气相排走并卸压，打开氮气手阀，将缓冲罐中的液体压至取样瓶 07/10：Sampling procedure: Open the three-way valve to fill the buffer drum. Open the valve on the vapor vent line of the buffer drum to vent the vapor inside and relieve pressure. Then open the nitrogen manual valve to pressurize and transfer the liquid from the buffer drum into the sampling bottle. | Pending | Chaoqun Hu
07/01 | SW Sampler System 取样系统 | Sampler behaviour under gas-rich flow regime 气相主导流态下取样器行为 With the intended process operating at a stoichiometric excess of hydrogen, the flow regime through the sampling point may be gas-rich with entrained liquid rather than liquid-continuous. Please advise how the sampler design accommodates this flow regime, and whether any sample point relocation, phase separator, or coalescer is being considered. 工艺预期在化学计量氢气过量条件下运行，取样点处流态可能为"气相夹带液体"而非液相连续。请说明取样器设计如何适应此流态，以及是否考虑取样点位置调整、加装相分离器或聚结器。 | 07/10：取样器的缓冲罐上有气体排放管线，取样罐充满后，打开气体排放管线，将气相排走并卸压，再用氮气将液相压至取样瓶 07/10：The buffer vessel of the sampler is equipped with a gas vent line. Once the sampling tank is full, open the gas vent line to vent the vapor phase and relieve pressure, then push the liquid phase into the sampling bottle with nitrogen. | Pending | Chaoqun Hu
07/01 | SW Instrumentation 仪表配置 | Guided-wave level transmitter — datasheet & cleanability Guided wave 液位变送器 —— 数据单与可清洁性 Please provide the guided-wave level transmitter datasheet and confirm: (a) the process compatibility of the probe assembly with the intended service (including any operating conditions in the supercritical or near-critical regime); and (b) the cleanability of the probe assembly under the adopted cleaning philosophy. 请提供 guided wave 液位变送器数据单，并确认：(a) 探头组件在拟定工况（含超临界或近临界工况）下的适用性；(b) 探头组件在拟采用清洗策略下的可清洁性。 | 7月10日反馈进展 (a) 导波雷达液位计工作原理是雷达波可以穿过介电常数较低的气相，遇到介电常数较大的液相返回，从而计算液位。适用蒸汽、粉尘、泡沫等工况。需了解超临界工况下的介质状态是否还存在液相，如果没有液相空间，则液位计无法识别。 The working principle of the guided-wave radar transmitter is that the radar wave can pass through the gas phase with a lower dielectric constant and return to the liquid phase with a larger dielectric constant, thereby calculating the liquid level. It is applicable to working conditions such as steam, dust and foam. It is necessary to understand whether there is still a liquid phase in the medium state under supercritical conditions. If there is no liquid phase space, the transmitter cannot identify it. 07/15进展：经内部评估，液位计所在容器操作工况下不存在超临界状态。 After internal assessment, it was determined that the liquid level gauge is not in a supercritical state under the operating conditions of the container it is located in. (b)BT01和BT04的导波雷达液位计为顶装内伸形式，可以利用设备内的喷淋头冲洗。SE-01的导波雷达液位计为侧装旁通式，可以选择在探头与旁通管的过程接口处增加配套冲洗环，并预留一路冲洗管线。 The guided-wave radar transmitters of BT01 and BT04 are top-mounted and iInsert type, and can be flushed by the spray heads inside the equipment. The guided-wave radar l transmitter of SE-01 is of side-mounted bypass type. A matching flushing ring can be added at the process interface between the probe and the bypass pipe, and a flushing pipeline can be reserved. 07/14进展：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用. Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. 07/17进展：气液分离器雷达液位计侧装改顶装，已完成图纸设计，筒体直径未变，邮件发出。 The radar level gauge for the gas-liquid separator has been redesigned from side-mounted to top-mounted. The drawing design has been completed, and the vessel diameter remains unchanged. The drawings have been sent out via email. | Pending | Yu gao/Chaoqun Hu/Zilaing Zhao
07/01 | SW Instrumentation 仪表配置 | Level switch position & interlock function 液位开关位置与联锁功能 Please confirm the finalised position (elevation, orientation, flange size and rating) and the interlock function of each level switch (LSL, LSLL, LSH, LSHH) on each vessel, together with the matching instrument selection. 请确认每台容器上各液位开关（低 LSL、低低 LSLL、高 LSH、高高 LSHH）的最终位置（标高、方位、法兰尺寸与压力等级）与联锁功能，以及对应的仪表选型。 | 7月10日反馈进展： 关于液位开关选型，之前寻价时只有VEGA的VEGASWING 63型号可以满足DN25 Class900 M的过程接口，其他厂家如E+H、Rosemount都不能满足。 About the selection of level switches, during the previous price search, only VEGA's VEGASWING 63 model could meet the DN25 Class 900 M process connection requirements. Other manufacturers such as E+H and Rosemount could not meet these requirements. 07/15：联锁值详见联锁条件表。 07/15：The interlock values can be found in the interlock condition table. | Pending | Chaoqun Hu/Yu gao
07/01 | SW Instrumentation 仪表配置 | Instrument datasheet next revision date 仪表数据单下一版本发出日期 Please advise the target issue date for the next revision of the Instrument Datasheet, reflecting the current SE01 design (post demister-configuration decision), the finalised interlock schedule, and the level switch position confirmation. 请说明反映当前 SE01 设计（demister 配置定稿后）、最终联锁清单以及液位开关位置确认的仪表数据单下一修订版本的目标发出日期。 | 7月10日反馈进展 仪表数据表已完成修订版，待意见讨论后看是否还需修改参数。 The instrument datasheet has been revised. After the discussion of opinions, we will see if the parameters still need to be modified. 08/05:根据最新设计温度和压力，更新仪表数据表，08/12发出 08/05:Update the instrument data sheet based on the latest design temperature and pressure, issued on 08/12 | YES | Chaoqun Hu/Yu gao
07/01 | SW Documentation Status 文档状态 | Current revision and next revision date of key deliverables 主要交付文件的当前版本与下一版本时间 Please confirm the current issued revision and the target date for the next revision of the following documents: • PFD • P&ID • URS • Equipment Datasheets • Control Philosophy • Instrument Datasheet • Operating Instructions • Cleaning Procedure • Vessel Design Calculation Package. 请确认以下文档的当前已发版本与下一修订版本的目标日期： · PFD · P&ID · URS · 设备数据单 · 控制策略 · 仪表数据单 · 操作说明 · 清洗程序 · 容器设计计算书。 | 7月10日反馈进展，操作手册还在编制中，其他设计文件已完成。On July 10th, we provided the progress update. The operation manual is still under preparation, while the other design documents have been completed. 08/21：工艺设计文件均已发出。 0821：The process design documents have been issued. | Pending | Shaofeng gao/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R1] Design Temperature — Vessel could fail during relief event. Equipment design temperature is specified for process requirements and does not consider elevated temperatures during relief events when short-term temperature increase has the potential to exceed the design temperature. 设计温度 —— 容器可能在泄放事件中失效。设备设计温度是按工艺需求设定的，未考虑泄放事件中的短时温升可能超过设计温度的情形。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：已更新数据表，提高设计温度，以满足工艺需求，图纸已升级。 07/10: Data sheet updated with elevated design temperature to meet process requirements; drawings revised accordingly. | YES | Chaoqun Hu/Ziliang zhao
07/02 | SW - Risk Register Engineering Design 工程设计 | [R2] Design Requirements — L:G ratio for plant is not clearly defined. Equipment design could result in very limited operating ranges and incorrect assumptions in plant capability and relief design. 设计条件 —— 装置的液气比（L:G ratio）未明确定义。可能导致设备设计的操作区间受限，以及在装置能力和泄放设计中做出错误假设。 | 7月10日反馈进展，根据最终确定的反应器尺寸核实气液比数据。On July 10th, the progress was reported. The gas-liquid ratio data was verified based on the final determined reactor size. 09/07: 根据08/25的会议确认PFD不更新，装置的气液比不改变 09/07: As confirmed in the meeting on 08/25, the PFD will not be updated, and the gas-to-liquid ratio of the unit will remain unchanged. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Engineering Design 工程设计 | [R3] Design Requirements — Catalyst specification is not available. Design may not be suitable for some catalysts. Dusty catalysts could cause blockages. 设计条件 —— 催化剂规格未明确。设计可能不适用于某些催化剂；含粉尘的催化剂可能导致堵塞。 | Keith / SW response: Design philosophy is based on catalyst beads/pellets which are dust-free, non-flammable and have exposure levels requiring OEB 3 or lower containment. Note: OEB 3 containment is a deviation from the URS and requires acceptance. Keith / SW 答复： 设计基于无粉尘、非燃、暴露等级 OEB 3 或更低的颗粒/粒状催化剂。注：OEB 3 的密闭要求相对 URS 存在偏离，需要接受确认。 | NO | SW
07/02 | SW - Risk Register Engineering Design 工程设计 | [R4] Access — Layouts are not available to assess whether access to equipment is acceptable for operations and maintenance. 通道 —— 布置图尚未提供，无法评估设备的操作与维护通道是否满足要求。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.1 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/YES | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R5] Maintenance — Lifting Aids (davit arms, lifting beams, etc.) have not been considered in design, with potential for injury to maintenance personnel removing heavy equipment for servicing / repair / replacement. 维护 —— 设计中尚未考虑起重辅助设施（吊臂、起吊梁等），维护人员在拆卸重型设备进行检修 / 修理 / 更换时可能存在人身伤害风险。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/YES | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R6] Lighting — Layouts are not available to assess whether lighting for routine operations and maintenance activities is acceptable. 照明 —— 布置图尚未提供，无法评估日常操作和维护活动的照明条件是否满足要求。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/YES | NO | UK/All
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R7] System leak detection — Pressure testing of high-pressure system will be hydraulically tested. Hydraulic testing demonstrates mechanical strength of the pressure system but does not demonstrate integrity for a hydrogen system. 系统检漏 —— 高压系统将进行水压试验。水压试验只能证明压力系统的机械强度，无法证明氢气系统的密封完整性。 | Keith / SW response: Helium testing is not routinely carried out in China. Keith / SW 答复： 国内通常不常规进行氦气检漏。 可以做气密性试验；国内整橇系统气密性试验后，分体运至英国，进入工厂房间后，再次组装，需重新进行泄漏试验，现场是否具备试验条件？现场可进行氦气检漏。 和CE认证机构确认一下具体方案。 A pneumatic test can be performed. After the complete skid system undergoes the pneumatic test in China, it will be shipped in split form to the UK. Upon arrival at the factory site and reassembly, a new leak test will be required. We need to confirm whether the site has the necessary conditions/facilities for this test. Helium leak detection is available on site. We will confirm the specific plan with the CE Notified Body. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R8] Line sizing / specification — Vents / headers incorrectly sized / specified, resulting in high back pressure and safety / operability issues, e.g. two-phase flow in emergency vent relief header. 管线规格 / 尺寸 —— 放空 / 泄放总管尺寸或规格不正确，导致背压过高及安全 / 可操作性问题，例如紧急泄放总管中出现两相流。 | 07/10：安全阀进出口尺寸详见P&ID 07/10：Refer to the P&ID for the inlet and outlet sizes of the safety valve. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R9] Insulation — Insulation requirements not specified, which could result in equipment / pipe layout not allowing space for insulation to be installed. 保温 —— 保温需求尚未明确，可能导致设备 / 管路布置未预留保温安装空间。 | Confirm the insulation material with Keith and determine the thickness. Once it's confirmed, provide a progress report on July 10th. 和Keith确认下保温材料，然后确定厚度。确定后，7月10日反馈进展 3D模型中管路的间距已按照保温厚度30-35mm预留了保温的安装空间。 The spacing between pipes in the 3D model has been designed to accommodate an insulation installation gap of 30-35mm, as per the insulation thickness requirements. | YES | Yinghui cheng/Chaoqun Hu/Shuangshuang fan/Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R10] Modular design — Modular design could introduce significant increase in site construction activities, e.g. mechanical and EC&I installation and subsequent testing. 模块化设计 —— 模块化设计可能大幅增加现场施工工作量，例如机械与电控仪表安装及后续测试。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 现有模块化设计的方案是根据进口电梯的尺寸，将整套设备拆分为4个撬块运输组装。 SW建议：需再考虑从屋顶直接吊装进去的方案，需要在后续周三会上进一步讨论。 The current modular design solution involves dividing the entire set of equipment into four skids for transportation and assembly based on the dimensions of imported elevators. SW Recommendation: Further consideration is needed for the direct hoisting-in-from-the-roof solution, which will be discussed in the upcoming Wednesday meeting. 07/29：会上澄清四撬块方案技术可行、屋顶吊装非必选；认证机构评估以 3D 定稿为前提，Keith 下周四返回后进一步确认。 07/29: Clarified that the four-module option is technically feasible and roof removal is not mandatory; the Notified Body assessment requires the finalised 3D layout, to be confirmed further with Keith after he returns next Thursday. 08/05:核实分撬是否与海运有关，和进出口部（公司内）请教下海运的最大尺寸事宜。 08/07：询问进出口部同事，集装箱内部高度有限，同时需要预留固定以及防撞等措施空间，所以橇块高度不要超过2.5m。整橇的话，有一种框架集装箱能放进去，但不密封，暴露在空气中，容易造成腐蚀，不建议采用。同时提醒，整橇运输也要考虑陆运高度限制。 09/08：根据SW最新建议的3撬块布置方案，框架高度不超过2.5m，超出部分管路采取预制加现场重新组装的安装方式。 09/08：According to the latest SW-recommended 3-pile block layout, the frame height shall not exceed 2.5m, with the excess portion of pipelines installed using a pre-fabrication and on-site reassembly method. | Pending | Chaoqun Hu/Shuangshuang fan
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R11] Skid assembled on site could result in CE / UKCA Responsible Person / Authorised Representative in China not being able to issue Declaration of Conformity for Skid Package. 撬块在现场组装可能导致中国境内的 CE / UKCA 负责人 / 授权代表无法为撬块整机签发符合性声明（Declaration of Conformity）。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 与CE认证方沟通确认好细节，特别是认证机构是否需要到UK现场验证，再发证。 We will communicate with the CE Notified Body to confirm all the details, in particular whether the certification body needs to attend the UK site for verification prior to issuing the certificate. 07/29：需以 3D 布置定稿版与 CE 认证机构沟通，评估现场组装后的验证方式、费用与工期。 07/29: The finalised 3D layout is required to engage the CE Notified Body and assess the post-assembly verification route, cost and duration. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R12] Wall penetrations — Layouts and cable schedules not available to confirm space is available for pipe / cable penetrations to / from R23 Module. 穿墙孔 —— 布置图和电缆清单尚未提供，无法确认与 R23 模块之间的管道 / 电缆穿墙位置有足够空间。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.6 | The initial cable schedule of CIMT is not fully aligned with the SW plan. SW has sent SLD, CIMT is verifying design discrepancies and will feed back comparison results, followed by discussions with SW CIMT初版线缆计划与SW计划没有完全匹配，SW已发出单线图，CIMT核对设计差异，返回对比结果，再与SW讨论。 7/23：CIMT根据SW提供的单线图，更新了电缆数量。部分流量控制器电缆待确认。硬联锁开关阀点位本安/隔爆待确认。 7/23：CIMT update the cable quantity based on the SLD provided by SW. some cables are still pending confirmed, 1. for flow controllers(modbus or 4-20mA). 2. for HW interlock on-off valve(I.S. or Ex d) 09/15：孟工补充一下问题： | NO | Dezhi meng
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R13] Catalyst charge point — Inlet pipe diameter is small and blockages may occur. 加料口 —— 加料管径较小，可能发生堵塞。 | Keith / SW response: Inlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking inlet pipe. Keith / SW 答复： 加料接口已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞加料管的风险。 | YES
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R14] Catalyst physical property requirements (size, shape, packing, etc.) are not defined, with the potential for incompatible catalyst to be charged to the reactors. 催化剂物性要求（粒径、形状、装填密度等）尚未定义，存在向反应器加入不兼容催化剂的风险。 | 07/10：催化剂直径0.5mm-5mm，形状不重要，球形，圆柱形，不规则颗粒状都可以，装填密度一般0.5g/mL来估算，但催化剂强度要高，不容易破碎起粉 07/10：The catalyst particle diameter ranges from 0.5 mm to 5 mm, with no specific shape requirement; spherical, cylindrical and irregular granular forms are all acceptable. The bulk density can be estimated at 0.5 g/mL in general. Meanwhile, the catalyst shall feature high mechanical strength to avoid fragmentation and dust generation. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R15] Packing of catalyst is not controlled, with the risk of reactants / gas channelling in the continuous reactor column, and the potential for incomplete reaction or impurities forming. 催化剂装填未受控，存在反应物 / 气体在连续反应柱内形成沟流的风险，可能导致反应不完全或杂质产生。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R16] Contained charge system design not available to assess risks and / or design limitation. 密闭加料系统的设计尚未提供，无法评估其风险与设计局限。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R17] Manual handling requirements for catalyst charging not assessed. 催化剂加料的人工搬运需求尚未评估。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R18] Access to charge point and support of charge container / bag not designed (access steps / integrated support shelf). 加料口的通道以及加料容器 / 料袋的支撑尚未设计（例如操作台阶、集成支撑架）。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R19] 20-micron catalyst retaining screen — Screen blockages prevent / limit flow of gas / reaction mix to continuous reactors. 20 微米催化剂拦截筛 —— 拦截筛堵塞会阻止 / 限制气体 / 反应液流入连续反应器。 | Keith / SW response: China Operations have reported blockages occur in local plant and screen has been removed and discarded. Keith / SW 答复： 国内运行反馈已在本地装置中发生堵塞，已将拦截筛拆除并弃用。 | YES
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R20] Polishing filter (FTR9832) — Filter blockages prevent / limit flow of gas / reaction mix through continuous reactors. Pressure increases in reactor system, with potential for undesirable reactions to occur, until reactor high-pressure trip is activated. 精滤器 (FTR9832) —— 滤芯堵塞会阻止 / 限制气体 / 反应液流经连续反应器；反应器压力升高，直到触发高压跳停前可能发生副反应。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 待定/To be determined 08/06:精滤器堵塞，加旁通，清洗时打开旁通，方便卸压 08/06: Fine filter clogged; bypass added. Open the bypass during cleaning to facilitate pressure release. | YES | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register CR01 – CR03 Reactors CR01 – CR03 反应器 | [R21] Temperature control — Jacket temperature control is configured to control jacket temperature only. Reactor internal temperatures are monitored, but no control, alarms or interlocks are configured for process control. 温度控制 —— 夹套温度仅控制夹套温度本身。反应器内部温度虽被监测，但未针对工艺过程配置控制、报警或联锁。 | Keith / SW response: Scale-up provides large operating envelopes for process temperature requirements and additional control, alarms and interlocks are not required. Keith / SW 答复： 由于放大试验提供了较大的工艺温度操作裕度，无需增加额外的控制、报警或联锁。 | YES
07/02 | SW - Risk Register System Pressure Monitoring 系统压力监测 | [R22] Differential pressure monitoring — Accuracy of static pressure measurements may not enable differential pressures to be calculated with any degree of accuracy or certainty. 差压监测 —— 静态压力测量精度可能不足以支持差压计算达到所需的精度或置信度。 | 通过反应柱上和反应器进出口管线上的的压力变送器精度估算，最大差压误差大约为40kPa。 Based on the accuracy estimation of the pressure transmitters on the reaction column and the inlet/outlet pipelines of the reactor, the maximum differential pressure error is approximately 40kPa. 07/14压力也增加了联锁。The pressure also increased the interlock. | YES | Chaoqun Hu/Yu gao
07/02 | SW - Risk Register Over Pressure Protection 过压保护 | [R23] Relief system design — Pressure systems not identified and relief studies not available. Identification of worst-case relief scenario not identified, and relief streams may be incorrectly categorised. Details of maximum reaction exotherm not fully documented. 泄放系统设计 —— 压力系统尚未识别、泄放研究尚未提供。最坏工况泄放情景未识别，泄放物流可能被错误归类。反应最大放热的详细信息尚未完整记录。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：详见安全阀计算书 07/10：See safety valve calculation sheet for details. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Separator 气液分离器 | [R24] Vessel design — Complete degassing of product stream not achieved, with the potential for hydrogen carry-over into BT04 and product transfer containers. 容器设计 —— 产品物流未实现完全脱气，H₂ 可能带入 BT04 及产品转运容器。 | 07/10：气液分离器满足气液分离的要求 07/10：The gas-liquid separator meets the requirements for gas-liquid separation. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Separator 气液分离器 | [R25] Cleaning of separator not fully understood but current concept relies on vessel free-draining to BT04. Current spray ball sizing is not consistent with this approach and may require significant rework to process piping. 分离器清洗方案尚未完全明确，当前概念依赖容器向 BT04 的自重排放。现有喷淋球规格与该思路不匹配，可能需要对工艺管路进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.4,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：R24-SE01采用喷淋循环冲洗，增加了DN15的排净口，不依赖R24-BT04的重力排放 09/07：R24-SE01 adopts spray circulation flushing. A DN15 drain port has been added so that gravity drainage from R24-BT04 is no longer required. | Pending | Chaoqun Hu/Ziliang zhao
07/02 | SW - Risk Register Separator 气液分离器 | [R26] Cleaning of LIT003 housing does not appear to be considered in design. LIT003 液位变送器外壳的清洗在设计中似乎尚未考虑。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.7 | 同上42行回复/Translation of the 42nd line above. | YES | Chaoqun Hu
07/02 | SW - Risk Register Separator 气液分离器 | [R27] P&ID does not clearly show nozzle locations and could lead to mal-ops / misunderstanding of the design intent by the Operations team. P&ID 上未清晰标注管嘴位置，可能导致运行团队误操作或误解设计意图。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.3 | 07/10：已标注，详见P&ID 07/10：Marked as indicated; refer to the P&ID for details. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Sampling 取样系统 | [R28] Sampler design — When depressurising the sample collection chamber, high gas or vapour vent rates could result in a bubbly or churn-turbulent flow regime, and sample will discharge to vent line as two-phase flow. 取样器设计 —— 对取样收集腔进行减压时，气体或蒸汽的高排放速率可能形成鼓泡或搅动湍流流态，样品将以两相流形式排入放空管。 Related Outstanding Questions ｜ 关联待澄清问题：Q5.1 | 07/10：缓冲罐静置一定时间，让气液分层，泄压时缓慢打开手阀 07/10：Allow the buffer tank to stand for a certain period for vapor-liquid stratification, then open the manual valve slowly during depressurization. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Sampling 取样系统 | [R29] With significantly more gas being present in the process stream, what will prevent overpressure of sample bottle and low-pressure nitrogen pipework? 由于工艺物流中气体明显较多，采用什么措施来防止取样瓶和低压氮气管路的超压？ | 07/10：取样瓶和氮气管线投用时，系统已泄压至常压 07/10：The system has been depressurized to atmospheric pressure prior to commissioning of sampling bottles and nitrogen pipelines. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R30] Catalyst Discharge Plug valve — Outlet pipe diameter is small and blockages may occur. 催化剂卸料闸阀 —— 出口管径较小，可能发生堵塞。 | Keith / SW response: Outlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking outlet pipe. Keith / SW 答复： 出口接管已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞出口管的风险。 | YES
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R31] Contained discharge system design not available. Layout design may not provide sufficient headroom for contained discharge system. 密闭卸料系统的设计尚未提供。当前布置可能无法为密闭卸料系统提供足够的顶部空间。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R32] Complete removal of catalyst during discharging operations is unlikely to remove 100% of the material, with the risk of cross contamination of catalyst material between campaigns. 卸料操作难以完全（100%）清除催化剂，存在批次间催化剂交叉污染的风险。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun Hu
07/02 | SW - Risk Register Cleaning 清洗 | [R33] CIP Design — CIP design incomplete. Initial spray ball sizing is inconsistent with process line sizing approach and may require significant rework to process piping and/or equipment layout. CIP 设计 —— 就地清洗设计不完整。初步喷淋球规格与工艺管路选型方式不匹配，可能需对工艺管路和 / 或设备布置进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.1,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed 09/07：配置喷淋球的设备，喷淋球的流量与排放管径匹配，采用喷淋循环冲洗 09/07：Equipment fitted with spray balls shall have spray ball flow rate matched to the drain line size for spray circulation flushing. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Cleaning 清洗 | [R34] Cleaning carried out at nominally atmospheric pressure with the risk of material being trapped between flanges, which tend to separate slightly during high-pressure operation, and could lead to cross contamination between batches. 清洗在近常压下进行，高压运行时法兰会出现微量分开，可能将物料残留于法兰间隙中，进而导致批次间交叉污染。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 09/07：法兰密封面擦拭取样，定期开盖检查清洁状况 09/07：Swab sampling of flange sealing faces and periodic vessel opening inspection for cleanliness. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Cleaning 清洗 | [R35] Validation / Verification — Cleaning validation / verification philosophy not available. QA may not accept that the continuous reactor achieves minimum cleaning standards. 验证 / 确认 —— 清洗验证 / 确认策略尚未提供。质量保证部门可能不接受连续反应器满足最低清洗标准。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.2,Q1.9 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 更新清洗方案后讨论/Discuss after updating the cleaning procedure. 09/07：与研发人员讨论后，由于国内外存在差异，建议由SW属地QA提供清洗验证 09/07：After discussion with the R&D team, considering regional differences between China and overseas sites, it is recommended that the local QA team of SW provide cleaning validation. | Pending | Chaoqun Hu/Xiantao Feng
07/02 | SW - Risk Register Cleaning 清洗 | [R36] Layout — Layouts are not available to evaluate the impact of bypasses, dead legs, drains, vents, etc. 布置 —— 布置图尚未提供，无法评估旁路、死管、排放、放空等的影响。 | 09/08：3D模型确定后推进。 09/08：After the 3D model is finalized, proceed with the advancement. | NO | Shuangshuang fan
07/02 | SW - Risk Register Cleaning 清洗 | [R37] Layout — Layouts are not available to evaluate access to equipment for visual inspections, which may impact the effectiveness of critical inspections. 布置 —— 布置图尚未提供，无法评估设备的目视检查通道，可能影响关键检查的有效性。 | 09/08：3D模型确定后推进。 09/08：After the 3D model is finalized, proceed with the advancement. | NO | Shuangshuang fan
07/02 | SW - Risk Register Cleaning 清洗 | [R38] Layout — Equipment design / layout does not allow for routine disassembly and manual cleaning. Equipment turnaround times and operating costs would be adversely impacted if CIP system cannot be validated. 布置 —— 设备设计 / 布置未考虑日常拆装和人工清洗。如 CIP 系统无法通过验证，设备周转时间和运行成本都会受到不利影响。 | 09/08：3D模型确定后推进。 09/08：After the 3D model is finalized, proceed with the advancement. | NO | Ziliang zhao
07/02 | SW - Risk Register FT001 FT001 流量计 | [R39] Liquid Stream Flow Sensor for flow control loop FIC001. FT001 is a Coriolis mass flow meter installed downstream of the metering pump MP01. Pulsed flow from the pump will impact on the flow measurement and accurate flow control may not be possible. 液相流量传感器（用于 FIC001 流控回路）—— FT001 是安装在计量泵 MP01 下游的科里奥利质量流量计。泵的脉冲流会影响流量测量，可能无法实现精确流量控制。 | Keith / SW response: China Team have previously used this configuration and not experienced flow control issues. No further action required. Keith / SW 答复： 国内团队此前采用过该配置，未出现流控问题。无需进一步动作。 | YES
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R40] Maximum flow may exceed separator design limitations and carry hydrogen over into BT04 / product collection containers. 泵的最大流量可能超出分离器的设计上限，将 H₂ 带入 BT04 / 产品收集容器。 | 07/10：分离器的直径足够大，泵为最大流量时能满足分离要求 07/10：The separator has a sufficiently large diameter to meet separation requirements even when the pump operates at maximum flow rate. | Pending | Chaoqun Hu
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R41] Pump turndown does not meet URS minimum flow requirements. 泵的调节比无法满足 URS 中规定的最低流量要求。 | 07/10：机泵条件中规定了泵的最小流量要求，待泵厂家返回资料时审查是否满足最低流量要求 07/10：Minimum flow requirements for pumps are specified in pump data sheets. Compliance with the minimum flow criteria shall be verified upon receipt of vendor documentation. 08/05：根据最新机泵数据单走采购流程询问厂家资料 08/05：Proceed with the procurement process and request vendor documentation based on the latest pump data sheet. | NO | Chaoqun Hu
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R42] Hydrogen gas flow controller — Flow controller does not support tight shut-off and system pressure increase during hold periods. 氢气流量控制器 —— 控制器不支持严密关断，系统在保压期间压力会持续上升。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller to provide tight shut-off. Keith / SW 答复： 在控制器下游追加一台切断阀以提供严密关断。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R43] Maximum flow through controller may exceed separator design limitations and carry liquid into the vent line. 流经控制器的最大流量可能超出分离器设计上限，将液体带入放空管。 | Keith / SW response: High level interlock installed in the separator to stop gas supply and close PIC028 shut-off valve (CV08). Keith / SW 答复： 在分离器上设置高液位联锁，停 H₂ 供给并关闭 PIC028 的切断阀（CV08）。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R44] Time required for pressure testing the system and nitrogen inertion may be excessively high. 系统加压试验及氮气钝化所需时间可能过长。 | Keith / SW response: Pressure test / inertion times to be evaluated during FIC003 selection. Manual vent installed on BT03 to reduce depressurisation times via FIC003. Keith / SW 答复： 在 FIC003 选型时评估压力试验 / 惰化时间。在 BT03 上加装人工放空阀，缩短经 FIC003 的减压时间。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R45] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端的差压超出厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register LIC003 LIC003 分离器液位 | [R46] SE01 Separator Level Indicator — Cleaning / decontamination of housing is not possible. Residual product in housing could lead to cross contamination between campaigns. SE01 分离器液位指示 —— 变送器外壳无法进行清洗 / 净化。外壳内的残留物料可能导致批次间交叉污染。 | Keith / SW response: Design relies on dissolution of residual material. 100% flood-fill of housing is not possible, therefore any residual trace contamination in the housing is deemed to be small and will not significantly impact cleaning verification. Keith / SW 答复： 设计依赖残余物料的溶解。外壳无法 100% 灌满，因此外壳内任何残余痕量污染被视为很小，不会显著影响清洗验证。 | YES
07/02 | SW - Risk Register FIC004 FIC004 分离器液位控制 | [R47] Separator outlet flow / level control — Differential pressure across the controller exceeds manufacturer's recommendations and controller capability. 分离器出口流量 / 液位控制 —— 控制器两端差压超出厂家建议范围及控制器能力。 | 分离器出口先通过减压阀减到0.2MpaG左右，可以满足厂家建议的差压范围 The outlet of the separator is first reduced to approximately 0.2MpaG through a pressure reducing valve, which can meet the differential pressure range recommended by the manufacturer | Pending | Chaoqun Hu/Yu gao
07/02 | SW - Risk Register FIC005 FIC005 BT01 氮气吹扫 | [R48] BT01 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT01 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register FIC007 FIC007 BT04 氮气吹扫 | [R49] BT04 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R50] System back pressure controller — The back pressure controller does not support tight shut-off during hold periods and system pressure will not be maintained. 系统背压控制器 —— 该控制器在保压期间不支持严密关断，系统压力无法保持。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller. Keith / SW 答复： 在该控制器下游追加一台切断阀。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R51] Time required for depressurising the system following pressure testing and nitrogen inertion may be excessively high. 加压试验和氮气钝化之后系统减压所需时间可能过长。 | Keith / SW response: Manual bypass installed around PIC028 controller. Keith / SW 答复： 在 PIC028 控制器周围加装人工旁路。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R52] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端差压超出厂家建议范围，可能导致控制器无法正常工作。 | 07/10：关于背压阀028，之前Bronkhorst的电子压力阀厂家计算反馈的阀前背压范围最大为0.9~6MpaG，范围量程比不能过大。 07/10：About the back pressure valve 028, previously, the manufacturer of Bronkhorst’s electronic pressure valve calculated and reported that the maximum range of the back pressure before the valve was 0.9 to 6MpaG, and the range-to-range ratio cannot be too large. 09/07: 关于气液分离器设计温度改为270℃后，与Bronkhorst电子背压阀厂家进行沟通，厂家反馈270℃的温度可能会很快损坏电子元件导致无法使用，厂家推荐的工作温度最高是50℃，短时间能承受100~120℃左右。然后又咨询了一些耐高温的气动调节阀厂家，反馈背压的范围过大且流量偏小，选不出合适的阀门CV值。 会上确认还用该电子背压阀，270℃泄放工况很少出现，当270℃时背压阀不会外漏，电子元件损坏可以接收，将选择耐高温的密封材质。 09/07: After the design temperature of the gas-liquid separator was changed to 270℃, we communicated with the Bronkhorst electronic back pressure valve manufacturer. The manufacturer reported that a temperature of 270℃ might quickly damage the electronic components and make it unusable. The manufacturer recommended a maximum working temperature of 50℃, and it can withstand around 100 to 120℃ for a short period of time. Then, we consulted some manufacturers of high-temperature resistant pneumatic control valves. The feedback was that the range of back pressure was too large and the flow rate was too small, making it impossible to select a suitable CV value for the valve. It was confirmed at the meeting that the electronic back pressure valve would still be used. The 270℃ discharge condition rarely occurs. When the temperature is 270℃, the back pressure valve will not leak out. The damage of electronic components can be accepted. High-temperature resistant sealing materials will be selected. | YES | Chaoqun Hu/Yu gao
07/02 | SW - Risk Register PIC030 PIC030 分离器液相出口减压 | [R53] Separator liquid outlet pressure reducer — Is this confirmed as a Bronkhorst pressure controller, or is a mechanical regulator still an option? Does this provide the required independence assumed in the relevant SIL / risk assessments? 分离器液相出口减压器 —— 该阀是否确认为 Bronkhorst 电子压力控制器？还是仍可能选用机械式减压阀？该配置能否提供相关 SIL / 风险评估中假设所需的独立性？ | 目前选型机械式减压阀。机械阀不是电子设备，没有相关的SIL认证。 At present, mechanical pressure reducing valves are being selected. Mechanical valves are not electronic devices and do not have the relevant SIL certification. | Pending | Chaoqun Hu/Yu gao
07/02 | SW - Risk Register PIC049 PIC049 BT04 背压控制 | [R54] BT04 back pressure controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 背压控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register Automation 自动化 | [R55] Automation Build — Philosophy and Design documentation not available to assess risks and limitations. 自动化建设 —— 自动化策略与设计文档尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q3.1,Q3.2 | 专题沟通后确定反馈 09/07：控制说明和联锁表已于08/21发给SW 09/07：The control description and interlocks table were sent to SW on 08/21. | Pending | Chaoqun Hu/Dezhi meng/Ziliang zhao
07/02 | SW - Risk Register Documentation 文档 | [R56] Technical File — Technical File not available to assess risks and limitations. 技术文件 —— 技术文件尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.5,Q7.1 | SW现场3D等事项确定后陆续提供。 At the SW site, final design files will be provided sequentially after the 3D models and other topics have been confirmed. | NO | Shaofeng gao/All
07/02 | SW - Risk Register Documentation 文档 | [R57] O&M Manual — O&M manual not available to assess risks and limitations. 操作维护手册 —— O&M 手册尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q7.1 | 07/10：操作手册的编制还在进行中 07/10：Preparation of the operation manual is still in progress. 07/29：操作维护手册预计 8 月中完成。 07/29: The O&M manual is scheduled for completion in mid-August. 09/07：操作手册已于08/21发给SW 09/07：The operating manual was sent to SW on 08/21. | Pending | Chaoqun Hu
07/02 | SW - Risk Register Documentation 文档 | [R58] Emissions Calculations — Calculations to demonstrate expected release of Class A and Class B VOCs to atmosphere are not available. These are required to demonstrate compliance with EA Permit limits. 排放量计算 —— 尚未提供证明 A 类和 B 类 VOC 向大气排放的预期计算。该计算是证明满足 EA 许可（英国环境署许可）限值要求所必需。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW负责排放量计算/SW is responsible for emissions calculation. | YES | Chaoqun Hu
07/02 | SW - Risk Register Regulatory Compliance 法规合规 | [R59] CE ¦ Functional Safety ¦ DSEAR / ATEX ¦ PSSR ¦ COSHH ¦ PUWER (Access, manual handling) ¦ Working at Height (Access Steps / Support Shelf) ¦ LOLER (Davit arms) ¦ Lighting ¦ Occupational Hygiene ¦ EA Permit — Regulatory non-conformance would prevent beneficial use of equipment in the UK. CE 认证 ¦ 功能安全 ¦ DSEAR / ATEX 防爆 ¦ PSSR 压力系统安全 ¦ COSHH 危害物质 ¦ PUWER 工作设备（含通道与人工搬运）¦ 高处作业（操作台阶 / 支撑架）¦ LOLER 起重设备（吊臂）¦ 照明 ¦ 职业卫生 ¦ EA 环境许可 —— 任何法规合规缺失都会导致设备无法在英国正常投入使用。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW内部的提醒事项。 CFCT核实加料步梯是否包含在内。 SW提供步梯平台尺寸。 Internal reminders for SW: CFCT to verify whether the feeding staircase is included. SW to provide dimensions of staircase and platform. 会后本博士发一下资料。 | NO | Zilang zhao/All
07/14 |  | 根据生产经验，研发建议原R24-CR01的直径由DN80改为DN50，导致产能下降，可能无法满足URS中的产能30kg/day Based on production experience, the R&D team proposes reducing the diameter of the original R24-CR01 from DN80 to DN50. This modification will result in lower production capacity, which may fail to meet the 30 kg/day throughput specified in the URS. | 07/14：周三会上确定/To be confirmed at Wednesday's meeting. 07/15：暂定R24-CR01的直径修改为DN65，等9月份研发提供DN65的反应器实验数据后最终确认反应器的尺寸为DN65或DN50 07/15：It is tentatively agreed to revise the diameter of R24-CR01 to DN65. The reactor size (either DN65 or DN50) will be finalized after the R&D department provides DN65 reactor test data in September. 07/29：会上确定按 DN65 / DN50 两套方案并行准备，并建立变更影响日志；待 9 月研发 DN65 实验数据后最终定案。 07/29: Agreed to prepare the DN65 and DN50 cases in parallel and to set up a change-impact log; final decision after the September DN65 R&D test data. | NO | Xiantao Feng/All
07/23 | SW | 气液分离器SE01容器承受从常压到60 barg的压力循环次数？ How many pressure cycles does the gas-liquid separator SE01 vessel undergo from atmospheric pressure to 60 barg? | 07/23:会上讨论了加氢装置的操作周期，意见存在不一致，关于连续加氢的年运行周期，SW内部沟通后反馈循环次数需求。 气液分离器的设计温度调整到270℃，对应设计压力调整到7.5MPaG。垫片选用金属环垫片。 07/23：The operating cycle of the hydrogenation unit was discussed at the meeting, and divergent opinions remain. SW shall coordinate internally and provide feedback on the required number of cycles regarding the annual operating cycle for continuous hydrogenation. The design temperature of the gas-liquid separator shall be revised to 270°C, with the corresponding design pressure adjusted to 7.5 MPaG. Metallic ring gaskets shall be adopted . 08/06：垫片材质？原料酸性 PEEK，再寻找合适的垫片，讨论。 09/07：管法兰与金属环垫片均可选316L，但需要做技术要求：①金属环垫片硬度≤150HB，管法兰硬度≥160HB；②以上材料需有硬度检测报告；③到厂后复验；④组装前按硬度差≥10HB配对使用。 09/07：Both the pipe flanges and the metal ring gaskets may be made of 316L. However, the following technical requirements shall be complied with: ①The hardness of the metal ring gasket shall be ≤ 150 HB, and the hardness of the pipe flange shall be ≥ 160 HB. ②Hardness test reports shall be provided for all the above materials. ③The materials shall be re-inspected upon arrival at site. ④Prior to assembly, the flange and gasket shall be paired based on a hardness difference of ≥ 10 HB (i.e., the flange hardness shall be at least 10 HB higher than that of the gasket). | YES | Zilang zhao/Chaoqun Hu
07/23 | IEPE | P&ID中压力表无根部阀，是否需要增加根部阀？ Pressure gauges shown on the P&ID are not equipped with root valves. Is it necessary to add root valves? | 07/23:按照现有P&ID配置。 07/23：Configure in accordance with the existing P&ID. | YES | Chaoqun Hu/Yu gao
07/23 | IEPE | PCV028侯径小，反应系统卸压时，全开PCV028卸压速度也很慢，建议将PCV028的旁通手阀改为开关阀 PCV028 has a small orifice. When depressurizing the reaction system, the depressurization rate remains low even if PCV028 is fully open. It is recommended to change the bypass manual valve of PCV028 to an on-off valve. | 07/23:按照现有P&ID配置。 07/23：Configure in accordance with the existing P&ID. | YES | Chaoqun Hu
07/29 | SW | 针对 R24-CR01 直径变更（DN80→DN65/DN50），建立变更影响日志/清单，逐项列出受影响的设备、仪表、管线、安全阀及相关文件与参数，确保无遗漏。 Establish a change log / impact list for the R24-CR01 diameter change (DN80→DN65/DN50), itemising every affected item of equipment, instrumentation, piping, relief device and the related documents and parameters, so that nothing is missed. | 07/29：会上同意建立变更影响日志，由国内团队逐项梳理受影响范围并跟踪关闭。 07/29: Agreed at the meeting to create a change-impact log; the China team will work through the affected scope item by item and track it to closure. 09/07:变更清单已整理完成，根据08/25的会议确认PFD不更新，目前只有反应器的设备数据表需要变更 09/07: The change list has been finalized. Based on the meeting on 08/25, it was confirmed that PFD will not be updated; currently, only the equipment data sheet for the reactor has changed. | NO | Shaofeng Gao/Chaoqun Hu
07/29 | SW | 反应器 DN65 与 DN50 两种规格并行准备设计方案：先确定处理量，再分别出 PFD 与物料平衡；并核实仪表选型、安全阀/泄放组合是否需相应调整。待 9 月研发提供 DN65 实验数据后定案。 Prepare two parallel design cases for the DN65 and DN50 reactor: fix the throughput first, then issue a PFD and mass balance for each, and verify whether instrument selection and the relief-valve combination need to change accordingly. To be finalised once R&D provides the DN65 test data in September. | 07/29：会上确定按 DN65 / DN50 两套方案并行准备，使 9 月数据到位后可直接定案，不影响整体进度。 07/29: Agreed to progress both the DN65 and DN50 cases in parallel so that the decision can be taken as soon as the September data is available, without affecting the overall schedule. 0914：和研发沟通DN50反应器尺寸，更新设备数据单。 0914: Communicate with the R&D department regarding the size of the DN50 reactor and update the equipment data sheet. | NO | Shaofeng Gao/Chaoqun Hu/Xiantao Feng
07/29 | IEPE | 容器设计压力由 80 barg 调整为 75 barg，以保持法兰等级 CLASS 900、避免材料选型受限；需在设备数据表、图纸及相关计算书中同步更新落实。 Vessel design pressure revised from 80 barg to 75 barg in order to retain the CLASS 900 flange rating and avoid limitations on material selection; to be updated consistently in the equipment datasheets, drawings and supporting calculations. | 07/29：周二与 Keith 讨论已取得初步一致，继续推进并在各设计文件中落实。 07/29: Initial agreement reached with Keith on Tuesday; to be carried forward and reflected in the design documents. 08/12：设备数据单已更新完成 08/12：The equipment data sheet has been updated. | YES | Chaoqun Hu/Ziliang Zhao
07/29 | SW | 四撬块分体运输 vs 屋顶整体吊装的决策路径：国内先完成 3D 布置定稿，再以定稿版与 CE 认证机构评估现场组装后的验证方式、费用与工期；Keith 下周四返回后确认四撬块方案可行性；SW 侧评估屋顶更换的费用、工期及 R23 停用影响。 Decision path for four-module split shipment vs a whole-unit lift through the roof: the China team to finalise the 3D layout first, then use the finalised version to evaluate with the CE Notified Body the post-assembly verification route, cost and duration; confirm the four-module option with Keith after he returns next Thursday; SW to assess the roof-replacement cost, duration and the impact of taking R23 out of service. | 07/29：会上提议需要澄清四撬块方案技术上可行，屋顶吊装并非必选项；认证机构评估需以 3D 定稿为前提，国内加快 3D 定稿以尽早取得费用与工期结论。 07/29: Clarified at the meeting that the four-module option is technically feasible and roof removal is not mandatory. The Notified Body assessment depends on the finalised 3D layout, so the China team will accelerate finalisation to obtain the cost and schedule answer as early as possible. | NO | Ziliang Zhao/Shaofeng Gao/Keith
07/29 | SW | 明确下阶段（建造 / FAT）文件的编制与签发流程：由谁编制、由谁签发；SW 场地有自有的 FAT / 验证模板。CE 认证方参与文件评审但不参与签发。约定后续安排专题讨论。 Define the preparation and sign-off process for the next-stage (construction / FAT) documentation — who prepares and who signs off. The SW site has its own FAT / validation template. The CE Notified Body will take part in document review but not in sign-off. A dedicated follow-up discussion to be arranged. | 07/29：双方同意尽早对比两侧模板并识别差异；倾向直接采用 UK 模板以便英国侧验证与确认，国内按该模板提供资料，避免后期返工。 07/29: Both sides agreed to compare the two templates early and identify any gaps; the preference is to adopt the UK template so that verification and validation on the UK side is straightforward, with the China team supplying information to that template to avoid rework later. | NO | Shaofeng Gao/Ziliang Zhao
07/29 | IEPE | 请 SW / Keith 提供英国现场验证（validation）所需的信息清单与模板，国内据此提供资料并按该模板执行，以便尽早识别中英双方要求差异。 SW / Keith to provide the list of information required for the UK site verification / validation process, together with the template, so that the China team can supply the information and work to that template and any differences between the UK and China requirements are identified early. | 07/29：会上确定由 SW 提供模板与信息需求清单，国内提供文件 / 信息并按模板填写；下周与 Keith 沟通落实。 07/29: Agreed that SW will provide the template and the information requirement list; the China team will supply the documents / information and complete them to that template. To be taken forward with Keith next week. | NO | Keith/Shaofeng Gao
07/29 | SW | HAZOP 前须与 Keith 就 3D 布置与控制说明（含操作手册）达成一致 —— 该两项目前仅国内内部讨论过，是余下唯二可能引发重大设计变更的环节，须在 HAZOP 前关闭，以确保 HAZOP 只做一次、避免重做。 The 3D layout and the control philosophy (including the operating manual) must be agreed with Keith before HAZOP. These two items have so far only been reviewed internally by the China team and are the only remaining items that could still trigger a significant design change; they must be closed out beforehand so that HAZOP is run once only and does not have to be repeated. | 07/29：会上确认目标为「HAZOP 只做一次」；两项在 9 月初 HAZOP 前与 Keith 讨论定稿。 07/29: The meeting confirmed the objective of running HAZOP only once; both items to be discussed and finalised with Keith ahead of the early September HAZOP. | NO | All
08/25 | IEPE | 反应柱 R24-CR01 直径变更（DN80→DN65/DN50），产能改变，进料量可能会调整，是否需要修改PFD？ The diameter of the reaction column R24-CR01 has been changed (from DN80 to DN65/DN50), resulting in a change in production capacity. The feed volume may need to be adjusted. Is it necessary to modify the PFD? | 08/25：反应柱 R24-CR01 直径变更（DN80→DN65/DN50），跟研发和Keith沟通后确认：流速不变工况下后续反应器可承担部分转化率，故产能不一定改变，PFD不做调整；对应的TCU功率匹配事宜可通过调整出口温度实现，方案由SW自行调整。 08/25: Diameter of reaction column R24-CR01 was changed (from DN80 to DN65/DN50). After communicating with R&D and Keith, it was confirmed that under the condition of unchanged flow rate, the subsequent reactor can handle a portion of the conversion rate. Therefore, the production capacity is not necessarily changed, and the PFD will not be adjusted. The power matching of the corresponding TCU can be achieved by adjusting the outlet temperature. The plan will be adjusted by SW on its own. | YES | Keith/Xiantao Feng
08/25 | SW | CFCT向SW提供R24-BT03的尺寸和3D模型，方便Keith优化3D方案 CFCT provides SW with the dimensions and 3D model of R24-BT03 to facilitate Keith's optimization of the 3D design. | 08/25：会后提供R24-BT03的尺寸和3D模型 08/25: Dimensions and 3D model of R24-BT03 will be provided after the meeting. | YES | Shuangshuang Fan
09/07 | CFCT | 根据SW建议的3撬的设备布置的3D模型，主要讨论气液分离器的安装高度、HTF管路的高度及撬外管路的安装。 Based on the three-skid equipment layout 3D model proposed by SW, the main focus is on the installation height of the gas-liquid separator, the height of the HTF pipeline, and the installation of external pipelines. | 09/08：①分离器的安装高度：会上确定分离器安装高度可以降低，不必自流到 BT04。新的高度反馈给胡工，用来确定减压阀后压力； ②HTF的10 根管穿墙：穿墙高度先维持原高度，撬内和现场的高度差通过弯头转接； ③撬外管路的安装：对于安装高度高于运输高度2.5m的管路，撬体组装时预制好，运输时拆下，现场再次安装； ④按照BT01 / BT04 / 分离器 / 冷凝器尽量前移，缩减中间通道，以及CIP 和排放接口在撬装前端操作的方案更新3D模型； ⑤对于拉撬方案可能存在的操作维修不便的问题，后续邮件沟通。 09/08：①Separator Installation Height: It will be confirmed that the separator installation height can be reduced and does not necessarily need to flow by gravity to BT04. The new height will be reported to Engineer Hu to determine the pressure after the pressure reducing valve; ②The 10 pipes of HTF penetrate the wall: the height of the penetration is initially maintained at the original level, while the height difference between the inside and the site is adjusted through elbows; ③Installation of external pipelines: For pipelines with an installation height exceeding the transportation height by 2.5m, the skid assembly is prefabricated, then disassembled during transportation and reinstalled on-site; ④Update the 3D model according to the plan of moving BT01/BT04/separator/condenser forward as much as possible, reducing the intermediate channel, and operating CIP and discharge interfaces at the front end of the assembly; ⑤Regarding the potential inconvenience in operation and maintenance of the pull and pry scheme, we will communicate via email . | Pending | Shuangshuang Fan

## 0812
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. 05/12：Keith建议用气液两相计算安全阀尺寸，不提供模板 05/12：Keith suggests using gas-liquid two-phase calculations for determining the size of the safety valve, but no template is provided. 05/20：根据API520的气液两相泄放时计算安全阀尺寸，部分已完成 05/20：Calculate the size of the safety valve based on the API520 standard for the two-phase gas-liquid discharge situation.Partially completed. 06/02：安全阀计算初版已完成（包含临界流体和气液两相），校审中。 06/02：Preliminary calculation of safety relief valve (covering critical fluid & gas-liquid two-phase flow) completed, under review. 06/09: General 1. What was the source/reference for the Specific Volumes stated in column D/D 列中比容数据的来源及参考依据是什么？ The Specific Volumes stated in column D are derived from Aspen Plus simulation results.比容数据来自Aspen模拟 2. There is no backpressure considered in the calculation. The emergency vent relief will create some backpressure which needs to be considered in the calculation./本次计算未考虑背压。紧急放空泄放过程会产生一定背压，该因素需纳入计算。 Backpressure consists of static backpressure and built-up backpressure. Given the wide total pressure range, backpressure effects shall be incorporated into the calculation.背压分为静背压和积聚背压，总压力范围大，将背压包含在其中 3. At the assumed relief pressure Ethyl Acetate will be a supercritical fluid, therefore the required relief mass flowrate will not be dependent on the latent heat of vapourisation, and the calculated ‘required discharge area’ will not be valid. Do you agree with this statement, or have you found a reference in the standard that allows for this? 在设定的泄放压力下，乙酸乙酯将处于超临界流体状态，因此所需泄放质量流量不再依赖汽化潜热，本次算出的所需泄放流通面积也不再适用。你是否认同该观点？或是你是否在相关标准中查到可支持该计算的依据？ 详见06/16回复. Please refer to the reply dated 06/16 for details. Cooling Failure Calculations 4. For the cooling failure calculation, I would suggest using 550kJ/mol rather than 501.48. This is based on Sandwich PSL experience of heats of reaction. 针对冷却失效工况计算，建议将反应热取值由 501.48 kJ/mol 改为 550 kJ/mol。该取值参考了桑威奇工艺安全实验室（Sandwich PSL）过往反应热项目经验。 OK 5. Is the feed flowrate used in the calculation, based on the maximum metering pump capabilities? Do you assume a maximum concentration of reactant in the feed stream? 计算中采用的进料流量，是否按照计量泵最大额定流量取值？计算时是否假定进料流中反应物浓度为最大浓度？ The flow rate used in the calculation is set at the maximum rated capacity of the metering pump, and the maximum reactant concentration is adopted for the feed stream.计算时流量是按照计量泵最大额定流量取值，反应物浓度为最大浓度 06/16：根据文献“Relief Calculation for Supercritical Fluids”计算超临界流体的质量泄放流量，会后向Keith发计算书审核 06/16：Calculate the mass relief flow rate of supercritical fluids in accordance with the document Relief Calculation for Supercritical Fluids, and send the calculation sheet to Keith for review after the meeting. | YES | Chaoqun Hu
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun HU
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. 06/16：06/11已收到审核完成的URS。 06/16：Received the reviewed URS on 06/11. | YES | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith确认CV08也是故障关，可以使用DS6080型，该型号没有5 bar 差压限制。 Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith confirmed that CV08 is also a faulty-close type, the DS6080 model can be used. This model does not have a 5-bar differential pressure limit. Keith offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. 06/02 进展：Habonim厂家反馈了样本资料，反馈可以满足工艺参数需求，货期大概16~20周。可以作为开关阀的备选品牌。 06/02 Progress: "Habonim" manufacturer has provided sample materials that can meet the process parameter requirements. The delivery time is approximately 16 to 20 weeks. It can be an alternative brand for on-off valves. | YES | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. 06/02：关于气液分离器液相出口减压，电子压力阀和自力式减压阀都可以满足使用，首选自力式减压阀。 06/02：For pressure reduction at the liquid outlet of the gas-liquid separator，both electronic pressure valves and self-operated pressure reducing valves can meet the requirements, with self-operated pressure reducing valves being the preferred choice. | YES | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. 05/20：SW已更新完URS并发出。The SW has been updated and the URS has been sent out. | YES | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表数据单。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. 06/23:仪表条件表已更新完成 06/23：The instrument conditions table has been updated and completed. 07/10：仪表数据单已更新完成 07/10：Instrument Data Sheet has been fully updated. | YES | Chaoqun Hu/Yu Gao
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. 05/20：SW已更新完PFD并发出。The SW has been updated and the PFD has been sent out. | YES | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? 9/7：当前分撬方案会增加穿线数量，待方案定好后更新电缆数量，同时评估走线空间 The current split skid layout will increase cable routing quantity. Cable schedule will be updated once the scheme is finalized, and routing space shall be assessed in parallel | Pending | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted?05/12Decided not to make any adjustments. 05/12确定不做调整。 05/12：It is determined that the height of the catalyst bed in the main reactor will not be adjusted. | YES | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. 06/16：会议澄清：待布局完成后，SW主导完成爆炸危险区域的划分 09/06：Meeting Clarification: SW shall take the lead in completing the classification of hazardous areas for explosion after layout design is finalized. | NO | All
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | YES | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements. | 05/20：与聂博沟通，小试使用的是进口是插底的分离器，生产使用的是侧进的分离器，按会议沟通的气体最大流量0.2Nm³/h，液体最大流量20L/h重新计算了分离器 05/20: Communicated with Nie Bo. The small-scale test used an imported bottom-insertion separator, while the production version used a side-inlet separator. Based on the maximum gas flow rate of 0.2 Nm³/h and the maximum liquid flow rate of 20 L/h for the communication at the meeting, the separator was recalculated.. | YES | Chaoqun Hu
06/02 | IEPE | 管道编号中的管线尺寸一般是指的公称直径，PID中尺寸为10mm的管道是Φ10mm，公称直径为6mm The line size in pipe line designations generally refers to the nominal diameter. In a P&ID, a pipe with a size of 10mm is specified as Φ10mm, corresponding to a nominal diameter of 6mm. | 06/02：会议澄清：DN15以下的管道，管道编号中的管径为外径，DN15及其以上的管道，管道编号中的管径为公称直径。 06/02：Clarification from meeting:For piping below DN15, the size specified in pipe tag number denotes outer diameter; for DN15 and above, the size in pipe tag refers to nominal diameter. | YES | Chaoqun Hu
06/02 | IEPE | 设备BT-01/03/04上的压力变送器不便于现场观察，是否可以考虑也选用WIKA的不带现场显示紧凑型的压力变送器？ The pressure transmitter on the equipment BT-01/03/04 is not convenient for on-site observation. Could it be considered to also choose WIKA's compact pressure transmitter without on-site display？ | 06/02：会上建议保留BT-01/04的现场显示，BT-03可不带现场显示。 06/02：It was suggested at the meeting that the on-site display of BT-01/04 be retained, while BT-03 may not have an on-site display. | YES | Yu Gao
06/02 | CFCT | 1-PID中V-9868，V-9965阀柄的含义？ What is the meaning of valve handles V-9868 and V-9965 in PID? 2-PID中压力变送器底部波纹含义是什么？ What does the corrugation at the bottom of the pressure transmitter signify? 3-与管道直径对应的保温厚度是多少？ What is the insulation thickness corresponding to the diameter of the pipeline? | 06/02： 1.PID中阀门V-9868，V-9965的阀柄为弹簧复位阀柄； In the PID,the valve handles of V-9868 and V-9965 are spring-reset handles； 2.PID中带底部波纹的压力变送器要求压力变送器带隔膜； The pressure transmitter with a bottom ripple in PID requires the pressure transmitter to be equipped with a diaphragm； 3.Keith分享了建议的管道直径与保温厚度表格，直径10到25mm的管路，保温厚度为30-35mm。 Keith shared the recommended pipe diameter and insulation thickness table, with insulation thickness ranging from 30-35mm for pipes with diameters of 10 to 25mm. | YES | ShuangshuangFan
06/16 | SW | 会议确认：气液分离器为侧进，尺寸为DN200*600mm，下次例会前CFCT向SW提供气液分离器的设备图纸 Confirmed at the meeting: The gas-liquid separator adopts side inlet configuration with dimensions DN200 × 600 mm. CFCT shall submit the equipment drawing of the gas-liquid separator to SW prior to the next regular meeting. | 06/22设备图纸已提供。06/23Keith回复意见，见06/23讨论内容。 Equipment drawings were provided on 06/22. Keith's feedback was received on 06/23 — please refer to the discussion notes from 06/23. | YES | Ziliang Zhao
06/17 | SW | 根据最新工作进展并结合HAZOP分析所需文件内容，更新“Sandwich Hydrogenation Implementation Schedule” Update the Sandwich Hydrogenation Implementation Schedule based on the latest progress and document requirements for HAZOP study. |  | NO | All
06/17 | SW | 讨论操作规程：哪些部分需要顺控？开停车步骤等 Discuss operation procedures: identify sections requiring sequence control, including startup and shutdown steps, etc. | 06/23：开车步骤：公用工程确认/催化剂装填→氮气置换（R24-BT01、R24-BT04和剩余部分），氧含量<0.5vol%→氢气置换→原料系统备料→TCU系统调温→反应器进料（氢气先进料背压至反应压力，液相再进料）→气液分离→产品转移 停车步骤：停进料→产品缓冲罐物料转移→反应器卸压→R24-BT03卸压→反应系统降温→氮气置换→关闭氮气和TCU Startup Procedures： 1.Verification of utility systems & catalyst loading 2.Nitrogen purging (for R24-BT01, R24-BT04 and the rest of the system), oxygen content controlled below 0.5 vol% 3.Hydrogen purging 4.Raw material preparation for feed system 5.Temperature adjustment of TCU system 6.Reactor feeding: Introduce hydrogen first to build backpressure up to reaction pressure, then feed liquid phase material 7.Gas-liquid separation 8.Product transfer Shutdown Procedures： 1.Cut off feed supply 2.Transfer materials from product buffer tank 3.Depressurize reactor 4.Depressurize R24-BT03 5.Cool down reaction system 6.Nitrogen purging 7.Shut down nitrogen supply and TCU system Keith提供HAZOP时的开停车步骤，结合上述文件，整理开停车和清洗步骤 Compile the plant start-up, shutdown and cleaning procedures based on the above documents together with the start-up & shutdown sequences supplied by Keith for HAZOP assessment. | NO | All
06/17 | SW | 会后确认：安全阀的泄放温度超过设备的设计温度，是否需要提高设备的设计温度？ To be confirmed after the meeting：If the relief temperature of the safety valve exceeds its design temperature, is it necessary to increase the design temperature rating? | 设备和管线材质为316L，结合设备和管道的壁厚，计算得出：在泄放温度下，材料的许用应力满足其强度要求，不需提高设备的设计温度 The equipment and piping are fabricated from 316L stainless steel. Wall thickness calculations for the equipment and piping demonstrate that the allowable stress of the material satisfies the strength requirements at relief temperature; therefore, no increase to the equipment design temperature is required. | Yes | Ziliang Zhao/Chaoqun Hu
06/17 | SW | CFCT做撬块设计时，注意清洗过程中的低点排净 CFCT shall take full consideration of low-point draining during cleaning when designing the skid package. | 06/23：在撬块设计时，设置管道的低点排净阀 When designing the layout, install a drain valve at the low point of the pipeline 06/23会议方案：管道最低点设置排净阀，操作说明中明确排放时用容器收集排放液体。 Meeting Plant: Install drain valves at the lowest point of the pipeline, and specify in the operating instructions to collect the discharged liquid with a container during the drainage process. | Yes | Shuangshuang Fan
06/17 | SW | CFCT提供放空缓冲罐T06是否放在撬内的方案 CFCT to provide a scheme on whether vent buffer tank T06 shall be installed inside the skid. | 06/23：按照现有空间的布置，T06放在撬块内的空间不足；撬块中间的操作维护通道宽度为300-350mm，能否将整体撬块宽度增加150-200mm？ According to the existing space arrangement, there is insufficient space for T06 to be placed inside the pry block; The width of the operation and maintenance channel in the middle of the pry block is 300-350mm. Can the overall pry block width be increased by 150-200mm? 06/23会议方案：T06不放在撬块内，放置在service area，同时反应柱/冷凝器的TCU出口管路上的温度变送器安装在近出口处，去掉手动球阀，安全阀可放到service area，并设置排净阀，进口管路手动球阀保持不变，温度变送器加套管，位置可前可后，低点设置排净阀，整体管路的高点设置排气阀。 Meeting Plant:: T06 is not placed inside the lever block but in the service area. The temperature transmitter on the TCU outlet pipeline of the reaction column/condenser is installed near the outlet. The manual ball valve is removed, and the safety valve can be placed in the service area. A drain valve is installed, while the manual ball valve on the inlet pipeline remains unchanged. The temperature transmitter is equipped with a protective sleeve, with its position adjustable forward or backward. A drain valve is set at the low point, and an air vent valve is installed at the high point of the entire pipeline. | Yes | Shuangshuang Fan
06/23 | SW | Keith意见： 基本设计：我们是否有经批准的分离器设计方案？我上次看到的摘录中，计算出的容器直径为3毫米，这表明计算或输入数据可能存在错误。 Basic design 1. Do we have an approved design for the separator. The last extract I saw had a calculated vessel diameter of 3mm, which suggests an error in the calculations or input data. | 06/23讨论： 基本设计：按最新设备数据表进行气液分离器设计。气液分离器的计算书已复核过，数据无误。 06/23Discussion—Basic Design: The gas-liquid separator shall be designed in accordance with the latest equipment data sheet. The calculation sheet for the gas-liquid separator has been reviewed and the data are confirmed to be correct. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 分离器内件 1、本设计中是否已考虑分离器内件，例如入口导流装置或入口旋风分离器、气相除雾器、液体出口处的防涡流挡板？ 2、喷淋球能否采用焊接固定方式，而非通过管接头引入容器内部？ 3、喷淋球是否必须为旋转式喷淋球？这会增加设备复杂度，并在工厂运行寿命期内带来检查与维护方面的问题。 4、喷淋球实际能否起到喷淋清洗作用，还是仅仅将容器注满清洗液直至触发高位液位开关？根据此前讨论，从空罐到高位跳闸点的时间不足25秒，这无法为分离器气相侧提供足够的机械清洗作用时间。 Separator internals 1. Have separator internals been considered for this design e.g. inlet diverters or inlet cyclones, demisting of the vapour stream, vortex breakers on the liquid outlet. 2. Can the spray ball be welded in position rather than introducing a tube fitting into the vessel. 3. Does the spray ball need to be a rotary spray ball. This adds complexity and inspection/maintenance issues during the life of the plant. 4. Will the spray ball actually work as a spray ball, or will it simply fill the vessel with cleaning fluid until the high-level switch is activated. Based on previous discussions this would be less than 25 seconds from empty to high-level trip point, which doesn’t allow much time for mechanical cleaning action in the gas side of the separator. | 06/23讨论： 分离器内件： 1、气液分离器设计采用重力式分离，无需额外的内件。 2、喷淋球相关事宜，CN团队内部结合喷淋球供应商商议方案。 06/23 Discussion — Separator Internals: 1.The gas-liquid separator is designed as a gravity-type separator; no additional internals are required. 2.Regarding the spray ball matters, the CN team will internally discuss and determine the solution in coordination with the spray ball supplier. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 设计参数 1、“流体性能”是否应定为“非致命性”？我推测此概念类似于PED容器设计中的流体分组，在英国规范中应属于Group 1气体（即可燃/爆炸/有毒），而非“非致命性”。 2、工作压力应为0至6MPaG。 3、设计温度应至少为150°C，并且我假设在泄压事故工况下，容器温度可能达到约300°C。 4、设计压力应为全真空至9MPaG。 5、规范是否要求进行焊后热处理（PWHT）？ 6、水压试验压力应为设计压力的1.5倍，即13.5MPaG，而非12MPaG。 7、对于该容器，S4应为DN32 Cl900 WN法兰。喷淋球接口是否应作为单独细节在本图纸上表示，还是另页图纸表示更为合适？ 8、充装系数（Fulling Factor）是多少？ Design Parameters 1. Should the ‘Fluid Performance’ be Non-Lethal? I assume this is similar to the fluid group for PED vessel design, which for the UK would be Group 1 gas i.e. flammable/explosive/toxic and not Non-Lethal. 2. The working pressure should be 0 to 6MPaG. 3. The design temperature should be at least 150 °C and I assume the vessel has the potential to reach circa 300°C during a relief event. 4. The design pressure should be FV to 9MPaG 5. Is PWHT required by the code. 6. Hydro test pressure should be 1.5x design pressure i.e. 13.5MPaG not 12 MPaG. 7. For the vessel, S4 should be a DN32 Cl900 WN Flange. Should the spray ball fitting be shown as a separate detail on this drawing or possibly shown on a separate drawing. 8. What is the Fulling Factor. | 06/23讨论： 设计参数 ： 1、介质调整为易爆。 2、CN团队结合URS，修正工作压力，更新设备数据表。 3、可以将泄压事故工况，纳入到常规设计考虑中，即可提高设计温度到300℃。 4、修正设计压力，更新设备数据表。 5、规范可不进行焊后热处理（PWHT）。 6、水压试验压力为设计压力的1.3倍，故试验压力可不做调整。 7、S4为喷淋口，口径为Φ10，DN32法兰接口结构为保证喷淋球可抽出，后续根据喷淋球整体方案做调整，判定是否需要可抽式。 8、充装系数是指物料实际容积与容器全容积之比。 06/23 Discussion — Design Parameters: 1.The medium classification is revised to "explosive." 2.The CN team will revise the working pressure based on the URS and update the equipment data sheet accordingly. 3.The relief event scenario can be incorporated into the normal design considerations — i.e., the design temperature can be raised to 300°C. 4.The design pressure will be revised and the equipment data sheet updated accordingly. 5.PWHT (post-weld heat treatment) is not required per the applicable code. 6.The hydrostatic test pressure is 1.3 × design pressure, so the test pressure does not need to be adjusted. 7.S4 is the spray ball connection, with a bore size of Φ10. The DN32 flange connection is designed to allow the spray ball to be withdrawable. This will be reviewed and adjusted as part of the overall spray ball solution, and a decision will be made on whether a withdrawable type is necessary. 8.The filling factor is defined as the ratio of the actual liquid volume to the total vessel volume. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 通用事项 1、管口方位是否已考虑设备布置的最优化？ 2、在撬装高度限制范围内，容器能否通过重力自由排液至产品收集罐？ 3、在顶部法兰上开孔用于引出管，是否会损害其机械完整性并违反安全规范？是否已重新计算法兰厚度或进行有限元分析（FEA），以确保足够的金属厚度和结构完整性？ 4、液位变送器/液位开关的规格是否已确认？法兰尺寸及位置是否与仪表相匹配？ 5、请更新P&ID，以显示S4正确的管口尺寸。 6、是否有容器设计计算书？技术文件中需要包含设计计算书，并应在FAT（工厂验收测试）时进行核查。 General 1. Does the nozzle orientation allow for optimum equipment layout. 2. Can the vessel free drain into the product collection tank, within the skid height constraints. 3. Does boring a hole in the top flange for the outlet pipe compromise its mechanical integrity and violate safety codes. Have you recalculated the flange thickness/carried out FEA to ensure adequate metal thickness and structural integrity. 4. Has the level transmitter/level switches been agreed – does the flange size/position align with the instruments. 5. Update P&ID to show correct nozzle size for S4. 6. Do you have vessel design calculations. Design calculations will be required in the technical file and should be checked at FAT. | 06/23讨论： 通用事项 ： 1、管口方位已结合3D撬装布置给定。 2、3D撬装设计已考虑，待3D模型复核时，详细讨论。 3、重新计算法兰厚度，以满足结构强度要求。 4、仪表工程师已经确认复核。 5、P&ID，不需要更改S4管口尺寸。 6、设计计算书是设备完整技术文件中必不可少的一部分，后续会提供。 06/23 Discussion — General Items: 1.Nozzle orientation has been determined based on the 3D skid layout. 2.The 3D skid design has taken this into consideration; detailed discussion will be held during the 3D model review. 3.The flange thickness will be recalculated to meet structural strength requirements. 4.The instrumentation engineer has confirmed and verified this. 5.The P&ID does not require changes to the S4 nozzle size. 6.The design calculation sheet is an essential part of the complete technical documentation for the equipment and will be provided in due course. | YES | Ziliang Zhao/Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Overall cleaning philosophy per vessel 各容器整体清洗策略 Please confirm the intended cleaning philosophy for each vessel in the skid — spray-only, soak-only, spray-and-soak combined, or an alternative approach. Please also indicate whether a single philosophy applies across all vessels or whether the strategy varies by vessel. 请确认撬块内各台容器的清洗策略：单独喷淋、单独浸泡、喷淋+浸泡组合，或其它方式。请同时说明是否所有容器采用同一策略，或按容器区别设计。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleanliness verification method & acceptance criteria 清洁度验证方法与验收标准 Please advise the verification method(s) used to confirm cleaning completion (visual inspection, swab / rinse sample analysis, mass balance, calculated residue, etc.) and the numerical acceptance criteria applied (e.g. residue mass, ppm concentration threshold). 请说明用于确认清洗完成的验证方法（目视检查 / 拭子或冲洗样分析 / 物料衡算 / 残余物计算等），以及所采用的数值验收标准（如残余物质量、浓度阈值 ppm）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Sight glass availability for SE01 SE01 视镜配置 The reactor vessels are understood to be fitted with sight glasses to support visual verification of cleanliness. The gas–liquid separator SE01, however, does not include a sight glass. Please confirm the intended method for verifying cleanliness on SE01. 反应柱已配置视镜以支持目视清洁度检查，但气液分离器 SE01 未配置视镜。请确认 SE01 清洁度验证的具体手段（，以及是否考虑将新增视镜作为设计变更纳入）。 | 07/10：反应柱和分离器因为操作压力高，无法配置视镜，清洁度的验证无法依靠目测，需取样分析测量残留物的浓度 07/10：Due to the high operating pressure of the reaction column and separator, sight glasses cannot be installed. Visual inspection is therefore not feasible for cleanliness verification, and residue concentration shall be determined via sampling analysis instead. 08/13：不增加视镜，冯博士提供国内清洁度验收限度的方法供SW参考。 08/13：Without adding a sight glass, Dr. Feng provided the domestic cleanliness acceptance criteria method for SW's reference. | NO | Xiantao feng/Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Spray ball flow rate vs. vessel fill time 喷淋球流量与容器充液时间的匹配 The lowest available spray ball flow rate (approximately 20 L/min) results in SE01 reaching the high-level trip point in under 25 seconds. This limits the time window in which mechanical spray action can achieve wetting coverage. Please advise the intended cleaning-time window on SE01 and the approach for ensuring adequate mechanical cleaning action within the design constraint. 现有最小可选喷淋球流量约 20 L/min，导致 SE01 容器在 25 秒内即达到高液位跳停，机械喷淋作用的有效时间窗口非常短。请说明 SE01 上预期的清洗时间窗口，以及在此设计约束下如何确保获得充分的机械清洗作用。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Drain line sizing and fill–drain cycle 排放管径与充液-排空循环 Under the current drain line configuration, the drain rate is significantly slower than the spray inflow rate. Please advise the intended drain line diameter (whether upsizing is planned), the estimated single-cycle fill and drain durations, and the number of cycles anticipated per cleaning campaign. 当前排放管径下，排放速率显著慢于喷淋进料速率。请说明拟采用的排放管径（是否放大）、单次循环的充液和排空时间估算，以及每次清洗预期需要的循环次数。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Soak cleaning vs. high-level interlock defeat mechanism 浸泡清洗与高液位联锁绕过机制 If soak cleaning is adopted on SE01, the liquid level during cleaning will exceed the high-level safety interlock (located at approximately one-third of vessel height). Please specify: (a) the physical mechanism intended for defeating this interlock during cleaning (key switch, procedural lockout, or other); (b) the authorisation and access controls surrounding the defeat mechanism; and (c) the safeguards against inadvertent defeat during normal processing operation. 若 SE01 采用浸泡清洗，清洗过程中的液位将超过位于容器约 1/3 高度的高液位安全联锁。请说明：(a) 清洗时用于绕过（defeat）该联锁的物理机制（钥匙开关 / 程序锁定 / 其它）；(b) 该绕过机制的授权与权限控制方式；(c) 防止正常运行时意外绕过的保护措施。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleaning of the guided-wave level transmitter housing Guided wave 液位变送器外壳的清洁 The guided-wave level transmitter housing (approximately 100 mm diameter, side-mounted on SE01) sits above the high-level switch and lies outside the spray ball coverage envelope. Please advise the intended cleaning approach for this housing, and any mechanical or procedural provisions required to ensure it can be cleaned to the acceptance criteria in Q1.2. 液位变送器外壳（约 100 mm 直径，SE01 侧接管上）位于高液位开关之上，不在喷淋球覆盖范围内。请说明该外壳的清洁方案，以及为达到 Q1.2 中的验收标准所需的机械或程序性措施。 | 07/14：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用 07/14：Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. | YES | Chaoqun Hu/Yu Gao
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Reactor cleaning cycle time and manual interventions 反应器清洗循环时间与人工干预 For the 200-L reactor vessels, a single spray-and-drain cycle involves an extended drain phase relative to the spray phase. Multiple cycles are expected to achieve the required cleanliness. Please advise: the anticipated number of cycles, the total cleaning duration per campaign, and the specific manual interventions required at each step (drain valve operation, sample point access, lockout re-set, etc.). 200-L 反应器进行单次"喷淋-排空"循环时，排空阶段远长于喷淋阶段，需多次循环以达到清洁度要求。请说明：预期循环次数、每次清洗总时长，以及各步骤所需的具体人工干预（排放阀操作 / 取样口操作 / 联锁复位等）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW 3D Layout 3D 布置与设备空间 | Operational access clearance 操作通道净空 The current 3D model shows approximately 300–350 mm clearance in certain operator access zones. Please confirm the target minimum clearance from a site operability and maintenance standpoint, and identify any specific zones where relaxation of the current clearance is acceptable, or where additional clearance is required. 当前 3D 模型显示部分操作人员通道净空约为 300–350 mm。请从现场操作与维护角度，确认目标最小净空要求，并识别可以放宽的具体区域，以及需要额外净空的区域。 | 7月10日反馈进展： 建议增加反应柱撬块的宽度，审核模型后给出建议的空间区域。 It is recommended to increase the width of the reaction column skid and provide the suggested spatial area after reviewing the model. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Free-drain feasibility from each vessel 各容器的自重排放可行性 The cleaning strategy relies on free-drain of cleaning fluid from each vessel into downstream collection (BT04 or equivalent). Considering the skid height constraint and each vessel elevation, please confirm the free-drain path is mechanically feasible from each source vessel to its destination. Please identify any vessels where drainage cannot be achieved by gravity and would require pumping or an alternative arrangement. 清洗策略要求清洗液自重从各容器排入下游收集罐（BT04 或等效容器）。考虑撬块高度限制与各容器标高，请确认每台源容器至其目标容器的自重排放路径机械可行。请识别无法通过重力实现排放、需要泵抽或采用替代方案的容器。 | 7月10日反馈进展： 根据目前容器的结构形式，反应柱可通过底部排放阀排放，缓冲罐可通过管路排放，预热器、冷凝器管路无排放口。具体排放方式参考清洗方案。 Based on the current structural design of the containers, the reaction column can be drained through the bottom discharge valve, the buffer tank can be discharged via piping, while the preheater and condenser have no discharge outlets in their pipelines.Refer to the cleaning plan for specific emission methods. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Nozzle orientation on pressure vessels 压力容器管嘴方位 Please review the nozzle orientation on all pressure vessels in the current 3D model. Confirm that nozzle positions provide adequate access for external piping tie-in, instrumentation installation, and maintenance (removal / reinstallation of internals, gasket replacement, catalyst service, etc.). 请审查当前 3D 模型中所有压力容器的管嘴方位。确认管嘴位置能够满足外部管路对接、仪表安装以及维护（内构件拆装 / 密封垫更换 / 催化剂检维修等）的空间要求。 | 7月10日反馈进展： 由于空间尺寸限制，部分管口的维护可能存在不便。优化管口布置或能否增加设备空间。 Due to space size limitations, maintenance of some pipe openings may be inconvenient. Optimize pipe layout or increase equipment space | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Catalyst charging & discharging arrangement 催化剂加料与卸料布置 Please confirm that the catalyst charging (loading) and discharging (unloading) arrangement is compatible with the current nozzle layout on the reactor vessels, and that adequate space is provided for charge / discharge equipment and operator access during catalyst service. 请确认催化剂加料与卸料的操作方式与当前反应柱的管嘴布置兼容，且在催化剂检维修期间为加料/卸料设备与操作人员留有充足空间。 | 7月10日反馈进展： 根据目前的布置方案，反应柱加料卸料口均在撬体端面，结合加料卸料方式看操作空间是否充足。 According to the current layout plan, the feeding and discharging ports of the reaction column are all located on the end face of the pry body. Considering the feeding and discharging methods, it is necessary to check whether the operating space is sufficient. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Tie-in points between skid and site utilities 撬块与现场公用工程接口 Please confirm the finalised location and specification of all tie-in points between the skid and the Sandwich site services, including process feed, product outlet, vent header, HTF supply and return, N₂ blanketing, instrument air, electrical supply, cable penetrations, and drain. Please advise the interfaces where design lock-down is still pending. 请确认撬块与 Sandwich 现场公用工程之间所有接口的最终位置与规格，包括工艺进料、产品出口、放空总管、导热油供回、氮气钝化、仪表空气、电气供应、电缆穿墙、排放。请说明尚未定稿的接口。 | 7月10日反馈进展： 根据现有的布置方案，有部分公用工程的的接口，无仪表空气接口，电气供应、电缆穿墙，后续更新撬块与公用工程接口的位置与规格。 According to the existing layout plan, there are interfaces for some public works without instrument air interfaces, electrical supply, and cable penetration through walls. The location and specifications of the interface between the pry block and the public works will be updated in the future. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Cable wall penetration capacity and cable compatibility 穿墙电缆孔容量与电缆兼容性 The current design indicates 14 available cable wall penetration slots. Please confirm this final count, the internal diameter of each slot, and the compatibility of the slot with the largest cable type intended to pass through (multi-core, armoured, or shielded cables of relevant cross-section). 当前设计显示可用穿墙电缆孔 14 个。请确认该数量的最终定案、每个孔的内径规格，以及与拟穿过的最大电缆类型（相应截面的多芯 / 铠装 / 屏蔽电缆）的兼容性。 | 寻求工程部支持，和宋小旭主管约会讨论如何推进，7月10日反馈进展 8/10：与宋小旭一起更新电缆型号、线径(按国内标准) | YES | Dezhi meng/Shaofeng gao
07/01 | SW Control Philosophy 控制策略 | Full Control Philosophy document issue date 完整《控制策略》文件发出日期 Please advise the target issue date for the complete Control Philosophy document, superseding the interim draft version previously circulated. 请说明完整版《控制策略》文件的目标发出日期（覆盖此前流转的过渡草稿版本）。 | 07/10：已完成初版，还在校核中，预计下周发出 07/10：The initial draft has been completed and is under review; it is expected to be issued next week. | NO | Chaoqun hu
07/01 | SW Control Philosophy 控制策略 | Interlock schedule — hardwired vs. software 联锁清单 —— 硬件联锁与软件联锁 Please provide a complete interlock schedule listing all safety interlocks, with clear delineation between hardwired (independent of the PLC) and software (PLC-implemented) interlocks. For each interlock, please include: initiating cause, sensing element, trip setpoint, action taken, and protective function fulfilled. 请提供完整的联锁清单，列出全部安全联锁，明确区分硬件联锁（独立于 PLC）与软件联锁（PLC 实现）。每一条联锁请包含：触发原因、检测元件、跳停设定值、联锁动作、承担的保护功能。 | 07/10：联锁条件已完成初版，还在校核中，预计下周发出 07/10：The initial draft of interlock conditions has been completed and is under review, which is expected to be issued next week. 8/21：已发出 | YES | Chaoqun hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Operational modes and mode-specific fail positions 操作模式与各模式下的故障位 Please define all operational modes of the skid (normal operation, start-up, shut-down, cleaning, catalyst change, emergency depressurisation, etc.), and for each mode specify: (a) the fail position of each control valve; (b) the state of each interlock (active / bypassed); and (c) the permissive conditions required to enter that mode. 请定义撬块的全部操作模式（正常运行 / 开车 / 停车 / 清洗 / 催化剂更换 / 紧急泄压等），并针对每一模式说明：(a) 每个控制阀的故障位；(b) 每个联锁的状态（激活 / 已绕过）；(c) 进入该模式所需的许可条件。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 分离器浸泡清洗时易触发液位高联锁，导致高液位以上清洗不彻底。增大分离器的排净管径可实现淋洗，同时系统处于清洗模式时，绕开液位高联锁。 High level interlock is prone to tripping during soaking cleaning of the separator, leading to inadequate cleaning of areas above the high liquid level. Increasing the drain pipe size of the separator allows shower rinsing. Meanwhile, the high level interlock can be bypassed when the system is under cleaning mode. | Pending | Chaoqun hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Mode-transition safeguards 操作模式切换的保护措施 Please advise the safeguards in place against inadvertent mode transitions, particularly from cleaning mode back to processing mode (e.g. an interlock bypass being left in place after cleaning is complete). Please describe both the technical safeguards (key switches, HMI confirmations) and the procedural safeguards (SOP requirements, dual sign-off). 请说明防止意外切换操作模式（尤其是从清洗模式返回处理模式时联锁绕过未复位）的保护措施。请分别描述技术性保护措施（钥匙开关 / HMI 确认）与程序性保护措施（SOP 要求 / 双签发）。 | 52条和Keith讨论后1周反馈。 | NO | Dezhi meng
07/01 | SW Sampler System 取样系统 | Sample vaporisation during pressure reduction 取样过程中的样品闪蒸 The sampler transfers process fluid from a line operating at up to 60 barG to a sample container at approximately atmospheric pressure. Please advise the analysis of vaporisation during this pressure reduction (fraction vaporised, temperature drop) and its impact on the compositional representativeness of the collected sample. 取样器将最高 60 barG 工艺管路的介质转移至常压取样瓶。请说明此压降过程中的闪蒸分析（气化比例、温度降低）及其对所采样品成分代表性的影响。 | 07/10：冷凝器出口的温度为30℃，压力从60barG 泄至常压，此温度条件下不会发生闪蒸 07/10：The temperature at the condenser outlet is 30°C. The pressure is relieved from 60 barG to atmospheric pressure, and no flashing will occur under this temperature condition. | Pending | Chaoqun hu
07/01 | SW Sampler System 取样系统 | Sample retention design 样品截留设计 Please advise the design of the sample bottle and sample-transfer system, including any vapour trap, septum, condenser, or other retention device intended to prevent loss of volatiles through the vent path and to ensure a representative liquid sample is captured. 请说明取样瓶及取样传输系统的设计，包括为防止挥发组分从放空路径流失、并确保获得代表性液样所采用的蒸汽阱、隔膜、冷凝器或其它截留装置。 | 07/10：取样器的流程：打开三通阀将缓冲罐充满，打开缓冲罐气相放空管线阀门，将缓冲罐中的气相排走并卸压，打开氮气手阀，将缓冲罐中的液体压至取样瓶 07/10：Sampling procedure: Open the three-way valve to fill the buffer drum. Open the valve on the vapor vent line of the buffer drum to vent the vapor inside and relieve pressure. Then open the nitrogen manual valve to pressurize and transfer the liquid from the buffer drum into the sampling bottle. | Pending | Chaoqun hu
07/01 | SW Sampler System 取样系统 | Sampler behaviour under gas-rich flow regime 气相主导流态下取样器行为 With the intended process operating at a stoichiometric excess of hydrogen, the flow regime through the sampling point may be gas-rich with entrained liquid rather than liquid-continuous. Please advise how the sampler design accommodates this flow regime, and whether any sample point relocation, phase separator, or coalescer is being considered. 工艺预期在化学计量氢气过量条件下运行，取样点处流态可能为"气相夹带液体"而非液相连续。请说明取样器设计如何适应此流态，以及是否考虑取样点位置调整、加装相分离器或聚结器。 | 07/10：取样器的缓冲罐上有气体排放管线，取样罐充满后，打开气体排放管线，将气相排走并卸压，再用氮气将液相压至取样瓶 07/10：The buffer vessel of the sampler is equipped with a gas vent line. Once the sampling tank is full, open the gas vent line to vent the vapor phase and relieve pressure, then push the liquid phase into the sampling bottle with nitrogen. | Pending | Chaoqun hu
07/01 | SW Instrumentation 仪表配置 | Guided-wave level transmitter — datasheet & cleanability Guided wave 液位变送器 —— 数据单与可清洁性 Please provide the guided-wave level transmitter datasheet and confirm: (a) the process compatibility of the probe assembly with the intended service (including any operating conditions in the supercritical or near-critical regime); and (b) the cleanability of the probe assembly under the adopted cleaning philosophy. 请提供 guided wave 液位变送器数据单，并确认：(a) 探头组件在拟定工况（含超临界或近临界工况）下的适用性；(b) 探头组件在拟采用清洗策略下的可清洁性。 | 7月10日反馈进展 (a) 导波雷达液位计工作原理是雷达波可以穿过介电常数较低的气相，遇到介电常数较大的液相返回，从而计算液位。适用蒸汽、粉尘、泡沫等工况。需了解超临界工况下的介质状态是否还存在液相，如果没有液相空间，则液位计无法识别。 The working principle of the guided-wave radar transmitter is that the radar wave can pass through the gas phase with a lower dielectric constant and return to the liquid phase with a larger dielectric constant, thereby calculating the liquid level. It is applicable to working conditions such as steam, dust and foam. It is necessary to understand whether there is still a liquid phase in the medium state under supercritical conditions. If there is no liquid phase space, the transmitter cannot identify it. 07/15进展：经内部评估，液位计所在容器操作工况下不存在超临界状态。 After internal assessment, it was determined that the liquid level gauge is not in a supercritical state under the operating conditions of the container it is located in. (b)BT01和BT04的导波雷达液位计为顶装内伸形式，可以利用设备内的喷淋头冲洗。SE-01的导波雷达液位计为侧装旁通式，可以选择在探头与旁通管的过程接口处增加配套冲洗环，并预留一路冲洗管线。 The guided-wave radar transmitters of BT01 and BT04 are top-mounted and iInsert type, and can be flushed by the spray heads inside the equipment. The guided-wave radar l transmitter of SE-01 is of side-mounted bypass type. A matching flushing ring can be added at the process interface between the probe and the bypass pipe, and a flushing pipeline can be reserved. 07/14进展：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用. Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. 07/17进展：气液分离器雷达液位计侧装改顶装，已完成图纸设计，筒体直径未变，邮件发出。 The radar level gauge for the gas-liquid separator has been redesigned from side-mounted to top-mounted. The drawing design has been completed, and the vessel diameter remains unchanged. The drawings have been sent out via email. | Pending | Yu gao/Chaoqun hu/Zilaing Zhao
07/01 | SW Instrumentation 仪表配置 | Level switch position & interlock function 液位开关位置与联锁功能 Please confirm the finalised position (elevation, orientation, flange size and rating) and the interlock function of each level switch (LSL, LSLL, LSH, LSHH) on each vessel, together with the matching instrument selection. 请确认每台容器上各液位开关（低 LSL、低低 LSLL、高 LSH、高高 LSHH）的最终位置（标高、方位、法兰尺寸与压力等级）与联锁功能，以及对应的仪表选型。 | 7月10日反馈进展： 关于液位开关选型，之前寻价时只有VEGA的VEGASWING 63型号可以满足DN25 Class900 M的过程接口，其他厂家如E+H、Rosemount都不能满足。 About the selection of level switches, during the previous price search, only VEGA's VEGASWING 63 model could meet the DN25 Class 900 M process connection requirements. Other manufacturers such as E+H and Rosemount could not meet these requirements. 07/15联锁值详见联锁条件表。The interlock values on 07/15 can be found in the interlock condition table. | Pending | Chaoqun hu/Yu gao
07/01 | SW Instrumentation 仪表配置 | Instrument datasheet next revision date 仪表数据单下一版本发出日期 Please advise the target issue date for the next revision of the Instrument Datasheet, reflecting the current SE01 design (post demister-configuration decision), the finalised interlock schedule, and the level switch position confirmation. 请说明反映当前 SE01 设计（demister 配置定稿后）、最终联锁清单以及液位开关位置确认的仪表数据单下一修订版本的目标发出日期。 | 7月10日反馈进展 仪表数据表已完成修订版，待意见讨论后看是否还需修改参数。 The instrument datasheet has been revised. After the discussion of opinions, we will see if the parameters still need to be modified. 08/05:根据最新设计温度和压力，更新仪表数据表，预计08/11发出 | NO | Chaoqun hu/Yu gao
07/01 | SW Documentation Status 文档状态 | Current revision and next revision date of key deliverables 主要交付文件的当前版本与下一版本时间 Please confirm the current issued revision and the target date for the next revision of the following documents: • PFD • P&ID • URS • Equipment Datasheets • Control Philosophy • Instrument Datasheet • Operating Instructions • Cleaning Procedure • Vessel Design Calculation Package. 请确认以下文档的当前已发版本与下一修订版本的目标日期： · PFD · P&ID · URS · 设备数据单 · 控制策略 · 仪表数据单 · 操作说明 · 清洗程序 · 容器设计计算书。 | 7月10日反馈进展，操作手册还在编制中，其他设计文件已完成。On July 10th, we provided the progress update. The operation manual is still under preparation, while the other design documents have been completed. 08/05：预计本周末发出 | NO | Shaofeng gao/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R1] Design Temperature — Vessel could fail during relief event. Equipment design temperature is specified for process requirements and does not consider elevated temperatures during relief events when short-term temperature increase has the potential to exceed the design temperature. 设计温度 —— 容器可能在泄放事件中失效。设备设计温度是按工艺需求设定的，未考虑泄放事件中的短时温升可能超过设计温度的情形。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：已更新数据表，提高设计温度，以满足工艺需求，图纸已升级。 07/10: Data sheet updated with elevated design temperature to meet process requirements; drawings revised accordingly. | YES | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register Engineering Design 工程设计 | [R2] Design Requirements — L:G ratio for plant is not clearly defined. Equipment design could result in very limited operating ranges and incorrect assumptions in plant capability and relief design. 设计条件 —— 装置的液气比（L:G ratio）未明确定义。可能导致设备设计的操作区间受限，以及在装置能力和泄放设计中做出错误假设。 | 7月10日反馈进展，根据最终确定的反应器尺寸核实气液比数据。On July 10th, the progress was reported. The gas-liquid ratio data was verified based on the final determined reactor size. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Engineering Design 工程设计 | [R3] Design Requirements — Catalyst specification is not available. Design may not be suitable for some catalysts. Dusty catalysts could cause blockages. 设计条件 —— 催化剂规格未明确。设计可能不适用于某些催化剂；含粉尘的催化剂可能导致堵塞。 | Keith / SW response: Design philosophy is based on catalyst beads/pellets which are dust-free, non-flammable and have exposure levels requiring OEB 3 or lower containment. Note: OEB 3 containment is a deviation from the URS and requires acceptance. Keith / SW 答复： 设计基于无粉尘、非燃、暴露等级 OEB 3 或更低的颗粒/粒状催化剂。注：OEB 3 的密闭要求相对 URS 存在偏离，需要接受确认。 | NO | SW
07/02 | SW - Risk Register Engineering Design 工程设计 | [R4] Access — Layouts are not available to assess whether access to equipment is acceptable for operations and maintenance. 通道 —— 布置图尚未提供，无法评估设备的操作与维护通道是否满足要求。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.1 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R5] Maintenance — Lifting Aids (davit arms, lifting beams, etc.) have not been considered in design, with potential for injury to maintenance personnel removing heavy equipment for servicing / repair / replacement. 维护 —— 设计中尚未考虑起重辅助设施（吊臂、起吊梁等），维护人员在拆卸重型设备进行检修 / 修理 / 更换时可能存在人身伤害风险。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R6] Lighting — Layouts are not available to assess whether lighting for routine operations and maintenance activities is acceptable. 照明 —— 布置图尚未提供，无法评估日常操作和维护活动的照明条件是否满足要求。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R7] System leak detection — Pressure testing of high-pressure system will be hydraulically tested. Hydraulic testing demonstrates mechanical strength of the pressure system but does not demonstrate integrity for a hydrogen system. 系统检漏 —— 高压系统将进行水压试验。水压试验只能证明压力系统的机械强度，无法证明氢气系统的密封完整性。 | Keith / SW response: Helium testing is not routinely carried out in China. Keith / SW 答复： 国内通常不常规进行氦气检漏。 可以做气密性试验；国内整橇系统气密性试验后，分体运至英国，进入工厂房间后，再次组装，需重新进行泄漏试验，现场是否具备试验条件？现场可进行氦气检漏。 和CE认证机构确认一下具体方案。 A pneumatic test can be performed. After the complete skid system undergoes the pneumatic test in China, it will be shipped in split form to the UK. Upon arrival at the factory site and reassembly, a new leak test will be required. We need to confirm whether the site has the necessary conditions/facilities for this test. Helium leak detection is available on site. We will confirm the specific plan with the CE Notified Body. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R8] Line sizing / specification — Vents / headers incorrectly sized / specified, resulting in high back pressure and safety / operability issues, e.g. two-phase flow in emergency vent relief header. 管线规格 / 尺寸 —— 放空 / 泄放总管尺寸或规格不正确，导致背压过高及安全 / 可操作性问题，例如紧急泄放总管中出现两相流。 | 07/10：安全阀进出口尺寸详见P&ID 07/10：Refer to the P&ID for the inlet and outlet sizes of the safety valve. | Pending | Chaoqun hu
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R9] Insulation — Insulation requirements not specified, which could result in equipment / pipe layout not allowing space for insulation to be installed. 保温 —— 保温需求尚未明确，可能导致设备 / 管路布置未预留保温安装空间。 | Confirm the insulation material with Keith and determine the thickness. Once it's confirmed, provide a progress report on July 10th. 和Keith确认下保温材料，然后确定厚度。确定后，7月10日反馈进展 3D模型中管路的间距已按照保温厚度30-35mm预留了保温的安装空间。 The spacing between pipes in the 3D model has been designed to accommodate an insulation installation gap of 30-35mm, as per the insulation thickness requirements. | YES | Yinghui cheng/Chaoqun hu/Shuangshuang fan/Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R10] Modular design — Modular design could introduce significant increase in site construction activities, e.g. mechanical and EC&I installation and subsequent testing. 模块化设计 —— 模块化设计可能大幅增加现场施工工作量，例如机械与电控仪表安装及后续测试。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 现有模块化设计的方案是根据进口电梯的尺寸，将整套设备拆分为4个撬块运输组装。 SW建议：需再考虑从屋顶直接吊装进去的方案，需要在后续周三会上进一步讨论。 The current modular design solution involves dividing the entire set of equipment into four skids for transportation and assembly based on the dimensions of imported elevators. SW Recommendation: Further consideration is needed for the direct hoisting-in-from-the-roof solution, which will be discussed in the upcoming Wednesday meeting. 07/29：会上澄清四撬块方案技术可行、屋顶吊装非必选；认证机构评估以 3D 定稿为前提，Keith 下周四返回后进一步确认。 07/29: Clarified that the four-module option is technically feasible and roof removal is not mandatory; the Notified Body assessment requires the finalised 3D layout, to be confirmed further with Keith after he returns next Thursday. 08/05:核实分撬是否与海运有关，和进出口部（公司内）请教下海运的最大尺寸事宜。 08/07：询问进出口部同事，集装箱内部高度有限，同时需要预留固定以及防撞等措施空间，所以橇块高度不要超过2.5m。整橇的话，有一种框架集装箱能放进去，但不密封，暴露在空气中，容易造成腐蚀，不建议采用。同时提醒，整橇运输也要考虑陆运高度限制。 | NO | Chaoqun hu/Shuangshuang fan
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R11] Skid assembled on site could result in CE / UKCA Responsible Person / Authorised Representative in China not being able to issue Declaration of Conformity for Skid Package. 撬块在现场组装可能导致中国境内的 CE / UKCA 负责人 / 授权代表无法为撬块整机签发符合性声明（Declaration of Conformity）。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 与CE认证方沟通确认好细节，特别是认证机构是否需要到UK现场验证，再发证。 We will communicate with the CE Notified Body to confirm all the details, in particular whether the certification body needs to attend the UK site for verification prior to issuing the certificate. 07/29：需以 3D 布置定稿版与 CE 认证机构沟通，评估现场组装后的验证方式、费用与工期。 07/29: The finalised 3D layout is required to engage the CE Notified Body and assess the post-assembly verification route, cost and duration. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R12] Wall penetrations — Layouts and cable schedules not available to confirm space is available for pipe / cable penetrations to / from R23 Module. 穿墙孔 —— 布置图和电缆清单尚未提供，无法确认与 R23 模块之间的管道 / 电缆穿墙位置有足够空间。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.6 | The initial cable schedule of CIMT is not fully aligned with the SW plan. SW has sent SLD, CIMT is verifying design discrepancies and will feed back comparison results, followed by discussions with SW CIMT初版线缆计划与SW计划没有完全匹配，SW已发出单线图，CIMT核对设计差异，返回对比结果，再与SW讨论。 7/23：CIMT根据SW提供的单线图，更新了电缆数量。部分流量控制器电缆待确认。硬联锁开关阀点位本安/隔爆待确认。 7/23：CIMT update the cable quantity based on the SLD provided by SW. some cables are still pending confirmed, 1. for flow controllers(modbus or 4-20mA). 2. for HW interlock on-off valve(I.S. or Ex d) | Pending | Dezhi meng
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R13] Catalyst charge point — Inlet pipe diameter is small and blockages may occur. 加料口 —— 加料管径较小，可能发生堵塞。 | Keith / SW response: Inlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking inlet pipe. Keith / SW 答复： 加料接口已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞加料管的风险。 | YES
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R14] Catalyst physical property requirements (size, shape, packing, etc.) are not defined, with the potential for incompatible catalyst to be charged to the reactors. 催化剂物性要求（粒径、形状、装填密度等）尚未定义，存在向反应器加入不兼容催化剂的风险。 | 07/10：催化剂直径0.5mm-5mm，形状不重要，球形，圆柱形，不规则颗粒状都可以，装填密度一般0.5g/mL来估算，但催化剂强度要高，不容易破碎起粉 07/10：The catalyst particle diameter ranges from 0.5 mm to 5 mm, with no specific shape requirement; spherical, cylindrical and irregular granular forms are all acceptable. The bulk density can be estimated at 0.5 g/mL in general. Meanwhile, the catalyst shall feature high mechanical strength to avoid fragmentation and dust generation. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R15] Packing of catalyst is not controlled, with the risk of reactants / gas channelling in the continuous reactor column, and the potential for incomplete reaction or impurities forming. 催化剂装填未受控，存在反应物 / 气体在连续反应柱内形成沟流的风险，可能导致反应不完全或杂质产生。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R16] Contained charge system design not available to assess risks and / or design limitation. 密闭加料系统的设计尚未提供，无法评估其风险与设计局限。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R17] Manual handling requirements for catalyst charging not assessed. 催化剂加料的人工搬运需求尚未评估。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R18] Access to charge point and support of charge container / bag not designed (access steps / integrated support shelf). 加料口的通道以及加料容器 / 料袋的支撑尚未设计（例如操作台阶、集成支撑架）。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R19] 20-micron catalyst retaining screen — Screen blockages prevent / limit flow of gas / reaction mix to continuous reactors. 20 微米催化剂拦截筛 —— 拦截筛堵塞会阻止 / 限制气体 / 反应液流入连续反应器。 | Keith / SW response: China Operations have reported blockages occur in local plant and screen has been removed and discarded. Keith / SW 答复： 国内运行反馈已在本地装置中发生堵塞，已将拦截筛拆除并弃用。 | YES
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R20] Polishing filter (FTR9832) — Filter blockages prevent / limit flow of gas / reaction mix through continuous reactors. Pressure increases in reactor system, with potential for undesirable reactions to occur, until reactor high-pressure trip is activated. 精滤器 (FTR9832) —— 滤芯堵塞会阻止 / 限制气体 / 反应液流经连续反应器；反应器压力升高，直到触发高压跳停前可能发生副反应。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 待定/To be determined 08/06:精滤器堵塞，加旁通，清洗时打开旁通，方便卸压 08/06: Fine filter clogged; bypass added. Open the bypass during cleaning to facilitate pressure release. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register CR01 – CR03 Reactors CR01 – CR03 反应器 | [R21] Temperature control — Jacket temperature control is configured to control jacket temperature only. Reactor internal temperatures are monitored, but no control, alarms or interlocks are configured for process control. 温度控制 —— 夹套温度仅控制夹套温度本身。反应器内部温度虽被监测，但未针对工艺过程配置控制、报警或联锁。 | Keith / SW response: Scale-up provides large operating envelopes for process temperature requirements and additional control, alarms and interlocks are not required. Keith / SW 答复： 由于放大试验提供了较大的工艺温度操作裕度，无需增加额外的控制、报警或联锁。 | YES
07/02 | SW - Risk Register System Pressure Monitoring 系统压力监测 | [R22] Differential pressure monitoring — Accuracy of static pressure measurements may not enable differential pressures to be calculated with any degree of accuracy or certainty. 差压监测 —— 静态压力测量精度可能不足以支持差压计算达到所需的精度或置信度。 | 通过反应柱上和反应器进出口管线上的的压力变送器精度估算，最大差压误差大约为40kPa。 Based on the accuracy estimation of the pressure transmitters on the reaction column and the inlet/outlet pipelines of the reactor, the maximum differential pressure error is approximately 40kPa. 07/14压力也增加了联锁。The pressure also increased the interlock. | YES | Chaoqun hu/Yu gao
07/02 | SW - Risk Register Over Pressure Protection 过压保护 | [R23] Relief system design — Pressure systems not identified and relief studies not available. Identification of worst-case relief scenario not identified, and relief streams may be incorrectly categorised. Details of maximum reaction exotherm not fully documented. 泄放系统设计 —— 压力系统尚未识别、泄放研究尚未提供。最坏工况泄放情景未识别，泄放物流可能被错误归类。反应最大放热的详细信息尚未完整记录。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：详见安全阀计算书 07/10：See safety valve calculation sheet for details. | Pending | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R24] Vessel design — Complete degassing of product stream not achieved, with the potential for hydrogen carry-over into BT04 and product transfer containers. 容器设计 —— 产品物流未实现完全脱气，H₂ 可能带入 BT04 及产品转运容器。 | 07/10：气液分离器满足气液分离的要求 07/10：The gas-liquid separator meets the requirements for gas-liquid separation. | Pending | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R25] Cleaning of separator not fully understood but current concept relies on vessel free-draining to BT04. Current spray ball sizing is not consistent with this approach and may require significant rework to process piping. 分离器清洗方案尚未完全明确，当前概念依赖容器向 BT04 的自重排放。现有喷淋球规格与该思路不匹配，可能需要对工艺管路进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.4,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register Separator 气液分离器 | [R26] Cleaning of LIT003 housing does not appear to be considered in design. LIT003 液位变送器外壳的清洗在设计中似乎尚未考虑。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.7 | 同上42行回复/Translation of the 42nd line above. | NO | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R27] P&ID does not clearly show nozzle locations and could lead to mal-ops / misunderstanding of the design intent by the Operations team. P&ID 上未清晰标注管嘴位置，可能导致运行团队误操作或误解设计意图。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.3 | 07/10：已标注，详见P&ID 07/10：Marked as indicated; refer to the P&ID for details. | Pending | Chaoqun hu
07/02 | SW - Risk Register Sampling 取样系统 | [R28] Sampler design — When depressurising the sample collection chamber, high gas or vapour vent rates could result in a bubbly or churn-turbulent flow regime, and sample will discharge to vent line as two-phase flow. 取样器设计 —— 对取样收集腔进行减压时，气体或蒸汽的高排放速率可能形成鼓泡或搅动湍流流态，样品将以两相流形式排入放空管。 Related Outstanding Questions ｜ 关联待澄清问题：Q5.1 | 07/10：缓冲罐静置一定时间，让气液分层，泄压时缓慢打开手阀 07/10：Allow the buffer tank to stand for a certain period for vapor-liquid stratification, then open the manual valve slowly during depressurization. | Pending | Chaoqun hu
07/02 | SW - Risk Register Sampling 取样系统 | [R29] With significantly more gas being present in the process stream, what will prevent overpressure of sample bottle and low-pressure nitrogen pipework? 由于工艺物流中气体明显较多，采用什么措施来防止取样瓶和低压氮气管路的超压？ | 07/10：取样瓶和氮气管线投用时，系统已泄压至常压 07/10：The system has been depressurized to atmospheric pressure prior to commissioning of sampling bottles and nitrogen pipelines. | Pending | Chaoqun hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R30] Catalyst Discharge Plug valve — Outlet pipe diameter is small and blockages may occur. 催化剂卸料闸阀 —— 出口管径较小，可能发生堵塞。 | Keith / SW response: Outlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking outlet pipe. Keith / SW 答复： 出口接管已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞出口管的风险。 | YES
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R31] Contained discharge system design not available. Layout design may not provide sufficient headroom for contained discharge system. 密闭卸料系统的设计尚未提供。当前布置可能无法为密闭卸料系统提供足够的顶部空间。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R32] Complete removal of catalyst during discharging operations is unlikely to remove 100% of the material, with the risk of cross contamination of catalyst material between campaigns. 卸料操作难以完全（100%）清除催化剂，存在批次间催化剂交叉污染的风险。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R33] CIP Design — CIP design incomplete. Initial spray ball sizing is inconsistent with process line sizing approach and may require significant rework to process piping and/or equipment layout. CIP 设计 —— 就地清洗设计不完整。初步喷淋球规格与工艺管路选型方式不匹配，可能需对工艺管路和 / 或设备布置进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.1,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R34] Cleaning carried out at nominally atmospheric pressure with the risk of material being trapped between flanges, which tend to separate slightly during high-pressure operation, and could lead to cross contamination between batches. 清洗在近常压下进行，高压运行时法兰会出现微量分开，可能将物料残留于法兰间隙中，进而导致批次间交叉污染。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. | NO | Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R35] Validation / Verification — Cleaning validation / verification philosophy not available. QA may not accept that the continuous reactor achieves minimum cleaning standards. 验证 / 确认 —— 清洗验证 / 确认策略尚未提供。质量保证部门可能不接受连续反应器满足最低清洗标准。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.2,Q1.9 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 更新清洗方案后讨论/Discuss after updating the cleaning procedure. | NO | Chaoqun hu/Xiantao Feng
07/02 | SW - Risk Register Cleaning 清洗 | [R36] Layout — Layouts are not available to evaluate the impact of bypasses, dead legs, drains, vents, etc. 布置 —— 布置图尚未提供，无法评估旁路、死管、排放、放空等的影响。 |  | NO | Shuangshuang fan/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R37] Layout — Layouts are not available to evaluate access to equipment for visual inspections, which may impact the effectiveness of critical inspections. 布置 —— 布置图尚未提供，无法评估设备的目视检查通道，可能影响关键检查的有效性。 |  | NO | Shuangshuang fan/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R38] Layout — Equipment design / layout does not allow for routine disassembly and manual cleaning. Equipment turnaround times and operating costs would be adversely impacted if CIP system cannot be validated. 布置 —— 设备设计 / 布置未考虑日常拆装和人工清洗。如 CIP 系统无法通过验证，设备周转时间和运行成本都会受到不利影响。 |  | NO | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register FT001 FT001 流量计 | [R39] Liquid Stream Flow Sensor for flow control loop FIC001. FT001 is a Coriolis mass flow meter installed downstream of the metering pump MP01. Pulsed flow from the pump will impact on the flow measurement and accurate flow control may not be possible. 液相流量传感器（用于 FIC001 流控回路）—— FT001 是安装在计量泵 MP01 下游的科里奥利质量流量计。泵的脉冲流会影响流量测量，可能无法实现精确流量控制。 | Keith / SW response: China Team have previously used this configuration and not experienced flow control issues. No further action required. Keith / SW 答复： 国内团队此前采用过该配置，未出现流控问题。无需进一步动作。 | YES
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R40] Maximum flow may exceed separator design limitations and carry hydrogen over into BT04 / product collection containers. 泵的最大流量可能超出分离器的设计上限，将 H₂ 带入 BT04 / 产品收集容器。 | 07/10：分离器的直径足够大，泵为最大流量时能满足分离要求 07/10：The separator has a sufficiently large diameter to meet separation requirements even when the pump operates at maximum flow rate. | Pending | Chaoqun hu
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R41] Pump turndown does not meet URS minimum flow requirements. 泵的调节比无法满足 URS 中规定的最低流量要求。 | 07/10：机泵条件中规定了泵的最小流量要求，待泵厂家返回资料时审查是否满足最低流量要求 07/10：Minimum flow requirements for pumps are specified in pump data sheets. Compliance with the minimum flow criteria shall be verified upon receipt of vendor documentation. 08/05：根据最新机泵数据单走采购流程询问厂家资料 | NO | Chaoqun hu
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R42] Hydrogen gas flow controller — Flow controller does not support tight shut-off and system pressure increase during hold periods. 氢气流量控制器 —— 控制器不支持严密关断，系统在保压期间压力会持续上升。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller to provide tight shut-off. Keith / SW 答复： 在控制器下游追加一台切断阀以提供严密关断。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R43] Maximum flow through controller may exceed separator design limitations and carry liquid into the vent line. 流经控制器的最大流量可能超出分离器设计上限，将液体带入放空管。 | Keith / SW response: High level interlock installed in the separator to stop gas supply and close PIC028 shut-off valve (CV08). Keith / SW 答复： 在分离器上设置高液位联锁，停 H₂ 供给并关闭 PIC028 的切断阀（CV08）。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R44] Time required for pressure testing the system and nitrogen inertion may be excessively high. 系统加压试验及氮气钝化所需时间可能过长。 | Keith / SW response: Pressure test / inertion times to be evaluated during FIC003 selection. Manual vent installed on BT03 to reduce depressurisation times via FIC003. Keith / SW 答复： 在 FIC003 选型时评估压力试验 / 惰化时间。在 BT03 上加装人工放空阀，缩短经 FIC003 的减压时间。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R45] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端的差压超出厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register LIC003 LIC003 分离器液位 | [R46] SE01 Separator Level Indicator — Cleaning / decontamination of housing is not possible. Residual product in housing could lead to cross contamination between campaigns. SE01 分离器液位指示 —— 变送器外壳无法进行清洗 / 净化。外壳内的残留物料可能导致批次间交叉污染。 | Keith / SW response: Design relies on dissolution of residual material. 100% flood-fill of housing is not possible, therefore any residual trace contamination in the housing is deemed to be small and will not significantly impact cleaning verification. Keith / SW 答复： 设计依赖残余物料的溶解。外壳无法 100% 灌满，因此外壳内任何残余痕量污染被视为很小，不会显著影响清洗验证。 | YES
07/02 | SW - Risk Register FIC004 FIC004 分离器液位控制 | [R47] Separator outlet flow / level control — Differential pressure across the controller exceeds manufacturer's recommendations and controller capability. 分离器出口流量 / 液位控制 —— 控制器两端差压超出厂家建议范围及控制器能力。 | 分离器出口先通过减压阀减到0.2MpaG左右，可以满足厂家建议的差压范围 The outlet of the separator is first reduced to approximately 0.2MpaG through a pressure reducing valve, which can meet the differential pressure range recommended by the manufacturer | Pending | Chaoqun hu/Yu gao
07/02 | SW - Risk Register FIC005 FIC005 BT01 氮气吹扫 | [R48] BT01 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT01 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register FIC007 FIC007 BT04 氮气吹扫 | [R49] BT04 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R50] System back pressure controller — The back pressure controller does not support tight shut-off during hold periods and system pressure will not be maintained. 系统背压控制器 —— 该控制器在保压期间不支持严密关断，系统压力无法保持。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller. Keith / SW 答复： 在该控制器下游追加一台切断阀。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R51] Time required for depressurising the system following pressure testing and nitrogen inertion may be excessively high. 加压试验和氮气钝化之后系统减压所需时间可能过长。 | Keith / SW response: Manual bypass installed around PIC028 controller. Keith / SW 答复： 在 PIC028 控制器周围加装人工旁路。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R52] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端差压超出厂家建议范围，可能导致控制器无法正常工作。 | 07/10：关于背压阀028，之前Bronkhorst的电子压力阀厂家计算反馈的阀前背压范围最大为0.9~6MpaG，范围量程比不能过大。 07/10：About the back pressure valve 028, previously, the manufacturer of Bronkhorst’s electronic pressure valve calculated and reported that the maximum range of the back pressure before the valve was 0.9 to 6MpaG, and the range-to-range ratio cannot be too large. 08/05:会后核实 | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register PIC030 PIC030 分离器液相出口减压 | [R53] Separator liquid outlet pressure reducer — Is this confirmed as a Bronkhorst pressure controller, or is a mechanical regulator still an option? Does this provide the required independence assumed in the relevant SIL / risk assessments? 分离器液相出口减压器 —— 该阀是否确认为 Bronkhorst 电子压力控制器？还是仍可能选用机械式减压阀？该配置能否提供相关 SIL / 风险评估中假设所需的独立性？ | 目前选型机械式减压阀。机械阀不是电子设备，没有相关的SIL认证。 At present, mechanical pressure reducing valves are being selected. Mechanical valves are not electronic devices and do not have the relevant SIL certification. | Pending | Chaoqun hu/Yu gao
07/02 | SW - Risk Register PIC049 PIC049 BT04 背压控制 | [R54] BT04 back pressure controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 背压控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register Automation 自动化 | [R55] Automation Build — Philosophy and Design documentation not available to assess risks and limitations. 自动化建设 —— 自动化策略与设计文档尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q3.1,Q3.2 | 8/21：控制说明已提供。专题沟通后确定反馈 | NO | Chaoqun hu/Dezhi meng/Ziliang zhao
07/02 | SW - Risk Register Documentation 文档 | [R56] Technical File — Technical File not available to assess risks and limitations. 技术文件 —— 技术文件尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.5,Q7.1 |  | NO | Shaofeng gao/All
07/02 | SW - Risk Register Documentation 文档 | [R57] O&M Manual — O&M manual not available to assess risks and limitations. 操作维护手册 —— O&M 手册尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q7.1 | 07/10：操作手册的编制还在进行中 07/10：Preparation of the operation manual is still in progress. 07/29：操作维护手册预计 8 月中完成。 07/29: The O&M manual is scheduled for completion in mid-August. | NO | Chaoqun hu
07/02 | SW - Risk Register Documentation 文档 | [R58] Emissions Calculations — Calculations to demonstrate expected release of Class A and Class B VOCs to atmosphere are not available. These are required to demonstrate compliance with EA Permit limits. 排放量计算 —— 尚未提供证明 A 类和 B 类 VOC 向大气排放的预期计算。该计算是证明满足 EA 许可（英国环境署许可）限值要求所必需。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW负责排放量计算/SW is responsible for emissions calculation. | YES | Chaoqun hu
07/02 | SW - Risk Register Regulatory Compliance 法规合规 | [R59] CE ¦ Functional Safety ¦ DSEAR / ATEX ¦ PSSR ¦ COSHH ¦ PUWER (Access, manual handling) ¦ Working at Height (Access Steps / Support Shelf) ¦ LOLER (Davit arms) ¦ Lighting ¦ Occupational Hygiene ¦ EA Permit — Regulatory non-conformance would prevent beneficial use of equipment in the UK. CE 认证 ¦ 功能安全 ¦ DSEAR / ATEX 防爆 ¦ PSSR 压力系统安全 ¦ COSHH 危害物质 ¦ PUWER 工作设备（含通道与人工搬运）¦ 高处作业（操作台阶 / 支撑架）¦ LOLER 起重设备（吊臂）¦ 照明 ¦ 职业卫生 ¦ EA 环境许可 —— 任何法规合规缺失都会导致设备无法在英国正常投入使用。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW内部的提醒事项。 CFCT核实加料步梯是否包含在内。 SW提供步梯平台尺寸(09/07暂未提供)。 Internal reminders for SW: CFCT to verify whether the feeding staircase is included. SW to provide dimensions of staircase and platform. | NO | Zilang zhao/All
07/14 |  | 根据生产经验，研发建议原R24-CR01的直径由DN80改为DN50，导致产能下降，可能无法满足URS中的产能30kg/day Based on production experience, the R&D team proposes reducing the diameter of the original R24-CR01 from DN80 to DN50. This modification will result in lower production capacity, which may fail to meet the 30 kg/day throughput specified in the URS. | 07/14：周三会上确定/To be confirmed at Wednesday's meeting. 07/15：暂定R24-CR01的直径修改为DN65，等9月份研发提供DN65的反应器实验数据后最终确认反应器的尺寸为DN65或DN50 07/15：It is tentatively agreed to revise the diameter of R24-CR01 to DN65. The reactor size (either DN65 or DN50) will be finalized after the R&D department provides DN65 reactor test data in September. 07/29：会上确定按 DN65 / DN50 两套方案并行准备，并建立变更影响日志；待 9 月研发 DN65 实验数据后最终定案。 07/29: Agreed to prepare the DN65 and DN50 cases in parallel and to set up a change-impact log; final decision after the September DN65 R&D test data. | NO | Xiantao Feng/All
07/23 | SW | 气液分离器SE01容器承受从常压到60 barg的压力循环次数？ How many pressure cycles does the gas-liquid separator SE01 vessel undergo from atmospheric pressure to 60 barg? | 07/23:会上讨论了加氢装置的操作周期，意见存在不一致，关于连续加氢的年运行周期，SW内部沟通后反馈循环次数需求。 气液分离器的设计温度调整到270℃，对应设计压力调整到7.5MPaG。垫片选用金属环垫片。 07/23：The operating cycle of the hydrogenation unit was discussed at the meeting, and divergent opinions remain. SW shall coordinate internally and provide feedback on the required number of cycles regarding the annual operating cycle for continuous hydrogenation. The design temperature of the gas-liquid separator shall be revised to 270°C, with the corresponding design pressure adjusted to 7.5 MPaG. Metallic ring gaskets shall be adopted . 08/06：垫片材质？原料酸性 PEEK，再寻找合适的垫片，讨论。 09/07：管法兰与金属环垫片均可选316L，但需要做技术要求：①金属环垫片硬度≤150HB，管法兰硬度≥160HB；②以上材料需有硬度检测报告；③到厂后复验；④组装前按硬度差≥10HB配对使用。 09/07：Both the pipe flanges and the metal ring gaskets may be made of 316L. However, the following technical requirements shall be complied with: ①The hardness of the metal ring gasket shall be ≤ 150 HB, and the hardness of the pipe flange shall be ≥ 160 HB. ②Hardness test reports shall be provided for all the above materials. ③The materials shall be re-inspected upon arrival at site. ④Prior to assembly, the flange and gasket shall be paired based on a hardness difference of ≥ 10 HB (i.e., the flange hardness shall be at least 10 HB higher than that of the gasket). | NO | Zilang zhao/Chaoqun hu
07/23 | IEPE | P&ID中压力表无根部阀，是否需要增加根部阀？ Pressure gauges shown on the P&ID are not equipped with root valves. Is it necessary to add root valves? | 07/23:按照现有P&ID配置。 07/23：Configure in accordance with the existing P&ID. | NO | Chaoqun hu/Yu gao
07/23 | IEPE | PCV028侯径小，反应系统卸压时，全开PCV028卸压速度也很慢，建议将PCV028的旁通手阀改为开关阀 PCV028 has a small orifice. When depressurizing the reaction system, the depressurization rate remains low even if PCV028 is fully open. It is recommended to change the bypass manual valve of PCV028 to an on-off valve. | 07/23:按照现有P&ID配置。 07/23：Configure in accordance with the existing P&ID. | NO | Chaoqun hu
07/29 | SW | 针对 R24-CR01 直径变更（DN80→DN65/DN50），建立变更影响日志/清单，逐项列出受影响的设备、仪表、管线、安全阀及相关文件与参数，确保无遗漏。 Establish a change log / impact list for the R24-CR01 diameter change (DN80→DN65/DN50), itemising every affected item of equipment, instrumentation, piping, relief device and the related documents and parameters, so that nothing is missed. | 07/29：会上同意建立变更影响日志，由国内团队逐项梳理受影响范围并跟踪关闭。 07/29: Agreed at the meeting to create a change-impact log; the China team will work through the affected scope item by item and track it to closure. | NO | Shaofeng Gao/Chaoqun Hu
07/29 | SW | 反应器 DN65 与 DN50 两种规格并行准备设计方案：先确定处理量，再分别出 PFD 与物料平衡；并核实仪表选型、安全阀/泄放组合是否需相应调整。待 9 月研发提供 DN65 实验数据后定案。 Prepare two parallel design cases for the DN65 and DN50 reactor: fix the throughput first, then issue a PFD and mass balance for each, and verify whether instrument selection and the relief-valve combination need to change accordingly. To be finalised once R&D provides the DN65 test data in September. | 07/29：会上确定按 DN65 / DN50 两套方案并行准备，使 9 月数据到位后可直接定案，不影响整体进度。 07/29: Agreed to progress both the DN65 and DN50 cases in parallel so that the decision can be taken as soon as the September data is available, without affecting the overall schedule. | NO | Shaofeng Gao/Chaoqun Hu/Xiantao Feng
07/29 | IEPE | 容器设计压力由 80 barg 调整为 75 barg，以保持法兰等级 CLASS 900、避免材料选型受限；需在设备数据表、图纸及相关计算书中同步更新落实。 Vessel design pressure revised from 80 barg to 75 barg in order to retain the CLASS 900 flange rating and avoid limitations on material selection; to be updated consistently in the equipment datasheets, drawings and supporting calculations. | 07/29：周二与 Keith 讨论已取得初步一致，继续推进并在各设计文件中落实。 07/29: Initial agreement reached with Keith on Tuesday; to be carried forward and reflected in the design documents. | NO | Chaoqun Hu/Ziliang Zhao
07/29 | SW | 四撬块分体运输 vs 屋顶整体吊装的决策路径：国内先完成 3D 布置定稿，再以定稿版与 CE 认证机构评估现场组装后的验证方式、费用与工期；Keith 下周四返回后确认四撬块方案可行性；SW 侧评估屋顶更换的费用、工期及 R23 停用影响。 Decision path for four-module split shipment vs a whole-unit lift through the roof: the China team to finalise the 3D layout first, then use the finalised version to evaluate with the CE Notified Body the post-assembly verification route, cost and duration; confirm the four-module option with Keith after he returns next Thursday; SW to assess the roof-replacement cost, duration and the impact of taking R23 out of service. | 07/29：会上提议需要澄清四撬块方案技术上可行，屋顶吊装并非必选项；认证机构评估需以 3D 定稿为前提，国内加快 3D 定稿以尽早取得费用与工期结论。 07/29: Clarified at the meeting that the four-module option is technically feasible and roof removal is not mandatory. The Notified Body assessment depends on the finalised 3D layout, so the China team will accelerate finalisation to obtain the cost and schedule answer as early as possible. | NO | Ziliang Zhao/Shaofeng Gao/Keith
07/29 | SW | 明确下阶段（建造 / FAT）文件的编制与签发流程：由谁编制、由谁签发；SW 场地有自有的 FAT / 验证模板。CE 认证方参与文件评审但不参与签发。约定后续安排专题讨论。 Define the preparation and sign-off process for the next-stage (construction / FAT) documentation — who prepares and who signs off. The SW site has its own FAT / validation template. The CE Notified Body will take part in document review but not in sign-off. A dedicated follow-up discussion to be arranged. | 07/29：双方同意尽早对比两侧模板并识别差异；倾向直接采用 UK 模板以便英国侧验证与确认，国内按该模板提供资料，避免后期返工。 07/29: Both sides agreed to compare the two templates early and identify any gaps; the preference is to adopt the UK template so that verification and validation on the UK side is straightforward, with the China team supplying information to that template to avoid rework later. | NO | Shaofeng Gao/Ziliang Zhao
07/29 | IEPE | 请 SW / Keith 提供英国现场验证（validation）所需的信息清单与模板，国内据此提供资料并按该模板执行，以便尽早识别中英双方要求差异。 SW / Keith to provide the list of information required for the UK site verification / validation process, together with the template, so that the China team can supply the information and work to that template and any differences between the UK and China requirements are identified early. | 07/29：会上确定由 SW 提供模板与信息需求清单，国内提供文件 / 信息并按模板填写；下周与 Keith 沟通落实。 07/29: Agreed that SW will provide the template and the information requirement list; the China team will supply the documents / information and complete them to that template. To be taken forward with Keith next week. | NO | Keith/Shaofeng Gao
07/29 | SW | HAZOP 前须与 Keith 就 3D 布置与控制说明（含操作手册）达成一致 —— 该两项目前仅国内内部讨论过，是余下唯二可能引发重大设计变更的环节，须在 HAZOP 前关闭，以确保 HAZOP 只做一次、避免重做。 The 3D layout and the control philosophy (including the operating manual) must be agreed with Keith before HAZOP. These two items have so far only been reviewed internally by the China team and are the only remaining items that could still trigger a significant design change; they must be closed out beforehand so that HAZOP is run once only and does not have to be repeated. | 07/29：会上确认目标为「HAZOP 只做一次」；两项在 9 月初 HAZOP 前与 Keith 讨论定稿。 07/29: The meeting confirmed the objective of running HAZOP only once; both items to be discussed and finalised with Keith ahead of the early September HAZOP. | NO | All
08/25 | IEPE | 反应柱 R24-CR01 直径变更（DN80→DN65/DN50），产能改变，进料量可能会调整，是否需要修改PFD？ The diameter of the reaction column R24-CR01 has been changed (from DN80 to DN65/DN50), resulting in a change in production capacity. The feed volume may need to be adjusted. Is it necessary to modify the PFD? | 08/25：反应柱 R24-CR01 直径变更（DN80→DN65/DN50），跟研发和Keith沟通后确认：流速不变工况下后续反应器可承担部分转化率，故产能不一定改变，PFD不做调整；对应的TCU功率匹配事宜可通过调整出口温度实现，方案由SW自行调整。 08/25: Diameter of reaction column R24-CR01 was changed (from DN80 to DN65/DN50). After communicating with R&D and Keith, it was confirmed that under the condition of unchanged flow rate, the subsequent reactor can handle a portion of the conversion rate. Therefore, the production capacity is not necessarily changed, and the PFD will not be adjusted. The power matching of the corresponding TCU can be achieved by adjusting the outlet temperature. The plan will be adjusted by SW on its own. | Yes | Keith/Xiantao Feng
08/25 | SW | CFCT向SW提供R24-BT03的尺寸和3D模型，方便Keith优化3D方案 CFCT provides SW with the dimensions and 3D model of R24-BT03 to facilitate Keith's optimization of the 3D design. | 08/25：会后提供R24-BT03的尺寸和3D模型 08/25: Dimensions and 3D model of R24-BT03 will be provided after the meeting. | Yes | Shuangshuang Fan

## 0730
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. 05/12：Keith建议用气液两相计算安全阀尺寸，不提供模板 05/12：Keith suggests using gas-liquid two-phase calculations for determining the size of the safety valve, but no template is provided. 05/20：根据API520的气液两相泄放时计算安全阀尺寸，部分已完成 05/20：Calculate the size of the safety valve based on the API520 standard for the two-phase gas-liquid discharge situation.Partially completed. 06/02：安全阀计算初版已完成（包含临界流体和气液两相），校审中。 06/02：Preliminary calculation of safety relief valve (covering critical fluid & gas-liquid two-phase flow) completed, under review. 06/09: General 1. What was the source/reference for the Specific Volumes stated in column D/D 列中比容数据的来源及参考依据是什么？ The Specific Volumes stated in column D are derived from Aspen Plus simulation results.比容数据来自Aspen模拟 2. There is no backpressure considered in the calculation. The emergency vent relief will create some backpressure which needs to be considered in the calculation./本次计算未考虑背压。紧急放空泄放过程会产生一定背压，该因素需纳入计算。 Backpressure consists of static backpressure and built-up backpressure. Given the wide total pressure range, backpressure effects shall be incorporated into the calculation.背压分为静背压和积聚背压，总压力范围大，将背压包含在其中 3. At the assumed relief pressure Ethyl Acetate will be a supercritical fluid, therefore the required relief mass flowrate will not be dependent on the latent heat of vapourisation, and the calculated ‘required discharge area’ will not be valid. Do you agree with this statement, or have you found a reference in the standard that allows for this? 在设定的泄放压力下，乙酸乙酯将处于超临界流体状态，因此所需泄放质量流量不再依赖汽化潜热，本次算出的所需泄放流通面积也不再适用。你是否认同该观点？或是你是否在相关标准中查到可支持该计算的依据？ 详见06/16回复. Please refer to the reply dated 06/16 for details. Cooling Failure Calculations 4. For the cooling failure calculation, I would suggest using 550kJ/mol rather than 501.48. This is based on Sandwich PSL experience of heats of reaction. 针对冷却失效工况计算，建议将反应热取值由 501.48 kJ/mol 改为 550 kJ/mol。该取值参考了桑威奇工艺安全实验室（Sandwich PSL）过往反应热项目经验。 OK 5. Is the feed flowrate used in the calculation, based on the maximum metering pump capabilities? Do you assume a maximum concentration of reactant in the feed stream? 计算中采用的进料流量，是否按照计量泵最大额定流量取值？计算时是否假定进料流中反应物浓度为最大浓度？ The flow rate used in the calculation is set at the maximum rated capacity of the metering pump, and the maximum reactant concentration is adopted for the feed stream.计算时流量是按照计量泵最大额定流量取值，反应物浓度为最大浓度 06/16：根据文献“Relief Calculation for Supercritical Fluids”计算超临界流体的质量泄放流量，会后向Keith发计算书审核 06/16：Calculate the mass relief flow rate of supercritical fluids in accordance with the document Relief Calculation for Supercritical Fluids, and send the calculation sheet to Keith for review after the meeting. | YES | Chaoqun Hu
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun HU
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. 06/16：06/11已收到审核完成的URS。 06/16：Received the reviewed URS on 06/11. | YES | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith确认CV08也是故障关，可以使用DS6080型，该型号没有5 bar 差压限制。 Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith confirmed that CV08 is also a faulty-close type, the DS6080 model can be used. This model does not have a 5-bar differential pressure limit. Keith offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. 06/02 进展：Habonim厂家反馈了样本资料，反馈可以满足工艺参数需求，货期大概16~20周。可以作为开关阀的备选品牌。 06/02 Progress: "Habonim" manufacturer has provided sample materials that can meet the process parameter requirements. The delivery time is approximately 16 to 20 weeks. It can be an alternative brand for on-off valves. | YES | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. 06/02：关于气液分离器液相出口减压，电子压力阀和自力式减压阀都可以满足使用，首选自力式减压阀。 06/02：For pressure reduction at the liquid outlet of the gas-liquid separator，both electronic pressure valves and self-operated pressure reducing valves can meet the requirements, with self-operated pressure reducing valves being the preferred choice. | YES | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. 05/20：SW已更新完URS并发出。The SW has been updated and the URS has been sent out. | YES | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表数据单。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. 06/23:仪表条件表已更新完成 06/23：The instrument conditions table has been updated and completed. 07/10：仪表数据单已更新完成 07/10：Instrument Data Sheet has been fully updated. | YES | Chaoqun Hu/Yu Gao
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. 05/20：SW已更新完PFD并发出。The SW has been updated and the PFD has been sent out. | YES | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ 4/30：Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? | NO | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted?05/12Decided not to make any adjustments. 05/12确定不做调整。 05/12：It is determined that the height of the catalyst bed in the main reactor will not be adjusted. | YES | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. 06/16：会议澄清：待布局完成后，SW主导完成爆炸危险区域的划分 09/06：Meeting Clarification: SW shall take the lead in completing the classification of hazardous areas for explosion after layout design is finalized. | NO | All
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | YES | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements. | 05/20：与聂博沟通，小试使用的是进口是插底的分离器，生产使用的是侧进的分离器，按会议沟通的气体最大流量0.2Nm³/h，液体最大流量20L/h重新计算了分离器 05/20: Communicated with Nie Bo. The small-scale test used an imported bottom-insertion separator, while the production version used a side-inlet separator. Based on the maximum gas flow rate of 0.2 Nm³/h and the maximum liquid flow rate of 20 L/h for the communication at the meeting, the separator was recalculated.. | YES | Chaoqun Hu
06/02 | IEPE | 管道编号中的管线尺寸一般是指的公称直径，PID中尺寸为10mm的管道是Φ10mm，公称直径为6mm The line size in pipe line designations generally refers to the nominal diameter. In a P&ID, a pipe with a size of 10mm is specified as Φ10mm, corresponding to a nominal diameter of 6mm. | 06/02：会议澄清：DN15以下的管道，管道编号中的管径为外径，DN15及其以上的管道，管道编号中的管径为公称直径。 06/02：Clarification from meeting:For piping below DN15, the size specified in pipe tag number denotes outer diameter; for DN15 and above, the size in pipe tag refers to nominal diameter. | YES | Chaoqun Hu
06/02 | IEPE | 设备BT-01/03/04上的压力变送器不便于现场观察，是否可以考虑也选用WIKA的不带现场显示紧凑型的压力变送器？ The pressure transmitter on the equipment BT-01/03/04 is not convenient for on-site observation. Could it be considered to also choose WIKA's compact pressure transmitter without on-site display？ | 06/02：会上建议保留BT-01/04的现场显示，BT-03可不带现场显示。 06/02：It was suggested at the meeting that the on-site display of BT-01/04 be retained, while BT-03 may not have an on-site display. | YES | Yu Gao
06/02 | CFCT | 1-PID中V-9868，V-9965阀柄的含义？ What is the meaning of valve handles V-9868 and V-9965 in PID? 2-PID中压力变送器底部波纹含义是什么？ What does the corrugation at the bottom of the pressure transmitter signify? 3-与管道直径对应的保温厚度是多少？ What is the insulation thickness corresponding to the diameter of the pipeline? | 06/02： 1.PID中阀门V-9868，V-9965的阀柄为弹簧复位阀柄； In the PID,the valve handles of V-9868 and V-9965 are spring-reset handles； 2.PID中带底部波纹的压力变送器要求压力变送器带隔膜； The pressure transmitter with a bottom ripple in PID requires the pressure transmitter to be equipped with a diaphragm； 3.Keith分享了建议的管道直径与保温厚度表格，直径10到25mm的管路，保温厚度为30-35mm。 Keith shared the recommended pipe diameter and insulation thickness table, with insulation thickness ranging from 30-35mm for pipes with diameters of 10 to 25mm. | YES | ShuangshuangFan
06/16 | SW | 会议确认：气液分离器为侧进，尺寸为DN200*600mm，下次例会前CFCT向SW提供气液分离器的设备图纸 Confirmed at the meeting: The gas-liquid separator adopts side inlet configuration with dimensions DN200 × 600 mm. CFCT shall submit the equipment drawing of the gas-liquid separator to SW prior to the next regular meeting. | 06/22设备图纸已提供。06/23Keith回复意见，见06/23讨论内容。 Equipment drawings were provided on 06/22. Keith's feedback was received on 06/23 — please refer to the discussion notes from 06/23. | YES | Ziliang Zhao
06/17 | SW | 根据最新工作进展并结合HAZOP分析所需文件内容，更新“Sandwich Hydrogenation Implementation Schedule” Update the Sandwich Hydrogenation Implementation Schedule based on the latest progress and document requirements for HAZOP study. |  | NO | All
06/17 | SW | 讨论操作规程：哪些部分需要顺控？开停车步骤等 Discuss operation procedures: identify sections requiring sequence control, including startup and shutdown steps, etc. | 06/23：开车步骤：公用工程确认/催化剂装填→氮气置换（R24-BT01、R24-BT04和剩余部分），氧含量<0.5vol%→氢气置换→原料系统备料→TCU系统调温→反应器进料（氢气先进料背压至反应压力，液相再进料）→气液分离→产品转移 停车步骤：停进料→产品缓冲罐物料转移→反应器卸压→R24-BT03卸压→反应系统降温→氮气置换→关闭氮气和TCU Startup Procedures： 1.Verification of utility systems & catalyst loading 2.Nitrogen purging (for R24-BT01, R24-BT04 and the rest of the system), oxygen content controlled below 0.5 vol% 3.Hydrogen purging 4.Raw material preparation for feed system 5.Temperature adjustment of TCU system 6.Reactor feeding: Introduce hydrogen first to build backpressure up to reaction pressure, then feed liquid phase material 7.Gas-liquid separation 8.Product transfer Shutdown Procedures： 1.Cut off feed supply 2.Transfer materials from product buffer tank 3.Depressurize reactor 4.Depressurize R24-BT03 5.Cool down reaction system 6.Nitrogen purging 7.Shut down nitrogen supply and TCU system Keith提供HAZOP时的开停车步骤，结合上述文件，整理开停车和清洗步骤 Compile the plant start-up, shutdown and cleaning procedures based on the above documents together with the start-up & shutdown sequences supplied by Keith for HAZOP assessment. | NO | All
06/17 | SW | 会后确认：安全阀的泄放温度超过设备的设计温度，是否需要提高设备的设计温度？ To be confirmed after the meeting：If the relief temperature of the safety valve exceeds its design temperature, is it necessary to increase the design temperature rating? | 设备和管线材质为316L，结合设备和管道的壁厚，计算得出：在泄放温度下，材料的许用应力满足其强度要求，不需提高设备的设计温度 The equipment and piping are fabricated from 316L stainless steel. Wall thickness calculations for the equipment and piping demonstrate that the allowable stress of the material satisfies the strength requirements at relief temperature; therefore, no increase to the equipment design temperature is required. | Yes | Ziliang Zhao/Chaoqun Hu
06/17 | SW | CFCT做撬块设计时，注意清洗过程中的低点排净 CFCT shall take full consideration of low-point draining during cleaning when designing the skid package. | 06/23：在撬块设计时，设置管道的低点排净阀 When designing the layout, install a drain valve at the low point of the pipeline 06/23会议方案：管道最低点设置排净阀，操作说明中明确排放时用容器收集排放液体。 Meeting Plant: Install drain valves at the lowest point of the pipeline, and specify in the operating instructions to collect the discharged liquid with a container during the drainage process. | Yes | Shuangshuang Fan
06/17 | SW | CFCT提供放空缓冲罐T06是否放在撬内的方案 CFCT to provide a scheme on whether vent buffer tank T06 shall be installed inside the skid. | 06/23：按照现有空间的布置，T06放在撬块内的空间不足；撬块中间的操作维护通道宽度为300-350mm，能否将整体撬块宽度增加150-200mm？ According to the existing space arrangement, there is insufficient space for T06 to be placed inside the pry block; The width of the operation and maintenance channel in the middle of the pry block is 300-350mm. Can the overall pry block width be increased by 150-200mm? 06/23会议方案：T06不放在撬块内，放置在service area，同时反应柱/冷凝器的TCU出口管路上的温度变送器安装在近出口处，去掉手动球阀，安全阀可放到service area，并设置排净阀，进口管路手动球阀保持不变，温度变送器加套管，位置可前可后，低点设置排净阀，整体管路的高点设置排气阀。 Meeting Plant:: T06 is not placed inside the lever block but in the service area. The temperature transmitter on the TCU outlet pipeline of the reaction column/condenser is installed near the outlet. The manual ball valve is removed, and the safety valve can be placed in the service area. A drain valve is installed, while the manual ball valve on the inlet pipeline remains unchanged. The temperature transmitter is equipped with a protective sleeve, with its position adjustable forward or backward. A drain valve is set at the low point, and an air vent valve is installed at the high point of the entire pipeline. | Yes | Shuangshuang Fan
06/23 | SW | Keith意见： 基本设计：我们是否有经批准的分离器设计方案？我上次看到的摘录中，计算出的容器直径为3毫米，这表明计算或输入数据可能存在错误。 Basic design 1. Do we have an approved design for the separator. The last extract I saw had a calculated vessel diameter of 3mm, which suggests an error in the calculations or input data. | 06/23讨论： 基本设计：按最新设备数据表进行气液分离器设计。气液分离器的计算书已复核过，数据无误。 06/23Discussion—Basic Design: The gas-liquid separator shall be designed in accordance with the latest equipment data sheet. The calculation sheet for the gas-liquid separator has been reviewed and the data are confirmed to be correct. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 分离器内件 1、本设计中是否已考虑分离器内件，例如入口导流装置或入口旋风分离器、气相除雾器、液体出口处的防涡流挡板？ 2、喷淋球能否采用焊接固定方式，而非通过管接头引入容器内部？ 3、喷淋球是否必须为旋转式喷淋球？这会增加设备复杂度，并在工厂运行寿命期内带来检查与维护方面的问题。 4、喷淋球实际能否起到喷淋清洗作用，还是仅仅将容器注满清洗液直至触发高位液位开关？根据此前讨论，从空罐到高位跳闸点的时间不足25秒，这无法为分离器气相侧提供足够的机械清洗作用时间。 Separator internals 1. Have separator internals been considered for this design e.g. inlet diverters or inlet cyclones, demisting of the vapour stream, vortex breakers on the liquid outlet. 2. Can the spray ball be welded in position rather than introducing a tube fitting into the vessel. 3. Does the spray ball need to be a rotary spray ball. This adds complexity and inspection/maintenance issues during the life of the plant. 4. Will the spray ball actually work as a spray ball, or will it simply fill the vessel with cleaning fluid until the high-level switch is activated. Based on previous discussions this would be less than 25 seconds from empty to high-level trip point, which doesn’t allow much time for mechanical cleaning action in the gas side of the separator. | 06/23讨论： 分离器内件： 1、气液分离器设计采用重力式分离，无需额外的内件。 2、喷淋球相关事宜，CN团队内部结合喷淋球供应商商议方案。 06/23 Discussion — Separator Internals: 1.The gas-liquid separator is designed as a gravity-type separator; no additional internals are required. 2.Regarding the spray ball matters, the CN team will internally discuss and determine the solution in coordination with the spray ball supplier. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 设计参数 1、“流体性能”是否应定为“非致命性”？我推测此概念类似于PED容器设计中的流体分组，在英国规范中应属于Group 1气体（即可燃/爆炸/有毒），而非“非致命性”。 2、工作压力应为0至6MPaG。 3、设计温度应至少为150°C，并且我假设在泄压事故工况下，容器温度可能达到约300°C。 4、设计压力应为全真空至9MPaG。 5、规范是否要求进行焊后热处理（PWHT）？ 6、水压试验压力应为设计压力的1.5倍，即13.5MPaG，而非12MPaG。 7、对于该容器，S4应为DN32 Cl900 WN法兰。喷淋球接口是否应作为单独细节在本图纸上表示，还是另页图纸表示更为合适？ 8、充装系数（Fulling Factor）是多少？ Design Parameters 1. Should the ‘Fluid Performance’ be Non-Lethal? I assume this is similar to the fluid group for PED vessel design, which for the UK would be Group 1 gas i.e. flammable/explosive/toxic and not Non-Lethal. 2. The working pressure should be 0 to 6MPaG. 3. The design temperature should be at least 150 °C and I assume the vessel has the potential to reach circa 300°C during a relief event. 4. The design pressure should be FV to 9MPaG 5. Is PWHT required by the code. 6. Hydro test pressure should be 1.5x design pressure i.e. 13.5MPaG not 12 MPaG. 7. For the vessel, S4 should be a DN32 Cl900 WN Flange. Should the spray ball fitting be shown as a separate detail on this drawing or possibly shown on a separate drawing. 8. What is the Fulling Factor. | 06/23讨论： 设计参数 ： 1、介质调整为易爆。 2、CN团队结合URS，修正工作压力，更新设备数据表。 3、可以将泄压事故工况，纳入到常规设计考虑中，即可提高设计温度到300℃。 4、修正设计压力，更新设备数据表。 5、规范可不进行焊后热处理（PWHT）。 6、水压试验压力为设计压力的1.3倍，故试验压力可不做调整。 7、S4为喷淋口，口径为Φ10，DN32法兰接口结构为保证喷淋球可抽出，后续根据喷淋球整体方案做调整，判定是否需要可抽式。 8、充装系数是指物料实际容积与容器全容积之比。 06/23 Discussion — Design Parameters: 1.The medium classification is revised to "explosive." 2.The CN team will revise the working pressure based on the URS and update the equipment data sheet accordingly. 3.The relief event scenario can be incorporated into the normal design considerations — i.e., the design temperature can be raised to 300°C. 4.The design pressure will be revised and the equipment data sheet updated accordingly. 5.PWHT (post-weld heat treatment) is not required per the applicable code. 6.The hydrostatic test pressure is 1.3 × design pressure, so the test pressure does not need to be adjusted. 7.S4 is the spray ball connection, with a bore size of Φ10. The DN32 flange connection is designed to allow the spray ball to be withdrawable. This will be reviewed and adjusted as part of the overall spray ball solution, and a decision will be made on whether a withdrawable type is necessary. 8.The filling factor is defined as the ratio of the actual liquid volume to the total vessel volume. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 通用事项 1、管口方位是否已考虑设备布置的最优化？ 2、在撬装高度限制范围内，容器能否通过重力自由排液至产品收集罐？ 3、在顶部法兰上开孔用于引出管，是否会损害其机械完整性并违反安全规范？是否已重新计算法兰厚度或进行有限元分析（FEA），以确保足够的金属厚度和结构完整性？ 4、液位变送器/液位开关的规格是否已确认？法兰尺寸及位置是否与仪表相匹配？ 5、请更新P&ID，以显示S4正确的管口尺寸。 6、是否有容器设计计算书？技术文件中需要包含设计计算书，并应在FAT（工厂验收测试）时进行核查。 General 1. Does the nozzle orientation allow for optimum equipment layout. 2. Can the vessel free drain into the product collection tank, within the skid height constraints. 3. Does boring a hole in the top flange for the outlet pipe compromise its mechanical integrity and violate safety codes. Have you recalculated the flange thickness/carried out FEA to ensure adequate metal thickness and structural integrity. 4. Has the level transmitter/level switches been agreed – does the flange size/position align with the instruments. 5. Update P&ID to show correct nozzle size for S4. 6. Do you have vessel design calculations. Design calculations will be required in the technical file and should be checked at FAT. | 06/23讨论： 通用事项 ： 1、管口方位已结合3D撬装布置给定。 2、3D撬装设计已考虑，待3D模型复核时，详细讨论。 3、重新计算法兰厚度，以满足结构强度要求。 4、仪表工程师已经确认复核。 5、P&ID，不需要更改S4管口尺寸。 6、设计计算书是设备完整技术文件中必不可少的一部分，后续会提供。 06/23 Discussion — General Items: 1.Nozzle orientation has been determined based on the 3D skid layout. 2.The 3D skid design has taken this into consideration; detailed discussion will be held during the 3D model review. 3.The flange thickness will be recalculated to meet structural strength requirements. 4.The instrumentation engineer has confirmed and verified this. 5.The P&ID does not require changes to the S4 nozzle size. 6.The design calculation sheet is an essential part of the complete technical documentation for the equipment and will be provided in due course. | YES | Ziliang Zhao/Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Overall cleaning philosophy per vessel 各容器整体清洗策略 Please confirm the intended cleaning philosophy for each vessel in the skid — spray-only, soak-only, spray-and-soak combined, or an alternative approach. Please also indicate whether a single philosophy applies across all vessels or whether the strategy varies by vessel. 请确认撬块内各台容器的清洗策略：单独喷淋、单独浸泡、喷淋+浸泡组合，或其它方式。请同时说明是否所有容器采用同一策略，或按容器区别设计。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleanliness verification method & acceptance criteria 清洁度验证方法与验收标准 Please advise the verification method(s) used to confirm cleaning completion (visual inspection, swab / rinse sample analysis, mass balance, calculated residue, etc.) and the numerical acceptance criteria applied (e.g. residue mass, ppm concentration threshold). 请说明用于确认清洗完成的验证方法（目视检查 / 拭子或冲洗样分析 / 物料衡算 / 残余物计算等），以及所采用的数值验收标准（如残余物质量、浓度阈值 ppm）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Sight glass availability for SE01 SE01 视镜配置 The reactor vessels are understood to be fitted with sight glasses to support visual verification of cleanliness. The gas–liquid separator SE01, however, does not include a sight glass. Please confirm the intended method for verifying cleanliness on SE01. 反应柱已配置视镜以支持目视清洁度检查，但气液分离器 SE01 未配置视镜。请确认 SE01 清洁度验证的具体手段（，以及是否考虑将新增视镜作为设计变更纳入）。 | 07/10：反应柱和分离器因为操作压力高，无法配置视镜，清洁度的验证无法依靠目测，需取样分析测量残留物的浓度 07/10：Due to the high operating pressure of the reaction column and separator, sight glasses cannot be installed. Visual inspection is therefore not feasible for cleanliness verification, and residue concentration shall be determined via sampling analysis instead. 已达成一致，需要沟通冯博士提供一下国内验收限度的方法供SW参考。 | NO | Xiantao feng/Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Spray ball flow rate vs. vessel fill time 喷淋球流量与容器充液时间的匹配 The lowest available spray ball flow rate (approximately 2 L/min) results in SE01 reaching the high-level trip point in under 25 seconds. This limits the time window in which mechanical spray action can achieve wetting coverage. Please advise the intended cleaning-time window on SE01 and the approach for ensuring adequate mechanical cleaning action within the design constraint. 现有最小可选喷淋球流量约 2 L/min，导致 SE01 容器在 25 秒内即达到高液位跳停，机械喷淋作用的有效时间窗口非常短。请说明 SE01 上预期的清洗时间窗口，以及在此设计约束下如何确保获得充分的机械清洗作用。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Drain line sizing and fill–drain cycle 排放管径与充液-排空循环 Under the current drain line configuration, the drain rate is significantly slower than the spray inflow rate. Please advise the intended drain line diameter (whether upsizing is planned), the estimated single-cycle fill and drain durations, and the number of cycles anticipated per cleaning campaign. 当前排放管径下，排放速率显著慢于喷淋进料速率。请说明拟采用的排放管径（是否放大）、单次循环的充液和排空时间估算，以及每次清洗预期需要的循环次数。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Soak cleaning vs. high-level interlock defeat mechanism 浸泡清洗与高液位联锁绕过机制 If soak cleaning is adopted on SE01, the liquid level during cleaning will exceed the high-level safety interlock (located at approximately one-third of vessel height). Please specify: (a) the physical mechanism intended for defeating this interlock during cleaning (key switch, procedural lockout, or other); (b) the authorisation and access controls surrounding the defeat mechanism; and (c) the safeguards against inadvertent defeat during normal processing operation. 若 SE01 采用浸泡清洗，清洗过程中的液位将超过位于容器约 1/3 高度的高液位安全联锁。请说明：(a) 清洗时用于绕过（defeat）该联锁的物理机制（钥匙开关 / 程序锁定 / 其它）；(b) 该绕过机制的授权与权限控制方式；(c) 防止正常运行时意外绕过的保护措施。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleaning of the guided-wave level transmitter housing Guided wave 液位变送器外壳的清洁 The guided-wave level transmitter housing (approximately 100 mm diameter, side-mounted on SE01) sits above the high-level switch and lies outside the spray ball coverage envelope. Please advise the intended cleaning approach for this housing, and any mechanical or procedural provisions required to ensure it can be cleaned to the acceptance criteria in Q1.2. 液位变送器外壳（约 100 mm 直径，SE01 侧接管上）位于高液位开关之上，不在喷淋球覆盖范围内。请说明该外壳的清洁方案，以及为达到 Q1.2 中的验收标准所需的机械或程序性措施。 | 07/14：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用 07/14：Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. | YES | Chaoqun Hu/Yu Gao
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Reactor cleaning cycle time and manual interventions 反应器清洗循环时间与人工干预 For the 200-L reactor vessels, a single spray-and-drain cycle involves an extended drain phase relative to the spray phase. Multiple cycles are expected to achieve the required cleanliness. Please advise: the anticipated number of cycles, the total cleaning duration per campaign, and the specific manual interventions required at each step (drain valve operation, sample point access, lockout re-set, etc.). 200-L 反应器进行单次"喷淋-排空"循环时，排空阶段远长于喷淋阶段，需多次循环以达到清洁度要求。请说明：预期循环次数、每次清洗总时长，以及各步骤所需的具体人工干预（排放阀操作 / 取样口操作 / 联锁复位等）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW 3D Layout 3D 布置与设备空间 | Operational access clearance 操作通道净空 The current 3D model shows approximately 300–350 mm clearance in certain operator access zones. Please confirm the target minimum clearance from a site operability and maintenance standpoint, and identify any specific zones where relaxation of the current clearance is acceptable, or where additional clearance is required. 当前 3D 模型显示部分操作人员通道净空约为 300–350 mm。请从现场操作与维护角度，确认目标最小净空要求，并识别可以放宽的具体区域，以及需要额外净空的区域。 | 7月10日反馈进展： 建议增加反应柱撬块的宽度，审核模型后给出建议的空间区域。 It is recommended to increase the width of the reaction column skid and provide the suggested spatial area after reviewing the model. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Free-drain feasibility from each vessel 各容器的自重排放可行性 The cleaning strategy relies on free-drain of cleaning fluid from each vessel into downstream collection (BT04 or equivalent). Considering the skid height constraint and each vessel elevation, please confirm the free-drain path is mechanically feasible from each source vessel to its destination. Please identify any vessels where drainage cannot be achieved by gravity and would require pumping or an alternative arrangement. 清洗策略要求清洗液自重从各容器排入下游收集罐（BT04 或等效容器）。考虑撬块高度限制与各容器标高，请确认每台源容器至其目标容器的自重排放路径机械可行。请识别无法通过重力实现排放、需要泵抽或采用替代方案的容器。 | 7月10日反馈进展： 根据目前容器的结构形式，反应柱可通过底部排放阀排放，缓冲罐可通过管路排放，预热器、冷凝器管路无排放口。具体排放方式参考清洗方案。 Based on the current structural design of the containers, the reaction column can be drained through the bottom discharge valve, the buffer tank can be discharged via piping, while the preheater and condenser have no discharge outlets in their pipelines.Refer to the cleaning plan for specific emission methods. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Nozzle orientation on pressure vessels 压力容器管嘴方位 Please review the nozzle orientation on all pressure vessels in the current 3D model. Confirm that nozzle positions provide adequate access for external piping tie-in, instrumentation installation, and maintenance (removal / reinstallation of internals, gasket replacement, catalyst service, etc.). 请审查当前 3D 模型中所有压力容器的管嘴方位。确认管嘴位置能够满足外部管路对接、仪表安装以及维护（内构件拆装 / 密封垫更换 / 催化剂检维修等）的空间要求。 | 7月10日反馈进展： 由于空间尺寸限制，部分管口的维护可能存在不便。优化管口布置或能否增加设备空间。 Due to space size limitations, maintenance of some pipe openings may be inconvenient. Optimize pipe layout or increase equipment space | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Catalyst charging & discharging arrangement 催化剂加料与卸料布置 Please confirm that the catalyst charging (loading) and discharging (unloading) arrangement is compatible with the current nozzle layout on the reactor vessels, and that adequate space is provided for charge / discharge equipment and operator access during catalyst service. 请确认催化剂加料与卸料的操作方式与当前反应柱的管嘴布置兼容，且在催化剂检维修期间为加料/卸料设备与操作人员留有充足空间。 | 7月10日反馈进展： 根据目前的布置方案，反应柱加料卸料口均在撬体端面，结合加料卸料方式看操作空间是否充足。 According to the current layout plan, the feeding and discharging ports of the reaction column are all located on the end face of the pry body. Considering the feeding and discharging methods, it is necessary to check whether the operating space is sufficient. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Tie-in points between skid and site utilities 撬块与现场公用工程接口 Please confirm the finalised location and specification of all tie-in points between the skid and the Sandwich site services, including process feed, product outlet, vent header, HTF supply and return, N₂ blanketing, instrument air, electrical supply, cable penetrations, and drain. Please advise the interfaces where design lock-down is still pending. 请确认撬块与 Sandwich 现场公用工程之间所有接口的最终位置与规格，包括工艺进料、产品出口、放空总管、导热油供回、氮气钝化、仪表空气、电气供应、电缆穿墙、排放。请说明尚未定稿的接口。 | 7月10日反馈进展： 根据现有的布置方案，有部分公用工程的的接口，无仪表空气接口，电气供应、电缆穿墙，后续更新撬块与公用工程接口的位置与规格。 According to the existing layout plan, there are interfaces for some public works without instrument air interfaces, electrical supply, and cable penetration through walls. The location and specifications of the interface between the pry block and the public works will be updated in the future. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Cable wall penetration capacity and cable compatibility 穿墙电缆孔容量与电缆兼容性 The current design indicates 14 available cable wall penetration slots. Please confirm this final count, the internal diameter of each slot, and the compatibility of the slot with the largest cable type intended to pass through (multi-core, armoured, or shielded cables of relevant cross-section). 当前设计显示可用穿墙电缆孔 14 个。请确认该数量的最终定案、每个孔的内径规格，以及与拟穿过的最大电缆类型（相应截面的多芯 / 铠装 / 屏蔽电缆）的兼容性。 | 寻求工程部支持，和宋小旭主管约会讨论如何推进，7月10日反馈进展 | YES | Dezhi meng/Shaofeng gao
07/01 | SW Control Philosophy 控制策略 | Full Control Philosophy document issue date 完整《控制策略》文件发出日期 Please advise the target issue date for the complete Control Philosophy document, superseding the interim draft version previously circulated. 请说明完整版《控制策略》文件的目标发出日期（覆盖此前流转的过渡草稿版本）。 | 07/10：已完成初版，还在校核中，预计下周发出 07/10：The initial draft has been completed and is under review; it is expected to be issued next week. | NO | Chaoqun hu
07/01 | SW Control Philosophy 控制策略 | Interlock schedule — hardwired vs. software 联锁清单 —— 硬件联锁与软件联锁 Please provide a complete interlock schedule listing all safety interlocks, with clear delineation between hardwired (independent of the PLC) and software (PLC-implemented) interlocks. For each interlock, please include: initiating cause, sensing element, trip setpoint, action taken, and protective function fulfilled. 请提供完整的联锁清单，列出全部安全联锁，明确区分硬件联锁（独立于 PLC）与软件联锁（PLC 实现）。每一条联锁请包含：触发原因、检测元件、跳停设定值、联锁动作、承担的保护功能。 | 07/10：联锁条件已完成初版，还在校核中，预计下周发出 07/10：The initial draft of interlock conditions has been completed and is under review, which is expected to be issued next week. | NO | Chaoqun hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Operational modes and mode-specific fail positions 操作模式与各模式下的故障位 Please define all operational modes of the skid (normal operation, start-up, shut-down, cleaning, catalyst change, emergency depressurisation, etc.), and for each mode specify: (a) the fail position of each control valve; (b) the state of each interlock (active / bypassed); and (c) the permissive conditions required to enter that mode. 请定义撬块的全部操作模式（正常运行 / 开车 / 停车 / 清洗 / 催化剂更换 / 紧急泄压等），并针对每一模式说明：(a) 每个控制阀的故障位；(b) 每个联锁的状态（激活 / 已绕过）；(c) 进入该模式所需的许可条件。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 分离器浸泡清洗时易触发液位高联锁，导致高液位以上清洗不彻底。增大分离器的排净管径可实现淋洗，同时系统处于清洗模式时，绕开液位高联锁。 High level interlock is prone to tripping during soaking cleaning of the separator, leading to inadequate cleaning of areas above the high liquid level. Increasing the drain pipe size of the separator allows shower rinsing. Meanwhile, the high level interlock can be bypassed when the system is under cleaning mode. | Pending | Chaoqun hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Mode-transition safeguards 操作模式切换的保护措施 Please advise the safeguards in place against inadvertent mode transitions, particularly from cleaning mode back to processing mode (e.g. an interlock bypass being left in place after cleaning is complete). Please describe both the technical safeguards (key switches, HMI confirmations) and the procedural safeguards (SOP requirements, dual sign-off). 请说明防止意外切换操作模式（尤其是从清洗模式返回处理模式时联锁绕过未复位）的保护措施。请分别描述技术性保护措施（钥匙开关 / HMI 确认）与程序性保护措施（SOP 要求 / 双签发）。 | 52条和Keith讨论后1周反馈。 | NO | Dezhi meng
07/01 | SW Sampler System 取样系统 | Sample vaporisation during pressure reduction 取样过程中的样品闪蒸 The sampler transfers process fluid from a line operating at up to 60 barG to a sample container at approximately atmospheric pressure. Please advise the analysis of vaporisation during this pressure reduction (fraction vaporised, temperature drop) and its impact on the compositional representativeness of the collected sample. 取样器将最高 60 barG 工艺管路的介质转移至常压取样瓶。请说明此压降过程中的闪蒸分析（气化比例、温度降低）及其对所采样品成分代表性的影响。 | 07/10：冷凝器出口的温度为30℃，压力从60barG 泄至常压，此温度条件下不会发生闪蒸 07/10：The temperature at the condenser outlet is 30°C. The pressure is relieved from 60 barG to atmospheric pressure, and no flashing will occur under this temperature condition. | Pending | Chaoqun hu
07/01 | SW Sampler System 取样系统 | Sample retention design 样品截留设计 Please advise the design of the sample bottle and sample-transfer system, including any vapour trap, septum, condenser, or other retention device intended to prevent loss of volatiles through the vent path and to ensure a representative liquid sample is captured. 请说明取样瓶及取样传输系统的设计，包括为防止挥发组分从放空路径流失、并确保获得代表性液样所采用的蒸汽阱、隔膜、冷凝器或其它截留装置。 | 07/10：取样器的流程：打开三通阀将缓冲罐充满，打开缓冲罐气相放空管线阀门，将缓冲罐中的气相排走并卸压，打开氮气手阀，将缓冲罐中的液体压至取样瓶 07/10：Sampling procedure: Open the three-way valve to fill the buffer drum. Open the valve on the vapor vent line of the buffer drum to vent the vapor inside and relieve pressure. Then open the nitrogen manual valve to pressurize and transfer the liquid from the buffer drum into the sampling bottle. | Pending | Chaoqun hu
07/01 | SW Sampler System 取样系统 | Sampler behaviour under gas-rich flow regime 气相主导流态下取样器行为 With the intended process operating at a stoichiometric excess of hydrogen, the flow regime through the sampling point may be gas-rich with entrained liquid rather than liquid-continuous. Please advise how the sampler design accommodates this flow regime, and whether any sample point relocation, phase separator, or coalescer is being considered. 工艺预期在化学计量氢气过量条件下运行，取样点处流态可能为"气相夹带液体"而非液相连续。请说明取样器设计如何适应此流态，以及是否考虑取样点位置调整、加装相分离器或聚结器。 | 07/10：取样器的缓冲罐上有气体排放管线，取样罐充满后，打开气体排放管线，将气相排走并卸压，再用氮气将液相压至取样瓶 07/10：The buffer vessel of the sampler is equipped with a gas vent line. Once the sampling tank is full, open the gas vent line to vent the vapor phase and relieve pressure, then push the liquid phase into the sampling bottle with nitrogen. | Pending | Chaoqun hu
07/01 | SW Instrumentation 仪表配置 | Guided-wave level transmitter — datasheet & cleanability Guided wave 液位变送器 —— 数据单与可清洁性 Please provide the guided-wave level transmitter datasheet and confirm: (a) the process compatibility of the probe assembly with the intended service (including any operating conditions in the supercritical or near-critical regime); and (b) the cleanability of the probe assembly under the adopted cleaning philosophy. 请提供 guided wave 液位变送器数据单，并确认：(a) 探头组件在拟定工况（含超临界或近临界工况）下的适用性；(b) 探头组件在拟采用清洗策略下的可清洁性。 | 7月10日反馈进展 (a) 导波雷达液位计工作原理是雷达波可以穿过介电常数较低的气相，遇到介电常数较大的液相返回，从而计算液位。适用蒸汽、粉尘、泡沫等工况。需了解超临界工况下的介质状态是否还存在液相，如果没有液相空间，则液位计无法识别。 The working principle of the guided-wave radar transmitter is that the radar wave can pass through the gas phase with a lower dielectric constant and return to the liquid phase with a larger dielectric constant, thereby calculating the liquid level. It is applicable to working conditions such as steam, dust and foam. It is necessary to understand whether there is still a liquid phase in the medium state under supercritical conditions. If there is no liquid phase space, the transmitter cannot identify it. 07/15进展：经内部评估，液位计所在容器操作工况下不存在超临界状态。 After internal assessment, it was determined that the liquid level gauge is not in a supercritical state under the operating conditions of the container it is located in. (b)BT01和BT04的导波雷达液位计为顶装内伸形式，可以利用设备内的喷淋头冲洗。SE-01的导波雷达液位计为侧装旁通式，可以选择在探头与旁通管的过程接口处增加配套冲洗环，并预留一路冲洗管线。 The guided-wave radar transmitters of BT01 and BT04 are top-mounted and iInsert type, and can be flushed by the spray heads inside the equipment. The guided-wave radar l transmitter of SE-01 is of side-mounted bypass type. A matching flushing ring can be added at the process interface between the probe and the bypass pipe, and a flushing pipeline can be reserved. 07/14进展：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用. Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. 07/17进展：气液分离器雷达液位计侧装改顶装，已完成图纸设计，筒体直径未变，邮件发出。 The radar level gauge for the gas-liquid separator has been redesigned from side-mounted to top-mounted. The drawing design has been completed, and the vessel diameter remains unchanged. The drawings have been sent out via email. | Pending | Yu gao/Chaoqun hu/Zilaing Zhao
07/01 | SW Instrumentation 仪表配置 | Level switch position & interlock function 液位开关位置与联锁功能 Please confirm the finalised position (elevation, orientation, flange size and rating) and the interlock function of each level switch (LSL, LSLL, LSH, LSHH) on each vessel, together with the matching instrument selection. 请确认每台容器上各液位开关（低 LSL、低低 LSLL、高 LSH、高高 LSHH）的最终位置（标高、方位、法兰尺寸与压力等级）与联锁功能，以及对应的仪表选型。 | 7月10日反馈进展： 关于液位开关选型，之前寻价时只有VEGA的VEGASWING 63型号可以满足DN25 Class900 M的过程接口，其他厂家如E+H、Rosemount都不能满足。 About the selection of level switches, during the previous price search, only VEGA's VEGASWING 63 model could meet the DN25 Class 900 M process connection requirements. Other manufacturers such as E+H and Rosemount could not meet these requirements. 07/15联锁值详见联锁条件表。The interlock values on 07/15 can be found in the interlock condition table. | Pending | Chaoqun hu/Yu gao
07/01 | SW Instrumentation 仪表配置 | Instrument datasheet next revision date 仪表数据单下一版本发出日期 Please advise the target issue date for the next revision of the Instrument Datasheet, reflecting the current SE01 design (post demister-configuration decision), the finalised interlock schedule, and the level switch position confirmation. 请说明反映当前 SE01 设计（demister 配置定稿后）、最终联锁清单以及液位开关位置确认的仪表数据单下一修订版本的目标发出日期。 | 7月10日反馈进展 仪表数据表已完成修订版，待意见讨论后看是否还需修改参数。 The instrument datasheet has been revised. After the discussion of opinions, we will see if the parameters still need to be modified. 08/05:根据最新设计温度和压力，更新仪表数据表，预计08/11发出 | NO | Chaoqun hu/Yu gao
07/01 | SW Documentation Status 文档状态 | Current revision and next revision date of key deliverables 主要交付文件的当前版本与下一版本时间 Please confirm the current issued revision and the target date for the next revision of the following documents: • PFD • P&ID • URS • Equipment Datasheets • Control Philosophy • Instrument Datasheet • Operating Instructions • Cleaning Procedure • Vessel Design Calculation Package. 请确认以下文档的当前已发版本与下一修订版本的目标日期： · PFD · P&ID · URS · 设备数据单 · 控制策略 · 仪表数据单 · 操作说明 · 清洗程序 · 容器设计计算书。 | 7月10日反馈进展，操作手册还在编制中，其他设计文件已完成。On July 10th, we provided the progress update. The operation manual is still under preparation, while the other design documents have been completed. 08/05：预计本周末发出 | NO | Shaofeng gao/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R1] Design Temperature — Vessel could fail during relief event. Equipment design temperature is specified for process requirements and does not consider elevated temperatures during relief events when short-term temperature increase has the potential to exceed the design temperature. 设计温度 —— 容器可能在泄放事件中失效。设备设计温度是按工艺需求设定的，未考虑泄放事件中的短时温升可能超过设计温度的情形。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：已更新数据表，提高设计温度，以满足工艺需求，图纸已升级。 07/10: Data sheet updated with elevated design temperature to meet process requirements; drawings revised accordingly. | YES | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register Engineering Design 工程设计 | [R2] Design Requirements — L:G ratio for plant is not clearly defined. Equipment design could result in very limited operating ranges and incorrect assumptions in plant capability and relief design. 设计条件 —— 装置的液气比（L:G ratio）未明确定义。可能导致设备设计的操作区间受限，以及在装置能力和泄放设计中做出错误假设。 | 7月10日反馈进展，根据最终确定的反应器尺寸核实气液比数据。On July 10th, the progress was reported. The gas-liquid ratio data was verified based on the final determined reactor size. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Engineering Design 工程设计 | [R3] Design Requirements — Catalyst specification is not available. Design may not be suitable for some catalysts. Dusty catalysts could cause blockages. 设计条件 —— 催化剂规格未明确。设计可能不适用于某些催化剂；含粉尘的催化剂可能导致堵塞。 | Keith / SW response: Design philosophy is based on catalyst beads/pellets which are dust-free, non-flammable and have exposure levels requiring OEB 3 or lower containment. Note: OEB 3 containment is a deviation from the URS and requires acceptance. Keith / SW 答复： 设计基于无粉尘、非燃、暴露等级 OEB 3 或更低的颗粒/粒状催化剂。注：OEB 3 的密闭要求相对 URS 存在偏离，需要接受确认。 | NO | SW
07/02 | SW - Risk Register Engineering Design 工程设计 | [R4] Access — Layouts are not available to assess whether access to equipment is acceptable for operations and maintenance. 通道 —— 布置图尚未提供，无法评估设备的操作与维护通道是否满足要求。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.1 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R5] Maintenance — Lifting Aids (davit arms, lifting beams, etc.) have not been considered in design, with potential for injury to maintenance personnel removing heavy equipment for servicing / repair / replacement. 维护 —— 设计中尚未考虑起重辅助设施（吊臂、起吊梁等），维护人员在拆卸重型设备进行检修 / 修理 / 更换时可能存在人身伤害风险。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R6] Lighting — Layouts are not available to assess whether lighting for routine operations and maintenance activities is acceptable. 照明 —— 布置图尚未提供，无法评估日常操作和维护活动的照明条件是否满足要求。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R7] System leak detection — Pressure testing of high-pressure system will be hydraulically tested. Hydraulic testing demonstrates mechanical strength of the pressure system but does not demonstrate integrity for a hydrogen system. 系统检漏 —— 高压系统将进行水压试验。水压试验只能证明压力系统的机械强度，无法证明氢气系统的密封完整性。 | Keith / SW response: Helium testing is not routinely carried out in China. Keith / SW 答复： 国内通常不常规进行氦气检漏。 可以做气密性试验；国内整橇系统气密性试验后，分体运至英国，进入工厂房间后，再次组装，需重新进行泄漏试验，现场是否具备试验条件？现场可进行氦气检漏。 和CE认证机构确认一下具体方案。 A pneumatic test can be performed. After the complete skid system undergoes the pneumatic test in China, it will be shipped in split form to the UK. Upon arrival at the factory site and reassembly, a new leak test will be required. We need to confirm whether the site has the necessary conditions/facilities for this test. Helium leak detection is available on site. We will confirm the specific plan with the CE Notified Body. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R8] Line sizing / specification — Vents / headers incorrectly sized / specified, resulting in high back pressure and safety / operability issues, e.g. two-phase flow in emergency vent relief header. 管线规格 / 尺寸 —— 放空 / 泄放总管尺寸或规格不正确，导致背压过高及安全 / 可操作性问题，例如紧急泄放总管中出现两相流。 | 07/10：安全阀进出口尺寸详见P&ID 07/10：Refer to the P&ID for the inlet and outlet sizes of the safety valve. | Pending | Chaoqun hu
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R9] Insulation — Insulation requirements not specified, which could result in equipment / pipe layout not allowing space for insulation to be installed. 保温 —— 保温需求尚未明确，可能导致设备 / 管路布置未预留保温安装空间。 | Confirm the insulation material with Keith and determine the thickness. Once it's confirmed, provide a progress report on July 10th. 和Keith确认下保温材料，然后确定厚度。确定后，7月10日反馈进展 3D模型中管路的间距已按照保温厚度30-35mm预留了保温的安装空间。 The spacing between pipes in the 3D model has been designed to accommodate an insulation installation gap of 30-35mm, as per the insulation thickness requirements. | YES | Yinghui cheng/Chaoqun hu/Shuangshuang fan/Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R10] Modular design — Modular design could introduce significant increase in site construction activities, e.g. mechanical and EC&I installation and subsequent testing. 模块化设计 —— 模块化设计可能大幅增加现场施工工作量，例如机械与电控仪表安装及后续测试。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 现有模块化设计的方案是根据进口电梯的尺寸，将整套设备拆分为4个撬块运输组装。 SW建议：需再考虑从屋顶直接吊装进去的方案，需要在后续周三会上进一步讨论。 The current modular design solution involves dividing the entire set of equipment into four skids for transportation and assembly based on the dimensions of imported elevators. SW Recommendation: Further consideration is needed for the direct hoisting-in-from-the-roof solution, which will be discussed in the upcoming Wednesday meeting. 07/29：会上澄清四撬块方案技术可行、屋顶吊装非必选；认证机构评估以 3D 定稿为前提，Keith 下周四返回后进一步确认。 07/29: Clarified that the four-module option is technically feasible and roof removal is not mandatory; the Notified Body assessment requires the finalised 3D layout, to be confirmed further with Keith after he returns next Thursday. 08/05:核实分撬是否与海运有关，和进出口部（公司内）请教下海运的最大尺寸事宜。 08/07：询问进出口部同事，集装箱内部高度有限，同时需要预留固定以及防撞等措施空间，所以橇块高度不要超过2.5m。整橇的话，有一种框架集装箱能放进去，但不密封，暴露在空气中，容易造成腐蚀，不建议采用。同时提醒，整橇运输也要考虑陆运高度限制。 | NO | Chaoqun hu/Shuangshuang fan
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R11] Skid assembled on site could result in CE / UKCA Responsible Person / Authorised Representative in China not being able to issue Declaration of Conformity for Skid Package. 撬块在现场组装可能导致中国境内的 CE / UKCA 负责人 / 授权代表无法为撬块整机签发符合性声明（Declaration of Conformity）。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 与CE认证方沟通确认好细节，特别是认证机构是否需要到UK现场验证，再发证。 We will communicate with the CE Notified Body to confirm all the details, in particular whether the certification body needs to attend the UK site for verification prior to issuing the certificate. 07/29：需以 3D 布置定稿版与 CE 认证机构沟通，评估现场组装后的验证方式、费用与工期。 07/29: The finalised 3D layout is required to engage the CE Notified Body and assess the post-assembly verification route, cost and duration. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R12] Wall penetrations — Layouts and cable schedules not available to confirm space is available for pipe / cable penetrations to / from R23 Module. 穿墙孔 —— 布置图和电缆清单尚未提供，无法确认与 R23 模块之间的管道 / 电缆穿墙位置有足够空间。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.6 | The initial cable schedule of CIMT is not fully aligned with the SW plan. SW has sent SLD, CIMT is verifying design discrepancies and will feed back comparison results, followed by discussions with SW CIMT初版线缆计划与SW计划没有完全匹配，SW已发出单线图，CIMT核对设计差异，返回对比结果，再与SW讨论。 7/23：CIMT根据SW提供的单线图，更新了电缆数量。部分流量控制器电缆待确认。硬联锁开关阀点位本安/隔爆待确认。 7/23：CIMT update the cable quantity based on the SLD provided by SW. some cables are still pending confirmed, 1. for flow controllers(modbus or 4-20mA). 2. for HW interlock on-off valve(I.S. or Ex d) | NO | Dezhi meng
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R13] Catalyst charge point — Inlet pipe diameter is small and blockages may occur. 加料口 —— 加料管径较小，可能发生堵塞。 | Keith / SW response: Inlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking inlet pipe. Keith / SW 答复： 加料接口已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞加料管的风险。 | YES
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R14] Catalyst physical property requirements (size, shape, packing, etc.) are not defined, with the potential for incompatible catalyst to be charged to the reactors. 催化剂物性要求（粒径、形状、装填密度等）尚未定义，存在向反应器加入不兼容催化剂的风险。 | 07/10：催化剂直径0.5mm-5mm，形状不重要，球形，圆柱形，不规则颗粒状都可以，装填密度一般0.5g/mL来估算，但催化剂强度要高，不容易破碎起粉 07/10：The catalyst particle diameter ranges from 0.5 mm to 5 mm, with no specific shape requirement; spherical, cylindrical and irregular granular forms are all acceptable. The bulk density can be estimated at 0.5 g/mL in general. Meanwhile, the catalyst shall feature high mechanical strength to avoid fragmentation and dust generation. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R15] Packing of catalyst is not controlled, with the risk of reactants / gas channelling in the continuous reactor column, and the potential for incomplete reaction or impurities forming. 催化剂装填未受控，存在反应物 / 气体在连续反应柱内形成沟流的风险，可能导致反应不完全或杂质产生。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R16] Contained charge system design not available to assess risks and / or design limitation. 密闭加料系统的设计尚未提供，无法评估其风险与设计局限。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R17] Manual handling requirements for catalyst charging not assessed. 催化剂加料的人工搬运需求尚未评估。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R18] Access to charge point and support of charge container / bag not designed (access steps / integrated support shelf). 加料口的通道以及加料容器 / 料袋的支撑尚未设计（例如操作台阶、集成支撑架）。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R19] 20-micron catalyst retaining screen — Screen blockages prevent / limit flow of gas / reaction mix to continuous reactors. 20 微米催化剂拦截筛 —— 拦截筛堵塞会阻止 / 限制气体 / 反应液流入连续反应器。 | Keith / SW response: China Operations have reported blockages occur in local plant and screen has been removed and discarded. Keith / SW 答复： 国内运行反馈已在本地装置中发生堵塞，已将拦截筛拆除并弃用。 | YES
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R20] Polishing filter (FTR9832) — Filter blockages prevent / limit flow of gas / reaction mix through continuous reactors. Pressure increases in reactor system, with potential for undesirable reactions to occur, until reactor high-pressure trip is activated. 精滤器 (FTR9832) —— 滤芯堵塞会阻止 / 限制气体 / 反应液流经连续反应器；反应器压力升高，直到触发高压跳停前可能发生副反应。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 待定/To be determined 精滤器堵塞，加旁通，清洗时打开旁通，方便卸压 | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register CR01 – CR03 Reactors CR01 – CR03 反应器 | [R21] Temperature control — Jacket temperature control is configured to control jacket temperature only. Reactor internal temperatures are monitored, but no control, alarms or interlocks are configured for process control. 温度控制 —— 夹套温度仅控制夹套温度本身。反应器内部温度虽被监测，但未针对工艺过程配置控制、报警或联锁。 | Keith / SW response: Scale-up provides large operating envelopes for process temperature requirements and additional control, alarms and interlocks are not required. Keith / SW 答复： 由于放大试验提供了较大的工艺温度操作裕度，无需增加额外的控制、报警或联锁。 | YES
07/02 | SW - Risk Register System Pressure Monitoring 系统压力监测 | [R22] Differential pressure monitoring — Accuracy of static pressure measurements may not enable differential pressures to be calculated with any degree of accuracy or certainty. 差压监测 —— 静态压力测量精度可能不足以支持差压计算达到所需的精度或置信度。 | 通过反应柱上和反应器进出口管线上的的压力变送器精度估算，最大差压误差大约为40kPa。 Based on the accuracy estimation of the pressure transmitters on the reaction column and the inlet/outlet pipelines of the reactor, the maximum differential pressure error is approximately 40kPa. 07/14压力也增加了联锁。The pressure also increased the interlock. | YES | Chaoqun hu/Yu gao
07/02 | SW - Risk Register Over Pressure Protection 过压保护 | [R23] Relief system design — Pressure systems not identified and relief studies not available. Identification of worst-case relief scenario not identified, and relief streams may be incorrectly categorised. Details of maximum reaction exotherm not fully documented. 泄放系统设计 —— 压力系统尚未识别、泄放研究尚未提供。最坏工况泄放情景未识别，泄放物流可能被错误归类。反应最大放热的详细信息尚未完整记录。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：详见安全阀计算书 07/10：See safety valve calculation sheet for details. | Pending | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R24] Vessel design — Complete degassing of product stream not achieved, with the potential for hydrogen carry-over into BT04 and product transfer containers. 容器设计 —— 产品物流未实现完全脱气，H₂ 可能带入 BT04 及产品转运容器。 | 07/10：气液分离器满足气液分离的要求 07/10：The gas-liquid separator meets the requirements for gas-liquid separation. | Pending | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R25] Cleaning of separator not fully understood but current concept relies on vessel free-draining to BT04. Current spray ball sizing is not consistent with this approach and may require significant rework to process piping. 分离器清洗方案尚未完全明确，当前概念依赖容器向 BT04 的自重排放。现有喷淋球规格与该思路不匹配，可能需要对工艺管路进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.4,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register Separator 气液分离器 | [R26] Cleaning of LIT003 housing does not appear to be considered in design. LIT003 液位变送器外壳的清洗在设计中似乎尚未考虑。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.7 | 同上42行回复/Translation of the 42nd line above. | NO | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R27] P&ID does not clearly show nozzle locations and could lead to mal-ops / misunderstanding of the design intent by the Operations team. P&ID 上未清晰标注管嘴位置，可能导致运行团队误操作或误解设计意图。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.3 | 07/10：已标注，详见P&ID 07/10：Marked as indicated; refer to the P&ID for details. | Pending | Chaoqun hu
07/02 | SW - Risk Register Sampling 取样系统 | [R28] Sampler design — When depressurising the sample collection chamber, high gas or vapour vent rates could result in a bubbly or churn-turbulent flow regime, and sample will discharge to vent line as two-phase flow. 取样器设计 —— 对取样收集腔进行减压时，气体或蒸汽的高排放速率可能形成鼓泡或搅动湍流流态，样品将以两相流形式排入放空管。 Related Outstanding Questions ｜ 关联待澄清问题：Q5.1 | 07/10：缓冲罐静置一定时间，让气液分层，泄压时缓慢打开手阀 07/10：Allow the buffer tank to stand for a certain period for vapor-liquid stratification, then open the manual valve slowly during depressurization. | Pending | Chaoqun hu
07/02 | SW - Risk Register Sampling 取样系统 | [R29] With significantly more gas being present in the process stream, what will prevent overpressure of sample bottle and low-pressure nitrogen pipework? 由于工艺物流中气体明显较多，采用什么措施来防止取样瓶和低压氮气管路的超压？ | 07/10：取样瓶和氮气管线投用时，系统已泄压至常压 07/10：The system has been depressurized to atmospheric pressure prior to commissioning of sampling bottles and nitrogen pipelines. | Pending | Chaoqun hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R30] Catalyst Discharge Plug valve — Outlet pipe diameter is small and blockages may occur. 催化剂卸料闸阀 —— 出口管径较小，可能发生堵塞。 | Keith / SW response: Outlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking outlet pipe. Keith / SW 答复： 出口接管已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞出口管的风险。 | YES
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R31] Contained discharge system design not available. Layout design may not provide sufficient headroom for contained discharge system. 密闭卸料系统的设计尚未提供。当前布置可能无法为密闭卸料系统提供足够的顶部空间。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R32] Complete removal of catalyst during discharging operations is unlikely to remove 100% of the material, with the risk of cross contamination of catalyst material between campaigns. 卸料操作难以完全（100%）清除催化剂，存在批次间催化剂交叉污染的风险。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | Pending | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R33] CIP Design — CIP design incomplete. Initial spray ball sizing is inconsistent with process line sizing approach and may require significant rework to process piping and/or equipment layout. CIP 设计 —— 就地清洗设计不完整。初步喷淋球规格与工艺管路选型方式不匹配，可能需对工艺管路和 / 或设备布置进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.1,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R34] Cleaning carried out at nominally atmospheric pressure with the risk of material being trapped between flanges, which tend to separate slightly during high-pressure operation, and could lead to cross contamination between batches. 清洗在近常压下进行，高压运行时法兰会出现微量分开，可能将物料残留于法兰间隙中，进而导致批次间交叉污染。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. | NO | Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R35] Validation / Verification — Cleaning validation / verification philosophy not available. QA may not accept that the continuous reactor achieves minimum cleaning standards. 验证 / 确认 —— 清洗验证 / 确认策略尚未提供。质量保证部门可能不接受连续反应器满足最低清洗标准。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.2,Q1.9 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 更新清洗方案后讨论/Discuss after updating the cleaning procedure. | NO | Chaoqun hu/Xiantao Feng
07/02 | SW - Risk Register Cleaning 清洗 | [R36] Layout — Layouts are not available to evaluate the impact of bypasses, dead legs, drains, vents, etc. 布置 —— 布置图尚未提供，无法评估旁路、死管、排放、放空等的影响。 |  | NO | Shuangshuang fan/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R37] Layout — Layouts are not available to evaluate access to equipment for visual inspections, which may impact the effectiveness of critical inspections. 布置 —— 布置图尚未提供，无法评估设备的目视检查通道，可能影响关键检查的有效性。 |  | NO | Shuangshuang fan/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R38] Layout — Equipment design / layout does not allow for routine disassembly and manual cleaning. Equipment turnaround times and operating costs would be adversely impacted if CIP system cannot be validated. 布置 —— 设备设计 / 布置未考虑日常拆装和人工清洗。如 CIP 系统无法通过验证，设备周转时间和运行成本都会受到不利影响。 |  | NO | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register FT001 FT001 流量计 | [R39] Liquid Stream Flow Sensor for flow control loop FIC001. FT001 is a Coriolis mass flow meter installed downstream of the metering pump MP01. Pulsed flow from the pump will impact on the flow measurement and accurate flow control may not be possible. 液相流量传感器（用于 FIC001 流控回路）—— FT001 是安装在计量泵 MP01 下游的科里奥利质量流量计。泵的脉冲流会影响流量测量，可能无法实现精确流量控制。 | Keith / SW response: China Team have previously used this configuration and not experienced flow control issues. No further action required. Keith / SW 答复： 国内团队此前采用过该配置，未出现流控问题。无需进一步动作。 | YES
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R40] Maximum flow may exceed separator design limitations and carry hydrogen over into BT04 / product collection containers. 泵的最大流量可能超出分离器的设计上限，将 H₂ 带入 BT04 / 产品收集容器。 | 07/10：分离器的直径足够大，泵为最大流量时能满足分离要求 07/10：The separator has a sufficiently large diameter to meet separation requirements even when the pump operates at maximum flow rate. | Pending | Chaoqun hu
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R41] Pump turndown does not meet URS minimum flow requirements. 泵的调节比无法满足 URS 中规定的最低流量要求。 | 07/10：机泵条件中规定了泵的最小流量要求，待泵厂家返回资料时审查是否满足最低流量要求 07/10：Minimum flow requirements for pumps are specified in pump data sheets. Compliance with the minimum flow criteria shall be verified upon receipt of vendor documentation. 08/05：根据最新机泵数据单走采购流程询问厂家资料 | NO | Chaoqun hu
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R42] Hydrogen gas flow controller — Flow controller does not support tight shut-off and system pressure increase during hold periods. 氢气流量控制器 —— 控制器不支持严密关断，系统在保压期间压力会持续上升。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller to provide tight shut-off. Keith / SW 答复： 在控制器下游追加一台切断阀以提供严密关断。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R43] Maximum flow through controller may exceed separator design limitations and carry liquid into the vent line. 流经控制器的最大流量可能超出分离器设计上限，将液体带入放空管。 | Keith / SW response: High level interlock installed in the separator to stop gas supply and close PIC028 shut-off valve (CV08). Keith / SW 答复： 在分离器上设置高液位联锁，停 H₂ 供给并关闭 PIC028 的切断阀（CV08）。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R44] Time required for pressure testing the system and nitrogen inertion may be excessively high. 系统加压试验及氮气钝化所需时间可能过长。 | Keith / SW response: Pressure test / inertion times to be evaluated during FIC003 selection. Manual vent installed on BT03 to reduce depressurisation times via FIC003. Keith / SW 答复： 在 FIC003 选型时评估压力试验 / 惰化时间。在 BT03 上加装人工放空阀，缩短经 FIC003 的减压时间。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R45] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端的差压超出厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register LIC003 LIC003 分离器液位 | [R46] SE01 Separator Level Indicator — Cleaning / decontamination of housing is not possible. Residual product in housing could lead to cross contamination between campaigns. SE01 分离器液位指示 —— 变送器外壳无法进行清洗 / 净化。外壳内的残留物料可能导致批次间交叉污染。 | Keith / SW response: Design relies on dissolution of residual material. 100% flood-fill of housing is not possible, therefore any residual trace contamination in the housing is deemed to be small and will not significantly impact cleaning verification. Keith / SW 答复： 设计依赖残余物料的溶解。外壳无法 100% 灌满，因此外壳内任何残余痕量污染被视为很小，不会显著影响清洗验证。 | YES
07/02 | SW - Risk Register FIC004 FIC004 分离器液位控制 | [R47] Separator outlet flow / level control — Differential pressure across the controller exceeds manufacturer's recommendations and controller capability. 分离器出口流量 / 液位控制 —— 控制器两端差压超出厂家建议范围及控制器能力。 | 分离器出口先通过减压阀减到0.2MpaG左右，可以满足厂家建议的差压范围 The outlet of the separator is first reduced to approximately 0.2MpaG through a pressure reducing valve, which can meet the differential pressure range recommended by the manufacturer | Pending | Chaoqun hu/Yu gao
07/02 | SW - Risk Register FIC005 FIC005 BT01 氮气吹扫 | [R48] BT01 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT01 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register FIC007 FIC007 BT04 氮气吹扫 | [R49] BT04 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R50] System back pressure controller — The back pressure controller does not support tight shut-off during hold periods and system pressure will not be maintained. 系统背压控制器 —— 该控制器在保压期间不支持严密关断，系统压力无法保持。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller. Keith / SW 答复： 在该控制器下游追加一台切断阀。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R51] Time required for depressurising the system following pressure testing and nitrogen inertion may be excessively high. 加压试验和氮气钝化之后系统减压所需时间可能过长。 | Keith / SW response: Manual bypass installed around PIC028 controller. Keith / SW 答复： 在 PIC028 控制器周围加装人工旁路。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R52] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端差压超出厂家建议范围，可能导致控制器无法正常工作。 | 07/10：关于背压阀028，之前Bronkhorst的电子压力阀厂家计算反馈的阀前背压范围最大为0.9~6MpaG，范围量程比不能过大。 07/10：About the back pressure valve 028, previously, the manufacturer of Bronkhorst’s electronic pressure valve calculated and reported that the maximum range of the back pressure before the valve was 0.9 to 6MpaG, and the range-to-range ratio cannot be too large. 08/05:会后核实 | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register PIC030 PIC030 分离器液相出口减压 | [R53] Separator liquid outlet pressure reducer — Is this confirmed as a Bronkhorst pressure controller, or is a mechanical regulator still an option? Does this provide the required independence assumed in the relevant SIL / risk assessments? 分离器液相出口减压器 —— 该阀是否确认为 Bronkhorst 电子压力控制器？还是仍可能选用机械式减压阀？该配置能否提供相关 SIL / 风险评估中假设所需的独立性？ | 目前选型机械式减压阀。机械阀不是电子设备，没有相关的SIL认证。 At present, mechanical pressure reducing valves are being selected. Mechanical valves are not electronic devices and do not have the relevant SIL certification. | Pending | Chaoqun hu/Yu gao
07/02 | SW - Risk Register PIC049 PIC049 BT04 背压控制 | [R54] BT04 back pressure controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 背压控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register Automation 自动化 | [R55] Automation Build — Philosophy and Design documentation not available to assess risks and limitations. 自动化建设 —— 自动化策略与设计文档尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q3.1,Q3.2 | 专题沟通后确定反馈 | NO | Chaoqun hu/Dezhi meng/Ziliang zhao
07/02 | SW - Risk Register Documentation 文档 | [R56] Technical File — Technical File not available to assess risks and limitations. 技术文件 —— 技术文件尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.5,Q7.1 |  | NO | Shaofeng gao/All
07/02 | SW - Risk Register Documentation 文档 | [R57] O&M Manual — O&M manual not available to assess risks and limitations. 操作维护手册 —— O&M 手册尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q7.1 | 07/10：操作手册的编制还在进行中 07/10：Preparation of the operation manual is still in progress. 07/29：操作维护手册预计 8 月中完成。 07/29: The O&M manual is scheduled for completion in mid-August. | NO | Chaoqun hu
07/02 | SW - Risk Register Documentation 文档 | [R58] Emissions Calculations — Calculations to demonstrate expected release of Class A and Class B VOCs to atmosphere are not available. These are required to demonstrate compliance with EA Permit limits. 排放量计算 —— 尚未提供证明 A 类和 B 类 VOC 向大气排放的预期计算。该计算是证明满足 EA 许可（英国环境署许可）限值要求所必需。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW负责排放量计算/SW is responsible for emissions calculation. | YES | Chaoqun hu
07/02 | SW - Risk Register Regulatory Compliance 法规合规 | [R59] CE ¦ Functional Safety ¦ DSEAR / ATEX ¦ PSSR ¦ COSHH ¦ PUWER (Access, manual handling) ¦ Working at Height (Access Steps / Support Shelf) ¦ LOLER (Davit arms) ¦ Lighting ¦ Occupational Hygiene ¦ EA Permit — Regulatory non-conformance would prevent beneficial use of equipment in the UK. CE 认证 ¦ 功能安全 ¦ DSEAR / ATEX 防爆 ¦ PSSR 压力系统安全 ¦ COSHH 危害物质 ¦ PUWER 工作设备（含通道与人工搬运）¦ 高处作业（操作台阶 / 支撑架）¦ LOLER 起重设备（吊臂）¦ 照明 ¦ 职业卫生 ¦ EA 环境许可 —— 任何法规合规缺失都会导致设备无法在英国正常投入使用。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW内部的提醒事项。 CFCT核实加料步梯是否包含在内。 SW提供步梯平台尺寸。 Internal reminders for SW: CFCT to verify whether the feeding staircase is included. SW to provide dimensions of staircase and platform. | NO | Zilang zhao/All
07/14 |  | 根据生产经验，研发建议原R24-CR01的直径由DN80改为DN50，导致产能下降，可能无法满足URS中的产能30kg/day Based on production experience, the R&D team proposes reducing the diameter of the original R24-CR01 from DN80 to DN50. This modification will result in lower production capacity, which may fail to meet the 30 kg/day throughput specified in the URS. | 07/14：周三会上确定/To be confirmed at Wednesday's meeting. 07/15：暂定R24-CR01的直径修改为DN65，等9月份研发提供DN65的反应器实验数据后最终确认反应器的尺寸为DN65或DN50 07/15：It is tentatively agreed to revise the diameter of R24-CR01 to DN65. The reactor size (either DN65 or DN50) will be finalized after the R&D department provides DN65 reactor test data in September. 07/29：会上确定按 DN65 / DN50 两套方案并行准备，并建立变更影响日志；待 9 月研发 DN65 实验数据后最终定案。 07/29: Agreed to prepare the DN65 and DN50 cases in parallel and to set up a change-impact log; final decision after the September DN65 R&D test data. | NO | Xiantao Feng/All
07/23 | SW | 气液分离器SE01容器承受从常压到60 barg的压力循环次数？ How many pressure cycles does the gas-liquid separator SE01 vessel undergo from atmospheric pressure to 60 barg? | 07/23:会上讨论了加氢装置的操作周期，意见存在不一致，关于连续加氢的年运行周期，SW内部沟通后反馈循环次数需求。 气液分离器的设计温度调整到270℃，对应设计压力调整到7.5MPaG。垫片选用金属环垫片。 07/23：The operating cycle of the hydrogenation unit was discussed at the meeting, and divergent opinions remain. SW shall coordinate internally and provide feedback on the required number of cycles regarding the annual operating cycle for continuous hydrogenation. The design temperature of the gas-liquid separator shall be revised to 270°C, with the corresponding design pressure adjusted to 7.5 MPaG. Metallic ring gaskets shall be adopted . 08/06：垫片材质？原料酸性 PEEK，再寻找合适的垫片，讨论。 | NO | Zilang zhao/Chaoqun hu
07/23 | IEPE | P&ID中压力表无根部阀，是否需要增加根部阀？ Pressure gauges shown on the P&ID are not equipped with root valves. Is it necessary to add root valves? | 07/23:按照现有P&ID配置。 07/23：Configure in accordance with the existing P&ID. | NO | Chaoqun hu/Yu gao
07/23 | IEPE | PCV028侯径小，反应系统卸压时，全开PCV028卸压速度也很慢，建议将PCV028的旁通手阀改为开关阀 PCV028 has a small orifice. When depressurizing the reaction system, the depressurization rate remains low even if PCV028 is fully open. It is recommended to change the bypass manual valve of PCV028 to an on-off valve. | 07/23:单独发邮件沟通。 07/23：We will communicate via separate email. | NO | Chaoqun hu
07/29 | SW | 针对 R24-CR01 直径变更（DN80→DN65/DN50），建立变更影响日志/清单，逐项列出受影响的设备、仪表、管线、安全阀及相关文件与参数，确保无遗漏。 Establish a change log / impact list for the R24-CR01 diameter change (DN80→DN65/DN50), itemising every affected item of equipment, instrumentation, piping, relief device and the related documents and parameters, so that nothing is missed. | 07/29：会上同意建立变更影响日志，由国内团队逐项梳理受影响范围并跟踪关闭。 07/29: Agreed at the meeting to create a change-impact log; the China team will work through the affected scope item by item and track it to closure. | NO | Shaofeng Gao/Chaoqun Hu
07/29 | SW | 反应器 DN65 与 DN50 两种规格并行准备设计方案：先确定处理量，再分别出 PFD 与物料平衡；并核实仪表选型、安全阀/泄放组合是否需相应调整。待 9 月研发提供 DN65 实验数据后定案。 Prepare two parallel design cases for the DN65 and DN50 reactor: fix the throughput first, then issue a PFD and mass balance for each, and verify whether instrument selection and the relief-valve combination need to change accordingly. To be finalised once R&D provides the DN65 test data in September. | 07/29：会上确定按 DN65 / DN50 两套方案并行准备，使 9 月数据到位后可直接定案，不影响整体进度。 07/29: Agreed to progress both the DN65 and DN50 cases in parallel so that the decision can be taken as soon as the September data is available, without affecting the overall schedule. | NO | Shaofeng Gao/Chaoqun Hu/Xiantao Feng
07/29 | IEPE | 容器设计压力由 80 barg 调整为 75 barg，以保持法兰等级 CLASS 900、避免材料选型受限；需在设备数据表、图纸及相关计算书中同步更新落实。 Vessel design pressure revised from 80 barg to 75 barg in order to retain the CLASS 900 flange rating and avoid limitations on material selection; to be updated consistently in the equipment datasheets, drawings and supporting calculations. | 07/29：周二与 Keith 讨论已取得初步一致，继续推进并在各设计文件中落实。 07/29: Initial agreement reached with Keith on Tuesday; to be carried forward and reflected in the design documents. | NO | Chaoqun Hu/Ziliang Zhao
07/29 | SW | 四撬块分体运输 vs 屋顶整体吊装的决策路径：国内先完成 3D 布置定稿，再以定稿版与 CE 认证机构评估现场组装后的验证方式、费用与工期；Keith 下周四返回后确认四撬块方案可行性；SW 侧评估屋顶更换的费用、工期及 R23 停用影响。 Decision path for four-module split shipment vs a whole-unit lift through the roof: the China team to finalise the 3D layout first, then use the finalised version to evaluate with the CE Notified Body the post-assembly verification route, cost and duration; confirm the four-module option with Keith after he returns next Thursday; SW to assess the roof-replacement cost, duration and the impact of taking R23 out of service. | 07/29：会上提议需要澄清四撬块方案技术上可行，屋顶吊装并非必选项；认证机构评估需以 3D 定稿为前提，国内加快 3D 定稿以尽早取得费用与工期结论。 07/29: Clarified at the meeting that the four-module option is technically feasible and roof removal is not mandatory. The Notified Body assessment depends on the finalised 3D layout, so the China team will accelerate finalisation to obtain the cost and schedule answer as early as possible. | NO | Ziliang Zhao/Shaofeng Gao/Keith
07/29 | SW | 明确下阶段（建造 / FAT）文件的编制与签发流程：由谁编制、由谁签发；SW 场地有自有的 FAT / 验证模板。CE 认证方参与文件评审但不参与签发。约定后续安排专题讨论。 Define the preparation and sign-off process for the next-stage (construction / FAT) documentation — who prepares and who signs off. The SW site has its own FAT / validation template. The CE Notified Body will take part in document review but not in sign-off. A dedicated follow-up discussion to be arranged. | 07/29：双方同意尽早对比两侧模板并识别差异；倾向直接采用 UK 模板以便英国侧验证与确认，国内按该模板提供资料，避免后期返工。 07/29: Both sides agreed to compare the two templates early and identify any gaps; the preference is to adopt the UK template so that verification and validation on the UK side is straightforward, with the China team supplying information to that template to avoid rework later. | NO | Shaofeng Gao/Ziliang Zhao
07/29 | IEPE | 请 SW / Keith 提供英国现场验证（validation）所需的信息清单与模板，国内据此提供资料并按该模板执行，以便尽早识别中英双方要求差异。 SW / Keith to provide the list of information required for the UK site verification / validation process, together with the template, so that the China team can supply the information and work to that template and any differences between the UK and China requirements are identified early. | 07/29：会上确定由 SW 提供模板与信息需求清单，国内提供文件 / 信息并按模板填写；下周与 Keith 沟通落实。 07/29: Agreed that SW will provide the template and the information requirement list; the China team will supply the documents / information and complete them to that template. To be taken forward with Keith next week. | NO | Keith/Shaofeng Gao
07/29 | SW | HAZOP 前须与 Keith 就 3D 布置与控制说明（含操作手册）达成一致 —— 该两项目前仅国内内部讨论过，是余下唯二可能引发重大设计变更的环节，须在 HAZOP 前关闭，以确保 HAZOP 只做一次、避免重做。 The 3D layout and the control philosophy (including the operating manual) must be agreed with Keith before HAZOP. These two items have so far only been reviewed internally by the China team and are the only remaining items that could still trigger a significant design change; they must be closed out beforehand so that HAZOP is run once only and does not have to be repeated. | 07/29：会上确认目标为「HAZOP 只做一次」；两项在 9 月初 HAZOP 前与 Keith 讨论定稿。 07/29: The meeting confirmed the objective of running HAZOP only once; both items to be discussed and finalised with Keith ahead of the early September HAZOP. | NO | All

## 0729
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. 05/12：Keith建议用气液两相计算安全阀尺寸，不提供模板 05/12：Keith suggests using gas-liquid two-phase calculations for determining the size of the safety valve, but no template is provided. 05/20：根据API520的气液两相泄放时计算安全阀尺寸，部分已完成 05/20：Calculate the size of the safety valve based on the API520 standard for the two-phase gas-liquid discharge situation.Partially completed. 06/02：安全阀计算初版已完成（包含临界流体和气液两相），校审中。 06/02：Preliminary calculation of safety relief valve (covering critical fluid & gas-liquid two-phase flow) completed, under review. 06/09: General 1. What was the source/reference for the Specific Volumes stated in column D/D 列中比容数据的来源及参考依据是什么？ The Specific Volumes stated in column D are derived from Aspen Plus simulation results.比容数据来自Aspen模拟 2. There is no backpressure considered in the calculation. The emergency vent relief will create some backpressure which needs to be considered in the calculation./本次计算未考虑背压。紧急放空泄放过程会产生一定背压，该因素需纳入计算。 Backpressure consists of static backpressure and built-up backpressure. Given the wide total pressure range, backpressure effects shall be incorporated into the calculation.背压分为静背压和积聚背压，总压力范围大，将背压包含在其中 3. At the assumed relief pressure Ethyl Acetate will be a supercritical fluid, therefore the required relief mass flowrate will not be dependent on the latent heat of vapourisation, and the calculated ‘required discharge area’ will not be valid. Do you agree with this statement, or have you found a reference in the standard that allows for this? 在设定的泄放压力下，乙酸乙酯将处于超临界流体状态，因此所需泄放质量流量不再依赖汽化潜热，本次算出的所需泄放流通面积也不再适用。你是否认同该观点？或是你是否在相关标准中查到可支持该计算的依据？ 详见06/16回复. Please refer to the reply dated 06/16 for details. Cooling Failure Calculations 4. For the cooling failure calculation, I would suggest using 550kJ/mol rather than 501.48. This is based on Sandwich PSL experience of heats of reaction. 针对冷却失效工况计算，建议将反应热取值由 501.48 kJ/mol 改为 550 kJ/mol。该取值参考了桑威奇工艺安全实验室（Sandwich PSL）过往反应热项目经验。 OK 5. Is the feed flowrate used in the calculation, based on the maximum metering pump capabilities? Do you assume a maximum concentration of reactant in the feed stream? 计算中采用的进料流量，是否按照计量泵最大额定流量取值？计算时是否假定进料流中反应物浓度为最大浓度？ The flow rate used in the calculation is set at the maximum rated capacity of the metering pump, and the maximum reactant concentration is adopted for the feed stream.计算时流量是按照计量泵最大额定流量取值，反应物浓度为最大浓度 06/16：根据文献“Relief Calculation for Supercritical Fluids”计算超临界流体的质量泄放流量，会后向Keith发计算书审核 06/16：Calculate the mass relief flow rate of supercritical fluids in accordance with the document Relief Calculation for Supercritical Fluids, and send the calculation sheet to Keith for review after the meeting. | YES | Chaoqun Hu
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun HU
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. 06/16：06/11已收到审核完成的URS。 06/16：Received the reviewed URS on 06/11. | YES | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith确认CV08也是故障关，可以使用DS6080型，该型号没有5 bar 差压限制。 Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith confirmed that CV08 is also a faulty-close type, the DS6080 model can be used. This model does not have a 5-bar differential pressure limit. Keith offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. 06/02 进展：Habonim厂家反馈了样本资料，反馈可以满足工艺参数需求，货期大概16~20周。可以作为开关阀的备选品牌。 06/02 Progress: "Habonim" manufacturer has provided sample materials that can meet the process parameter requirements. The delivery time is approximately 16 to 20 weeks. It can be an alternative brand for on-off valves. | YES | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. 06/02：关于气液分离器液相出口减压，电子压力阀和自力式减压阀都可以满足使用，首选自力式减压阀。 06/02：For pressure reduction at the liquid outlet of the gas-liquid separator，both electronic pressure valves and self-operated pressure reducing valves can meet the requirements, with self-operated pressure reducing valves being the preferred choice. | YES | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. 05/20：SW已更新完URS并发出。The SW has been updated and the URS has been sent out. | YES | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表数据单。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. 06/23:仪表条件表已更新完成 06/23：The instrument conditions table has been updated and completed. 07/10：仪表数据单已更新完成 07/10：Instrument Data Sheet has been fully updated. | YES | Chaoqun Hu/Yu Gao
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. 05/20：SW已更新完PFD并发出。The SW has been updated and the PFD has been sent out. | YES | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ 4/30：Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? | NO | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted?05/12Decided not to make any adjustments. 05/12确定不做调整。 05/12：It is determined that the height of the catalyst bed in the main reactor will not be adjusted. | YES | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. 06/16：会议澄清：待布局完成后，SW主导完成爆炸危险区域的划分 09/06：Meeting Clarification: SW shall take the lead in completing the classification of hazardous areas for explosion after layout design is finalized. | NO | All
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | YES | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements. | 05/20：与聂博沟通，小试使用的是进口是插底的分离器，生产使用的是侧进的分离器，按会议沟通的气体最大流量0.2Nm³/h，液体最大流量20L/h重新计算了分离器 05/20: Communicated with Nie Bo. The small-scale test used an imported bottom-insertion separator, while the production version used a side-inlet separator. Based on the maximum gas flow rate of 0.2 Nm³/h and the maximum liquid flow rate of 20 L/h for the communication at the meeting, the separator was recalculated.. | YES | Chaoqun Hu
06/02 | IEPE | 管道编号中的管线尺寸一般是指的公称直径，PID中尺寸为10mm的管道是Φ10mm，公称直径为6mm The line size in pipe line designations generally refers to the nominal diameter. In a P&ID, a pipe with a size of 10mm is specified as Φ10mm, corresponding to a nominal diameter of 6mm. | 06/02：会议澄清：DN15以下的管道，管道编号中的管径为外径，DN15及其以上的管道，管道编号中的管径为公称直径。 06/02：Clarification from meeting:For piping below DN15, the size specified in pipe tag number denotes outer diameter; for DN15 and above, the size in pipe tag refers to nominal diameter. | YES | Chaoqun Hu
06/02 | IEPE | 设备BT-01/03/04上的压力变送器不便于现场观察，是否可以考虑也选用WIKA的不带现场显示紧凑型的压力变送器？ The pressure transmitter on the equipment BT-01/03/04 is not convenient for on-site observation. Could it be considered to also choose WIKA's compact pressure transmitter without on-site display？ | 06/02：会上建议保留BT-01/04的现场显示，BT-03可不带现场显示。 06/02：It was suggested at the meeting that the on-site display of BT-01/04 be retained, while BT-03 may not have an on-site display. | YES | Yu Gao
06/02 | CFCT | 1-PID中V-9868，V-9965阀柄的含义？ What is the meaning of valve handles V-9868 and V-9965 in PID? 2-PID中压力变送器底部波纹含义是什么？ What does the corrugation at the bottom of the pressure transmitter signify? 3-与管道直径对应的保温厚度是多少？ What is the insulation thickness corresponding to the diameter of the pipeline? | 06/02： 1.PID中阀门V-9868，V-9965的阀柄为弹簧复位阀柄； In the PID,the valve handles of V-9868 and V-9965 are spring-reset handles； 2.PID中带底部波纹的压力变送器要求压力变送器带隔膜； The pressure transmitter with a bottom ripple in PID requires the pressure transmitter to be equipped with a diaphragm； 3.Keith分享了建议的管道直径与保温厚度表格，直径10到25mm的管路，保温厚度为30-35mm。 Keith shared the recommended pipe diameter and insulation thickness table, with insulation thickness ranging from 30-35mm for pipes with diameters of 10 to 25mm. | YES | ShuangshuangFan
06/16 | SW | 会议确认：气液分离器为侧进，尺寸为DN200*600mm，下次例会前CFCT向SW提供气液分离器的设备图纸 Confirmed at the meeting: The gas-liquid separator adopts side inlet configuration with dimensions DN200 × 600 mm. CFCT shall submit the equipment drawing of the gas-liquid separator to SW prior to the next regular meeting. | 06/22设备图纸已提供。06/23Keith回复意见，见06/23讨论内容。 Equipment drawings were provided on 06/22. Keith's feedback was received on 06/23 — please refer to the discussion notes from 06/23. | YES | Ziliang Zhao
06/17 | SW | 根据最新工作进展并结合HAZOP分析所需文件内容，更新“Sandwich Hydrogenation Implementation Schedule” Update the Sandwich Hydrogenation Implementation Schedule based on the latest progress and document requirements for HAZOP study. |  | NO | All
06/17 | SW | 讨论操作规程：哪些部分需要顺控？开停车步骤等 Discuss operation procedures: identify sections requiring sequence control, including startup and shutdown steps, etc. | 06/23：开车步骤：公用工程确认/催化剂装填→氮气置换（R24-BT01、R24-BT04和剩余部分），氧含量<0.5vol%→氢气置换→原料系统备料→TCU系统调温→反应器进料（氢气先进料背压至反应压力，液相再进料）→气液分离→产品转移 停车步骤：停进料→产品缓冲罐物料转移→反应器卸压→R24-BT03卸压→反应系统降温→氮气置换→关闭氮气和TCU Startup Procedures： 1.Verification of utility systems & catalyst loading 2.Nitrogen purging (for R24-BT01, R24-BT04 and the rest of the system), oxygen content controlled below 0.5 vol% 3.Hydrogen purging 4.Raw material preparation for feed system 5.Temperature adjustment of TCU system 6.Reactor feeding: Introduce hydrogen first to build backpressure up to reaction pressure, then feed liquid phase material 7.Gas-liquid separation 8.Product transfer Shutdown Procedures： 1.Cut off feed supply 2.Transfer materials from product buffer tank 3.Depressurize reactor 4.Depressurize R24-BT03 5.Cool down reaction system 6.Nitrogen purging 7.Shut down nitrogen supply and TCU system Keith提供HAZOP时的开停车步骤，结合上述文件，整理开停车和清洗步骤 Compile the plant start-up, shutdown and cleaning procedures based on the above documents together with the start-up & shutdown sequences supplied by Keith for HAZOP assessment. | NO | All
06/17 | SW | 会后确认：安全阀的泄放温度超过设备的设计温度，是否需要提高设备的设计温度？ To be confirmed after the meeting：If the relief temperature of the safety valve exceeds its design temperature, is it necessary to increase the design temperature rating? | 设备和管线材质为316L，结合设备和管道的壁厚，计算得出：在泄放温度下，材料的许用应力满足其强度要求，不需提高设备的设计温度 The equipment and piping are fabricated from 316L stainless steel. Wall thickness calculations for the equipment and piping demonstrate that the allowable stress of the material satisfies the strength requirements at relief temperature; therefore, no increase to the equipment design temperature is required. | Yes | Ziliang Zhao/Chaoqun Hu
06/17 | SW | CFCT做撬块设计时，注意清洗过程中的低点排净 CFCT shall take full consideration of low-point draining during cleaning when designing the skid package. | 06/23：在撬块设计时，设置管道的低点排净阀 When designing the layout, install a drain valve at the low point of the pipeline 06/23会议方案：管道最低点设置排净阀，操作说明中明确排放时用容器收集排放液体。 Meeting Plant: Install drain valves at the lowest point of the pipeline, and specify in the operating instructions to collect the discharged liquid with a container during the drainage process. | Yes | Shuangshuang Fan
06/17 | SW | CFCT提供放空缓冲罐T06是否放在撬内的方案 CFCT to provide a scheme on whether vent buffer tank T06 shall be installed inside the skid. | 06/23：按照现有空间的布置，T06放在撬块内的空间不足；撬块中间的操作维护通道宽度为300-350mm，能否将整体撬块宽度增加150-200mm？ According to the existing space arrangement, there is insufficient space for T06 to be placed inside the pry block; The width of the operation and maintenance channel in the middle of the pry block is 300-350mm. Can the overall pry block width be increased by 150-200mm? 06/23会议方案：T06不放在撬块内，放置在service area，同时反应柱/冷凝器的TCU出口管路上的温度变送器安装在近出口处，去掉手动球阀，安全阀可放到service area，并设置排净阀，进口管路手动球阀保持不变，温度变送器加套管，位置可前可后，低点设置排净阀，整体管路的高点设置排气阀。 Meeting Plant:: T06 is not placed inside the lever block but in the service area. The temperature transmitter on the TCU outlet pipeline of the reaction column/condenser is installed near the outlet. The manual ball valve is removed, and the safety valve can be placed in the service area. A drain valve is installed, while the manual ball valve on the inlet pipeline remains unchanged. The temperature transmitter is equipped with a protective sleeve, with its position adjustable forward or backward. A drain valve is set at the low point, and an air vent valve is installed at the high point of the entire pipeline. | Yes | Shuangshuang Fan
06/23 | SW | Keith意见： 基本设计：我们是否有经批准的分离器设计方案？我上次看到的摘录中，计算出的容器直径为3毫米，这表明计算或输入数据可能存在错误。 Basic design 1. Do we have an approved design for the separator. The last extract I saw had a calculated vessel diameter of 3mm, which suggests an error in the calculations or input data. | 06/23讨论： 基本设计：按最新设备数据表进行气液分离器设计。气液分离器的计算书已复核过，数据无误。 06/23Discussion—Basic Design: The gas-liquid separator shall be designed in accordance with the latest equipment data sheet. The calculation sheet for the gas-liquid separator has been reviewed and the data are confirmed to be correct. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 分离器内件 1、本设计中是否已考虑分离器内件，例如入口导流装置或入口旋风分离器、气相除雾器、液体出口处的防涡流挡板？ 2、喷淋球能否采用焊接固定方式，而非通过管接头引入容器内部？ 3、喷淋球是否必须为旋转式喷淋球？这会增加设备复杂度，并在工厂运行寿命期内带来检查与维护方面的问题。 4、喷淋球实际能否起到喷淋清洗作用，还是仅仅将容器注满清洗液直至触发高位液位开关？根据此前讨论，从空罐到高位跳闸点的时间不足25秒，这无法为分离器气相侧提供足够的机械清洗作用时间。 Separator internals 1. Have separator internals been considered for this design e.g. inlet diverters or inlet cyclones, demisting of the vapour stream, vortex breakers on the liquid outlet. 2. Can the spray ball be welded in position rather than introducing a tube fitting into the vessel. 3. Does the spray ball need to be a rotary spray ball. This adds complexity and inspection/maintenance issues during the life of the plant. 4. Will the spray ball actually work as a spray ball, or will it simply fill the vessel with cleaning fluid until the high-level switch is activated. Based on previous discussions this would be less than 25 seconds from empty to high-level trip point, which doesn’t allow much time for mechanical cleaning action in the gas side of the separator. | 06/23讨论： 分离器内件： 1、气液分离器设计采用重力式分离，无需额外的内件。 2、喷淋球相关事宜，CN团队内部结合喷淋球供应商商议方案。 06/23 Discussion — Separator Internals: 1.The gas-liquid separator is designed as a gravity-type separator; no additional internals are required. 2.Regarding the spray ball matters, the CN team will internally discuss and determine the solution in coordination with the spray ball supplier. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 设计参数 1、“流体性能”是否应定为“非致命性”？我推测此概念类似于PED容器设计中的流体分组，在英国规范中应属于Group 1气体（即可燃/爆炸/有毒），而非“非致命性”。 2、工作压力应为0至6MPaG。 3、设计温度应至少为150°C，并且我假设在泄压事故工况下，容器温度可能达到约300°C。 4、设计压力应为全真空至9MPaG。 5、规范是否要求进行焊后热处理（PWHT）？ 6、水压试验压力应为设计压力的1.5倍，即13.5MPaG，而非12MPaG。 7、对于该容器，S4应为DN32 Cl900 WN法兰。喷淋球接口是否应作为单独细节在本图纸上表示，还是另页图纸表示更为合适？ 8、充装系数（Fulling Factor）是多少？ Design Parameters 1. Should the ‘Fluid Performance’ be Non-Lethal? I assume this is similar to the fluid group for PED vessel design, which for the UK would be Group 1 gas i.e. flammable/explosive/toxic and not Non-Lethal. 2. The working pressure should be 0 to 6MPaG. 3. The design temperature should be at least 150 °C and I assume the vessel has the potential to reach circa 300°C during a relief event. 4. The design pressure should be FV to 9MPaG 5. Is PWHT required by the code. 6. Hydro test pressure should be 1.5x design pressure i.e. 13.5MPaG not 12 MPaG. 7. For the vessel, S4 should be a DN32 Cl900 WN Flange. Should the spray ball fitting be shown as a separate detail on this drawing or possibly shown on a separate drawing. 8. What is the Fulling Factor. | 06/23讨论： 设计参数 ： 1、介质调整为易爆。 2、CN团队结合URS，修正工作压力，更新设备数据表。 3、可以将泄压事故工况，纳入到常规设计考虑中，即可提高设计温度到300℃。 4、修正设计压力，更新设备数据表。 5、规范可不进行焊后热处理（PWHT）。 6、水压试验压力为设计压力的1.3倍，故试验压力可不做调整。 7、S4为喷淋口，口径为Φ10，DN32法兰接口结构为保证喷淋球可抽出，后续根据喷淋球整体方案做调整，判定是否需要可抽式。 8、充装系数是指物料实际容积与容器全容积之比。 06/23 Discussion — Design Parameters: 1.The medium classification is revised to "explosive." 2.The CN team will revise the working pressure based on the URS and update the equipment data sheet accordingly. 3.The relief event scenario can be incorporated into the normal design considerations — i.e., the design temperature can be raised to 300°C. 4.The design pressure will be revised and the equipment data sheet updated accordingly. 5.PWHT (post-weld heat treatment) is not required per the applicable code. 6.The hydrostatic test pressure is 1.3 × design pressure, so the test pressure does not need to be adjusted. 7.S4 is the spray ball connection, with a bore size of Φ10. The DN32 flange connection is designed to allow the spray ball to be withdrawable. This will be reviewed and adjusted as part of the overall spray ball solution, and a decision will be made on whether a withdrawable type is necessary. 8.The filling factor is defined as the ratio of the actual liquid volume to the total vessel volume. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 通用事项 1、管口方位是否已考虑设备布置的最优化？ 2、在撬装高度限制范围内，容器能否通过重力自由排液至产品收集罐？ 3、在顶部法兰上开孔用于引出管，是否会损害其机械完整性并违反安全规范？是否已重新计算法兰厚度或进行有限元分析（FEA），以确保足够的金属厚度和结构完整性？ 4、液位变送器/液位开关的规格是否已确认？法兰尺寸及位置是否与仪表相匹配？ 5、请更新P&ID，以显示S4正确的管口尺寸。 6、是否有容器设计计算书？技术文件中需要包含设计计算书，并应在FAT（工厂验收测试）时进行核查。 General 1. Does the nozzle orientation allow for optimum equipment layout. 2. Can the vessel free drain into the product collection tank, within the skid height constraints. 3. Does boring a hole in the top flange for the outlet pipe compromise its mechanical integrity and violate safety codes. Have you recalculated the flange thickness/carried out FEA to ensure adequate metal thickness and structural integrity. 4. Has the level transmitter/level switches been agreed – does the flange size/position align with the instruments. 5. Update P&ID to show correct nozzle size for S4. 6. Do you have vessel design calculations. Design calculations will be required in the technical file and should be checked at FAT. | 06/23讨论： 通用事项 ： 1、管口方位已结合3D撬装布置给定。 2、3D撬装设计已考虑，待3D模型复核时，详细讨论。 3、重新计算法兰厚度，以满足结构强度要求。 4、仪表工程师已经确认复核。 5、P&ID，不需要更改S4管口尺寸。 6、设计计算书是设备完整技术文件中必不可少的一部分，后续会提供。 06/23 Discussion — General Items: 1.Nozzle orientation has been determined based on the 3D skid layout. 2.The 3D skid design has taken this into consideration; detailed discussion will be held during the 3D model review. 3.The flange thickness will be recalculated to meet structural strength requirements. 4.The instrumentation engineer has confirmed and verified this. 5.The P&ID does not require changes to the S4 nozzle size. 6.The design calculation sheet is an essential part of the complete technical documentation for the equipment and will be provided in due course. | YES | Ziliang Zhao/Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Overall cleaning philosophy per vessel 各容器整体清洗策略 Please confirm the intended cleaning philosophy for each vessel in the skid — spray-only, soak-only, spray-and-soak combined, or an alternative approach. Please also indicate whether a single philosophy applies across all vessels or whether the strategy varies by vessel. 请确认撬块内各台容器的清洗策略：单独喷淋、单独浸泡、喷淋+浸泡组合，或其它方式。请同时说明是否所有容器采用同一策略，或按容器区别设计。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleanliness verification method & acceptance criteria 清洁度验证方法与验收标准 Please advise the verification method(s) used to confirm cleaning completion (visual inspection, swab / rinse sample analysis, mass balance, calculated residue, etc.) and the numerical acceptance criteria applied (e.g. residue mass, ppm concentration threshold). 请说明用于确认清洗完成的验证方法（目视检查 / 拭子或冲洗样分析 / 物料衡算 / 残余物计算等），以及所采用的数值验收标准（如残余物质量、浓度阈值 ppm）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Sight glass availability for SE01 SE01 视镜配置 The reactor vessels are understood to be fitted with sight glasses to support visual verification of cleanliness. The gas–liquid separator SE01, however, does not include a sight glass. Please confirm the intended method for verifying cleanliness on SE01. 反应柱已配置视镜以支持目视清洁度检查，但气液分离器 SE01 未配置视镜。请确认 SE01 清洁度验证的具体手段（，以及是否考虑将新增视镜作为设计变更纳入）。 | 07/10：反应柱和分离器因为操作压力高，无法配置视镜，清洁度的验证无法依靠目测，需取样分析测量残留物的浓度 07/10：Due to the high operating pressure of the reaction column and separator, sight glasses cannot be installed. Visual inspection is therefore not feasible for cleanliness verification, and residue concentration shall be determined via sampling analysis instead. | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Spray ball flow rate vs. vessel fill time 喷淋球流量与容器充液时间的匹配 The lowest available spray ball flow rate (approximately 2 L/min) results in SE01 reaching the high-level trip point in under 25 seconds. This limits the time window in which mechanical spray action can achieve wetting coverage. Please advise the intended cleaning-time window on SE01 and the approach for ensuring adequate mechanical cleaning action within the design constraint. 现有最小可选喷淋球流量约 2 L/min，导致 SE01 容器在 25 秒内即达到高液位跳停，机械喷淋作用的有效时间窗口非常短。请说明 SE01 上预期的清洗时间窗口，以及在此设计约束下如何确保获得充分的机械清洗作用。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Drain line sizing and fill–drain cycle 排放管径与充液-排空循环 Under the current drain line configuration, the drain rate is significantly slower than the spray inflow rate. Please advise the intended drain line diameter (whether upsizing is planned), the estimated single-cycle fill and drain durations, and the number of cycles anticipated per cleaning campaign. 当前排放管径下，排放速率显著慢于喷淋进料速率。请说明拟采用的排放管径（是否放大）、单次循环的充液和排空时间估算，以及每次清洗预期需要的循环次数。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Soak cleaning vs. high-level interlock defeat mechanism 浸泡清洗与高液位联锁绕过机制 If soak cleaning is adopted on SE01, the liquid level during cleaning will exceed the high-level safety interlock (located at approximately one-third of vessel height). Please specify: (a) the physical mechanism intended for defeating this interlock during cleaning (key switch, procedural lockout, or other); (b) the authorisation and access controls surrounding the defeat mechanism; and (c) the safeguards against inadvertent defeat during normal processing operation. 若 SE01 采用浸泡清洗，清洗过程中的液位将超过位于容器约 1/3 高度的高液位安全联锁。请说明：(a) 清洗时用于绕过（defeat）该联锁的物理机制（钥匙开关 / 程序锁定 / 其它）；(b) 该绕过机制的授权与权限控制方式；(c) 防止正常运行时意外绕过的保护措施。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleaning of the guided-wave level transmitter housing Guided wave 液位变送器外壳的清洁 The guided-wave level transmitter housing (approximately 100 mm diameter, side-mounted on SE01) sits above the high-level switch and lies outside the spray ball coverage envelope. Please advise the intended cleaning approach for this housing, and any mechanical or procedural provisions required to ensure it can be cleaned to the acceptance criteria in Q1.2. 液位变送器外壳（约 100 mm 直径，SE01 侧接管上）位于高液位开关之上，不在喷淋球覆盖范围内。请说明该外壳的清洁方案，以及为达到 Q1.2 中的验收标准所需的机械或程序性措施。 | 07/14：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用 07/14：Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. | NO | Chaoqun Hu/Yu Gao
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Reactor cleaning cycle time and manual interventions 反应器清洗循环时间与人工干预 For the 200-L reactor vessels, a single spray-and-drain cycle involves an extended drain phase relative to the spray phase. Multiple cycles are expected to achieve the required cleanliness. Please advise: the anticipated number of cycles, the total cleaning duration per campaign, and the specific manual interventions required at each step (drain valve operation, sample point access, lockout re-set, etc.). 200-L 反应器进行单次"喷淋-排空"循环时，排空阶段远长于喷淋阶段，需多次循环以达到清洁度要求。请说明：预期循环次数、每次清洗总时长，以及各步骤所需的具体人工干预（排放阀操作 / 取样口操作 / 联锁复位等）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW 3D Layout 3D 布置与设备空间 | Operational access clearance 操作通道净空 The current 3D model shows approximately 300–350 mm clearance in certain operator access zones. Please confirm the target minimum clearance from a site operability and maintenance standpoint, and identify any specific zones where relaxation of the current clearance is acceptable, or where additional clearance is required. 当前 3D 模型显示部分操作人员通道净空约为 300–350 mm。请从现场操作与维护角度，确认目标最小净空要求，并识别可以放宽的具体区域，以及需要额外净空的区域。 | 7月10日反馈进展： 建议增加反应柱撬块的宽度，审核模型后给出建议的空间区域。 It is recommended to increase the width of the reaction column skid and provide the suggested spatial area after reviewing the model. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Free-drain feasibility from each vessel 各容器的自重排放可行性 The cleaning strategy relies on free-drain of cleaning fluid from each vessel into downstream collection (BT04 or equivalent). Considering the skid height constraint and each vessel elevation, please confirm the free-drain path is mechanically feasible from each source vessel to its destination. Please identify any vessels where drainage cannot be achieved by gravity and would require pumping or an alternative arrangement. 清洗策略要求清洗液自重从各容器排入下游收集罐（BT04 或等效容器）。考虑撬块高度限制与各容器标高，请确认每台源容器至其目标容器的自重排放路径机械可行。请识别无法通过重力实现排放、需要泵抽或采用替代方案的容器。 | 7月10日反馈进展： 根据目前容器的结构形式，反应柱可通过底部排放阀排放，缓冲罐可通过管路排放，预热器、冷凝器管路无排放口。具体排放方式参考清洗方案。 Based on the current structural design of the containers, the reaction column can be drained through the bottom discharge valve, the buffer tank can be discharged via piping, while the preheater and condenser have no discharge outlets in their pipelines.Refer to the cleaning plan for specific emission methods. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Nozzle orientation on pressure vessels 压力容器管嘴方位 Please review the nozzle orientation on all pressure vessels in the current 3D model. Confirm that nozzle positions provide adequate access for external piping tie-in, instrumentation installation, and maintenance (removal / reinstallation of internals, gasket replacement, catalyst service, etc.). 请审查当前 3D 模型中所有压力容器的管嘴方位。确认管嘴位置能够满足外部管路对接、仪表安装以及维护（内构件拆装 / 密封垫更换 / 催化剂检维修等）的空间要求。 | 7月10日反馈进展： 由于空间尺寸限制，部分管口的维护可能存在不便。优化管口布置或能否增加设备空间。 Due to space size limitations, maintenance of some pipe openings may be inconvenient. Optimize pipe layout or increase equipment space | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Catalyst charging & discharging arrangement 催化剂加料与卸料布置 Please confirm that the catalyst charging (loading) and discharging (unloading) arrangement is compatible with the current nozzle layout on the reactor vessels, and that adequate space is provided for charge / discharge equipment and operator access during catalyst service. 请确认催化剂加料与卸料的操作方式与当前反应柱的管嘴布置兼容，且在催化剂检维修期间为加料/卸料设备与操作人员留有充足空间。 | 7月10日反馈进展： 根据目前的布置方案，反应柱加料卸料口均在撬体端面，结合加料卸料方式看操作空间是否充足。 According to the current layout plan, the feeding and discharging ports of the reaction column are all located on the end face of the pry body. Considering the feeding and discharging methods, it is necessary to check whether the operating space is sufficient. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Tie-in points between skid and site utilities 撬块与现场公用工程接口 Please confirm the finalised location and specification of all tie-in points between the skid and the Sandwich site services, including process feed, product outlet, vent header, HTF supply and return, N₂ blanketing, instrument air, electrical supply, cable penetrations, and drain. Please advise the interfaces where design lock-down is still pending. 请确认撬块与 Sandwich 现场公用工程之间所有接口的最终位置与规格，包括工艺进料、产品出口、放空总管、导热油供回、氮气钝化、仪表空气、电气供应、电缆穿墙、排放。请说明尚未定稿的接口。 | 7月10日反馈进展： 根据现有的布置方案，有部分公用工程的的接口，无仪表空气接口，电气供应、电缆穿墙，后续更新撬块与公用工程接口的位置与规格。 According to the existing layout plan, there are interfaces for some public works without instrument air interfaces, electrical supply, and cable penetration through walls. The location and specifications of the interface between the pry block and the public works will be updated in the future. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Cable wall penetration capacity and cable compatibility 穿墙电缆孔容量与电缆兼容性 The current design indicates 14 available cable wall penetration slots. Please confirm this final count, the internal diameter of each slot, and the compatibility of the slot with the largest cable type intended to pass through (multi-core, armoured, or shielded cables of relevant cross-section). 当前设计显示可用穿墙电缆孔 14 个。请确认该数量的最终定案、每个孔的内径规格，以及与拟穿过的最大电缆类型（相应截面的多芯 / 铠装 / 屏蔽电缆）的兼容性。 | 寻求工程部支持，和宋小旭主管约会讨论如何推进，7月10日反馈进展 | NO | Dezhi meng/Shaofeng gao
07/01 | SW Control Philosophy 控制策略 | Full Control Philosophy document issue date 完整《控制策略》文件发出日期 Please advise the target issue date for the complete Control Philosophy document, superseding the interim draft version previously circulated. 请说明完整版《控制策略》文件的目标发出日期（覆盖此前流转的过渡草稿版本）。 | 07/10：已完成初版，还在校核中，预计下周发出 07/10：The initial draft has been completed and is under review; it is expected to be issued next week. | NO | Chaoqun hu
07/01 | SW Control Philosophy 控制策略 | Interlock schedule — hardwired vs. software 联锁清单 —— 硬件联锁与软件联锁 Please provide a complete interlock schedule listing all safety interlocks, with clear delineation between hardwired (independent of the PLC) and software (PLC-implemented) interlocks. For each interlock, please include: initiating cause, sensing element, trip setpoint, action taken, and protective function fulfilled. 请提供完整的联锁清单，列出全部安全联锁，明确区分硬件联锁（独立于 PLC）与软件联锁（PLC 实现）。每一条联锁请包含：触发原因、检测元件、跳停设定值、联锁动作、承担的保护功能。 | 07/10：联锁条件已完成初版，还在校核中，预计下周发出 07/10：The initial draft of interlock conditions has been completed and is under review, which is expected to be issued next week. | NO | Chaoqun hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Operational modes and mode-specific fail positions 操作模式与各模式下的故障位 Please define all operational modes of the skid (normal operation, start-up, shut-down, cleaning, catalyst change, emergency depressurisation, etc.), and for each mode specify: (a) the fail position of each control valve; (b) the state of each interlock (active / bypassed); and (c) the permissive conditions required to enter that mode. 请定义撬块的全部操作模式（正常运行 / 开车 / 停车 / 清洗 / 催化剂更换 / 紧急泄压等），并针对每一模式说明：(a) 每个控制阀的故障位；(b) 每个联锁的状态（激活 / 已绕过）；(c) 进入该模式所需的许可条件。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 分离器浸泡清洗时易触发液位高联锁，导致高液位以上清洗不彻底。增大分离器的排净管径可实现淋洗，同时系统处于清洗模式时，绕开液位高联锁。 High level interlock is prone to tripping during soaking cleaning of the separator, leading to inadequate cleaning of areas above the high liquid level. Increasing the drain pipe size of the separator allows shower rinsing. Meanwhile, the high level interlock can be bypassed when the system is under cleaning mode. | NO | Chaoqun hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Mode-transition safeguards 操作模式切换的保护措施 Please advise the safeguards in place against inadvertent mode transitions, particularly from cleaning mode back to processing mode (e.g. an interlock bypass being left in place after cleaning is complete). Please describe both the technical safeguards (key switches, HMI confirmations) and the procedural safeguards (SOP requirements, dual sign-off). 请说明防止意外切换操作模式（尤其是从清洗模式返回处理模式时联锁绕过未复位）的保护措施。请分别描述技术性保护措施（钥匙开关 / HMI 确认）与程序性保护措施（SOP 要求 / 双签发）。 | 52条和Keith讨论后1周反馈。 | NO | Dezhi meng
07/01 | SW Sampler System 取样系统 | Sample vaporisation during pressure reduction 取样过程中的样品闪蒸 The sampler transfers process fluid from a line operating at up to 60 barG to a sample container at approximately atmospheric pressure. Please advise the analysis of vaporisation during this pressure reduction (fraction vaporised, temperature drop) and its impact on the compositional representativeness of the collected sample. 取样器将最高 60 barG 工艺管路的介质转移至常压取样瓶。请说明此压降过程中的闪蒸分析（气化比例、温度降低）及其对所采样品成分代表性的影响。 | 07/10：冷凝器出口的温度为30℃，压力从60barG 泄至常压，此温度条件下不会发生闪蒸 07/10：The temperature at the condenser outlet is 30°C. The pressure is relieved from 60 barG to atmospheric pressure, and no flashing will occur under this temperature condition. | NO | Chaoqun hu
07/01 | SW Sampler System 取样系统 | Sample retention design 样品截留设计 Please advise the design of the sample bottle and sample-transfer system, including any vapour trap, septum, condenser, or other retention device intended to prevent loss of volatiles through the vent path and to ensure a representative liquid sample is captured. 请说明取样瓶及取样传输系统的设计，包括为防止挥发组分从放空路径流失、并确保获得代表性液样所采用的蒸汽阱、隔膜、冷凝器或其它截留装置。 | 07/10：取样器的流程：打开三通阀将缓冲罐充满，打开缓冲罐气相放空管线阀门，将缓冲罐中的气相排走并卸压，打开氮气手阀，将缓冲罐中的液体压至取样瓶 07/10：Sampling procedure: Open the three-way valve to fill the buffer drum. Open the valve on the vapor vent line of the buffer drum to vent the vapor inside and relieve pressure. Then open the nitrogen manual valve to pressurize and transfer the liquid from the buffer drum into the sampling bottle. | NO | Chaoqun hu
07/01 | SW Sampler System 取样系统 | Sampler behaviour under gas-rich flow regime 气相主导流态下取样器行为 With the intended process operating at a stoichiometric excess of hydrogen, the flow regime through the sampling point may be gas-rich with entrained liquid rather than liquid-continuous. Please advise how the sampler design accommodates this flow regime, and whether any sample point relocation, phase separator, or coalescer is being considered. 工艺预期在化学计量氢气过量条件下运行，取样点处流态可能为"气相夹带液体"而非液相连续。请说明取样器设计如何适应此流态，以及是否考虑取样点位置调整、加装相分离器或聚结器。 | 07/10：取样器的缓冲罐上有气体排放管线，取样罐充满后，打开气体排放管线，将气相排走并卸压，再用氮气将液相压至取样瓶 07/10：The buffer vessel of the sampler is equipped with a gas vent line. Once the sampling tank is full, open the gas vent line to vent the vapor phase and relieve pressure, then push the liquid phase into the sampling bottle with nitrogen. | NO | Chaoqun hu
07/01 | SW Instrumentation 仪表配置 | Guided-wave level transmitter — datasheet & cleanability Guided wave 液位变送器 —— 数据单与可清洁性 Please provide the guided-wave level transmitter datasheet and confirm: (a) the process compatibility of the probe assembly with the intended service (including any operating conditions in the supercritical or near-critical regime); and (b) the cleanability of the probe assembly under the adopted cleaning philosophy. 请提供 guided wave 液位变送器数据单，并确认：(a) 探头组件在拟定工况（含超临界或近临界工况）下的适用性；(b) 探头组件在拟采用清洗策略下的可清洁性。 | 7月10日反馈进展 (a) 导波雷达液位计工作原理是雷达波可以穿过介电常数较低的气相，遇到介电常数较大的液相返回，从而计算液位。适用蒸汽、粉尘、泡沫等工况。需了解超临界工况下的介质状态是否还存在液相，如果没有液相空间，则液位计无法识别。 The working principle of the guided-wave radar transmitter is that the radar wave can pass through the gas phase with a lower dielectric constant and return to the liquid phase with a larger dielectric constant, thereby calculating the liquid level. It is applicable to working conditions such as steam, dust and foam. It is necessary to understand whether there is still a liquid phase in the medium state under supercritical conditions. If there is no liquid phase space, the transmitter cannot identify it. 07/15进展：经内部评估，液位计所在容器操作工况下不存在超临界状态。 After internal assessment, it was determined that the liquid level gauge is not in a supercritical state under the operating conditions of the container it is located in. (b)BT01和BT04的导波雷达液位计为顶装内伸形式，可以利用设备内的喷淋头冲洗。SE-01的导波雷达液位计为侧装旁通式，可以选择在探头与旁通管的过程接口处增加配套冲洗环，并预留一路冲洗管线。 The guided-wave radar transmitters of BT01 and BT04 are top-mounted and iInsert type, and can be flushed by the spray heads inside the equipment. The guided-wave radar l transmitter of SE-01 is of side-mounted bypass type. A matching flushing ring can be added at the process interface between the probe and the bypass pipe, and a flushing pipeline can be reserved. 07/14进展：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用. Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. 07/17进展：气液分离器雷达液位计侧装改顶装，已完成图纸设计，筒体直径未变，邮件发出。 The radar level gauge for the gas-liquid separator has been redesigned from side-mounted to top-mounted. The drawing design has been completed, and the vessel diameter remains unchanged. The drawings have been sent out via email. | NO | Yu gao/Chaoqun hu/Zilaing Zhao
07/01 | SW Instrumentation 仪表配置 | Level switch position & interlock function 液位开关位置与联锁功能 Please confirm the finalised position (elevation, orientation, flange size and rating) and the interlock function of each level switch (LSL, LSLL, LSH, LSHH) on each vessel, together with the matching instrument selection. 请确认每台容器上各液位开关（低 LSL、低低 LSLL、高 LSH、高高 LSHH）的最终位置（标高、方位、法兰尺寸与压力等级）与联锁功能，以及对应的仪表选型。 | 7月10日反馈进展： 关于液位开关选型，之前寻价时只有VEGA的VEGASWING 63型号可以满足DN25 Class900 M的过程接口，其他厂家如E+H、Rosemount都不能满足。 About the selection of level switches, during the previous price search, only VEGA's VEGASWING 63 model could meet the DN25 Class 900 M process connection requirements. Other manufacturers such as E+H and Rosemount could not meet these requirements. 07/15联锁值详见联锁条件表。The interlock values on 07/15 can be found in the interlock condition table. | NO | Chaoqun hu/Yu gao
07/01 | SW Instrumentation 仪表配置 | Instrument datasheet next revision date 仪表数据单下一版本发出日期 Please advise the target issue date for the next revision of the Instrument Datasheet, reflecting the current SE01 design (post demister-configuration decision), the finalised interlock schedule, and the level switch position confirmation. 请说明反映当前 SE01 设计（demister 配置定稿后）、最终联锁清单以及液位开关位置确认的仪表数据单下一修订版本的目标发出日期。 | 7月10日反馈进展 仪表数据表已完成修订版，待意见讨论后看是否还需修改参数。 The instrument datasheet has been revised. After the discussion of opinions, we will see if the parameters still need to be modified. | NO | Chaoqun hu/Yu gao
07/01 | SW Documentation Status 文档状态 | Current revision and next revision date of key deliverables 主要交付文件的当前版本与下一版本时间 Please confirm the current issued revision and the target date for the next revision of the following documents: • PFD • P&ID • URS • Equipment Datasheets • Control Philosophy • Instrument Datasheet • Operating Instructions • Cleaning Procedure • Vessel Design Calculation Package. 请确认以下文档的当前已发版本与下一修订版本的目标日期： · PFD · P&ID · URS · 设备数据单 · 控制策略 · 仪表数据单 · 操作说明 · 清洗程序 · 容器设计计算书。 | 7月10日反馈进展，操作手册还在编制中，其他设计文件已完成。On July 10th, we provided the progress update. The operation manual is still under preparation, while the other design documents have been completed. | NO | Shaofeng gao/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R1] Design Temperature — Vessel could fail during relief event. Equipment design temperature is specified for process requirements and does not consider elevated temperatures during relief events when short-term temperature increase has the potential to exceed the design temperature. 设计温度 —— 容器可能在泄放事件中失效。设备设计温度是按工艺需求设定的，未考虑泄放事件中的短时温升可能超过设计温度的情形。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：已更新数据表，提高设计温度，以满足工艺需求，图纸已升级。 07/10: Data sheet updated with elevated design temperature to meet process requirements; drawings revised accordingly. | YES | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register Engineering Design 工程设计 | [R2] Design Requirements — L:G ratio for plant is not clearly defined. Equipment design could result in very limited operating ranges and incorrect assumptions in plant capability and relief design. 设计条件 —— 装置的液气比（L:G ratio）未明确定义。可能导致设备设计的操作区间受限，以及在装置能力和泄放设计中做出错误假设。 | 7月10日反馈进展，根据最终确定的反应器尺寸核实气液比数据。On July 10th, the progress was reported. The gas-liquid ratio data was verified based on the final determined reactor size. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Engineering Design 工程设计 | [R3] Design Requirements — Catalyst specification is not available. Design may not be suitable for some catalysts. Dusty catalysts could cause blockages. 设计条件 —— 催化剂规格未明确。设计可能不适用于某些催化剂；含粉尘的催化剂可能导致堵塞。 | Keith / SW response: Design philosophy is based on catalyst beads/pellets which are dust-free, non-flammable and have exposure levels requiring OEB 3 or lower containment. Note: OEB 3 containment is a deviation from the URS and requires acceptance. Keith / SW 答复： 设计基于无粉尘、非燃、暴露等级 OEB 3 或更低的颗粒/粒状催化剂。注：OEB 3 的密闭要求相对 URS 存在偏离，需要接受确认。 | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Engineering Design 工程设计 | [R4] Access — Layouts are not available to assess whether access to equipment is acceptable for operations and maintenance. 通道 —— 布置图尚未提供，无法评估设备的操作与维护通道是否满足要求。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.1 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R5] Maintenance — Lifting Aids (davit arms, lifting beams, etc.) have not been considered in design, with potential for injury to maintenance personnel removing heavy equipment for servicing / repair / replacement. 维护 —— 设计中尚未考虑起重辅助设施（吊臂、起吊梁等），维护人员在拆卸重型设备进行检修 / 修理 / 更换时可能存在人身伤害风险。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R6] Lighting — Layouts are not available to assess whether lighting for routine operations and maintenance activities is acceptable. 照明 —— 布置图尚未提供，无法评估日常操作和维护活动的照明条件是否满足要求。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R7] System leak detection — Pressure testing of high-pressure system will be hydraulically tested. Hydraulic testing demonstrates mechanical strength of the pressure system but does not demonstrate integrity for a hydrogen system. 系统检漏 —— 高压系统将进行水压试验。水压试验只能证明压力系统的机械强度，无法证明氢气系统的密封完整性。 | Keith / SW response: Helium testing is not routinely carried out in China. Keith / SW 答复： 国内通常不常规进行氦气检漏。 可以做气密性试验；国内整橇系统气密性试验后，分体运至英国，进入工厂房间后，再次组装，需重新进行泄漏试验，现场是否具备试验条件？现场可进行氦气检漏。 和CE认证机构确认一下具体方案。 A pneumatic test can be performed. After the complete skid system undergoes the pneumatic test in China, it will be shipped in split form to the UK. Upon arrival at the factory site and reassembly, a new leak test will be required. We need to confirm whether the site has the necessary conditions/facilities for this test. Helium leak detection is available on site. We will confirm the specific plan with the CE Notified Body. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R8] Line sizing / specification — Vents / headers incorrectly sized / specified, resulting in high back pressure and safety / operability issues, e.g. two-phase flow in emergency vent relief header. 管线规格 / 尺寸 —— 放空 / 泄放总管尺寸或规格不正确，导致背压过高及安全 / 可操作性问题，例如紧急泄放总管中出现两相流。 | 07/10：安全阀进出口尺寸详见P&ID 07/10：Refer to the P&ID for the inlet and outlet sizes of the safety valve. | NO | Chaoqun hu
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R9] Insulation — Insulation requirements not specified, which could result in equipment / pipe layout not allowing space for insulation to be installed. 保温 —— 保温需求尚未明确，可能导致设备 / 管路布置未预留保温安装空间。 | Confirm the insulation material with Keith and determine the thickness. Once it's confirmed, provide a progress report on July 10th. 和Keith确认下保温材料，然后确定厚度。确定后，7月10日反馈进展 3D模型中管路的间距已按照保温厚度30-35mm预留了保温的安装空间。 The spacing between pipes in the 3D model has been designed to accommodate an insulation installation gap of 30-35mm, as per the insulation thickness requirements. | NO | Yinghui cheng/Chaoqun hu/Shuangshuang fan/Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R10] Modular design — Modular design could introduce significant increase in site construction activities, e.g. mechanical and EC&I installation and subsequent testing. 模块化设计 —— 模块化设计可能大幅增加现场施工工作量，例如机械与电控仪表安装及后续测试。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 现有模块化设计的方案是根据进口电梯的尺寸，将整套设备拆分为4个撬块运输组装。 SW建议：需再考虑从屋顶直接吊装进去的方案，需要在后续周三会上进一步讨论。 The current modular design solution involves dividing the entire set of equipment into four skids for transportation and assembly based on the dimensions of imported elevators. SW Recommendation: Further consideration is needed for the direct hoisting-in-from-the-roof solution, which will be discussed in the upcoming Wednesday meeting. | NO | Chaoqun hu/Shuangshuang fan
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R11] Skid assembled on site could result in CE / UKCA Responsible Person / Authorised Representative in China not being able to issue Declaration of Conformity for Skid Package. 撬块在现场组装可能导致中国境内的 CE / UKCA 负责人 / 授权代表无法为撬块整机签发符合性声明（Declaration of Conformity）。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 与CE认证方沟通确认好细节，特别是认证机构是否需要到UK现场验证，再发证。 We will communicate with the CE Notified Body to confirm all the details, in particular whether the certification body needs to attend the UK site for verification prior to issuing the certificate. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R12] Wall penetrations — Layouts and cable schedules not available to confirm space is available for pipe / cable penetrations to / from R23 Module. 穿墙孔 —— 布置图和电缆清单尚未提供，无法确认与 R23 模块之间的管道 / 电缆穿墙位置有足够空间。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.6 | The initial cable schedule of CIMT is not fully aligned with the SW plan. SW has sent SLD, CIMT is verifying design discrepancies and will feed back comparison results, followed by discussions with SW CIMT初版线缆计划与SW计划没有完全匹配，SW已发出单线图，CIMT核对设计差异，返回对比结果，再与SW讨论。 7/23：CIMT根据SW提供的单线图，更新了电缆数量。部分流量控制器电缆待确认。硬联锁开关阀点位本安/隔爆待确认。 7/23：CIMT update the cable quantity based on the SLD provided by SW. some cables are still pending confirmed, 1. for flow controllers(modbus or 4-20mA). 2. for HW interlock on-off valve(I.S. or Ex d) | NO | Dezhi meng
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R13] Catalyst charge point — Inlet pipe diameter is small and blockages may occur. 加料口 —— 加料管径较小，可能发生堵塞。 | Keith / SW response: Inlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking inlet pipe. Keith / SW 答复： 加料接口已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞加料管的风险。 | YES
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R14] Catalyst physical property requirements (size, shape, packing, etc.) are not defined, with the potential for incompatible catalyst to be charged to the reactors. 催化剂物性要求（粒径、形状、装填密度等）尚未定义，存在向反应器加入不兼容催化剂的风险。 | 07/10：催化剂直径0.5mm-5mm，形状不重要，球形，圆柱形，不规则颗粒状都可以，装填密度一般0.5g/mL来估算，但催化剂强度要高，不容易破碎起粉 07/10：The catalyst particle diameter ranges from 0.5 mm to 5 mm, with no specific shape requirement; spherical, cylindrical and irregular granular forms are all acceptable. The bulk density can be estimated at 0.5 g/mL in general. Meanwhile, the catalyst shall feature high mechanical strength to avoid fragmentation and dust generation. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R15] Packing of catalyst is not controlled, with the risk of reactants / gas channelling in the continuous reactor column, and the potential for incomplete reaction or impurities forming. 催化剂装填未受控，存在反应物 / 气体在连续反应柱内形成沟流的风险，可能导致反应不完全或杂质产生。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R16] Contained charge system design not available to assess risks and / or design limitation. 密闭加料系统的设计尚未提供，无法评估其风险与设计局限。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R17] Manual handling requirements for catalyst charging not assessed. 催化剂加料的人工搬运需求尚未评估。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R18] Access to charge point and support of charge container / bag not designed (access steps / integrated support shelf). 加料口的通道以及加料容器 / 料袋的支撑尚未设计（例如操作台阶、集成支撑架）。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R19] 20-micron catalyst retaining screen — Screen blockages prevent / limit flow of gas / reaction mix to continuous reactors. 20 微米催化剂拦截筛 —— 拦截筛堵塞会阻止 / 限制气体 / 反应液流入连续反应器。 | Keith / SW response: China Operations have reported blockages occur in local plant and screen has been removed and discarded. Keith / SW 答复： 国内运行反馈已在本地装置中发生堵塞，已将拦截筛拆除并弃用。 | YES
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R20] Polishing filter (FTR9832) — Filter blockages prevent / limit flow of gas / reaction mix through continuous reactors. Pressure increases in reactor system, with potential for undesirable reactions to occur, until reactor high-pressure trip is activated. 精滤器 (FTR9832) —— 滤芯堵塞会阻止 / 限制气体 / 反应液流经连续反应器；反应器压力升高，直到触发高压跳停前可能发生副反应。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 待定/To be determined | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register CR01 – CR03 Reactors CR01 – CR03 反应器 | [R21] Temperature control — Jacket temperature control is configured to control jacket temperature only. Reactor internal temperatures are monitored, but no control, alarms or interlocks are configured for process control. 温度控制 —— 夹套温度仅控制夹套温度本身。反应器内部温度虽被监测，但未针对工艺过程配置控制、报警或联锁。 | Keith / SW response: Scale-up provides large operating envelopes for process temperature requirements and additional control, alarms and interlocks are not required. Keith / SW 答复： 由于放大试验提供了较大的工艺温度操作裕度，无需增加额外的控制、报警或联锁。 | YES
07/02 | SW - Risk Register System Pressure Monitoring 系统压力监测 | [R22] Differential pressure monitoring — Accuracy of static pressure measurements may not enable differential pressures to be calculated with any degree of accuracy or certainty. 差压监测 —— 静态压力测量精度可能不足以支持差压计算达到所需的精度或置信度。 | 通过反应柱上和反应器进出口管线上的的压力变送器精度估算，最大差压误差大约为40kPa。 Based on the accuracy estimation of the pressure transmitters on the reaction column and the inlet/outlet pipelines of the reactor, the maximum differential pressure error is approximately 40kPa. 07/14压力也增加了联锁。The pressure also increased the interlock. | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register Over Pressure Protection 过压保护 | [R23] Relief system design — Pressure systems not identified and relief studies not available. Identification of worst-case relief scenario not identified, and relief streams may be incorrectly categorised. Details of maximum reaction exotherm not fully documented. 泄放系统设计 —— 压力系统尚未识别、泄放研究尚未提供。最坏工况泄放情景未识别，泄放物流可能被错误归类。反应最大放热的详细信息尚未完整记录。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：详见安全阀计算书 07/10：See safety valve calculation sheet for details. | NO | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R24] Vessel design — Complete degassing of product stream not achieved, with the potential for hydrogen carry-over into BT04 and product transfer containers. 容器设计 —— 产品物流未实现完全脱气，H₂ 可能带入 BT04 及产品转运容器。 | 07/10：气液分离器满足气液分离的要求 07/10：The gas-liquid separator meets the requirements for gas-liquid separation. | NO | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R25] Cleaning of separator not fully understood but current concept relies on vessel free-draining to BT04. Current spray ball sizing is not consistent with this approach and may require significant rework to process piping. 分离器清洗方案尚未完全明确，当前概念依赖容器向 BT04 的自重排放。现有喷淋球规格与该思路不匹配，可能需要对工艺管路进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.4,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register Separator 气液分离器 | [R26] Cleaning of LIT003 housing does not appear to be considered in design. LIT003 液位变送器外壳的清洗在设计中似乎尚未考虑。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.7 | 同上42行回复/Translation of the 42nd line above. | NO | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R27] P&ID does not clearly show nozzle locations and could lead to mal-ops / misunderstanding of the design intent by the Operations team. P&ID 上未清晰标注管嘴位置，可能导致运行团队误操作或误解设计意图。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.3 | 07/10：已标注，详见P&ID 07/10：Marked as indicated; refer to the P&ID for details. | NO | Chaoqun hu
07/02 | SW - Risk Register Sampling 取样系统 | [R28] Sampler design — When depressurising the sample collection chamber, high gas or vapour vent rates could result in a bubbly or churn-turbulent flow regime, and sample will discharge to vent line as two-phase flow. 取样器设计 —— 对取样收集腔进行减压时，气体或蒸汽的高排放速率可能形成鼓泡或搅动湍流流态，样品将以两相流形式排入放空管。 Related Outstanding Questions ｜ 关联待澄清问题：Q5.1 | 07/10：缓冲罐静置一定时间，让气液分层，泄压时缓慢打开手阀 07/10：Allow the buffer tank to stand for a certain period for vapor-liquid stratification, then open the manual valve slowly during depressurization. | NO | Chaoqun hu
07/02 | SW - Risk Register Sampling 取样系统 | [R29] With significantly more gas being present in the process stream, what will prevent overpressure of sample bottle and low-pressure nitrogen pipework? 由于工艺物流中气体明显较多，采用什么措施来防止取样瓶和低压氮气管路的超压？ | 07/10：取样瓶和氮气管线投用时，系统已泄压至常压 07/10：The system has been depressurized to atmospheric pressure prior to commissioning of sampling bottles and nitrogen pipelines. | NO | Chaoqun hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R30] Catalyst Discharge Plug valve — Outlet pipe diameter is small and blockages may occur. 催化剂卸料闸阀 —— 出口管径较小，可能发生堵塞。 | Keith / SW response: Outlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking outlet pipe. Keith / SW 答复： 出口接管已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞出口管的风险。 | YES
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R31] Contained discharge system design not available. Layout design may not provide sufficient headroom for contained discharge system. 密闭卸料系统的设计尚未提供。当前布置可能无法为密闭卸料系统提供足够的顶部空间。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R32] Complete removal of catalyst during discharging operations is unlikely to remove 100% of the material, with the risk of cross contamination of catalyst material between campaigns. 卸料操作难以完全（100%）清除催化剂，存在批次间催化剂交叉污染的风险。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R33] CIP Design — CIP design incomplete. Initial spray ball sizing is inconsistent with process line sizing approach and may require significant rework to process piping and/or equipment layout. CIP 设计 —— 就地清洗设计不完整。初步喷淋球规格与工艺管路选型方式不匹配，可能需对工艺管路和 / 或设备布置进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.1,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R34] Cleaning carried out at nominally atmospheric pressure with the risk of material being trapped between flanges, which tend to separate slightly during high-pressure operation, and could lead to cross contamination between batches. 清洗在近常压下进行，高压运行时法兰会出现微量分开，可能将物料残留于法兰间隙中，进而导致批次间交叉污染。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. | NO | Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R35] Validation / Verification — Cleaning validation / verification philosophy not available. QA may not accept that the continuous reactor achieves minimum cleaning standards. 验证 / 确认 —— 清洗验证 / 确认策略尚未提供。质量保证部门可能不接受连续反应器满足最低清洗标准。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.2,Q1.9 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 更新清洗方案后讨论/Discuss after updating the cleaning procedure. | NO | Chaoqun hu/Xiantao Feng
07/02 | SW - Risk Register Cleaning 清洗 | [R36] Layout — Layouts are not available to evaluate the impact of bypasses, dead legs, drains, vents, etc. 布置 —— 布置图尚未提供，无法评估旁路、死管、排放、放空等的影响。 |  | NO | Shuangshuang fan/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R37] Layout — Layouts are not available to evaluate access to equipment for visual inspections, which may impact the effectiveness of critical inspections. 布置 —— 布置图尚未提供，无法评估设备的目视检查通道，可能影响关键检查的有效性。 |  | NO | Shuangshuang fan/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R38] Layout — Equipment design / layout does not allow for routine disassembly and manual cleaning. Equipment turnaround times and operating costs would be adversely impacted if CIP system cannot be validated. 布置 —— 设备设计 / 布置未考虑日常拆装和人工清洗。如 CIP 系统无法通过验证，设备周转时间和运行成本都会受到不利影响。 |  | NO | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register FT001 FT001 流量计 | [R39] Liquid Stream Flow Sensor for flow control loop FIC001. FT001 is a Coriolis mass flow meter installed downstream of the metering pump MP01. Pulsed flow from the pump will impact on the flow measurement and accurate flow control may not be possible. 液相流量传感器（用于 FIC001 流控回路）—— FT001 是安装在计量泵 MP01 下游的科里奥利质量流量计。泵的脉冲流会影响流量测量，可能无法实现精确流量控制。 | Keith / SW response: China Team have previously used this configuration and not experienced flow control issues. No further action required. Keith / SW 答复： 国内团队此前采用过该配置，未出现流控问题。无需进一步动作。 | YES
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R40] Maximum flow may exceed separator design limitations and carry hydrogen over into BT04 / product collection containers. 泵的最大流量可能超出分离器的设计上限，将 H₂ 带入 BT04 / 产品收集容器。 | 07/10：分离器的直径足够大，泵为最大流量时能满足分离要求 07/10：The separator has a sufficiently large diameter to meet separation requirements even when the pump operates at maximum flow rate. | NO | Chaoqun hu
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R41] Pump turndown does not meet URS minimum flow requirements. 泵的调节比无法满足 URS 中规定的最低流量要求。 | 07/10：机泵条件中规定了泵的最小流量要求，待泵厂家返回资料时审查是否满足最低流量要求 07/10：Minimum flow requirements for pumps are specified in pump data sheets. Compliance with the minimum flow criteria shall be verified upon receipt of vendor documentation. | NO | Chaoqun hu
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R42] Hydrogen gas flow controller — Flow controller does not support tight shut-off and system pressure increase during hold periods. 氢气流量控制器 —— 控制器不支持严密关断，系统在保压期间压力会持续上升。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller to provide tight shut-off. Keith / SW 答复： 在控制器下游追加一台切断阀以提供严密关断。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R43] Maximum flow through controller may exceed separator design limitations and carry liquid into the vent line. 流经控制器的最大流量可能超出分离器设计上限，将液体带入放空管。 | Keith / SW response: High level interlock installed in the separator to stop gas supply and close PIC028 shut-off valve (CV08). Keith / SW 答复： 在分离器上设置高液位联锁，停 H₂ 供给并关闭 PIC028 的切断阀（CV08）。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R44] Time required for pressure testing the system and nitrogen inertion may be excessively high. 系统加压试验及氮气钝化所需时间可能过长。 | Keith / SW response: Pressure test / inertion times to be evaluated during FIC003 selection. Manual vent installed on BT03 to reduce depressurisation times via FIC003. Keith / SW 答复： 在 FIC003 选型时评估压力试验 / 惰化时间。在 BT03 上加装人工放空阀，缩短经 FIC003 的减压时间。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R45] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端的差压超出厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register LIC003 LIC003 分离器液位 | [R46] SE01 Separator Level Indicator — Cleaning / decontamination of housing is not possible. Residual product in housing could lead to cross contamination between campaigns. SE01 分离器液位指示 —— 变送器外壳无法进行清洗 / 净化。外壳内的残留物料可能导致批次间交叉污染。 | Keith / SW response: Design relies on dissolution of residual material. 100% flood-fill of housing is not possible, therefore any residual trace contamination in the housing is deemed to be small and will not significantly impact cleaning verification. Keith / SW 答复： 设计依赖残余物料的溶解。外壳无法 100% 灌满，因此外壳内任何残余痕量污染被视为很小，不会显著影响清洗验证。 | YES
07/02 | SW - Risk Register FIC004 FIC004 分离器液位控制 | [R47] Separator outlet flow / level control — Differential pressure across the controller exceeds manufacturer's recommendations and controller capability. 分离器出口流量 / 液位控制 —— 控制器两端差压超出厂家建议范围及控制器能力。 | 分离器出口先通过减压阀减到0.2MpaG左右，可以满足厂家建议的差压范围 The outlet of the separator is first reduced to approximately 0.2MpaG through a pressure reducing valve, which can meet the differential pressure range recommended by the manufacturer | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register FIC005 FIC005 BT01 氮气吹扫 | [R48] BT01 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT01 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register FIC007 FIC007 BT04 氮气吹扫 | [R49] BT04 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R50] System back pressure controller — The back pressure controller does not support tight shut-off during hold periods and system pressure will not be maintained. 系统背压控制器 —— 该控制器在保压期间不支持严密关断，系统压力无法保持。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller. Keith / SW 答复： 在该控制器下游追加一台切断阀。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R51] Time required for depressurising the system following pressure testing and nitrogen inertion may be excessively high. 加压试验和氮气钝化之后系统减压所需时间可能过长。 | Keith / SW response: Manual bypass installed around PIC028 controller. Keith / SW 答复： 在 PIC028 控制器周围加装人工旁路。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R52] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端差压超出厂家建议范围，可能导致控制器无法正常工作。 | 关于背压阀028，之前厂家计算反馈的阀前背压范围最大为0.9~6MpaG，范围量程比不能过大。 About the back pressure valve 028, previously, the manufacturer calculated and reported that the maximum range of the back pressure before the valve was 0.9 to 6MpaG, and the range-to-range ratio cannot be too large. | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register PIC030 PIC030 分离器液相出口减压 | [R53] Separator liquid outlet pressure reducer — Is this confirmed as a Bronkhorst pressure controller, or is a mechanical regulator still an option? Does this provide the required independence assumed in the relevant SIL / risk assessments? 分离器液相出口减压器 —— 该阀是否确认为 Bronkhorst 电子压力控制器？还是仍可能选用机械式减压阀？该配置能否提供相关 SIL / 风险评估中假设所需的独立性？ | 目前选型机械式减压阀。机械阀不是电子设备，没有相关的SIL认证。 At present, mechanical pressure reducing valves are being selected. Mechanical valves are not electronic devices and do not have the relevant SIL certification. | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register PIC049 PIC049 BT04 背压控制 | [R54] BT04 back pressure controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 背压控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register Automation 自动化 | [R55] Automation Build — Philosophy and Design documentation not available to assess risks and limitations. 自动化建设 —— 自动化策略与设计文档尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q3.1,Q3.2 | 专题沟通后确定反馈 | NO | Chaoqun hu/Dezhi meng/Ziliang zhao
07/02 | SW - Risk Register Documentation 文档 | [R56] Technical File — Technical File not available to assess risks and limitations. 技术文件 —— 技术文件尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.5,Q7.1 |  | NO | Shaofeng gao/All
07/02 | SW - Risk Register Documentation 文档 | [R57] O&M Manual — O&M manual not available to assess risks and limitations. 操作维护手册 —— O&M 手册尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q7.1 | 07/10：操作手册的编制还在进行中 07/10：Preparation of the operation manual is still in progress. | NO | Chaoqun hu
07/02 | SW - Risk Register Documentation 文档 | [R58] Emissions Calculations — Calculations to demonstrate expected release of Class A and Class B VOCs to atmosphere are not available. These are required to demonstrate compliance with EA Permit limits. 排放量计算 —— 尚未提供证明 A 类和 B 类 VOC 向大气排放的预期计算。该计算是证明满足 EA 许可（英国环境署许可）限值要求所必需。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW负责排放量计算/SW is responsible for emissions calculation. | NO | Chaoqun hu
07/02 | SW - Risk Register Regulatory Compliance 法规合规 | [R59] CE ¦ Functional Safety ¦ DSEAR / ATEX ¦ PSSR ¦ COSHH ¦ PUWER (Access, manual handling) ¦ Working at Height (Access Steps / Support Shelf) ¦ LOLER (Davit arms) ¦ Lighting ¦ Occupational Hygiene ¦ EA Permit — Regulatory non-conformance would prevent beneficial use of equipment in the UK. CE 认证 ¦ 功能安全 ¦ DSEAR / ATEX 防爆 ¦ PSSR 压力系统安全 ¦ COSHH 危害物质 ¦ PUWER 工作设备（含通道与人工搬运）¦ 高处作业（操作台阶 / 支撑架）¦ LOLER 起重设备（吊臂）¦ 照明 ¦ 职业卫生 ¦ EA 环境许可 —— 任何法规合规缺失都会导致设备无法在英国正常投入使用。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW内部的提醒事项。 CFCT核实加料步梯是否包含在内。 SW提供步梯平台尺寸。 Internal reminders for SW: CFCT to verify whether the feeding staircase is included. SW to provide dimensions of staircase and platform. | NO | Zilang zhao/All
07/14 |  | 根据生产经验，研发建议原R24-CR01的直径由DN80改为DN50，导致产能下降，可能无法满足URS中的产能30kg/day Based on production experience, the R&D team proposes reducing the diameter of the original R24-CR01 from DN80 to DN50. This modification will result in lower production capacity, which may fail to meet the 30 kg/day throughput specified in the URS. | 07/14：周三会上确定/To be confirmed at Wednesday's meeting. 07/15：暂定R24-CR01的直径修改为DN65，等9月份研发提供DN65的反应器实验数据后最终确认反应器的尺寸为DN65或DN50 07/15：It is tentatively agreed to revise the diameter of R24-CR01 to DN65. The reactor size (either DN65 or DN50) will be finalized after the R&D department provides DN65 reactor test data in September. | NO | Xiantao Feng/All
07/23 | SW | 气液分离器SE01容器承受从常压到60 barg的压力循环次数？ How many pressure cycles does the gas-liquid separator SE01 vessel undergo from atmospheric pressure to 60 barg? | 07/23:会上讨论了加氢装置的操作周期，意见存在不一致，关于连续加氢的年运行周期，SW内部沟通后反馈循环次数需求。 气液分离器的设计温度调整到270℃，对应设计压力调整到7.5MPaG。垫片选用金属环垫片。 07/23：The operating cycle of the hydrogenation unit was discussed at the meeting, and divergent opinions remain. SW shall coordinate internally and provide feedback on the required number of cycles regarding the annual operating cycle for continuous hydrogenation. The design temperature of the gas-liquid separator shall be revised to 270°C, with the corresponding design pressure adjusted to 7.5 MPaG. Metallic ring gaskets shall be adopted . | NO | Zilang zhao/Chaoqun hu
07/23 | IEPE | P&ID中压力表无根部阀，是否需要增加根部阀？ Pressure gauges shown on the P&ID are not equipped with root valves. Is it necessary to add root valves? | 07/23:按照现有P&ID配置。 07/23：Configure in accordance with the existing P&ID. | NO | Chaoqun hu/Yu gao
07/23 | IEPE | PCV028侯径小，反应系统卸压时，全开PCV028卸压速度也很慢，建议将PCV028的旁通手阀改为开关阀 PCV028 has a small orifice. When depressurizing the reaction system, the depressurization rate remains low even if PCV028 is fully open. It is recommended to change the bypass manual valve of PCV028 to an on-off valve. | 07/23:单独发邮件沟通。 07/23：We will communicate via separate email. | NO | Chaoqun hu

## 0723
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. 05/12：Keith建议用气液两相计算安全阀尺寸，不提供模板 05/12：Keith suggests using gas-liquid two-phase calculations for determining the size of the safety valve, but no template is provided. 05/20：根据API520的气液两相泄放时计算安全阀尺寸，部分已完成 05/20：Calculate the size of the safety valve based on the API520 standard for the two-phase gas-liquid discharge situation.Partially completed. 06/02：安全阀计算初版已完成（包含临界流体和气液两相），校审中。 06/02：Preliminary calculation of safety relief valve (covering critical fluid & gas-liquid two-phase flow) completed, under review. 06/09: General 1. What was the source/reference for the Specific Volumes stated in column D/D 列中比容数据的来源及参考依据是什么？ The Specific Volumes stated in column D are derived from Aspen Plus simulation results.比容数据来自Aspen模拟 2. There is no backpressure considered in the calculation. The emergency vent relief will create some backpressure which needs to be considered in the calculation./本次计算未考虑背压。紧急放空泄放过程会产生一定背压，该因素需纳入计算。 Backpressure consists of static backpressure and built-up backpressure. Given the wide total pressure range, backpressure effects shall be incorporated into the calculation.背压分为静背压和积聚背压，总压力范围大，将背压包含在其中 3. At the assumed relief pressure Ethyl Acetate will be a supercritical fluid, therefore the required relief mass flowrate will not be dependent on the latent heat of vapourisation, and the calculated ‘required discharge area’ will not be valid. Do you agree with this statement, or have you found a reference in the standard that allows for this? 在设定的泄放压力下，乙酸乙酯将处于超临界流体状态，因此所需泄放质量流量不再依赖汽化潜热，本次算出的所需泄放流通面积也不再适用。你是否认同该观点？或是你是否在相关标准中查到可支持该计算的依据？ 详见06/16回复. Please refer to the reply dated 06/16 for details. Cooling Failure Calculations 4. For the cooling failure calculation, I would suggest using 550kJ/mol rather than 501.48. This is based on Sandwich PSL experience of heats of reaction. 针对冷却失效工况计算，建议将反应热取值由 501.48 kJ/mol 改为 550 kJ/mol。该取值参考了桑威奇工艺安全实验室（Sandwich PSL）过往反应热项目经验。 OK 5. Is the feed flowrate used in the calculation, based on the maximum metering pump capabilities? Do you assume a maximum concentration of reactant in the feed stream? 计算中采用的进料流量，是否按照计量泵最大额定流量取值？计算时是否假定进料流中反应物浓度为最大浓度？ The flow rate used in the calculation is set at the maximum rated capacity of the metering pump, and the maximum reactant concentration is adopted for the feed stream.计算时流量是按照计量泵最大额定流量取值，反应物浓度为最大浓度 06/16：根据文献“Relief Calculation for Supercritical Fluids”计算超临界流体的质量泄放流量，会后向Keith发计算书审核 06/16：Calculate the mass relief flow rate of supercritical fluids in accordance with the document Relief Calculation for Supercritical Fluids, and send the calculation sheet to Keith for review after the meeting. | YES | Chaoqun Hu
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun HU
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. 06/16：06/11已收到审核完成的URS。 06/16：Received the reviewed URS on 06/11. | YES | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith确认CV08也是故障关，可以使用DS6080型，该型号没有5 bar 差压限制。 Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith confirmed that CV08 is also a faulty-close type, the DS6080 model can be used. This model does not have a 5-bar differential pressure limit. Keith offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. 06/02 进展：Habonim厂家反馈了样本资料，反馈可以满足工艺参数需求，货期大概16~20周。可以作为开关阀的备选品牌。 06/02 Progress: "Habonim" manufacturer has provided sample materials that can meet the process parameter requirements. The delivery time is approximately 16 to 20 weeks. It can be an alternative brand for on-off valves. | YES | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. 06/02：关于气液分离器液相出口减压，电子压力阀和自力式减压阀都可以满足使用，首选自力式减压阀。 06/02：For pressure reduction at the liquid outlet of the gas-liquid separator，both electronic pressure valves and self-operated pressure reducing valves can meet the requirements, with self-operated pressure reducing valves being the preferred choice. | YES | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. 05/20：SW已更新完URS并发出。The SW has been updated and the URS has been sent out. | YES | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表数据单。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. 06/23:仪表条件表已更新完成 06/23：The instrument conditions table has been updated and completed. 07/10：仪表数据单已更新完成 07/10：Instrument Data Sheet has been fully updated. | YES | Chaoqun Hu/Yu Gao
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. 05/20：SW已更新完PFD并发出。The SW has been updated and the PFD has been sent out. | YES | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ 4/30：Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? | NO | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted?05/12Decided not to make any adjustments. 05/12确定不做调整。 05/12：It is determined that the height of the catalyst bed in the main reactor will not be adjusted. | YES | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. 06/16：会议澄清：待布局完成后，SW主导完成爆炸危险区域的划分 09/06：Meeting Clarification: SW shall take the lead in completing the classification of hazardous areas for explosion after layout design is finalized. | NO | All
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | YES | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements. | 05/20：与聂博沟通，小试使用的是进口是插底的分离器，生产使用的是侧进的分离器，按会议沟通的气体最大流量0.2Nm³/h，液体最大流量20L/h重新计算了分离器 05/20: Communicated with Nie Bo. The small-scale test used an imported bottom-insertion separator, while the production version used a side-inlet separator. Based on the maximum gas flow rate of 0.2 Nm³/h and the maximum liquid flow rate of 20 L/h for the communication at the meeting, the separator was recalculated.. | YES | Chaoqun Hu
06/02 | IEPE | 管道编号中的管线尺寸一般是指的公称直径，PID中尺寸为10mm的管道是Φ10mm，公称直径为6mm The line size in pipe line designations generally refers to the nominal diameter. In a P&ID, a pipe with a size of 10mm is specified as Φ10mm, corresponding to a nominal diameter of 6mm. | 06/02：会议澄清：DN15以下的管道，管道编号中的管径为外径，DN15及其以上的管道，管道编号中的管径为公称直径。 06/02：Clarification from meeting:For piping below DN15, the size specified in pipe tag number denotes outer diameter; for DN15 and above, the size in pipe tag refers to nominal diameter. | YES | Chaoqun Hu
06/02 | IEPE | 设备BT-01/03/04上的压力变送器不便于现场观察，是否可以考虑也选用WIKA的不带现场显示紧凑型的压力变送器？ The pressure transmitter on the equipment BT-01/03/04 is not convenient for on-site observation. Could it be considered to also choose WIKA's compact pressure transmitter without on-site display？ | 06/02：会上建议保留BT-01/04的现场显示，BT-03可不带现场显示。 06/02：It was suggested at the meeting that the on-site display of BT-01/04 be retained, while BT-03 may not have an on-site display. | YES | Yu Gao
06/02 | CFCT | 1-PID中V-9868，V-9965阀柄的含义？ What is the meaning of valve handles V-9868 and V-9965 in PID? 2-PID中压力变送器底部波纹含义是什么？ What does the corrugation at the bottom of the pressure transmitter signify? 3-与管道直径对应的保温厚度是多少？ What is the insulation thickness corresponding to the diameter of the pipeline? | 06/02： 1.PID中阀门V-9868，V-9965的阀柄为弹簧复位阀柄； In the PID,the valve handles of V-9868 and V-9965 are spring-reset handles； 2.PID中带底部波纹的压力变送器要求压力变送器带隔膜； The pressure transmitter with a bottom ripple in PID requires the pressure transmitter to be equipped with a diaphragm； 3.Keith分享了建议的管道直径与保温厚度表格，直径10到25mm的管路，保温厚度为30-35mm。 Keith shared the recommended pipe diameter and insulation thickness table, with insulation thickness ranging from 30-35mm for pipes with diameters of 10 to 25mm. | YES | ShuangshuangFan
06/16 | SW | 会议确认：气液分离器为侧进，尺寸为DN200*600mm，下次例会前CFCT向SW提供气液分离器的设备图纸 Confirmed at the meeting: The gas-liquid separator adopts side inlet configuration with dimensions DN200 × 600 mm. CFCT shall submit the equipment drawing of the gas-liquid separator to SW prior to the next regular meeting. | 06/22设备图纸已提供。06/23Keith回复意见，见06/23讨论内容。 Equipment drawings were provided on 06/22. Keith's feedback was received on 06/23 — please refer to the discussion notes from 06/23. | YES | Ziliang Zhao
06/17 | SW | 根据最新工作进展并结合HAZOP分析所需文件内容，更新“Sandwich Hydrogenation Implementation Schedule” Update the Sandwich Hydrogenation Implementation Schedule based on the latest progress and document requirements for HAZOP study. |  | NO | All
06/17 | SW | 讨论操作规程：哪些部分需要顺控？开停车步骤等 Discuss operation procedures: identify sections requiring sequence control, including startup and shutdown steps, etc. | 06/23：开车步骤：公用工程确认/催化剂装填→氮气置换（R24-BT01、R24-BT04和剩余部分），氧含量<0.5vol%→氢气置换→原料系统备料→TCU系统调温→反应器进料（氢气先进料背压至反应压力，液相再进料）→气液分离→产品转移 停车步骤：停进料→产品缓冲罐物料转移→反应器卸压→R24-BT03卸压→反应系统降温→氮气置换→关闭氮气和TCU Startup Procedures： 1.Verification of utility systems & catalyst loading 2.Nitrogen purging (for R24-BT01, R24-BT04 and the rest of the system), oxygen content controlled below 0.5 vol% 3.Hydrogen purging 4.Raw material preparation for feed system 5.Temperature adjustment of TCU system 6.Reactor feeding: Introduce hydrogen first to build backpressure up to reaction pressure, then feed liquid phase material 7.Gas-liquid separation 8.Product transfer Shutdown Procedures： 1.Cut off feed supply 2.Transfer materials from product buffer tank 3.Depressurize reactor 4.Depressurize R24-BT03 5.Cool down reaction system 6.Nitrogen purging 7.Shut down nitrogen supply and TCU system Keith提供HAZOP时的开停车步骤，结合上述文件，整理开停车和清洗步骤 Compile the plant start-up, shutdown and cleaning procedures based on the above documents together with the start-up & shutdown sequences supplied by Keith for HAZOP assessment. | NO | All
06/17 | SW | 会后确认：安全阀的泄放温度超过设备的设计温度，是否需要提高设备的设计温度？ To be confirmed after the meeting：If the relief temperature of the safety valve exceeds its design temperature, is it necessary to increase the design temperature rating? | 设备和管线材质为316L，结合设备和管道的壁厚，计算得出：在泄放温度下，材料的许用应力满足其强度要求，不需提高设备的设计温度 The equipment and piping are fabricated from 316L stainless steel. Wall thickness calculations for the equipment and piping demonstrate that the allowable stress of the material satisfies the strength requirements at relief temperature; therefore, no increase to the equipment design temperature is required. | Yes | Ziliang Zhao/Chaoqun Hu
06/17 | SW | CFCT做撬块设计时，注意清洗过程中的低点排净 CFCT shall take full consideration of low-point draining during cleaning when designing the skid package. | 06/23：在撬块设计时，设置管道的低点排净阀 When designing the layout, install a drain valve at the low point of the pipeline 06/23会议方案：管道最低点设置排净阀，操作说明中明确排放时用容器收集排放液体。 Meeting Plant: Install drain valves at the lowest point of the pipeline, and specify in the operating instructions to collect the discharged liquid with a container during the drainage process. | Yes | Shuangshuang Fan
06/17 | SW | CFCT提供放空缓冲罐T06是否放在撬内的方案 CFCT to provide a scheme on whether vent buffer tank T06 shall be installed inside the skid. | 06/23：按照现有空间的布置，T06放在撬块内的空间不足；撬块中间的操作维护通道宽度为300-350mm，能否将整体撬块宽度增加150-200mm？ According to the existing space arrangement, there is insufficient space for T06 to be placed inside the pry block; The width of the operation and maintenance channel in the middle of the pry block is 300-350mm. Can the overall pry block width be increased by 150-200mm? 06/23会议方案：T06不放在撬块内，放置在service area，同时反应柱/冷凝器的TCU出口管路上的温度变送器安装在近出口处，去掉手动球阀，安全阀可放到service area，并设置排净阀，进口管路手动球阀保持不变，温度变送器加套管，位置可前可后，低点设置排净阀，整体管路的高点设置排气阀。 Meeting Plant:: T06 is not placed inside the lever block but in the service area. The temperature transmitter on the TCU outlet pipeline of the reaction column/condenser is installed near the outlet. The manual ball valve is removed, and the safety valve can be placed in the service area. A drain valve is installed, while the manual ball valve on the inlet pipeline remains unchanged. The temperature transmitter is equipped with a protective sleeve, with its position adjustable forward or backward. A drain valve is set at the low point, and an air vent valve is installed at the high point of the entire pipeline. | Yes | Shuangshuang Fan
06/23 | SW | Keith意见： 基本设计：我们是否有经批准的分离器设计方案？我上次看到的摘录中，计算出的容器直径为3毫米，这表明计算或输入数据可能存在错误。 Basic design 1. Do we have an approved design for the separator. The last extract I saw had a calculated vessel diameter of 3mm, which suggests an error in the calculations or input data. | 06/23讨论： 基本设计：按最新设备数据表进行气液分离器设计。气液分离器的计算书已复核过，数据无误。 06/23Discussion—Basic Design: The gas-liquid separator shall be designed in accordance with the latest equipment data sheet. The calculation sheet for the gas-liquid separator has been reviewed and the data are confirmed to be correct. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 分离器内件 1、本设计中是否已考虑分离器内件，例如入口导流装置或入口旋风分离器、气相除雾器、液体出口处的防涡流挡板？ 2、喷淋球能否采用焊接固定方式，而非通过管接头引入容器内部？ 3、喷淋球是否必须为旋转式喷淋球？这会增加设备复杂度，并在工厂运行寿命期内带来检查与维护方面的问题。 4、喷淋球实际能否起到喷淋清洗作用，还是仅仅将容器注满清洗液直至触发高位液位开关？根据此前讨论，从空罐到高位跳闸点的时间不足25秒，这无法为分离器气相侧提供足够的机械清洗作用时间。 Separator internals 1. Have separator internals been considered for this design e.g. inlet diverters or inlet cyclones, demisting of the vapour stream, vortex breakers on the liquid outlet. 2. Can the spray ball be welded in position rather than introducing a tube fitting into the vessel. 3. Does the spray ball need to be a rotary spray ball. This adds complexity and inspection/maintenance issues during the life of the plant. 4. Will the spray ball actually work as a spray ball, or will it simply fill the vessel with cleaning fluid until the high-level switch is activated. Based on previous discussions this would be less than 25 seconds from empty to high-level trip point, which doesn’t allow much time for mechanical cleaning action in the gas side of the separator. | 06/23讨论： 分离器内件： 1、气液分离器设计采用重力式分离，无需额外的内件。 2、喷淋球相关事宜，CN团队内部结合喷淋球供应商商议方案。 06/23 Discussion — Separator Internals: 1.The gas-liquid separator is designed as a gravity-type separator; no additional internals are required. 2.Regarding the spray ball matters, the CN team will internally discuss and determine the solution in coordination with the spray ball supplier. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 设计参数 1、“流体性能”是否应定为“非致命性”？我推测此概念类似于PED容器设计中的流体分组，在英国规范中应属于Group 1气体（即可燃/爆炸/有毒），而非“非致命性”。 2、工作压力应为0至6MPaG。 3、设计温度应至少为150°C，并且我假设在泄压事故工况下，容器温度可能达到约300°C。 4、设计压力应为全真空至9MPaG。 5、规范是否要求进行焊后热处理（PWHT）？ 6、水压试验压力应为设计压力的1.5倍，即13.5MPaG，而非12MPaG。 7、对于该容器，S4应为DN32 Cl900 WN法兰。喷淋球接口是否应作为单独细节在本图纸上表示，还是另页图纸表示更为合适？ 8、充装系数（Fulling Factor）是多少？ Design Parameters 1. Should the ‘Fluid Performance’ be Non-Lethal? I assume this is similar to the fluid group for PED vessel design, which for the UK would be Group 1 gas i.e. flammable/explosive/toxic and not Non-Lethal. 2. The working pressure should be 0 to 6MPaG. 3. The design temperature should be at least 150 °C and I assume the vessel has the potential to reach circa 300°C during a relief event. 4. The design pressure should be FV to 9MPaG 5. Is PWHT required by the code. 6. Hydro test pressure should be 1.5x design pressure i.e. 13.5MPaG not 12 MPaG. 7. For the vessel, S4 should be a DN32 Cl900 WN Flange. Should the spray ball fitting be shown as a separate detail on this drawing or possibly shown on a separate drawing. 8. What is the Fulling Factor. | 06/23讨论： 设计参数 ： 1、介质调整为易爆。 2、CN团队结合URS，修正工作压力，更新设备数据表。 3、可以将泄压事故工况，纳入到常规设计考虑中，即可提高设计温度到300℃。 4、修正设计压力，更新设备数据表。 5、规范可不进行焊后热处理（PWHT）。 6、水压试验压力为设计压力的1.3倍，故试验压力可不做调整。 7、S4为喷淋口，口径为Φ10，DN32法兰接口结构为保证喷淋球可抽出，后续根据喷淋球整体方案做调整，判定是否需要可抽式。 8、充装系数是指物料实际容积与容器全容积之比。 06/23 Discussion — Design Parameters: 1.The medium classification is revised to "explosive." 2.The CN team will revise the working pressure based on the URS and update the equipment data sheet accordingly. 3.The relief event scenario can be incorporated into the normal design considerations — i.e., the design temperature can be raised to 300°C. 4.The design pressure will be revised and the equipment data sheet updated accordingly. 5.PWHT (post-weld heat treatment) is not required per the applicable code. 6.The hydrostatic test pressure is 1.3 × design pressure, so the test pressure does not need to be adjusted. 7.S4 is the spray ball connection, with a bore size of Φ10. The DN32 flange connection is designed to allow the spray ball to be withdrawable. This will be reviewed and adjusted as part of the overall spray ball solution, and a decision will be made on whether a withdrawable type is necessary. 8.The filling factor is defined as the ratio of the actual liquid volume to the total vessel volume. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 通用事项 1、管口方位是否已考虑设备布置的最优化？ 2、在撬装高度限制范围内，容器能否通过重力自由排液至产品收集罐？ 3、在顶部法兰上开孔用于引出管，是否会损害其机械完整性并违反安全规范？是否已重新计算法兰厚度或进行有限元分析（FEA），以确保足够的金属厚度和结构完整性？ 4、液位变送器/液位开关的规格是否已确认？法兰尺寸及位置是否与仪表相匹配？ 5、请更新P&ID，以显示S4正确的管口尺寸。 6、是否有容器设计计算书？技术文件中需要包含设计计算书，并应在FAT（工厂验收测试）时进行核查。 General 1. Does the nozzle orientation allow for optimum equipment layout. 2. Can the vessel free drain into the product collection tank, within the skid height constraints. 3. Does boring a hole in the top flange for the outlet pipe compromise its mechanical integrity and violate safety codes. Have you recalculated the flange thickness/carried out FEA to ensure adequate metal thickness and structural integrity. 4. Has the level transmitter/level switches been agreed – does the flange size/position align with the instruments. 5. Update P&ID to show correct nozzle size for S4. 6. Do you have vessel design calculations. Design calculations will be required in the technical file and should be checked at FAT. | 06/23讨论： 通用事项 ： 1、管口方位已结合3D撬装布置给定。 2、3D撬装设计已考虑，待3D模型复核时，详细讨论。 3、重新计算法兰厚度，以满足结构强度要求。 4、仪表工程师已经确认复核。 5、P&ID，不需要更改S4管口尺寸。 6、设计计算书是设备完整技术文件中必不可少的一部分，后续会提供。 06/23 Discussion — General Items: 1.Nozzle orientation has been determined based on the 3D skid layout. 2.The 3D skid design has taken this into consideration; detailed discussion will be held during the 3D model review. 3.The flange thickness will be recalculated to meet structural strength requirements. 4.The instrumentation engineer has confirmed and verified this. 5.The P&ID does not require changes to the S4 nozzle size. 6.The design calculation sheet is an essential part of the complete technical documentation for the equipment and will be provided in due course. | YES | Ziliang Zhao/Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Overall cleaning philosophy per vessel 各容器整体清洗策略 Please confirm the intended cleaning philosophy for each vessel in the skid — spray-only, soak-only, spray-and-soak combined, or an alternative approach. Please also indicate whether a single philosophy applies across all vessels or whether the strategy varies by vessel. 请确认撬块内各台容器的清洗策略：单独喷淋、单独浸泡、喷淋+浸泡组合，或其它方式。请同时说明是否所有容器采用同一策略，或按容器区别设计。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleanliness verification method & acceptance criteria 清洁度验证方法与验收标准 Please advise the verification method(s) used to confirm cleaning completion (visual inspection, swab / rinse sample analysis, mass balance, calculated residue, etc.) and the numerical acceptance criteria applied (e.g. residue mass, ppm concentration threshold). 请说明用于确认清洗完成的验证方法（目视检查 / 拭子或冲洗样分析 / 物料衡算 / 残余物计算等），以及所采用的数值验收标准（如残余物质量、浓度阈值 ppm）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Sight glass availability for SE01 SE01 视镜配置 The reactor vessels are understood to be fitted with sight glasses to support visual verification of cleanliness. The gas–liquid separator SE01, however, does not include a sight glass. Please confirm the intended method for verifying cleanliness on SE01. 反应柱已配置视镜以支持目视清洁度检查，但气液分离器 SE01 未配置视镜。请确认 SE01 清洁度验证的具体手段（，以及是否考虑将新增视镜作为设计变更纳入）。 | 07/10：反应柱和分离器因为操作压力高，无法配置视镜，清洁度的验证无法依靠目测，需取样分析测量残留物的浓度 07/10：Due to the high operating pressure of the reaction column and separator, sight glasses cannot be installed. Visual inspection is therefore not feasible for cleanliness verification, and residue concentration shall be determined via sampling analysis instead. | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Spray ball flow rate vs. vessel fill time 喷淋球流量与容器充液时间的匹配 The lowest available spray ball flow rate (approximately 2 L/min) results in SE01 reaching the high-level trip point in under 25 seconds. This limits the time window in which mechanical spray action can achieve wetting coverage. Please advise the intended cleaning-time window on SE01 and the approach for ensuring adequate mechanical cleaning action within the design constraint. 现有最小可选喷淋球流量约 2 L/min，导致 SE01 容器在 25 秒内即达到高液位跳停，机械喷淋作用的有效时间窗口非常短。请说明 SE01 上预期的清洗时间窗口，以及在此设计约束下如何确保获得充分的机械清洗作用。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Drain line sizing and fill–drain cycle 排放管径与充液-排空循环 Under the current drain line configuration, the drain rate is significantly slower than the spray inflow rate. Please advise the intended drain line diameter (whether upsizing is planned), the estimated single-cycle fill and drain durations, and the number of cycles anticipated per cleaning campaign. 当前排放管径下，排放速率显著慢于喷淋进料速率。请说明拟采用的排放管径（是否放大）、单次循环的充液和排空时间估算，以及每次清洗预期需要的循环次数。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Soak cleaning vs. high-level interlock defeat mechanism 浸泡清洗与高液位联锁绕过机制 If soak cleaning is adopted on SE01, the liquid level during cleaning will exceed the high-level safety interlock (located at approximately one-third of vessel height). Please specify: (a) the physical mechanism intended for defeating this interlock during cleaning (key switch, procedural lockout, or other); (b) the authorisation and access controls surrounding the defeat mechanism; and (c) the safeguards against inadvertent defeat during normal processing operation. 若 SE01 采用浸泡清洗，清洗过程中的液位将超过位于容器约 1/3 高度的高液位安全联锁。请说明：(a) 清洗时用于绕过（defeat）该联锁的物理机制（钥匙开关 / 程序锁定 / 其它）；(b) 该绕过机制的授权与权限控制方式；(c) 防止正常运行时意外绕过的保护措施。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleaning of the guided-wave level transmitter housing Guided wave 液位变送器外壳的清洁 The guided-wave level transmitter housing (approximately 100 mm diameter, side-mounted on SE01) sits above the high-level switch and lies outside the spray ball coverage envelope. Please advise the intended cleaning approach for this housing, and any mechanical or procedural provisions required to ensure it can be cleaned to the acceptance criteria in Q1.2. 液位变送器外壳（约 100 mm 直径，SE01 侧接管上）位于高液位开关之上，不在喷淋球覆盖范围内。请说明该外壳的清洁方案，以及为达到 Q1.2 中的验收标准所需的机械或程序性措施。 | 07/14：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用 07/14：Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. | NO | Chaoqun Hu/Yu Gao
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Reactor cleaning cycle time and manual interventions 反应器清洗循环时间与人工干预 For the 200-L reactor vessels, a single spray-and-drain cycle involves an extended drain phase relative to the spray phase. Multiple cycles are expected to achieve the required cleanliness. Please advise: the anticipated number of cycles, the total cleaning duration per campaign, and the specific manual interventions required at each step (drain valve operation, sample point access, lockout re-set, etc.). 200-L 反应器进行单次"喷淋-排空"循环时，排空阶段远长于喷淋阶段，需多次循环以达到清洁度要求。请说明：预期循环次数、每次清洗总时长，以及各步骤所需的具体人工干预（排放阀操作 / 取样口操作 / 联锁复位等）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW 3D Layout 3D 布置与设备空间 | Operational access clearance 操作通道净空 The current 3D model shows approximately 300–350 mm clearance in certain operator access zones. Please confirm the target minimum clearance from a site operability and maintenance standpoint, and identify any specific zones where relaxation of the current clearance is acceptable, or where additional clearance is required. 当前 3D 模型显示部分操作人员通道净空约为 300–350 mm。请从现场操作与维护角度，确认目标最小净空要求，并识别可以放宽的具体区域，以及需要额外净空的区域。 | 7月10日反馈进展： 建议增加反应柱撬块的宽度，审核模型后给出建议的空间区域。 It is recommended to increase the width of the reaction column skid and provide the suggested spatial area after reviewing the model. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Free-drain feasibility from each vessel 各容器的自重排放可行性 The cleaning strategy relies on free-drain of cleaning fluid from each vessel into downstream collection (BT04 or equivalent). Considering the skid height constraint and each vessel elevation, please confirm the free-drain path is mechanically feasible from each source vessel to its destination. Please identify any vessels where drainage cannot be achieved by gravity and would require pumping or an alternative arrangement. 清洗策略要求清洗液自重从各容器排入下游收集罐（BT04 或等效容器）。考虑撬块高度限制与各容器标高，请确认每台源容器至其目标容器的自重排放路径机械可行。请识别无法通过重力实现排放、需要泵抽或采用替代方案的容器。 | 7月10日反馈进展： 根据目前容器的结构形式，反应柱可通过底部排放阀排放，缓冲罐可通过管路排放，预热器、冷凝器管路无排放口。具体排放方式参考清洗方案。 Based on the current structural design of the containers, the reaction column can be drained through the bottom discharge valve, the buffer tank can be discharged via piping, while the preheater and condenser have no discharge outlets in their pipelines.Refer to the cleaning plan for specific emission methods. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Nozzle orientation on pressure vessels 压力容器管嘴方位 Please review the nozzle orientation on all pressure vessels in the current 3D model. Confirm that nozzle positions provide adequate access for external piping tie-in, instrumentation installation, and maintenance (removal / reinstallation of internals, gasket replacement, catalyst service, etc.). 请审查当前 3D 模型中所有压力容器的管嘴方位。确认管嘴位置能够满足外部管路对接、仪表安装以及维护（内构件拆装 / 密封垫更换 / 催化剂检维修等）的空间要求。 | 7月10日反馈进展： 由于空间尺寸限制，部分管口的维护可能存在不便。优化管口布置或能否增加设备空间。 Due to space size limitations, maintenance of some pipe openings may be inconvenient. Optimize pipe layout or increase equipment space | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Catalyst charging & discharging arrangement 催化剂加料与卸料布置 Please confirm that the catalyst charging (loading) and discharging (unloading) arrangement is compatible with the current nozzle layout on the reactor vessels, and that adequate space is provided for charge / discharge equipment and operator access during catalyst service. 请确认催化剂加料与卸料的操作方式与当前反应柱的管嘴布置兼容，且在催化剂检维修期间为加料/卸料设备与操作人员留有充足空间。 | 7月10日反馈进展： 根据目前的布置方案，反应柱加料卸料口均在撬体端面，结合加料卸料方式看操作空间是否充足。 According to the current layout plan, the feeding and discharging ports of the reaction column are all located on the end face of the pry body. Considering the feeding and discharging methods, it is necessary to check whether the operating space is sufficient. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Tie-in points between skid and site utilities 撬块与现场公用工程接口 Please confirm the finalised location and specification of all tie-in points between the skid and the Sandwich site services, including process feed, product outlet, vent header, HTF supply and return, N₂ blanketing, instrument air, electrical supply, cable penetrations, and drain. Please advise the interfaces where design lock-down is still pending. 请确认撬块与 Sandwich 现场公用工程之间所有接口的最终位置与规格，包括工艺进料、产品出口、放空总管、导热油供回、氮气钝化、仪表空气、电气供应、电缆穿墙、排放。请说明尚未定稿的接口。 | 7月10日反馈进展： 根据现有的布置方案，有部分公用工程的的接口，无仪表空气接口，电气供应、电缆穿墙，后续更新撬块与公用工程接口的位置与规格。 According to the existing layout plan, there are interfaces for some public works without instrument air interfaces, electrical supply, and cable penetration through walls. The location and specifications of the interface between the pry block and the public works will be updated in the future. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Cable wall penetration capacity and cable compatibility 穿墙电缆孔容量与电缆兼容性 The current design indicates 14 available cable wall penetration slots. Please confirm this final count, the internal diameter of each slot, and the compatibility of the slot with the largest cable type intended to pass through (multi-core, armoured, or shielded cables of relevant cross-section). 当前设计显示可用穿墙电缆孔 14 个。请确认该数量的最终定案、每个孔的内径规格，以及与拟穿过的最大电缆类型（相应截面的多芯 / 铠装 / 屏蔽电缆）的兼容性。 | 寻求工程部支持，和宋小旭主管约会讨论如何推进，7月10日反馈进展 | NO | Dezhi meng/Shaofeng gao
07/01 | SW Control Philosophy 控制策略 | Full Control Philosophy document issue date 完整《控制策略》文件发出日期 Please advise the target issue date for the complete Control Philosophy document, superseding the interim draft version previously circulated. 请说明完整版《控制策略》文件的目标发出日期（覆盖此前流转的过渡草稿版本）。 | 07/10：已完成初版，还在校核中，预计下周发出 07/10：The initial draft has been completed and is under review; it is expected to be issued next week. | NO | Chaoqun hu
07/01 | SW Control Philosophy 控制策略 | Interlock schedule — hardwired vs. software 联锁清单 —— 硬件联锁与软件联锁 Please provide a complete interlock schedule listing all safety interlocks, with clear delineation between hardwired (independent of the PLC) and software (PLC-implemented) interlocks. For each interlock, please include: initiating cause, sensing element, trip setpoint, action taken, and protective function fulfilled. 请提供完整的联锁清单，列出全部安全联锁，明确区分硬件联锁（独立于 PLC）与软件联锁（PLC 实现）。每一条联锁请包含：触发原因、检测元件、跳停设定值、联锁动作、承担的保护功能。 | 07/10：联锁条件已完成初版，还在校核中，预计下周发出 07/10：The initial draft of interlock conditions has been completed and is under review, which is expected to be issued next week. | NO | Chaoqun hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Operational modes and mode-specific fail positions 操作模式与各模式下的故障位 Please define all operational modes of the skid (normal operation, start-up, shut-down, cleaning, catalyst change, emergency depressurisation, etc.), and for each mode specify: (a) the fail position of each control valve; (b) the state of each interlock (active / bypassed); and (c) the permissive conditions required to enter that mode. 请定义撬块的全部操作模式（正常运行 / 开车 / 停车 / 清洗 / 催化剂更换 / 紧急泄压等），并针对每一模式说明：(a) 每个控制阀的故障位；(b) 每个联锁的状态（激活 / 已绕过）；(c) 进入该模式所需的许可条件。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 分离器浸泡清洗时易触发液位高联锁，导致高液位以上清洗不彻底。增大分离器的排净管径可实现淋洗，同时系统处于清洗模式时，绕开液位高联锁。 High level interlock is prone to tripping during soaking cleaning of the separator, leading to inadequate cleaning of areas above the high liquid level. Increasing the drain pipe size of the separator allows shower rinsing. Meanwhile, the high level interlock can be bypassed when the system is under cleaning mode. | NO | Chaoqun hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Mode-transition safeguards 操作模式切换的保护措施 Please advise the safeguards in place against inadvertent mode transitions, particularly from cleaning mode back to processing mode (e.g. an interlock bypass being left in place after cleaning is complete). Please describe both the technical safeguards (key switches, HMI confirmations) and the procedural safeguards (SOP requirements, dual sign-off). 请说明防止意外切换操作模式（尤其是从清洗模式返回处理模式时联锁绕过未复位）的保护措施。请分别描述技术性保护措施（钥匙开关 / HMI 确认）与程序性保护措施（SOP 要求 / 双签发）。 | 52条和Keith讨论后1周反馈。 | NO | Dezhi meng
07/01 | SW Sampler System 取样系统 | Sample vaporisation during pressure reduction 取样过程中的样品闪蒸 The sampler transfers process fluid from a line operating at up to 60 barG to a sample container at approximately atmospheric pressure. Please advise the analysis of vaporisation during this pressure reduction (fraction vaporised, temperature drop) and its impact on the compositional representativeness of the collected sample. 取样器将最高 60 barG 工艺管路的介质转移至常压取样瓶。请说明此压降过程中的闪蒸分析（气化比例、温度降低）及其对所采样品成分代表性的影响。 | 07/10：冷凝器出口的温度为30℃，压力从60barG 泄至常压，此温度条件下不会发生闪蒸 07/10：The temperature at the condenser outlet is 30°C. The pressure is relieved from 60 barG to atmospheric pressure, and no flashing will occur under this temperature condition. | NO | Chaoqun hu
07/01 | SW Sampler System 取样系统 | Sample retention design 样品截留设计 Please advise the design of the sample bottle and sample-transfer system, including any vapour trap, septum, condenser, or other retention device intended to prevent loss of volatiles through the vent path and to ensure a representative liquid sample is captured. 请说明取样瓶及取样传输系统的设计，包括为防止挥发组分从放空路径流失、并确保获得代表性液样所采用的蒸汽阱、隔膜、冷凝器或其它截留装置。 | 07/10：取样器的流程：打开三通阀将缓冲罐充满，打开缓冲罐气相放空管线阀门，将缓冲罐中的气相排走并卸压，打开氮气手阀，将缓冲罐中的液体压至取样瓶 07/10：Sampling procedure: Open the three-way valve to fill the buffer drum. Open the valve on the vapor vent line of the buffer drum to vent the vapor inside and relieve pressure. Then open the nitrogen manual valve to pressurize and transfer the liquid from the buffer drum into the sampling bottle. | NO | Chaoqun hu
07/01 | SW Sampler System 取样系统 | Sampler behaviour under gas-rich flow regime 气相主导流态下取样器行为 With the intended process operating at a stoichiometric excess of hydrogen, the flow regime through the sampling point may be gas-rich with entrained liquid rather than liquid-continuous. Please advise how the sampler design accommodates this flow regime, and whether any sample point relocation, phase separator, or coalescer is being considered. 工艺预期在化学计量氢气过量条件下运行，取样点处流态可能为"气相夹带液体"而非液相连续。请说明取样器设计如何适应此流态，以及是否考虑取样点位置调整、加装相分离器或聚结器。 | 07/10：取样器的缓冲罐上有气体排放管线，取样罐充满后，打开气体排放管线，将气相排走并卸压，再用氮气将液相压至取样瓶 07/10：The buffer vessel of the sampler is equipped with a gas vent line. Once the sampling tank is full, open the gas vent line to vent the vapor phase and relieve pressure, then push the liquid phase into the sampling bottle with nitrogen. | NO | Chaoqun hu
07/01 | SW Instrumentation 仪表配置 | Guided-wave level transmitter — datasheet & cleanability Guided wave 液位变送器 —— 数据单与可清洁性 Please provide the guided-wave level transmitter datasheet and confirm: (a) the process compatibility of the probe assembly with the intended service (including any operating conditions in the supercritical or near-critical regime); and (b) the cleanability of the probe assembly under the adopted cleaning philosophy. 请提供 guided wave 液位变送器数据单，并确认：(a) 探头组件在拟定工况（含超临界或近临界工况）下的适用性；(b) 探头组件在拟采用清洗策略下的可清洁性。 | 7月10日反馈进展 (a) 导波雷达液位计工作原理是雷达波可以穿过介电常数较低的气相，遇到介电常数较大的液相返回，从而计算液位。适用蒸汽、粉尘、泡沫等工况。需了解超临界工况下的介质状态是否还存在液相，如果没有液相空间，则液位计无法识别。 The working principle of the guided-wave radar transmitter is that the radar wave can pass through the gas phase with a lower dielectric constant and return to the liquid phase with a larger dielectric constant, thereby calculating the liquid level. It is applicable to working conditions such as steam, dust and foam. It is necessary to understand whether there is still a liquid phase in the medium state under supercritical conditions. If there is no liquid phase space, the transmitter cannot identify it. 07/15进展：经内部评估，液位计所在容器操作工况下不存在超临界状态。 After internal assessment, it was determined that the liquid level gauge is not in a supercritical state under the operating conditions of the container it is located in. (b)BT01和BT04的导波雷达液位计为顶装内伸形式，可以利用设备内的喷淋头冲洗。SE-01的导波雷达液位计为侧装旁通式，可以选择在探头与旁通管的过程接口处增加配套冲洗环，并预留一路冲洗管线。 The guided-wave radar transmitters of BT01 and BT04 are top-mounted and iInsert type, and can be flushed by the spray heads inside the equipment. The guided-wave radar l transmitter of SE-01 is of side-mounted bypass type. A matching flushing ring can be added at the process interface between the probe and the bypass pipe, and a flushing pipeline can be reserved. 07/14进展：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用. Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. 07/17进展：气液分离器雷达液位计侧装改顶装，已完成图纸设计，筒体直径未变，邮件发出。 The radar level gauge for the gas-liquid separator has been redesigned from side-mounted to top-mounted. The drawing design has been completed, and the vessel diameter remains unchanged. The drawings have been sent out via email. | NO | Yu gao/Chaoqun hu/Zilaing Zhao
07/01 | SW Instrumentation 仪表配置 | Level switch position & interlock function 液位开关位置与联锁功能 Please confirm the finalised position (elevation, orientation, flange size and rating) and the interlock function of each level switch (LSL, LSLL, LSH, LSHH) on each vessel, together with the matching instrument selection. 请确认每台容器上各液位开关（低 LSL、低低 LSLL、高 LSH、高高 LSHH）的最终位置（标高、方位、法兰尺寸与压力等级）与联锁功能，以及对应的仪表选型。 | 7月10日反馈进展： 关于液位开关选型，之前寻价时只有VEGA的VEGASWING 63型号可以满足DN25 Class900 M的过程接口，其他厂家如E+H、Rosemount都不能满足。 About the selection of level switches, during the previous price search, only VEGA's VEGASWING 63 model could meet the DN25 Class 900 M process connection requirements. Other manufacturers such as E+H and Rosemount could not meet these requirements. 07/15联锁值详见联锁条件表。The interlock values on 07/15 can be found in the interlock condition table. | NO | Chaoqun hu/Yu gao
07/01 | SW Instrumentation 仪表配置 | Instrument datasheet next revision date 仪表数据单下一版本发出日期 Please advise the target issue date for the next revision of the Instrument Datasheet, reflecting the current SE01 design (post demister-configuration decision), the finalised interlock schedule, and the level switch position confirmation. 请说明反映当前 SE01 设计（demister 配置定稿后）、最终联锁清单以及液位开关位置确认的仪表数据单下一修订版本的目标发出日期。 | 7月10日反馈进展 仪表数据表已完成修订版，待意见讨论后看是否还需修改参数。 The instrument datasheet has been revised. After the discussion of opinions, we will see if the parameters still need to be modified. | NO | Chaoqun hu/Yu gao
07/01 | SW Documentation Status 文档状态 | Current revision and next revision date of key deliverables 主要交付文件的当前版本与下一版本时间 Please confirm the current issued revision and the target date for the next revision of the following documents: • PFD • P&ID • URS • Equipment Datasheets • Control Philosophy • Instrument Datasheet • Operating Instructions • Cleaning Procedure • Vessel Design Calculation Package. 请确认以下文档的当前已发版本与下一修订版本的目标日期： · PFD · P&ID · URS · 设备数据单 · 控制策略 · 仪表数据单 · 操作说明 · 清洗程序 · 容器设计计算书。 | 7月10日反馈进展，操作手册还在编制中，其他设计文件已完成。On July 10th, we provided the progress update. The operation manual is still under preparation, while the other design documents have been completed. | NO | Shaofeng gao/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R1] Design Temperature — Vessel could fail during relief event. Equipment design temperature is specified for process requirements and does not consider elevated temperatures during relief events when short-term temperature increase has the potential to exceed the design temperature. 设计温度 —— 容器可能在泄放事件中失效。设备设计温度是按工艺需求设定的，未考虑泄放事件中的短时温升可能超过设计温度的情形。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：已更新数据表，提高设计温度，以满足工艺需求，图纸已升级。 07/10: Data sheet updated with elevated design temperature to meet process requirements; drawings revised accordingly. | YES | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register Engineering Design 工程设计 | [R2] Design Requirements — L:G ratio for plant is not clearly defined. Equipment design could result in very limited operating ranges and incorrect assumptions in plant capability and relief design. 设计条件 —— 装置的液气比（L:G ratio）未明确定义。可能导致设备设计的操作区间受限，以及在装置能力和泄放设计中做出错误假设。 | 7月10日反馈进展，根据最终确定的反应器尺寸核实气液比数据。On July 10th, the progress was reported. The gas-liquid ratio data was verified based on the final determined reactor size. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Engineering Design 工程设计 | [R3] Design Requirements — Catalyst specification is not available. Design may not be suitable for some catalysts. Dusty catalysts could cause blockages. 设计条件 —— 催化剂规格未明确。设计可能不适用于某些催化剂；含粉尘的催化剂可能导致堵塞。 | Keith / SW response: Design philosophy is based on catalyst beads/pellets which are dust-free, non-flammable and have exposure levels requiring OEB 3 or lower containment. Note: OEB 3 containment is a deviation from the URS and requires acceptance. Keith / SW 答复： 设计基于无粉尘、非燃、暴露等级 OEB 3 或更低的颗粒/粒状催化剂。注：OEB 3 的密闭要求相对 URS 存在偏离，需要接受确认。 | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Engineering Design 工程设计 | [R4] Access — Layouts are not available to assess whether access to equipment is acceptable for operations and maintenance. 通道 —— 布置图尚未提供，无法评估设备的操作与维护通道是否满足要求。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.1 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R5] Maintenance — Lifting Aids (davit arms, lifting beams, etc.) have not been considered in design, with potential for injury to maintenance personnel removing heavy equipment for servicing / repair / replacement. 维护 —— 设计中尚未考虑起重辅助设施（吊臂、起吊梁等），维护人员在拆卸重型设备进行检修 / 修理 / 更换时可能存在人身伤害风险。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R6] Lighting — Layouts are not available to assess whether lighting for routine operations and maintenance activities is acceptable. 照明 —— 布置图尚未提供，无法评估日常操作和维护活动的照明条件是否满足要求。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R7] System leak detection — Pressure testing of high-pressure system will be hydraulically tested. Hydraulic testing demonstrates mechanical strength of the pressure system but does not demonstrate integrity for a hydrogen system. 系统检漏 —— 高压系统将进行水压试验。水压试验只能证明压力系统的机械强度，无法证明氢气系统的密封完整性。 | Keith / SW response: Helium testing is not routinely carried out in China. Keith / SW 答复： 国内通常不常规进行氦气检漏。 可以做气密性试验；国内整橇系统气密性试验后，分体运至英国，进入工厂房间后，再次组装，需重新进行泄漏试验，现场是否具备试验条件？现场可进行氦气检漏。 和CE认证机构确认一下具体方案。 A pneumatic test can be performed. After the complete skid system undergoes the pneumatic test in China, it will be shipped in split form to the UK. Upon arrival at the factory site and reassembly, a new leak test will be required. We need to confirm whether the site has the necessary conditions/facilities for this test. Helium leak detection is available on site. We will confirm the specific plan with the CE Notified Body. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R8] Line sizing / specification — Vents / headers incorrectly sized / specified, resulting in high back pressure and safety / operability issues, e.g. two-phase flow in emergency vent relief header. 管线规格 / 尺寸 —— 放空 / 泄放总管尺寸或规格不正确，导致背压过高及安全 / 可操作性问题，例如紧急泄放总管中出现两相流。 | 07/10：安全阀进出口尺寸详见P&ID 07/10：Refer to the P&ID for the inlet and outlet sizes of the safety valve. | NO | Chaoqun hu
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R9] Insulation — Insulation requirements not specified, which could result in equipment / pipe layout not allowing space for insulation to be installed. 保温 —— 保温需求尚未明确，可能导致设备 / 管路布置未预留保温安装空间。 | Confirm the insulation material with Keith and determine the thickness. Once it's confirmed, provide a progress report on July 10th. 和Keith确认下保温材料，然后确定厚度。确定后，7月10日反馈进展 3D模型中管路的间距已按照保温厚度30-35mm预留了保温的安装空间。 The spacing between pipes in the 3D model has been designed to accommodate an insulation installation gap of 30-35mm, as per the insulation thickness requirements. | NO | Yinghui cheng/Chaoqun hu/Shuangshuang fan/Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R10] Modular design — Modular design could introduce significant increase in site construction activities, e.g. mechanical and EC&I installation and subsequent testing. 模块化设计 —— 模块化设计可能大幅增加现场施工工作量，例如机械与电控仪表安装及后续测试。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 现有模块化设计的方案是根据进口电梯的尺寸，将整套设备拆分为4个撬块运输组装。 SW建议：需再考虑从屋顶直接吊装进去的方案，需要在后续周三会上进一步讨论。 The current modular design solution involves dividing the entire set of equipment into four skids for transportation and assembly based on the dimensions of imported elevators. SW Recommendation: Further consideration is needed for the direct hoisting-in-from-the-roof solution, which will be discussed in the upcoming Wednesday meeting. | NO | Chaoqun hu/Shuangshuang fan
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R11] Skid assembled on site could result in CE / UKCA Responsible Person / Authorised Representative in China not being able to issue Declaration of Conformity for Skid Package. 撬块在现场组装可能导致中国境内的 CE / UKCA 负责人 / 授权代表无法为撬块整机签发符合性声明（Declaration of Conformity）。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 与CE认证方沟通确认好细节，特别是认证机构是否需要到UK现场验证，再发证。 We will communicate with the CE Notified Body to confirm all the details, in particular whether the certification body needs to attend the UK site for verification prior to issuing the certificate. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R12] Wall penetrations — Layouts and cable schedules not available to confirm space is available for pipe / cable penetrations to / from R23 Module. 穿墙孔 —— 布置图和电缆清单尚未提供，无法确认与 R23 模块之间的管道 / 电缆穿墙位置有足够空间。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.6 | The initial cable schedule of CIMT is not fully aligned with the SW plan. SW has sent SLD, CIMT is verifying design discrepancies and will feed back comparison results, followed by discussions with SW CIMT初版线缆计划与SW计划没有完全匹配，SW已发出单线图，CIMT核对设计差异，返回对比结果，再与SW讨论。 7/23：CIMT根据SW提供的单线图，更新了电缆数量。部分流量控制器电缆待确认。硬联锁开关阀点位本安/隔爆待确认。 7/29: 已返回对比结果，待与SW讨论确认 7/23：CIMT update the cable quantity based on the SLD provided by SW. some cables are still pending confirmed, 1. for flow controllers(modbus or 4-20mA). 2. for HW interlock on-off valve(I.S. or Ex d) comparison has been made , pending conifrm | NO | Dezhi meng
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R13] Catalyst charge point — Inlet pipe diameter is small and blockages may occur. 加料口 —— 加料管径较小，可能发生堵塞。 | Keith / SW response: Inlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking inlet pipe. Keith / SW 答复： 加料接口已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞加料管的风险。 | YES
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R14] Catalyst physical property requirements (size, shape, packing, etc.) are not defined, with the potential for incompatible catalyst to be charged to the reactors. 催化剂物性要求（粒径、形状、装填密度等）尚未定义，存在向反应器加入不兼容催化剂的风险。 | 07/10：催化剂直径0.5mm-5mm，形状不重要，球形，圆柱形，不规则颗粒状都可以，装填密度一般0.5g/mL来估算，但催化剂强度要高，不容易破碎起粉 07/10：The catalyst particle diameter ranges from 0.5 mm to 5 mm, with no specific shape requirement; spherical, cylindrical and irregular granular forms are all acceptable. The bulk density can be estimated at 0.5 g/mL in general. Meanwhile, the catalyst shall feature high mechanical strength to avoid fragmentation and dust generation. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R15] Packing of catalyst is not controlled, with the risk of reactants / gas channelling in the continuous reactor column, and the potential for incomplete reaction or impurities forming. 催化剂装填未受控，存在反应物 / 气体在连续反应柱内形成沟流的风险，可能导致反应不完全或杂质产生。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R16] Contained charge system design not available to assess risks and / or design limitation. 密闭加料系统的设计尚未提供，无法评估其风险与设计局限。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R17] Manual handling requirements for catalyst charging not assessed. 催化剂加料的人工搬运需求尚未评估。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R18] Access to charge point and support of charge container / bag not designed (access steps / integrated support shelf). 加料口的通道以及加料容器 / 料袋的支撑尚未设计（例如操作台阶、集成支撑架）。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R19] 20-micron catalyst retaining screen — Screen blockages prevent / limit flow of gas / reaction mix to continuous reactors. 20 微米催化剂拦截筛 —— 拦截筛堵塞会阻止 / 限制气体 / 反应液流入连续反应器。 | Keith / SW response: China Operations have reported blockages occur in local plant and screen has been removed and discarded. Keith / SW 答复： 国内运行反馈已在本地装置中发生堵塞，已将拦截筛拆除并弃用。 | YES
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R20] Polishing filter (FTR9832) — Filter blockages prevent / limit flow of gas / reaction mix through continuous reactors. Pressure increases in reactor system, with potential for undesirable reactions to occur, until reactor high-pressure trip is activated. 精滤器 (FTR9832) —— 滤芯堵塞会阻止 / 限制气体 / 反应液流经连续反应器；反应器压力升高，直到触发高压跳停前可能发生副反应。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 待定/To be determined | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register CR01 – CR03 Reactors CR01 – CR03 反应器 | [R21] Temperature control — Jacket temperature control is configured to control jacket temperature only. Reactor internal temperatures are monitored, but no control, alarms or interlocks are configured for process control. 温度控制 —— 夹套温度仅控制夹套温度本身。反应器内部温度虽被监测，但未针对工艺过程配置控制、报警或联锁。 | Keith / SW response: Scale-up provides large operating envelopes for process temperature requirements and additional control, alarms and interlocks are not required. Keith / SW 答复： 由于放大试验提供了较大的工艺温度操作裕度，无需增加额外的控制、报警或联锁。 | YES
07/02 | SW - Risk Register System Pressure Monitoring 系统压力监测 | [R22] Differential pressure monitoring — Accuracy of static pressure measurements may not enable differential pressures to be calculated with any degree of accuracy or certainty. 差压监测 —— 静态压力测量精度可能不足以支持差压计算达到所需的精度或置信度。 | 通过反应柱上和反应器进出口管线上的的压力变送器精度估算，最大差压误差大约为40kPa。 Based on the accuracy estimation of the pressure transmitters on the reaction column and the inlet/outlet pipelines of the reactor, the maximum differential pressure error is approximately 40kPa. 07/14压力也增加了联锁。The pressure also increased the interlock. | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register Over Pressure Protection 过压保护 | [R23] Relief system design — Pressure systems not identified and relief studies not available. Identification of worst-case relief scenario not identified, and relief streams may be incorrectly categorised. Details of maximum reaction exotherm not fully documented. 泄放系统设计 —— 压力系统尚未识别、泄放研究尚未提供。最坏工况泄放情景未识别，泄放物流可能被错误归类。反应最大放热的详细信息尚未完整记录。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：详见安全阀计算书 07/10：See safety valve calculation sheet for details. | NO | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R24] Vessel design — Complete degassing of product stream not achieved, with the potential for hydrogen carry-over into BT04 and product transfer containers. 容器设计 —— 产品物流未实现完全脱气，H₂ 可能带入 BT04 及产品转运容器。 | 07/10：气液分离器满足气液分离的要求 07/10：The gas-liquid separator meets the requirements for gas-liquid separation. | NO | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R25] Cleaning of separator not fully understood but current concept relies on vessel free-draining to BT04. Current spray ball sizing is not consistent with this approach and may require significant rework to process piping. 分离器清洗方案尚未完全明确，当前概念依赖容器向 BT04 的自重排放。现有喷淋球规格与该思路不匹配，可能需要对工艺管路进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.4,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register Separator 气液分离器 | [R26] Cleaning of LIT003 housing does not appear to be considered in design. LIT003 液位变送器外壳的清洗在设计中似乎尚未考虑。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.7 | 同上42行回复/Translation of the 42nd line above. | NO | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R27] P&ID does not clearly show nozzle locations and could lead to mal-ops / misunderstanding of the design intent by the Operations team. P&ID 上未清晰标注管嘴位置，可能导致运行团队误操作或误解设计意图。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.3 | 07/10：已标注，详见P&ID 07/10：Marked as indicated; refer to the P&ID for details. | NO | Chaoqun hu
07/02 | SW - Risk Register Sampling 取样系统 | [R28] Sampler design — When depressurising the sample collection chamber, high gas or vapour vent rates could result in a bubbly or churn-turbulent flow regime, and sample will discharge to vent line as two-phase flow. 取样器设计 —— 对取样收集腔进行减压时，气体或蒸汽的高排放速率可能形成鼓泡或搅动湍流流态，样品将以两相流形式排入放空管。 Related Outstanding Questions ｜ 关联待澄清问题：Q5.1 | 07/10：缓冲罐静置一定时间，让气液分层，泄压时缓慢打开手阀 07/10：Allow the buffer tank to stand for a certain period for vapor-liquid stratification, then open the manual valve slowly during depressurization. | NO | Chaoqun hu
07/02 | SW - Risk Register Sampling 取样系统 | [R29] With significantly more gas being present in the process stream, what will prevent overpressure of sample bottle and low-pressure nitrogen pipework? 由于工艺物流中气体明显较多，采用什么措施来防止取样瓶和低压氮气管路的超压？ | 07/10：取样瓶和氮气管线投用时，系统已泄压至常压 07/10：The system has been depressurized to atmospheric pressure prior to commissioning of sampling bottles and nitrogen pipelines. | NO | Chaoqun hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R30] Catalyst Discharge Plug valve — Outlet pipe diameter is small and blockages may occur. 催化剂卸料闸阀 —— 出口管径较小，可能发生堵塞。 | Keith / SW response: Outlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking outlet pipe. Keith / SW 答复： 出口接管已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞出口管的风险。 | YES
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R31] Contained discharge system design not available. Layout design may not provide sufficient headroom for contained discharge system. 密闭卸料系统的设计尚未提供。当前布置可能无法为密闭卸料系统提供足够的顶部空间。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R32] Complete removal of catalyst during discharging operations is unlikely to remove 100% of the material, with the risk of cross contamination of catalyst material between campaigns. 卸料操作难以完全（100%）清除催化剂，存在批次间催化剂交叉污染的风险。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R33] CIP Design — CIP design incomplete. Initial spray ball sizing is inconsistent with process line sizing approach and may require significant rework to process piping and/or equipment layout. CIP 设计 —— 就地清洗设计不完整。初步喷淋球规格与工艺管路选型方式不匹配，可能需对工艺管路和 / 或设备布置进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.1,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R34] Cleaning carried out at nominally atmospheric pressure with the risk of material being trapped between flanges, which tend to separate slightly during high-pressure operation, and could lead to cross contamination between batches. 清洗在近常压下进行，高压运行时法兰会出现微量分开，可能将物料残留于法兰间隙中，进而导致批次间交叉污染。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. | NO | Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R35] Validation / Verification — Cleaning validation / verification philosophy not available. QA may not accept that the continuous reactor achieves minimum cleaning standards. 验证 / 确认 —— 清洗验证 / 确认策略尚未提供。质量保证部门可能不接受连续反应器满足最低清洗标准。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.2,Q1.9 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 更新清洗方案后讨论/Discuss after updating the cleaning procedure. | NO | Chaoqun hu/Xiantao Feng
07/02 | SW - Risk Register Cleaning 清洗 | [R36] Layout — Layouts are not available to evaluate the impact of bypasses, dead legs, drains, vents, etc. 布置 —— 布置图尚未提供，无法评估旁路、死管、排放、放空等的影响。 |  | NO | Shuangshuang fan/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R37] Layout — Layouts are not available to evaluate access to equipment for visual inspections, which may impact the effectiveness of critical inspections. 布置 —— 布置图尚未提供，无法评估设备的目视检查通道，可能影响关键检查的有效性。 |  | NO | Shuangshuang fan/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R38] Layout — Equipment design / layout does not allow for routine disassembly and manual cleaning. Equipment turnaround times and operating costs would be adversely impacted if CIP system cannot be validated. 布置 —— 设备设计 / 布置未考虑日常拆装和人工清洗。如 CIP 系统无法通过验证，设备周转时间和运行成本都会受到不利影响。 |  | NO | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register FT001 FT001 流量计 | [R39] Liquid Stream Flow Sensor for flow control loop FIC001. FT001 is a Coriolis mass flow meter installed downstream of the metering pump MP01. Pulsed flow from the pump will impact on the flow measurement and accurate flow control may not be possible. 液相流量传感器（用于 FIC001 流控回路）—— FT001 是安装在计量泵 MP01 下游的科里奥利质量流量计。泵的脉冲流会影响流量测量，可能无法实现精确流量控制。 | Keith / SW response: China Team have previously used this configuration and not experienced flow control issues. No further action required. Keith / SW 答复： 国内团队此前采用过该配置，未出现流控问题。无需进一步动作。 | YES
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R40] Maximum flow may exceed separator design limitations and carry hydrogen over into BT04 / product collection containers. 泵的最大流量可能超出分离器的设计上限，将 H₂ 带入 BT04 / 产品收集容器。 | 07/10：分离器的直径足够大，泵为最大流量时能满足分离要求 07/10：The separator has a sufficiently large diameter to meet separation requirements even when the pump operates at maximum flow rate. | NO | Chaoqun hu
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R41] Pump turndown does not meet URS minimum flow requirements. 泵的调节比无法满足 URS 中规定的最低流量要求。 | 07/10：机泵条件中规定了泵的最小流量要求，待泵厂家返回资料时审查是否满足最低流量要求 07/10：Minimum flow requirements for pumps are specified in pump data sheets. Compliance with the minimum flow criteria shall be verified upon receipt of vendor documentation. | NO | Chaoqun hu
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R42] Hydrogen gas flow controller — Flow controller does not support tight shut-off and system pressure increase during hold periods. 氢气流量控制器 —— 控制器不支持严密关断，系统在保压期间压力会持续上升。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller to provide tight shut-off. Keith / SW 答复： 在控制器下游追加一台切断阀以提供严密关断。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R43] Maximum flow through controller may exceed separator design limitations and carry liquid into the vent line. 流经控制器的最大流量可能超出分离器设计上限，将液体带入放空管。 | Keith / SW response: High level interlock installed in the separator to stop gas supply and close PIC028 shut-off valve (CV08). Keith / SW 答复： 在分离器上设置高液位联锁，停 H₂ 供给并关闭 PIC028 的切断阀（CV08）。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R44] Time required for pressure testing the system and nitrogen inertion may be excessively high. 系统加压试验及氮气钝化所需时间可能过长。 | Keith / SW response: Pressure test / inertion times to be evaluated during FIC003 selection. Manual vent installed on BT03 to reduce depressurisation times via FIC003. Keith / SW 答复： 在 FIC003 选型时评估压力试验 / 惰化时间。在 BT03 上加装人工放空阀，缩短经 FIC003 的减压时间。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R45] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端的差压超出厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register LIC003 LIC003 分离器液位 | [R46] SE01 Separator Level Indicator — Cleaning / decontamination of housing is not possible. Residual product in housing could lead to cross contamination between campaigns. SE01 分离器液位指示 —— 变送器外壳无法进行清洗 / 净化。外壳内的残留物料可能导致批次间交叉污染。 | Keith / SW response: Design relies on dissolution of residual material. 100% flood-fill of housing is not possible, therefore any residual trace contamination in the housing is deemed to be small and will not significantly impact cleaning verification. Keith / SW 答复： 设计依赖残余物料的溶解。外壳无法 100% 灌满，因此外壳内任何残余痕量污染被视为很小，不会显著影响清洗验证。 | YES
07/02 | SW - Risk Register FIC004 FIC004 分离器液位控制 | [R47] Separator outlet flow / level control — Differential pressure across the controller exceeds manufacturer's recommendations and controller capability. 分离器出口流量 / 液位控制 —— 控制器两端差压超出厂家建议范围及控制器能力。 | 分离器出口先通过减压阀减到0.2MpaG左右，可以满足厂家建议的差压范围 The outlet of the separator is first reduced to approximately 0.2MpaG through a pressure reducing valve, which can meet the differential pressure range recommended by the manufacturer | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register FIC005 FIC005 BT01 氮气吹扫 | [R48] BT01 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT01 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register FIC007 FIC007 BT04 氮气吹扫 | [R49] BT04 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R50] System back pressure controller — The back pressure controller does not support tight shut-off during hold periods and system pressure will not be maintained. 系统背压控制器 —— 该控制器在保压期间不支持严密关断，系统压力无法保持。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller. Keith / SW 答复： 在该控制器下游追加一台切断阀。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R51] Time required for depressurising the system following pressure testing and nitrogen inertion may be excessively high. 加压试验和氮气钝化之后系统减压所需时间可能过长。 | Keith / SW response: Manual bypass installed around PIC028 controller. Keith / SW 答复： 在 PIC028 控制器周围加装人工旁路。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R52] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端差压超出厂家建议范围，可能导致控制器无法正常工作。 | 关于背压阀028，之前厂家计算反馈的阀前背压范围最大为0.9~6MpaG，范围量程比不能过大。 About the back pressure valve 028, previously, the manufacturer calculated and reported that the maximum range of the back pressure before the valve was 0.9 to 6MpaG, and the range-to-range ratio cannot be too large. | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register PIC030 PIC030 分离器液相出口减压 | [R53] Separator liquid outlet pressure reducer — Is this confirmed as a Bronkhorst pressure controller, or is a mechanical regulator still an option? Does this provide the required independence assumed in the relevant SIL / risk assessments? 分离器液相出口减压器 —— 该阀是否确认为 Bronkhorst 电子压力控制器？还是仍可能选用机械式减压阀？该配置能否提供相关 SIL / 风险评估中假设所需的独立性？ | 目前选型机械式减压阀。机械阀不是电子设备，没有相关的SIL认证。 At present, mechanical pressure reducing valves are being selected. Mechanical valves are not electronic devices and do not have the relevant SIL certification. | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register PIC049 PIC049 BT04 背压控制 | [R54] BT04 back pressure controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 背压控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register Automation 自动化 | [R55] Automation Build — Philosophy and Design documentation not available to assess risks and limitations. 自动化建设 —— 自动化策略与设计文档尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q3.1,Q3.2 | 专题沟通后确定反馈 | NO | Chaoqun hu/Dezhi meng/Ziliang zhao
07/02 | SW - Risk Register Documentation 文档 | [R56] Technical File — Technical File not available to assess risks and limitations. 技术文件 —— 技术文件尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.5,Q7.1 |  | NO | Shaofeng gao/All
07/02 | SW - Risk Register Documentation 文档 | [R57] O&M Manual — O&M manual not available to assess risks and limitations. 操作维护手册 —— O&M 手册尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q7.1 | 07/10：操作手册的编制还在进行中 07/10：Preparation of the operation manual is still in progress. | NO | Chaoqun hu
07/02 | SW - Risk Register Documentation 文档 | [R58] Emissions Calculations — Calculations to demonstrate expected release of Class A and Class B VOCs to atmosphere are not available. These are required to demonstrate compliance with EA Permit limits. 排放量计算 —— 尚未提供证明 A 类和 B 类 VOC 向大气排放的预期计算。该计算是证明满足 EA 许可（英国环境署许可）限值要求所必需。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW负责排放量计算/SW is responsible for emissions calculation. | NO | Chaoqun hu
07/02 | SW - Risk Register Regulatory Compliance 法规合规 | [R59] CE ¦ Functional Safety ¦ DSEAR / ATEX ¦ PSSR ¦ COSHH ¦ PUWER (Access, manual handling) ¦ Working at Height (Access Steps / Support Shelf) ¦ LOLER (Davit arms) ¦ Lighting ¦ Occupational Hygiene ¦ EA Permit — Regulatory non-conformance would prevent beneficial use of equipment in the UK. CE 认证 ¦ 功能安全 ¦ DSEAR / ATEX 防爆 ¦ PSSR 压力系统安全 ¦ COSHH 危害物质 ¦ PUWER 工作设备（含通道与人工搬运）¦ 高处作业（操作台阶 / 支撑架）¦ LOLER 起重设备（吊臂）¦ 照明 ¦ 职业卫生 ¦ EA 环境许可 —— 任何法规合规缺失都会导致设备无法在英国正常投入使用。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW内部的提醒事项。 CFCT核实加料步梯是否包含在内。 SW提供步梯平台尺寸。 Internal reminders for SW: CFCT to verify whether the feeding staircase is included. SW to provide dimensions of staircase and platform. | NO | Zilang zhao/All
07/14 |  | 根据生产经验，研发建议原R24-CR01的直径由DN80改为DN50，导致产能下降，可能无法满足URS中的产能30kg/day Based on production experience, the R&D team proposes reducing the diameter of the original R24-CR01 from DN80 to DN50. This modification will result in lower production capacity, which may fail to meet the 30 kg/day throughput specified in the URS. | 07/14：周三会上确定/To be confirmed at Wednesday's meeting. 07/15：暂定R24-CR01的直径修改为DN65，等9月份研发提供DN65的反应器实验数据后最终确认反应器的尺寸为DN65或DN50 07/15：It is tentatively agreed to revise the diameter of R24-CR01 to DN65. The reactor size (either DN65 or DN50) will be finalized after the R&D department provides DN65 reactor test data in September. | NO | Xiantao Feng/All
07/23 | SW | 气液分离器SE01容器承受从常压到60 barg的压力循环次数？ How many pressure cycles does the gas-liquid separator SE01 vessel undergo from atmospheric pressure to 60 barg? | 07/23:会上讨论了加氢装置的操作周期，意见存在不一致，关于连续加氢的年运行周期，SW内部沟通后反馈循环次数需求。 气液分离器的设计温度调整到270℃，对应设计压力调整到7.5MPaG。垫片选用金属环垫片。 07/23：The operating cycle of the hydrogenation unit was discussed at the meeting, and divergent opinions remain. SW shall coordinate internally and provide feedback on the required number of cycles regarding the annual operating cycle for continuous hydrogenation. The design temperature of the gas-liquid separator shall be revised to 270°C, with the corresponding design pressure adjusted to 7.5 MPaG. Metallic ring gaskets shall be adopted . | NO | Zilang zhao/Chaoqun hu
07/23 | IEPE | P&ID中压力表无根部阀，是否需要增加根部阀？ Pressure gauges shown on the P&ID are not equipped with root valves. Is it necessary to add root valves? | 07/23:按照现有P&ID配置。 07/23：Configure in accordance with the existing P&ID. | NO | Chaoqun hu/Yu gao
07/23 | IEPE | PCV028侯径小，反应系统卸压时，全开PCV028卸压速度也很慢，建议将PCV028的旁通手阀改为开关阀 PCV028 has a small orifice. When depressurizing the reaction system, the depressurization rate remains low even if PCV028 is fully open. It is recommended to change the bypass manual valve of PCV028 to an on-off valve. | 07/23:单独发邮件沟通。 07/23：We will communicate via separate email. | NO | Chaoqun hu

## 0701
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. 05/12：Keith建议用气液两相计算安全阀尺寸，不提供模板 05/12：Keith suggests using gas-liquid two-phase calculations for determining the size of the safety valve, but no template is provided. 05/20：根据API520的气液两相泄放时计算安全阀尺寸，部分已完成 05/20：Calculate the size of the safety valve based on the API520 standard for the two-phase gas-liquid discharge situation.Partially completed. 06/02：安全阀计算初版已完成（包含临界流体和气液两相），校审中。 06/02：Preliminary calculation of safety relief valve (covering critical fluid & gas-liquid two-phase flow) completed, under review. 06/09: General 1. What was the source/reference for the Specific Volumes stated in column D/D 列中比容数据的来源及参考依据是什么？ The Specific Volumes stated in column D are derived from Aspen Plus simulation results.比容数据来自Aspen模拟 2. There is no backpressure considered in the calculation. The emergency vent relief will create some backpressure which needs to be considered in the calculation./本次计算未考虑背压。紧急放空泄放过程会产生一定背压，该因素需纳入计算。 Backpressure consists of static backpressure and built-up backpressure. Given the wide total pressure range, backpressure effects shall be incorporated into the calculation.背压分为静背压和积聚背压，总压力范围大，将背压包含在其中 3. At the assumed relief pressure Ethyl Acetate will be a supercritical fluid, therefore the required relief mass flowrate will not be dependent on the latent heat of vapourisation, and the calculated ‘required discharge area’ will not be valid. Do you agree with this statement, or have you found a reference in the standard that allows for this? 在设定的泄放压力下，乙酸乙酯将处于超临界流体状态，因此所需泄放质量流量不再依赖汽化潜热，本次算出的所需泄放流通面积也不再适用。你是否认同该观点？或是你是否在相关标准中查到可支持该计算的依据？ 详见06/16回复. Please refer to the reply dated 06/16 for details. Cooling Failure Calculations 4. For the cooling failure calculation, I would suggest using 550kJ/mol rather than 501.48. This is based on Sandwich PSL experience of heats of reaction. 针对冷却失效工况计算，建议将反应热取值由 501.48 kJ/mol 改为 550 kJ/mol。该取值参考了桑威奇工艺安全实验室（Sandwich PSL）过往反应热项目经验。 OK 5. Is the feed flowrate used in the calculation, based on the maximum metering pump capabilities? Do you assume a maximum concentration of reactant in the feed stream? 计算中采用的进料流量，是否按照计量泵最大额定流量取值？计算时是否假定进料流中反应物浓度为最大浓度？ The flow rate used in the calculation is set at the maximum rated capacity of the metering pump, and the maximum reactant concentration is adopted for the feed stream.计算时流量是按照计量泵最大额定流量取值，反应物浓度为最大浓度 06/16：根据文献“Relief Calculation for Supercritical Fluids”计算超临界流体的质量泄放流量，会后向Keith发计算书审核 06/16：Calculate the mass relief flow rate of supercritical fluids in accordance with the document Relief Calculation for Supercritical Fluids, and send the calculation sheet to Keith for review after the meeting. | YES | Chaoqun Hu
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun HU
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. 06/16：06/11已收到审核完成的URS。 06/16：Received the reviewed URS on 06/11. | YES | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith确认CV08也是故障关，可以使用DS6080型，该型号没有5 bar 差压限制。 Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith confirmed that CV08 is also a faulty-close type, the DS6080 model can be used. This model does not have a 5-bar differential pressure limit. Keith offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. 06/02 进展：Habonim厂家反馈了样本资料，反馈可以满足工艺参数需求，货期大概16~20周。可以作为开关阀的备选品牌。 06/02 Progress: "Habonim" manufacturer has provided sample materials that can meet the process parameter requirements. The delivery time is approximately 16 to 20 weeks. It can be an alternative brand for on-off valves. | YES | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. 06/02：关于气液分离器液相出口减压，电子压力阀和自力式减压阀都可以满足使用，首选自力式减压阀。 06/02：For pressure reduction at the liquid outlet of the gas-liquid separator，both electronic pressure valves and self-operated pressure reducing valves can meet the requirements, with self-operated pressure reducing valves being the preferred choice. | YES | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. 05/20：SW已更新完URS并发出。The SW has been updated and the URS has been sent out. | YES | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表数据单。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. 06/23:仪表条件表已更新完成 06/23：The instrument conditions table has been updated and completed. 07/10：仪表数据单已更新完成 07/10：Instrument Data Sheet has been fully updated. | YES | Chaoqun Hu/Yu Gao
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. 05/20：SW已更新完PFD并发出。The SW has been updated and the PFD has been sent out. | YES | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ 4/30：Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? | NO | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted?05/12Decided not to make any adjustments. 05/12确定不做调整。 05/12：It is determined that the height of the catalyst bed in the main reactor will not be adjusted. | YES | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. 06/16：会议澄清：待布局完成后，SW主导完成爆炸危险区域的划分 09/06：Meeting Clarification: SW shall take the lead in completing the classification of hazardous areas for explosion after layout design is finalized. | NO | All
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | YES | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements. | 05/20：与聂博沟通，小试使用的是进口是插底的分离器，生产使用的是侧进的分离器，按会议沟通的气体最大流量0.2Nm³/h，液体最大流量20L/h重新计算了分离器 05/20: Communicated with Nie Bo. The small-scale test used an imported bottom-insertion separator, while the production version used a side-inlet separator. Based on the maximum gas flow rate of 0.2 Nm³/h and the maximum liquid flow rate of 20 L/h for the communication at the meeting, the separator was recalculated.. | YES | Chaoqun Hu
06/02 | IEPE | 管道编号中的管线尺寸一般是指的公称直径，PID中尺寸为10mm的管道是Φ10mm，公称直径为6mm The line size in pipe line designations generally refers to the nominal diameter. In a P&ID, a pipe with a size of 10mm is specified as Φ10mm, corresponding to a nominal diameter of 6mm. | 06/02：会议澄清：DN15以下的管道，管道编号中的管径为外径，DN15及其以上的管道，管道编号中的管径为公称直径。 06/02：Clarification from meeting:For piping below DN15, the size specified in pipe tag number denotes outer diameter; for DN15 and above, the size in pipe tag refers to nominal diameter. | YES | Chaoqun Hu
06/02 | IEPE | 设备BT-01/03/04上的压力变送器不便于现场观察，是否可以考虑也选用WIKA的不带现场显示紧凑型的压力变送器？ The pressure transmitter on the equipment BT-01/03/04 is not convenient for on-site observation. Could it be considered to also choose WIKA's compact pressure transmitter without on-site display？ | 06/02：会上建议保留BT-01/04的现场显示，BT-03可不带现场显示。 06/02：It was suggested at the meeting that the on-site display of BT-01/04 be retained, while BT-03 may not have an on-site display. | YES | Yu Gao
06/02 | CFCT | 1-PID中V-9868，V-9965阀柄的含义？ What is the meaning of valve handles V-9868 and V-9965 in PID? 2-PID中压力变送器底部波纹含义是什么？ What does the corrugation at the bottom of the pressure transmitter signify? 3-与管道直径对应的保温厚度是多少？ What is the insulation thickness corresponding to the diameter of the pipeline? | 06/02： 1.PID中阀门V-9868，V-9965的阀柄为弹簧复位阀柄； In the PID,the valve handles of V-9868 and V-9965 are spring-reset handles； 2.PID中带底部波纹的压力变送器要求压力变送器带隔膜； The pressure transmitter with a bottom ripple in PID requires the pressure transmitter to be equipped with a diaphragm； 3.Keith分享了建议的管道直径与保温厚度表格，直径10到25mm的管路，保温厚度为30-35mm。 Keith shared the recommended pipe diameter and insulation thickness table, with insulation thickness ranging from 30-35mm for pipes with diameters of 10 to 25mm. | YES | ShuangshuangFan
06/16 | SW | 会议确认：气液分离器为侧进，尺寸为DN200*600mm，下次例会前CFCT向SW提供气液分离器的设备图纸 Confirmed at the meeting: The gas-liquid separator adopts side inlet configuration with dimensions DN200 × 600 mm. CFCT shall submit the equipment drawing of the gas-liquid separator to SW prior to the next regular meeting. | 06/22设备图纸已提供。06/23Keith回复意见，见06/23讨论内容。 Equipment drawings were provided on 06/22. Keith's feedback was received on 06/23 — please refer to the discussion notes from 06/23. | YES | Ziliang Zhao
06/17 | SW | 根据最新工作进展并结合HAZOP分析所需文件内容，更新“Sandwich Hydrogenation Implementation Schedule” Update the Sandwich Hydrogenation Implementation Schedule based on the latest progress and document requirements for HAZOP study. |  | NO | All
06/17 | SW | 讨论操作规程：哪些部分需要顺控？开停车步骤等 Discuss operation procedures: identify sections requiring sequence control, including startup and shutdown steps, etc. | 06/23：开车步骤：公用工程确认/催化剂装填→氮气置换（R24-BT01、R24-BT04和剩余部分），氧含量<0.5vol%→氢气置换→原料系统备料→TCU系统调温→反应器进料（氢气先进料背压至反应压力，液相再进料）→气液分离→产品转移 停车步骤：停进料→产品缓冲罐物料转移→反应器卸压→R24-BT03卸压→反应系统降温→氮气置换→关闭氮气和TCU Startup Procedures： 1.Verification of utility systems & catalyst loading 2.Nitrogen purging (for R24-BT01, R24-BT04 and the rest of the system), oxygen content controlled below 0.5 vol% 3.Hydrogen purging 4.Raw material preparation for feed system 5.Temperature adjustment of TCU system 6.Reactor feeding: Introduce hydrogen first to build backpressure up to reaction pressure, then feed liquid phase material 7.Gas-liquid separation 8.Product transfer Shutdown Procedures： 1.Cut off feed supply 2.Transfer materials from product buffer tank 3.Depressurize reactor 4.Depressurize R24-BT03 5.Cool down reaction system 6.Nitrogen purging 7.Shut down nitrogen supply and TCU system Keith提供HAZOP时的开停车步骤，结合上述文件，整理开停车和清洗步骤 Compile the plant start-up, shutdown and cleaning procedures based on the above documents together with the start-up & shutdown sequences supplied by Keith for HAZOP assessment. | NO | All
06/17 | SW | 会后确认：安全阀的泄放温度超过设备的设计温度，是否需要提高设备的设计温度？ To be confirmed after the meeting：If the relief temperature of the safety valve exceeds its design temperature, is it necessary to increase the design temperature rating? | 设备和管线材质为316L，结合设备和管道的壁厚，计算得出：在泄放温度下，材料的许用应力满足其强度要求，不需提高设备的设计温度 The equipment and piping are fabricated from 316L stainless steel. Wall thickness calculations for the equipment and piping demonstrate that the allowable stress of the material satisfies the strength requirements at relief temperature; therefore, no increase to the equipment design temperature is required. | Yes | Ziliang Zhao/Chaoqun Hu
06/17 | SW | CFCT做撬块设计时，注意清洗过程中的低点排净 CFCT shall take full consideration of low-point draining during cleaning when designing the skid package. | 06/23：在撬块设计时，设置管道的低点排净阀 When designing the layout, install a drain valve at the low point of the pipeline 06/23会议方案：管道最低点设置排净阀，操作说明中明确排放时用容器收集排放液体。 Meeting Plant: Install drain valves at the lowest point of the pipeline, and specify in the operating instructions to collect the discharged liquid with a container during the drainage process. | Yes | Shuangshuang Fan
06/17 | SW | CFCT提供放空缓冲罐T06是否放在撬内的方案 CFCT to provide a scheme on whether vent buffer tank T06 shall be installed inside the skid. | 06/23：按照现有空间的布置，T06放在撬块内的空间不足；撬块中间的操作维护通道宽度为300-350mm，能否将整体撬块宽度增加150-200mm？ According to the existing space arrangement, there is insufficient space for T06 to be placed inside the pry block; The width of the operation and maintenance channel in the middle of the pry block is 300-350mm. Can the overall pry block width be increased by 150-200mm? 06/23会议方案：T06不放在撬块内，放置在service area，同时反应柱/冷凝器的TCU出口管路上的温度变送器安装在近出口处，去掉手动球阀，安全阀可放到service area，并设置排净阀，进口管路手动球阀保持不变，温度变送器加套管，位置可前可后，低点设置排净阀，整体管路的高点设置排气阀。 Meeting Plant:: T06 is not placed inside the lever block but in the service area. The temperature transmitter on the TCU outlet pipeline of the reaction column/condenser is installed near the outlet. The manual ball valve is removed, and the safety valve can be placed in the service area. A drain valve is installed, while the manual ball valve on the inlet pipeline remains unchanged. The temperature transmitter is equipped with a protective sleeve, with its position adjustable forward or backward. A drain valve is set at the low point, and an air vent valve is installed at the high point of the entire pipeline. | Yes | Shuangshuang Fan
06/23 | SW | Keith意见： 基本设计：我们是否有经批准的分离器设计方案？我上次看到的摘录中，计算出的容器直径为3毫米，这表明计算或输入数据可能存在错误。 Basic design 1. Do we have an approved design for the separator. The last extract I saw had a calculated vessel diameter of 3mm, which suggests an error in the calculations or input data. | 06/23讨论： 基本设计：按最新设备数据表进行气液分离器设计。气液分离器的计算书已复核过，数据无误。 06/23Discussion—Basic Design: The gas-liquid separator shall be designed in accordance with the latest equipment data sheet. The calculation sheet for the gas-liquid separator has been reviewed and the data are confirmed to be correct. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 分离器内件 1、本设计中是否已考虑分离器内件，例如入口导流装置或入口旋风分离器、气相除雾器、液体出口处的防涡流挡板？ 2、喷淋球能否采用焊接固定方式，而非通过管接头引入容器内部？ 3、喷淋球是否必须为旋转式喷淋球？这会增加设备复杂度，并在工厂运行寿命期内带来检查与维护方面的问题。 4、喷淋球实际能否起到喷淋清洗作用，还是仅仅将容器注满清洗液直至触发高位液位开关？根据此前讨论，从空罐到高位跳闸点的时间不足25秒，这无法为分离器气相侧提供足够的机械清洗作用时间。 Separator internals 1. Have separator internals been considered for this design e.g. inlet diverters or inlet cyclones, demisting of the vapour stream, vortex breakers on the liquid outlet. 2. Can the spray ball be welded in position rather than introducing a tube fitting into the vessel. 3. Does the spray ball need to be a rotary spray ball. This adds complexity and inspection/maintenance issues during the life of the plant. 4. Will the spray ball actually work as a spray ball, or will it simply fill the vessel with cleaning fluid until the high-level switch is activated. Based on previous discussions this would be less than 25 seconds from empty to high-level trip point, which doesn’t allow much time for mechanical cleaning action in the gas side of the separator. | 06/23讨论： 分离器内件： 1、气液分离器设计采用重力式分离，无需额外的内件。 2、喷淋球相关事宜，CN团队内部结合喷淋球供应商商议方案。 06/23 Discussion — Separator Internals: 1.The gas-liquid separator is designed as a gravity-type separator; no additional internals are required. 2.Regarding the spray ball matters, the CN team will internally discuss and determine the solution in coordination with the spray ball supplier. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 设计参数 1、“流体性能”是否应定为“非致命性”？我推测此概念类似于PED容器设计中的流体分组，在英国规范中应属于Group 1气体（即可燃/爆炸/有毒），而非“非致命性”。 2、工作压力应为0至6MPaG。 3、设计温度应至少为150°C，并且我假设在泄压事故工况下，容器温度可能达到约300°C。 4、设计压力应为全真空至9MPaG。 5、规范是否要求进行焊后热处理（PWHT）？ 6、水压试验压力应为设计压力的1.5倍，即13.5MPaG，而非12MPaG。 7、对于该容器，S4应为DN32 Cl900 WN法兰。喷淋球接口是否应作为单独细节在本图纸上表示，还是另页图纸表示更为合适？ 8、充装系数（Fulling Factor）是多少？ Design Parameters 1. Should the ‘Fluid Performance’ be Non-Lethal? I assume this is similar to the fluid group for PED vessel design, which for the UK would be Group 1 gas i.e. flammable/explosive/toxic and not Non-Lethal. 2. The working pressure should be 0 to 6MPaG. 3. The design temperature should be at least 150 °C and I assume the vessel has the potential to reach circa 300°C during a relief event. 4. The design pressure should be FV to 9MPaG 5. Is PWHT required by the code. 6. Hydro test pressure should be 1.5x design pressure i.e. 13.5MPaG not 12 MPaG. 7. For the vessel, S4 should be a DN32 Cl900 WN Flange. Should the spray ball fitting be shown as a separate detail on this drawing or possibly shown on a separate drawing. 8. What is the Fulling Factor. | 06/23讨论： 设计参数 ： 1、介质调整为易爆。 2、CN团队结合URS，修正工作压力，更新设备数据表。 3、可以将泄压事故工况，纳入到常规设计考虑中，即可提高设计温度到300℃。 4、修正设计压力，更新设备数据表。 5、规范可不进行焊后热处理（PWHT）。 6、水压试验压力为设计压力的1.3倍，故试验压力可不做调整。 7、S4为喷淋口，口径为Φ10，DN32法兰接口结构为保证喷淋球可抽出，后续根据喷淋球整体方案做调整，判定是否需要可抽式。 8、充装系数是指物料实际容积与容器全容积之比。 06/23 Discussion — Design Parameters: 1.The medium classification is revised to "explosive." 2.The CN team will revise the working pressure based on the URS and update the equipment data sheet accordingly. 3.The relief event scenario can be incorporated into the normal design considerations — i.e., the design temperature can be raised to 300°C. 4.The design pressure will be revised and the equipment data sheet updated accordingly. 5.PWHT (post-weld heat treatment) is not required per the applicable code. 6.The hydrostatic test pressure is 1.3 × design pressure, so the test pressure does not need to be adjusted. 7.S4 is the spray ball connection, with a bore size of Φ10. The DN32 flange connection is designed to allow the spray ball to be withdrawable. This will be reviewed and adjusted as part of the overall spray ball solution, and a decision will be made on whether a withdrawable type is necessary. 8.The filling factor is defined as the ratio of the actual liquid volume to the total vessel volume. | YES | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 通用事项 1、管口方位是否已考虑设备布置的最优化？ 2、在撬装高度限制范围内，容器能否通过重力自由排液至产品收集罐？ 3、在顶部法兰上开孔用于引出管，是否会损害其机械完整性并违反安全规范？是否已重新计算法兰厚度或进行有限元分析（FEA），以确保足够的金属厚度和结构完整性？ 4、液位变送器/液位开关的规格是否已确认？法兰尺寸及位置是否与仪表相匹配？ 5、请更新P&ID，以显示S4正确的管口尺寸。 6、是否有容器设计计算书？技术文件中需要包含设计计算书，并应在FAT（工厂验收测试）时进行核查。 General 1. Does the nozzle orientation allow for optimum equipment layout. 2. Can the vessel free drain into the product collection tank, within the skid height constraints. 3. Does boring a hole in the top flange for the outlet pipe compromise its mechanical integrity and violate safety codes. Have you recalculated the flange thickness/carried out FEA to ensure adequate metal thickness and structural integrity. 4. Has the level transmitter/level switches been agreed – does the flange size/position align with the instruments. 5. Update P&ID to show correct nozzle size for S4. 6. Do you have vessel design calculations. Design calculations will be required in the technical file and should be checked at FAT. | 06/23讨论： 通用事项 ： 1、管口方位已结合3D撬装布置给定。 2、3D撬装设计已考虑，待3D模型复核时，详细讨论。 3、重新计算法兰厚度，以满足结构强度要求。 4、仪表工程师已经确认复核。 5、P&ID，不需要更改S4管口尺寸。 6、设计计算书是设备完整技术文件中必不可少的一部分，后续会提供。 06/23 Discussion — General Items: 1.Nozzle orientation has been determined based on the 3D skid layout. 2.The 3D skid design has taken this into consideration; detailed discussion will be held during the 3D model review. 3.The flange thickness will be recalculated to meet structural strength requirements. 4.The instrumentation engineer has confirmed and verified this. 5.The P&ID does not require changes to the S4 nozzle size. 6.The design calculation sheet is an essential part of the complete technical documentation for the equipment and will be provided in due course. | YES | Ziliang Zhao/Chaoqun Hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Overall cleaning philosophy per vessel 各容器整体清洗策略 Please confirm the intended cleaning philosophy for each vessel in the skid — spray-only, soak-only, spray-and-soak combined, or an alternative approach. Please also indicate whether a single philosophy applies across all vessels or whether the strategy varies by vessel. 请确认撬块内各台容器的清洗策略：单独喷淋、单独浸泡、喷淋+浸泡组合，或其它方式。请同时说明是否所有容器采用同一策略，或按容器区别设计。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleanliness verification method & acceptance criteria 清洁度验证方法与验收标准 Please advise the verification method(s) used to confirm cleaning completion (visual inspection, swab / rinse sample analysis, mass balance, calculated residue, etc.) and the numerical acceptance criteria applied (e.g. residue mass, ppm concentration threshold). 请说明用于确认清洗完成的验证方法（目视检查 / 拭子或冲洗样分析 / 物料衡算 / 残余物计算等），以及所采用的数值验收标准（如残余物质量、浓度阈值 ppm）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Sight glass availability for SE01 SE01 视镜配置 The reactor vessels are understood to be fitted with sight glasses to support visual verification of cleanliness. The gas–liquid separator SE01, however, does not include a sight glass. Please confirm the intended method for verifying cleanliness on SE01. 反应柱已配置视镜以支持目视清洁度检查，但气液分离器 SE01 未配置视镜。请确认 SE01 清洁度验证的具体手段（，以及是否考虑将新增视镜作为设计变更纳入）。 | 07/10：反应柱和分离器因为操作压力高，无法配置视镜，清洁度的验证无法依靠目测，需取样分析测量残留物的浓度 07/10：Due to the high operating pressure of the reaction column and separator, sight glasses cannot be installed. Visual inspection is therefore not feasible for cleanliness verification, and residue concentration shall be determined via sampling analysis instead. | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Spray ball flow rate vs. vessel fill time 喷淋球流量与容器充液时间的匹配 The lowest available spray ball flow rate (approximately 2 L/min) results in SE01 reaching the high-level trip point in under 25 seconds. This limits the time window in which mechanical spray action can achieve wetting coverage. Please advise the intended cleaning-time window on SE01 and the approach for ensuring adequate mechanical cleaning action within the design constraint. 现有最小可选喷淋球流量约 2 L/min，导致 SE01 容器在 25 秒内即达到高液位跳停，机械喷淋作用的有效时间窗口非常短。请说明 SE01 上预期的清洗时间窗口，以及在此设计约束下如何确保获得充分的机械清洗作用。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Drain line sizing and fill–drain cycle 排放管径与充液-排空循环 Under the current drain line configuration, the drain rate is significantly slower than the spray inflow rate. Please advise the intended drain line diameter (whether upsizing is planned), the estimated single-cycle fill and drain durations, and the number of cycles anticipated per cleaning campaign. 当前排放管径下，排放速率显著慢于喷淋进料速率。请说明拟采用的排放管径（是否放大）、单次循环的充液和排空时间估算，以及每次清洗预期需要的循环次数。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Soak cleaning vs. high-level interlock defeat mechanism 浸泡清洗与高液位联锁绕过机制 If soak cleaning is adopted on SE01, the liquid level during cleaning will exceed the high-level safety interlock (located at approximately one-third of vessel height). Please specify: (a) the physical mechanism intended for defeating this interlock during cleaning (key switch, procedural lockout, or other); (b) the authorisation and access controls surrounding the defeat mechanism; and (c) the safeguards against inadvertent defeat during normal processing operation. 若 SE01 采用浸泡清洗，清洗过程中的液位将超过位于容器约 1/3 高度的高液位安全联锁。请说明：(a) 清洗时用于绕过（defeat）该联锁的物理机制（钥匙开关 / 程序锁定 / 其它）；(b) 该绕过机制的授权与权限控制方式；(c) 防止正常运行时意外绕过的保护措施。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Cleaning of the guided-wave level transmitter housing Guided wave 液位变送器外壳的清洁 The guided-wave level transmitter housing (approximately 100 mm diameter, side-mounted on SE01) sits above the high-level switch and lies outside the spray ball coverage envelope. Please advise the intended cleaning approach for this housing, and any mechanical or procedural provisions required to ensure it can be cleaned to the acceptance criteria in Q1.2. 液位变送器外壳（约 100 mm 直径，SE01 侧接管上）位于高液位开关之上，不在喷淋球覆盖范围内。请说明该外壳的清洁方案，以及为达到 Q1.2 中的验收标准所需的机械或程序性措施。 | 07/14：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用 07/14：Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. | NO | Chaoqun Hu/Yu Gao
07/01 | SW Cleaning Philosophy 清洗策略与清洗程序 | Reactor cleaning cycle time and manual interventions 反应器清洗循环时间与人工干预 For the 200-L reactor vessels, a single spray-and-drain cycle involves an extended drain phase relative to the spray phase. Multiple cycles are expected to achieve the required cleanliness. Please advise: the anticipated number of cycles, the total cleaning duration per campaign, and the specific manual interventions required at each step (drain valve operation, sample point access, lockout re-set, etc.). 200-L 反应器进行单次"喷淋-排空"循环时，排空阶段远长于喷淋阶段，需多次循环以达到清洁度要求。请说明：预期循环次数、每次清洗总时长，以及各步骤所需的具体人工干预（排放阀操作 / 取样口操作 / 联锁复位等）。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/01 | SW 3D Layout 3D 布置与设备空间 | Operational access clearance 操作通道净空 The current 3D model shows approximately 300–350 mm clearance in certain operator access zones. Please confirm the target minimum clearance from a site operability and maintenance standpoint, and identify any specific zones where relaxation of the current clearance is acceptable, or where additional clearance is required. 当前 3D 模型显示部分操作人员通道净空约为 300–350 mm。请从现场操作与维护角度，确认目标最小净空要求，并识别可以放宽的具体区域，以及需要额外净空的区域。 | 7月10日反馈进展： 建议增加反应柱撬块的宽度，审核模型后给出建议的空间区域。 It is recommended to increase the width of the reaction column skid and provide the suggested spatial area after reviewing the model. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Free-drain feasibility from each vessel 各容器的自重排放可行性 The cleaning strategy relies on free-drain of cleaning fluid from each vessel into downstream collection (BT04 or equivalent). Considering the skid height constraint and each vessel elevation, please confirm the free-drain path is mechanically feasible from each source vessel to its destination. Please identify any vessels where drainage cannot be achieved by gravity and would require pumping or an alternative arrangement. 清洗策略要求清洗液自重从各容器排入下游收集罐（BT04 或等效容器）。考虑撬块高度限制与各容器标高，请确认每台源容器至其目标容器的自重排放路径机械可行。请识别无法通过重力实现排放、需要泵抽或采用替代方案的容器。 | 7月10日反馈进展： 根据目前容器的结构形式，反应柱可通过底部排放阀排放，缓冲罐可通过管路排放，预热器、冷凝器管路无排放口。具体排放方式参考清洗方案。 Based on the current structural design of the containers, the reaction column can be drained through the bottom discharge valve, the buffer tank can be discharged via piping, while the preheater and condenser have no discharge outlets in their pipelines.Refer to the cleaning plan for specific emission methods. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Nozzle orientation on pressure vessels 压力容器管嘴方位 Please review the nozzle orientation on all pressure vessels in the current 3D model. Confirm that nozzle positions provide adequate access for external piping tie-in, instrumentation installation, and maintenance (removal / reinstallation of internals, gasket replacement, catalyst service, etc.). 请审查当前 3D 模型中所有压力容器的管嘴方位。确认管嘴位置能够满足外部管路对接、仪表安装以及维护（内构件拆装 / 密封垫更换 / 催化剂检维修等）的空间要求。 | 7月10日反馈进展： 由于空间尺寸限制，部分管口的维护可能存在不便。优化管口布置或能否增加设备空间。 Due to space size limitations, maintenance of some pipe openings may be inconvenient. Optimize pipe layout or increase equipment space | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Catalyst charging & discharging arrangement 催化剂加料与卸料布置 Please confirm that the catalyst charging (loading) and discharging (unloading) arrangement is compatible with the current nozzle layout on the reactor vessels, and that adequate space is provided for charge / discharge equipment and operator access during catalyst service. 请确认催化剂加料与卸料的操作方式与当前反应柱的管嘴布置兼容，且在催化剂检维修期间为加料/卸料设备与操作人员留有充足空间。 | 7月10日反馈进展： 根据目前的布置方案，反应柱加料卸料口均在撬体端面，结合加料卸料方式看操作空间是否充足。 According to the current layout plan, the feeding and discharging ports of the reaction column are all located on the end face of the pry body. Considering the feeding and discharging methods, it is necessary to check whether the operating space is sufficient. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Tie-in points between skid and site utilities 撬块与现场公用工程接口 Please confirm the finalised location and specification of all tie-in points between the skid and the Sandwich site services, including process feed, product outlet, vent header, HTF supply and return, N₂ blanketing, instrument air, electrical supply, cable penetrations, and drain. Please advise the interfaces where design lock-down is still pending. 请确认撬块与 Sandwich 现场公用工程之间所有接口的最终位置与规格，包括工艺进料、产品出口、放空总管、导热油供回、氮气钝化、仪表空气、电气供应、电缆穿墙、排放。请说明尚未定稿的接口。 | 7月10日反馈进展： 根据现有的布置方案，有部分公用工程的的接口，无仪表空气接口，电气供应、电缆穿墙，后续更新撬块与公用工程接口的位置与规格。 According to the existing layout plan, there are interfaces for some public works without instrument air interfaces, electrical supply, and cable penetration through walls. The location and specifications of the interface between the pry block and the public works will be updated in the future. | NO | Shuangshuang fan/ALL
07/01 | SW 3D Layout 3D 布置与设备空间 | Cable wall penetration capacity and cable compatibility 穿墙电缆孔容量与电缆兼容性 The current design indicates 14 available cable wall penetration slots. Please confirm this final count, the internal diameter of each slot, and the compatibility of the slot with the largest cable type intended to pass through (multi-core, armoured, or shielded cables of relevant cross-section). 当前设计显示可用穿墙电缆孔 14 个。请确认该数量的最终定案、每个孔的内径规格，以及与拟穿过的最大电缆类型（相应截面的多芯 / 铠装 / 屏蔽电缆）的兼容性。 | 寻求工程部支持，和宋小旭主管约会讨论如何推进，7月10日反馈进展 | NO | Dezhi meng/Shaofeng gao
07/01 | SW Control Philosophy 控制策略 | Full Control Philosophy document issue date 完整《控制策略》文件发出日期 Please advise the target issue date for the complete Control Philosophy document, superseding the interim draft version previously circulated. 请说明完整版《控制策略》文件的目标发出日期（覆盖此前流转的过渡草稿版本）。 | 07/10：已完成初版，还在校核中，预计下周发出 07/10：The initial draft has been completed and is under review; it is expected to be issued next week. | NO | Chaoqun hu
07/01 | SW Control Philosophy 控制策略 | Interlock schedule — hardwired vs. software 联锁清单 —— 硬件联锁与软件联锁 Please provide a complete interlock schedule listing all safety interlocks, with clear delineation between hardwired (independent of the PLC) and software (PLC-implemented) interlocks. For each interlock, please include: initiating cause, sensing element, trip setpoint, action taken, and protective function fulfilled. 请提供完整的联锁清单，列出全部安全联锁，明确区分硬件联锁（独立于 PLC）与软件联锁（PLC 实现）。每一条联锁请包含：触发原因、检测元件、跳停设定值、联锁动作、承担的保护功能。 | 07/10：联锁条件已完成初版，还在校核中，预计下周发出 07/10：The initial draft of interlock conditions has been completed and is under review, which is expected to be issued next week. | NO | Chaoqun hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Operational modes and mode-specific fail positions 操作模式与各模式下的故障位 Please define all operational modes of the skid (normal operation, start-up, shut-down, cleaning, catalyst change, emergency depressurisation, etc.), and for each mode specify: (a) the fail position of each control valve; (b) the state of each interlock (active / bypassed); and (c) the permissive conditions required to enter that mode. 请定义撬块的全部操作模式（正常运行 / 开车 / 停车 / 清洗 / 催化剂更换 / 紧急泄压等），并针对每一模式说明：(a) 每个控制阀的故障位；(b) 每个联锁的状态（激活 / 已绕过）；(c) 进入该模式所需的许可条件。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 分离器浸泡清洗时易触发液位高联锁，导致高液位以上清洗不彻底。增大分离器的排净管径可实现淋洗，同时系统处于清洗模式时，绕开液位高联锁。 High level interlock is prone to tripping during soaking cleaning of the separator, leading to inadequate cleaning of areas above the high liquid level. Increasing the drain pipe size of the separator allows shower rinsing. Meanwhile, the high level interlock can be bypassed when the system is under cleaning mode. | NO | Chaoqun hu/Dezhi meng
07/01 | SW Control Philosophy 控制策略 | Mode-transition safeguards 操作模式切换的保护措施 Please advise the safeguards in place against inadvertent mode transitions, particularly from cleaning mode back to processing mode (e.g. an interlock bypass being left in place after cleaning is complete). Please describe both the technical safeguards (key switches, HMI confirmations) and the procedural safeguards (SOP requirements, dual sign-off). 请说明防止意外切换操作模式（尤其是从清洗模式返回处理模式时联锁绕过未复位）的保护措施。请分别描述技术性保护措施（钥匙开关 / HMI 确认）与程序性保护措施（SOP 要求 / 双签发）。 | 52条和Keith讨论后1周反馈。 | NO | Dezhi meng
07/01 | SW Sampler System 取样系统 | Sample vaporisation during pressure reduction 取样过程中的样品闪蒸 The sampler transfers process fluid from a line operating at up to 60 barG to a sample container at approximately atmospheric pressure. Please advise the analysis of vaporisation during this pressure reduction (fraction vaporised, temperature drop) and its impact on the compositional representativeness of the collected sample. 取样器将最高 60 barG 工艺管路的介质转移至常压取样瓶。请说明此压降过程中的闪蒸分析（气化比例、温度降低）及其对所采样品成分代表性的影响。 | 07/10：冷凝器出口的温度为30℃，压力从60barG 泄至常压，此温度条件下不会发生闪蒸 07/10：The temperature at the condenser outlet is 30°C. The pressure is relieved from 60 barG to atmospheric pressure, and no flashing will occur under this temperature condition. | NO | Chaoqun hu
07/01 | SW Sampler System 取样系统 | Sample retention design 样品截留设计 Please advise the design of the sample bottle and sample-transfer system, including any vapour trap, septum, condenser, or other retention device intended to prevent loss of volatiles through the vent path and to ensure a representative liquid sample is captured. 请说明取样瓶及取样传输系统的设计，包括为防止挥发组分从放空路径流失、并确保获得代表性液样所采用的蒸汽阱、隔膜、冷凝器或其它截留装置。 | 07/10：取样器的流程：打开三通阀将缓冲罐充满，打开缓冲罐气相放空管线阀门，将缓冲罐中的气相排走并卸压，打开氮气手阀，将缓冲罐中的液体压至取样瓶 07/10：Sampling procedure: Open the three-way valve to fill the buffer drum. Open the valve on the vapor vent line of the buffer drum to vent the vapor inside and relieve pressure. Then open the nitrogen manual valve to pressurize and transfer the liquid from the buffer drum into the sampling bottle. | NO | Chaoqun hu
07/01 | SW Sampler System 取样系统 | Sampler behaviour under gas-rich flow regime 气相主导流态下取样器行为 With the intended process operating at a stoichiometric excess of hydrogen, the flow regime through the sampling point may be gas-rich with entrained liquid rather than liquid-continuous. Please advise how the sampler design accommodates this flow regime, and whether any sample point relocation, phase separator, or coalescer is being considered. 工艺预期在化学计量氢气过量条件下运行，取样点处流态可能为"气相夹带液体"而非液相连续。请说明取样器设计如何适应此流态，以及是否考虑取样点位置调整、加装相分离器或聚结器。 | 07/10：取样器的缓冲罐上有气体排放管线，取样罐充满后，打开气体排放管线，将气相排走并卸压，再用氮气将液相压至取样瓶 07/10：The buffer vessel of the sampler is equipped with a gas vent line. Once the sampling tank is full, open the gas vent line to vent the vapor phase and relieve pressure, then push the liquid phase into the sampling bottle with nitrogen. | NO | Chaoqun hu
07/01 | SW Instrumentation 仪表配置 | Guided-wave level transmitter — datasheet & cleanability Guided wave 液位变送器 —— 数据单与可清洁性 Please provide the guided-wave level transmitter datasheet and confirm: (a) the process compatibility of the probe assembly with the intended service (including any operating conditions in the supercritical or near-critical regime); and (b) the cleanability of the probe assembly under the adopted cleaning philosophy. 请提供 guided wave 液位变送器数据单，并确认：(a) 探头组件在拟定工况（含超临界或近临界工况）下的适用性；(b) 探头组件在拟采用清洗策略下的可清洁性。 | 7月10日反馈进展 (a) 导波雷达液位计工作原理是雷达波可以穿过介电常数较低的气相，遇到介电常数较大的液相返回，从而计算液位。适用蒸汽、粉尘、泡沫等工况。需了解超临界工况下的介质状态是否还存在液相，如果没有液相空间，则液位计无法识别。 The working principle of the guided-wave radar transmitter is that the radar wave can pass through the gas phase with a lower dielectric constant and return to the liquid phase with a larger dielectric constant, thereby calculating the liquid level. It is applicable to working conditions such as steam, dust and foam. It is necessary to understand whether there is still a liquid phase in the medium state under supercritical conditions. If there is no liquid phase space, the transmitter cannot identify it. 07/15进展：经内部评估，液位计所在容器操作工况下不存在超临界状态。 After internal assessment, it was determined that the liquid level gauge is not in a supercritical state under the operating conditions of the container it is located in. (b)BT01和BT04的导波雷达液位计为顶装内伸形式，可以利用设备内的喷淋头冲洗。SE-01的导波雷达液位计为侧装旁通式，可以选择在探头与旁通管的过程接口处增加配套冲洗环，并预留一路冲洗管线。 The guided-wave radar transmitters of BT01 and BT04 are top-mounted and iInsert type, and can be flushed by the spray heads inside the equipment. The guided-wave radar l transmitter of SE-01 is of side-mounted bypass type. A matching flushing ring can be added at the process interface between the probe and the bypass pipe, and a flushing pipeline can be reserved. 07/14进展：分离器的液位计按照顶装内伸优先考虑，分离器采用平顶的型式以尽可能多的布置管口，若管口布置不下可适当放大分离器直径，安全阀起跳压力和分离器设计压力调整为7.5MPaG，保证法兰等级CLASS900适用. Level transmitters for separators shall preferably be top-mounted with internal extension. The separator shall adopt a flat-top design to accommodate maximum nozzle arrangements. If nozzles cannot be arranged sufficiently, the separator diameter may be enlarged appropriately. The safety valve set pressure and separator design pressure shall be adjusted to 7.5 MPaG to ensure compatibility with CLASS 900 flange rating. 07/17进展：气液分离器雷达液位计侧装改顶装，已完成图纸设计，筒体直径未变，邮件发出。 The radar level gauge for the gas-liquid separator has been redesigned from side-mounted to top-mounted. The drawing design has been completed, and the vessel diameter remains unchanged. The drawings have been sent out via email. | NO | Yu gao/Chaoqun hu/Zilaing Zhao
07/01 | SW Instrumentation 仪表配置 | Level switch position & interlock function 液位开关位置与联锁功能 Please confirm the finalised position (elevation, orientation, flange size and rating) and the interlock function of each level switch (LSL, LSLL, LSH, LSHH) on each vessel, together with the matching instrument selection. 请确认每台容器上各液位开关（低 LSL、低低 LSLL、高 LSH、高高 LSHH）的最终位置（标高、方位、法兰尺寸与压力等级）与联锁功能，以及对应的仪表选型。 | 7月10日反馈进展： 关于液位开关选型，之前寻价时只有VEGA的VEGASWING 63型号可以满足DN25 Class900 M的过程接口，其他厂家如E+H、Rosemount都不能满足。 About the selection of level switches, during the previous price search, only VEGA's VEGASWING 63 model could meet the DN25 Class 900 M process connection requirements. Other manufacturers such as E+H and Rosemount could not meet these requirements. 07/15联锁值详见联锁条件表。The interlock values on 07/15 can be found in the interlock condition table. | NO | Chaoqun hu/Yu gao
07/01 | SW Instrumentation 仪表配置 | Instrument datasheet next revision date 仪表数据单下一版本发出日期 Please advise the target issue date for the next revision of the Instrument Datasheet, reflecting the current SE01 design (post demister-configuration decision), the finalised interlock schedule, and the level switch position confirmation. 请说明反映当前 SE01 设计（demister 配置定稿后）、最终联锁清单以及液位开关位置确认的仪表数据单下一修订版本的目标发出日期。 | 7月10日反馈进展 仪表数据表已完成修订版，待意见讨论后看是否还需修改参数。 The instrument datasheet has been revised. After the discussion of opinions, we will see if the parameters still need to be modified. | NO | Chaoqun hu/Yu gao
07/01 | SW Documentation Status 文档状态 | Current revision and next revision date of key deliverables 主要交付文件的当前版本与下一版本时间 Please confirm the current issued revision and the target date for the next revision of the following documents: • PFD • P&ID • URS • Equipment Datasheets • Control Philosophy • Instrument Datasheet • Operating Instructions • Cleaning Procedure • Vessel Design Calculation Package. 请确认以下文档的当前已发版本与下一修订版本的目标日期： · PFD · P&ID · URS · 设备数据单 · 控制策略 · 仪表数据单 · 操作说明 · 清洗程序 · 容器设计计算书。 | 7月10日反馈进展，操作手册还在编制中，其他设计文件已完成。On July 10th, we provided the progress update. The operation manual is still under preparation, while the other design documents have been completed. | NO | Shaofeng gao/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R1] Design Temperature — Vessel could fail during relief event. Equipment design temperature is specified for process requirements and does not consider elevated temperatures during relief events when short-term temperature increase has the potential to exceed the design temperature. 设计温度 —— 容器可能在泄放事件中失效。设备设计温度是按工艺需求设定的，未考虑泄放事件中的短时温升可能超过设计温度的情形。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：已更新数据表，提高设计温度，以满足工艺需求，图纸已升级。 07/10: Data sheet updated with elevated design temperature to meet process requirements; drawings revised accordingly. | YES | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register Engineering Design 工程设计 | [R2] Design Requirements — L:G ratio for plant is not clearly defined. Equipment design could result in very limited operating ranges and incorrect assumptions in plant capability and relief design. 设计条件 —— 装置的液气比（L:G ratio）未明确定义。可能导致设备设计的操作区间受限，以及在装置能力和泄放设计中做出错误假设。 | 7月10日反馈进展，根据最终确定的反应器尺寸核实气液比数据。On July 10th, the progress was reported. The gas-liquid ratio data was verified based on the final determined reactor size. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Engineering Design 工程设计 | [R3] Design Requirements — Catalyst specification is not available. Design may not be suitable for some catalysts. Dusty catalysts could cause blockages. 设计条件 —— 催化剂规格未明确。设计可能不适用于某些催化剂；含粉尘的催化剂可能导致堵塞。 | Keith / SW response: Design philosophy is based on catalyst beads/pellets which are dust-free, non-flammable and have exposure levels requiring OEB 3 or lower containment. Note: OEB 3 containment is a deviation from the URS and requires acceptance. Keith / SW 答复： 设计基于无粉尘、非燃、暴露等级 OEB 3 或更低的颗粒/粒状催化剂。注：OEB 3 的密闭要求相对 URS 存在偏离，需要接受确认。 | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Engineering Design 工程设计 | [R4] Access — Layouts are not available to assess whether access to equipment is acceptable for operations and maintenance. 通道 —— 布置图尚未提供，无法评估设备的操作与维护通道是否满足要求。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.1 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R5] Maintenance — Lifting Aids (davit arms, lifting beams, etc.) have not been considered in design, with potential for injury to maintenance personnel removing heavy equipment for servicing / repair / replacement. 维护 —— 设计中尚未考虑起重辅助设施（吊臂、起吊梁等），维护人员在拆卸重型设备进行检修 / 修理 / 更换时可能存在人身伤害风险。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Engineering Design 工程设计 | [R6] Lighting — Layouts are not available to assess whether lighting for routine operations and maintenance activities is acceptable. 照明 —— 布置图尚未提供，无法评估日常操作和维护活动的照明条件是否满足要求。 | Once the 3D model is determined, then SW can proceed？ 3D模型确定后是否SW就可以推进了？ 是的/Yes | NO | UK/All
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R7] System leak detection — Pressure testing of high-pressure system will be hydraulically tested. Hydraulic testing demonstrates mechanical strength of the pressure system but does not demonstrate integrity for a hydrogen system. 系统检漏 —— 高压系统将进行水压试验。水压试验只能证明压力系统的机械强度，无法证明氢气系统的密封完整性。 | Keith / SW response: Helium testing is not routinely carried out in China. Keith / SW 答复： 国内通常不常规进行氦气检漏。 可以做气密性试验；国内整橇系统气密性试验后，分体运至英国，进入工厂房间后，再次组装，需重新进行泄漏试验，现场是否具备试验条件？现场可进行氦气检漏。 和CE认证机构确认一下具体方案。 A pneumatic test can be performed. After the complete skid system undergoes the pneumatic test in China, it will be shipped in split form to the UK. Upon arrival at the factory site and reassembly, a new leak test will be required. We need to confirm whether the site has the necessary conditions/facilities for this test. Helium leak detection is available on site. We will confirm the specific plan with the CE Notified Body. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R8] Line sizing / specification — Vents / headers incorrectly sized / specified, resulting in high back pressure and safety / operability issues, e.g. two-phase flow in emergency vent relief header. 管线规格 / 尺寸 —— 放空 / 泄放总管尺寸或规格不正确，导致背压过高及安全 / 可操作性问题，例如紧急泄放总管中出现两相流。 | 07/10：安全阀进出口尺寸详见P&ID 07/10：Refer to the P&ID for the inlet and outlet sizes of the safety valve. | NO | Chaoqun hu
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R9] Insulation — Insulation requirements not specified, which could result in equipment / pipe layout not allowing space for insulation to be installed. 保温 —— 保温需求尚未明确，可能导致设备 / 管路布置未预留保温安装空间。 | Confirm the insulation material with Keith and determine the thickness. Once it's confirmed, provide a progress report on July 10th. 和Keith确认下保温材料，然后确定厚度。确定后，7月10日反馈进展 3D模型中管路的间距已按照保温厚度30-35mm预留了保温的安装空间。 The spacing between pipes in the 3D model has been designed to accommodate an insulation installation gap of 30-35mm, as per the insulation thickness requirements. | NO | Yinghui cheng/Chaoqun hu/Shuangshuang fan/Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R10] Modular design — Modular design could introduce significant increase in site construction activities, e.g. mechanical and EC&I installation and subsequent testing. 模块化设计 —— 模块化设计可能大幅增加现场施工工作量，例如机械与电控仪表安装及后续测试。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 现有模块化设计的方案是根据进口电梯的尺寸，将整套设备拆分为4个撬块运输组装。 SW建议：需再考虑从屋顶直接吊装进去的方案，需要在后续周三会上进一步讨论。 The current modular design solution involves dividing the entire set of equipment into four skids for transportation and assembly based on the dimensions of imported elevators. SW Recommendation: Further consideration is needed for the direct hoisting-in-from-the-roof solution, which will be discussed in the upcoming Wednesday meeting. | NO | Chaoqun hu/Shuangshuang fan
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R11] Skid assembled on site could result in CE / UKCA Responsible Person / Authorised Representative in China not being able to issue Declaration of Conformity for Skid Package. 撬块在现场组装可能导致中国境内的 CE / UKCA 负责人 / 授权代表无法为撬块整机签发符合性声明（Declaration of Conformity）。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 与CE认证方沟通确认好细节，特别是认证机构是否需要到UK现场验证，再发证。 We will communicate with the CE Notified Body to confirm all the details, in particular whether the certification body needs to attend the UK site for verification prior to issuing the certificate. | NO | Ziliang zhao
07/02 | SW - Risk Register Continuous Reactor Build 连续反应器建造 | [R12] Wall penetrations — Layouts and cable schedules not available to confirm space is available for pipe / cable penetrations to / from R23 Module. 穿墙孔 —— 布置图和电缆清单尚未提供，无法确认与 R23 模块之间的管道 / 电缆穿墙位置有足够空间。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.6 | The initial cable schedule of CIMT is not fully aligned with the SW plan. SW has sent SLD, CIMT is verifying design discrepancies and will feed back comparison results, followed by discussions with SW CIMT初版线缆计划与SW计划没有完全匹配，SW已发出单线图，CIMT核对设计差异，返回对比结果，再与SW讨论。 7/23：CIMT根据SW提供的单线图，更新了电缆数量。部分流量控制器电缆待确认。硬联锁开关阀点位本安/隔爆待确认。 7/23：CIMT update the cable quantity based on the SLD provided by SW. some cables are still pending confirmed, 1. for flow controllers(modbus or 4-20mA). 2. for HW interlock on-off valve(I.S. or Ex d) | NO | Dezhi meng
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R13] Catalyst charge point — Inlet pipe diameter is small and blockages may occur. 加料口 —— 加料管径较小，可能发生堵塞。 | Keith / SW response: Inlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking inlet pipe. Keith / SW 答复： 加料接口已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞加料管的风险。 | YES
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R14] Catalyst physical property requirements (size, shape, packing, etc.) are not defined, with the potential for incompatible catalyst to be charged to the reactors. 催化剂物性要求（粒径、形状、装填密度等）尚未定义，存在向反应器加入不兼容催化剂的风险。 | 07/10：催化剂直径0.5mm-5mm，形状不重要，球形，圆柱形，不规则颗粒状都可以，装填密度一般0.5g/mL来估算，但催化剂强度要高，不容易破碎起粉 07/10：The catalyst particle diameter ranges from 0.5 mm to 5 mm, with no specific shape requirement; spherical, cylindrical and irregular granular forms are all acceptable. The bulk density can be estimated at 0.5 g/mL in general. Meanwhile, the catalyst shall feature high mechanical strength to avoid fragmentation and dust generation. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R15] Packing of catalyst is not controlled, with the risk of reactants / gas channelling in the continuous reactor column, and the potential for incomplete reaction or impurities forming. 催化剂装填未受控，存在反应物 / 气体在连续反应柱内形成沟流的风险，可能导致反应不完全或杂质产生。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R16] Contained charge system design not available to assess risks and / or design limitation. 密闭加料系统的设计尚未提供，无法评估其风险与设计局限。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R17] Manual handling requirements for catalyst charging not assessed. 催化剂加料的人工搬运需求尚未评估。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Charging 催化剂加料 | [R18] Access to charge point and support of charge container / bag not designed (access steps / integrated support shelf). 加料口的通道以及加料容器 / 料袋的支撑尚未设计（例如操作台阶、集成支撑架）。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R19] 20-micron catalyst retaining screen — Screen blockages prevent / limit flow of gas / reaction mix to continuous reactors. 20 微米催化剂拦截筛 —— 拦截筛堵塞会阻止 / 限制气体 / 反应液流入连续反应器。 | Keith / SW response: China Operations have reported blockages occur in local plant and screen has been removed and discarded. Keith / SW 答复： 国内运行反馈已在本地装置中发生堵塞，已将拦截筛拆除并弃用。 | YES
07/02 | SW - Risk Register Reactor Feed 反应器进料 | [R20] Polishing filter (FTR9832) — Filter blockages prevent / limit flow of gas / reaction mix through continuous reactors. Pressure increases in reactor system, with potential for undesirable reactions to occur, until reactor high-pressure trip is activated. 精滤器 (FTR9832) —— 滤芯堵塞会阻止 / 限制气体 / 反应液流经连续反应器；反应器压力升高，直到触发高压跳停前可能发生副反应。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 待定/To be determined | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register CR01 – CR03 Reactors CR01 – CR03 反应器 | [R21] Temperature control — Jacket temperature control is configured to control jacket temperature only. Reactor internal temperatures are monitored, but no control, alarms or interlocks are configured for process control. 温度控制 —— 夹套温度仅控制夹套温度本身。反应器内部温度虽被监测，但未针对工艺过程配置控制、报警或联锁。 | Keith / SW response: Scale-up provides large operating envelopes for process temperature requirements and additional control, alarms and interlocks are not required. Keith / SW 答复： 由于放大试验提供了较大的工艺温度操作裕度，无需增加额外的控制、报警或联锁。 | YES
07/02 | SW - Risk Register System Pressure Monitoring 系统压力监测 | [R22] Differential pressure monitoring — Accuracy of static pressure measurements may not enable differential pressures to be calculated with any degree of accuracy or certainty. 差压监测 —— 静态压力测量精度可能不足以支持差压计算达到所需的精度或置信度。 | 通过反应柱上和反应器进出口管线上的的压力变送器精度估算，最大差压误差大约为40kPa。 Based on the accuracy estimation of the pressure transmitters on the reaction column and the inlet/outlet pipelines of the reactor, the maximum differential pressure error is approximately 40kPa. 07/14压力也增加了联锁。The pressure also increased the interlock. | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register Over Pressure Protection 过压保护 | [R23] Relief system design — Pressure systems not identified and relief studies not available. Identification of worst-case relief scenario not identified, and relief streams may be incorrectly categorised. Details of maximum reaction exotherm not fully documented. 泄放系统设计 —— 压力系统尚未识别、泄放研究尚未提供。最坏工况泄放情景未识别，泄放物流可能被错误归类。反应最大放热的详细信息尚未完整记录。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.1 | 07/10：详见安全阀计算书 07/10：See safety valve calculation sheet for details. | NO | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R24] Vessel design — Complete degassing of product stream not achieved, with the potential for hydrogen carry-over into BT04 and product transfer containers. 容器设计 —— 产品物流未实现完全脱气，H₂ 可能带入 BT04 及产品转运容器。 | 07/10：气液分离器满足气液分离的要求 07/10：The gas-liquid separator meets the requirements for gas-liquid separation. | NO | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R25] Cleaning of separator not fully understood but current concept relies on vessel free-draining to BT04. Current spray ball sizing is not consistent with this approach and may require significant rework to process piping. 分离器清洗方案尚未完全明确，当前概念依赖容器向 BT04 的自重排放。现有喷淋球规格与该思路不匹配，可能需要对工艺管路进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.4,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register Separator 气液分离器 | [R26] Cleaning of LIT003 housing does not appear to be considered in design. LIT003 液位变送器外壳的清洗在设计中似乎尚未考虑。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.7 | 同上42行回复/Translation of the 42nd line above. | NO | Chaoqun hu
07/02 | SW - Risk Register Separator 气液分离器 | [R27] P&ID does not clearly show nozzle locations and could lead to mal-ops / misunderstanding of the design intent by the Operations team. P&ID 上未清晰标注管嘴位置，可能导致运行团队误操作或误解设计意图。 Related Outstanding Questions ｜ 关联待澄清问题：Q2.3 | 07/10：已标注，详见P&ID 07/10：Marked as indicated; refer to the P&ID for details. | NO | Chaoqun hu
07/02 | SW - Risk Register Sampling 取样系统 | [R28] Sampler design — When depressurising the sample collection chamber, high gas or vapour vent rates could result in a bubbly or churn-turbulent flow regime, and sample will discharge to vent line as two-phase flow. 取样器设计 —— 对取样收集腔进行减压时，气体或蒸汽的高排放速率可能形成鼓泡或搅动湍流流态，样品将以两相流形式排入放空管。 Related Outstanding Questions ｜ 关联待澄清问题：Q5.1 | 07/10：缓冲罐静置一定时间，让气液分层，泄压时缓慢打开手阀 07/10：Allow the buffer tank to stand for a certain period for vapor-liquid stratification, then open the manual valve slowly during depressurization. | NO | Chaoqun hu
07/02 | SW - Risk Register Sampling 取样系统 | [R29] With significantly more gas being present in the process stream, what will prevent overpressure of sample bottle and low-pressure nitrogen pipework? 由于工艺物流中气体明显较多，采用什么措施来防止取样瓶和低压氮气管路的超压？ | 07/10：取样瓶和氮气管线投用时，系统已泄压至常压 07/10：The system has been depressurized to atmospheric pressure prior to commissioning of sampling bottles and nitrogen pipelines. | NO | Chaoqun hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R30] Catalyst Discharge Plug valve — Outlet pipe diameter is small and blockages may occur. 催化剂卸料闸阀 —— 出口管径较小，可能发生堵塞。 | Keith / SW response: Outlet connection maximised (DN32 for CR01 and DN25 for CR02/CR03). Material is deemed to be free-flowing beads or pellets with no risk of blocking outlet pipe. Keith / SW 答复： 出口接管已最大化（CR01 采用 DN32，CR02/CR03 采用 DN25）。物料按自由流动的颗粒 / 珠状催化剂考虑，无堵塞出口管的风险。 | YES
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R31] Contained discharge system design not available. Layout design may not provide sufficient headroom for contained discharge system. 密闭卸料系统的设计尚未提供。当前布置可能无法为密闭卸料系统提供足够的顶部空间。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Catalyst Discharging 催化剂卸料 | [R32] Complete removal of catalyst during discharging operations is unlikely to remove 100% of the material, with the risk of cross contamination of catalyst material between campaigns. 卸料操作难以完全（100%）清除催化剂，存在批次间催化剂交叉污染的风险。 | 07/10：催化剂装卸方案待讨论后反馈 07/10：The catalyst loading and unloading plan is pending discussion and will be updated accordingly. 07/15：会议确认SW负责催化剂的装卸方案 07/15：It was confirmed in the meeting that SW shall be responsible for the catalyst loading and unloading scheme. | NO | Xiantao feng/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R33] CIP Design — CIP design incomplete. Initial spray ball sizing is inconsistent with process line sizing approach and may require significant rework to process piping and/or equipment layout. CIP 设计 —— 就地清洗设计不完整。初步喷淋球规格与工艺管路选型方式不匹配，可能需对工艺管路和 / 或设备布置进行较大改动。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.1,Q1.5 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. 07/23：清洗方案完成初版 07/23：Initial version of cleaning scheme completed | NO | Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R34] Cleaning carried out at nominally atmospheric pressure with the risk of material being trapped between flanges, which tend to separate slightly during high-pressure operation, and could lead to cross contamination between batches. 清洗在近常压下进行，高压运行时法兰会出现微量分开，可能将物料残留于法兰间隙中，进而导致批次间交叉污染。 | 07/10：详见清洗方案，下周提供清洗方案 07/10：The detailed cleaning plan will be provided next week; please refer to it for full details. | NO | Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R35] Validation / Verification — Cleaning validation / verification philosophy not available. QA may not accept that the continuous reactor achieves minimum cleaning standards. 验证 / 确认 —— 清洗验证 / 确认策略尚未提供。质量保证部门可能不接受连续反应器满足最低清洗标准。 Related Outstanding Questions ｜ 关联待澄清问题：Q1.2,Q1.9 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 更新清洗方案后讨论/Discuss after updating the cleaning procedure. | NO | Chaoqun hu/Xiantao Feng
07/02 | SW - Risk Register Cleaning 清洗 | [R36] Layout — Layouts are not available to evaluate the impact of bypasses, dead legs, drains, vents, etc. 布置 —— 布置图尚未提供，无法评估旁路、死管、排放、放空等的影响。 |  | NO | Shuangshuang fan/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R37] Layout — Layouts are not available to evaluate access to equipment for visual inspections, which may impact the effectiveness of critical inspections. 布置 —— 布置图尚未提供，无法评估设备的目视检查通道，可能影响关键检查的有效性。 |  | NO | Shuangshuang fan/Chaoqun hu
07/02 | SW - Risk Register Cleaning 清洗 | [R38] Layout — Equipment design / layout does not allow for routine disassembly and manual cleaning. Equipment turnaround times and operating costs would be adversely impacted if CIP system cannot be validated. 布置 —— 设备设计 / 布置未考虑日常拆装和人工清洗。如 CIP 系统无法通过验证，设备周转时间和运行成本都会受到不利影响。 |  | NO | Chaoqun hu/Ziliang zhao
07/02 | SW - Risk Register FT001 FT001 流量计 | [R39] Liquid Stream Flow Sensor for flow control loop FIC001. FT001 is a Coriolis mass flow meter installed downstream of the metering pump MP01. Pulsed flow from the pump will impact on the flow measurement and accurate flow control may not be possible. 液相流量传感器（用于 FIC001 流控回路）—— FT001 是安装在计量泵 MP01 下游的科里奥利质量流量计。泵的脉冲流会影响流量测量，可能无法实现精确流量控制。 | Keith / SW response: China Team have previously used this configuration and not experienced flow control issues. No further action required. Keith / SW 答复： 国内团队此前采用过该配置，未出现流控问题。无需进一步动作。 | YES
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R40] Maximum flow may exceed separator design limitations and carry hydrogen over into BT04 / product collection containers. 泵的最大流量可能超出分离器的设计上限，将 H₂ 带入 BT04 / 产品收集容器。 | 07/10：分离器的直径足够大，泵为最大流量时能满足分离要求 07/10：The separator has a sufficiently large diameter to meet separation requirements even when the pump operates at maximum flow rate. | NO | Chaoqun hu
07/02 | SW - Risk Register MP01 Metering Pump MP01 计量泵 | [R41] Pump turndown does not meet URS minimum flow requirements. 泵的调节比无法满足 URS 中规定的最低流量要求。 | 07/10：机泵条件中规定了泵的最小流量要求，待泵厂家返回资料时审查是否满足最低流量要求 07/10：Minimum flow requirements for pumps are specified in pump data sheets. Compliance with the minimum flow criteria shall be verified upon receipt of vendor documentation. | NO | Chaoqun hu
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R42] Hydrogen gas flow controller — Flow controller does not support tight shut-off and system pressure increase during hold periods. 氢气流量控制器 —— 控制器不支持严密关断，系统在保压期间压力会持续上升。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller to provide tight shut-off. Keith / SW 答复： 在控制器下游追加一台切断阀以提供严密关断。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R43] Maximum flow through controller may exceed separator design limitations and carry liquid into the vent line. 流经控制器的最大流量可能超出分离器设计上限，将液体带入放空管。 | Keith / SW response: High level interlock installed in the separator to stop gas supply and close PIC028 shut-off valve (CV08). Keith / SW 答复： 在分离器上设置高液位联锁，停 H₂ 供给并关闭 PIC028 的切断阀（CV08）。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R44] Time required for pressure testing the system and nitrogen inertion may be excessively high. 系统加压试验及氮气钝化所需时间可能过长。 | Keith / SW response: Pressure test / inertion times to be evaluated during FIC003 selection. Manual vent installed on BT03 to reduce depressurisation times via FIC003. Keith / SW 答复： 在 FIC003 选型时评估压力试验 / 惰化时间。在 BT03 上加装人工放空阀，缩短经 FIC003 的减压时间。 | YES
07/02 | SW - Risk Register FIC003 FIC003 氢气流量控制 | [R45] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端的差压超出厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register LIC003 LIC003 分离器液位 | [R46] SE01 Separator Level Indicator — Cleaning / decontamination of housing is not possible. Residual product in housing could lead to cross contamination between campaigns. SE01 分离器液位指示 —— 变送器外壳无法进行清洗 / 净化。外壳内的残留物料可能导致批次间交叉污染。 | Keith / SW response: Design relies on dissolution of residual material. 100% flood-fill of housing is not possible, therefore any residual trace contamination in the housing is deemed to be small and will not significantly impact cleaning verification. Keith / SW 答复： 设计依赖残余物料的溶解。外壳无法 100% 灌满，因此外壳内任何残余痕量污染被视为很小，不会显著影响清洗验证。 | YES
07/02 | SW - Risk Register FIC004 FIC004 分离器液位控制 | [R47] Separator outlet flow / level control — Differential pressure across the controller exceeds manufacturer's recommendations and controller capability. 分离器出口流量 / 液位控制 —— 控制器两端差压超出厂家建议范围及控制器能力。 | 分离器出口先通过减压阀减到0.2MpaG左右，可以满足厂家建议的差压范围 The outlet of the separator is first reduced to approximately 0.2MpaG through a pressure reducing valve, which can meet the differential pressure range recommended by the manufacturer | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register FIC005 FIC005 BT01 氮气吹扫 | [R48] BT01 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT01 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register FIC007 FIC007 BT04 氮气吹扫 | [R49] BT04 nitrogen sweep flow controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 氮气吹扫流量控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R50] System back pressure controller — The back pressure controller does not support tight shut-off during hold periods and system pressure will not be maintained. 系统背压控制器 —— 该控制器在保压期间不支持严密关断，系统压力无法保持。 | Keith / SW response: Additional shut-off valve to be installed downstream of the controller. Keith / SW 答复： 在该控制器下游追加一台切断阀。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R51] Time required for depressurising the system following pressure testing and nitrogen inertion may be excessively high. 加压试验和氮气钝化之后系统减压所需时间可能过长。 | Keith / SW response: Manual bypass installed around PIC028 controller. Keith / SW 答复： 在 PIC028 控制器周围加装人工旁路。 | YES
07/02 | SW - Risk Register PIC028 PIC028 系统背压控制 | [R52] Differential pressure across the controller exceeds manufacturer's recommendations and controller may not function correctly. 控制器两端差压超出厂家建议范围，可能导致控制器无法正常工作。 | 关于背压阀028，之前厂家计算反馈的阀前背压范围最大为0.9~6MpaG，范围量程比不能过大。 About the back pressure valve 028, previously, the manufacturer calculated and reported that the maximum range of the back pressure before the valve was 0.9 to 6MpaG, and the range-to-range ratio cannot be too large. | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register PIC030 PIC030 分离器液相出口减压 | [R53] Separator liquid outlet pressure reducer — Is this confirmed as a Bronkhorst pressure controller, or is a mechanical regulator still an option? Does this provide the required independence assumed in the relevant SIL / risk assessments? 分离器液相出口减压器 —— 该阀是否确认为 Bronkhorst 电子压力控制器？还是仍可能选用机械式减压阀？该配置能否提供相关 SIL / 风险评估中假设所需的独立性？ | 目前选型机械式减压阀。机械阀不是电子设备，没有相关的SIL认证。 At present, mechanical pressure reducing valves are being selected. Mechanical valves are not electronic devices and do not have the relevant SIL certification. | NO | Chaoqun hu/Yu gao
07/02 | SW - Risk Register PIC049 PIC049 BT04 背压控制 | [R54] BT04 back pressure controller — Differential pressure across the controller is less than manufacturer's recommendations and controller may not function correctly. BT04 背压控制器 —— 控制器两端差压低于厂家建议范围，可能导致控制器无法正常工作。 | Keith / SW response: China Team reviewed with manufacturer and accuracy of flow control may be compromised but this is not deemed significant and no further action is required. Keith / SW 答复： 国内团队已与厂家复核，流控精度可能有所下降但不显著，无需进一步动作。 | YES
07/02 | SW - Risk Register Automation 自动化 | [R55] Automation Build — Philosophy and Design documentation not available to assess risks and limitations. 自动化建设 —— 自动化策略与设计文档尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q3.1,Q3.2 | 专题沟通后确定反馈 | NO | Chaoqun hu/Dezhi meng/Ziliang zhao
07/02 | SW - Risk Register Documentation 文档 | [R56] Technical File — Technical File not available to assess risks and limitations. 技术文件 —— 技术文件尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q4.5,Q7.1 |  | NO | Shaofeng gao/All
07/02 | SW - Risk Register Documentation 文档 | [R57] O&M Manual — O&M manual not available to assess risks and limitations. 操作维护手册 —— O&M 手册尚未提供，无法评估其风险与局限。 Related Outstanding Questions ｜ 关联待澄清问题：Q7.1 | 07/10：操作手册的编制还在进行中 07/10：Preparation of the operation manual is still in progress. | NO | Chaoqun hu
07/02 | SW - Risk Register Documentation 文档 | [R58] Emissions Calculations — Calculations to demonstrate expected release of Class A and Class B VOCs to atmosphere are not available. These are required to demonstrate compliance with EA Permit limits. 排放量计算 —— 尚未提供证明 A 类和 B 类 VOC 向大气排放的预期计算。该计算是证明满足 EA 许可（英国环境署许可）限值要求所必需。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW负责排放量计算/SW is responsible for emissions calculation. | NO | Chaoqun hu
07/02 | SW - Risk Register Regulatory Compliance 法规合规 | [R59] CE ¦ Functional Safety ¦ DSEAR / ATEX ¦ PSSR ¦ COSHH ¦ PUWER (Access, manual handling) ¦ Working at Height (Access Steps / Support Shelf) ¦ LOLER (Davit arms) ¦ Lighting ¦ Occupational Hygiene ¦ EA Permit — Regulatory non-conformance would prevent beneficial use of equipment in the UK. CE 认证 ¦ 功能安全 ¦ DSEAR / ATEX 防爆 ¦ PSSR 压力系统安全 ¦ COSHH 危害物质 ¦ PUWER 工作设备（含通道与人工搬运）¦ 高处作业（操作台阶 / 支撑架）¦ LOLER 起重设备（吊臂）¦ 照明 ¦ 职业卫生 ¦ EA 环境许可 —— 任何法规合规缺失都会导致设备无法在英国正常投入使用。 | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 SW内部的提醒事项。 CFCT核实加料步梯是否包含在内。 SW提供步梯平台尺寸。 Internal reminders for SW: CFCT to verify whether the feeding staircase is included. SW to provide dimensions of staircase and platform. | NO | Zilang zhao/All
07/14 |  | 根据生产经验，研发建议原R24-CR01的直径由DN80改为DN50，导致产能下降，可能无法满足URS中的产能30kg/day Based on production experience, the R&D team proposes reducing the diameter of the original R24-CR01 from DN80 to DN50. This modification will result in lower production capacity, which may fail to meet the 30 kg/day throughput specified in the URS. | 07/14：周三会上确定/To be confirmed at Wednesday's meeting. 07/15：暂定R24-CR01的直径修改为DN65，等9月份研发提供DN65的反应器实验数据后最终确认反应器的尺寸为DN65或DN50 07/15：It is tentatively agreed to revise the diameter of R24-CR01 to DN65. The reactor size (either DN65 or DN50) will be finalized after the R&D department provides DN65 reactor test data in September. | NO | Xiantao Feng/All
07/23 |  | 气液分离器SE01容器承受从常压到60 barg的压力循环次数？ How many pressure cycles does the gas-liquid separator SE01 vessel undergo from atmospheric pressure to 60 barg? | And we will clarify the requirements with Keith at the meeting. 和Keith澄清下需求 | NO | Zilang zhao/Chaoqun hu
07/23 |  | P&ID中压力表无根部阀，是否需要增加根部阀？ Pressure gauges shown on the P&ID are not equipped with root valves. Is it necessary to add root valves?
07/23 |  | PCV028侯径小，反应系统卸压时，全开PCV028卸压速度也很慢，建议将PCV028的旁通手阀改为开关阀 PCV028 has a small orifice. When depressurizing the reaction system, the depressurization rate remains low even if PCV028 is fully open. It is recommended to change the bypass manual valve of PCV028 to an on-off valve.

## 0623
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. 05/12：Keith建议用气液两相计算安全阀尺寸，不提供模板 05/12：Keith suggests using gas-liquid two-phase calculations for determining the size of the safety valve, but no template is provided. 05/20：根据API520的气液两相泄放时计算安全阀尺寸，部分已完成 05/20：Calculate the size of the safety valve based on the API520 standard for the two-phase gas-liquid discharge situation.Partially completed. 06/02：安全阀计算初版已完成（包含临界流体和气液两相），校审中。 06/02：Preliminary calculation of safety relief valve (covering critical fluid & gas-liquid two-phase flow) completed, under review. 06/09: General 1. What was the source/reference for the Specific Volumes stated in column D/D 列中比容数据的来源及参考依据是什么？ The Specific Volumes stated in column D are derived from Aspen Plus simulation results.比容数据来自Aspen模拟 2. There is no backpressure considered in the calculation. The emergency vent relief will create some backpressure which needs to be considered in the calculation./本次计算未考虑背压。紧急放空泄放过程会产生一定背压，该因素需纳入计算。 Backpressure consists of static backpressure and built-up backpressure. Given the wide total pressure range, backpressure effects shall be incorporated into the calculation.背压分为静背压和积聚背压，总压力范围大，将背压包含在其中 3. At the assumed relief pressure Ethyl Acetate will be a supercritical fluid, therefore the required relief mass flowrate will not be dependent on the latent heat of vapourisation, and the calculated ‘required discharge area’ will not be valid. Do you agree with this statement, or have you found a reference in the standard that allows for this? 在设定的泄放压力下，乙酸乙酯将处于超临界流体状态，因此所需泄放质量流量不再依赖汽化潜热，本次算出的所需泄放流通面积也不再适用。你是否认同该观点？或是你是否在相关标准中查到可支持该计算的依据？ 详见06/16回复. Please refer to the reply dated 06/16 for details. Cooling Failure Calculations 4. For the cooling failure calculation, I would suggest using 550kJ/mol rather than 501.48. This is based on Sandwich PSL experience of heats of reaction. 针对冷却失效工况计算，建议将反应热取值由 501.48 kJ/mol 改为 550 kJ/mol。该取值参考了桑威奇工艺安全实验室（Sandwich PSL）过往反应热项目经验。 OK 5. Is the feed flowrate used in the calculation, based on the maximum metering pump capabilities? Do you assume a maximum concentration of reactant in the feed stream? 计算中采用的进料流量，是否按照计量泵最大额定流量取值？计算时是否假定进料流中反应物浓度为最大浓度？ The flow rate used in the calculation is set at the maximum rated capacity of the metering pump, and the maximum reactant concentration is adopted for the feed stream.计算时流量是按照计量泵最大额定流量取值，反应物浓度为最大浓度 06/16：根据文献“Relief Calculation for Supercritical Fluids”计算超临界流体的质量泄放流量，会后向Keith发计算书审核 06/16：Calculate the mass relief flow rate of supercritical fluids in accordance with the document Relief Calculation for Supercritical Fluids, and send the calculation sheet to Keith for review after the meeting. | Yes | Chaoqun Hu
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun HU
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. 06/16：06/11已收到审核完成的URS。 06/16：Received the reviewed URS on 06/11. | YES | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith确认CV08也是故障关，可以使用DS6080型，该型号没有5 bar 差压限制。 Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith confirmed that CV08 is also a faulty-close type, the DS6080 model can be used. This model does not have a 5-bar differential pressure limit. Keith offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. 06/02 进展：Habonim厂家反馈了样本资料，反馈可以满足工艺参数需求，货期大概16~20周。可以作为开关阀的备选品牌。 06/02 Progress: "Habonim" manufacturer has provided sample materials that can meet the process parameter requirements. The delivery time is approximately 16 to 20 weeks. It can be an alternative brand for on-off valves. | YES | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. 06/02：关于气液分离器液相出口减压，电子压力阀和自力式减压阀都可以满足使用，首选自力式减压阀。 06/02：For pressure reduction at the liquid outlet of the gas-liquid separator，both electronic pressure valves and self-operated pressure reducing valves can meet the requirements, with self-operated pressure reducing valves being the preferred choice. | YES | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. 05/20：SW已更新完URS并发出。The SW has been updated and the URS has been sent out. | YES | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表数据单。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. 06/23:仪表条件表已更新完成 06/23：The instrument conditions table has been updated and completed. | NO | Chaoqun Hu/Yu Gao
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. 05/20：SW已更新完PFD并发出。The SW has been updated and the PFD has been sent out. | YES | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ 4/30：Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? | NO | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted?05/12Decided not to make any adjustments. 05/12确定不做调整。 05/12：It is determined that the height of the catalyst bed in the main reactor will not be adjusted. | YES | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. 06/16：会议澄清：待布局完成后，SW主导完成爆炸危险区域的划分 09/06：Meeting Clarification: SW shall take the lead in completing the classification of hazardous areas for explosion after layout design is finalized. | NO | All
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | YES | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements. | 05/20：与聂博沟通，小试使用的是进口是插底的分离器，生产使用的是侧进的分离器，按会议沟通的气体最大流量0.2Nm³/h，液体最大流量20L/h重新计算了分离器 05/20: Communicated with Nie Bo. The small-scale test used an imported bottom-insertion separator, while the production version used a side-inlet separator. Based on the maximum gas flow rate of 0.2 Nm³/h and the maximum liquid flow rate of 20 L/h for the communication at the meeting, the separator was recalculated.. | YES | Chaoqun Hu
06/02 | IEPE | 管道编号中的管线尺寸一般是指的公称直径，PID中尺寸为10mm的管道是Φ10mm，公称直径为6mm The line size in pipe line designations generally refers to the nominal diameter. In a P&ID, a pipe with a size of 10mm is specified as Φ10mm, corresponding to a nominal diameter of 6mm. | 06/02：会议澄清：DN15以下的管道，管道编号中的管径为外径，DN15及其以上的管道，管道编号中的管径为公称直径。 06/02：Clarification from meeting:For piping below DN15, the size specified in pipe tag number denotes outer diameter; for DN15 and above, the size in pipe tag refers to nominal diameter. | YES | Chaoqun Hu
06/02 | IEPE | 设备BT-01/03/04上的压力变送器不便于现场观察，是否可以考虑也选用WIKA的不带现场显示紧凑型的压力变送器？ The pressure transmitter on the equipment BT-01/03/04 is not convenient for on-site observation. Could it be considered to also choose WIKA's compact pressure transmitter without on-site display？ | 06/02：会上建议保留BT-01/04的现场显示，BT-03可不带现场显示。 06/02：It was suggested at the meeting that the on-site display of BT-01/04 be retained, while BT-03 may not have an on-site display. | YES | Yu Gao
06/02 | CFCT | 1-PID中V-9868，V-9965阀柄的含义？ What is the meaning of valve handles V-9868 and V-9965 in PID? 2-PID中压力变送器底部波纹含义是什么？ What does the corrugation at the bottom of the pressure transmitter signify? 3-与管道直径对应的保温厚度是多少？ What is the insulation thickness corresponding to the diameter of the pipeline? | 06/02： 1.PID中阀门V-9868，V-9965的阀柄为弹簧复位阀柄； In the PID,the valve handles of V-9868 and V-9965 are spring-reset handles； 2.PID中带底部波纹的压力变送器要求压力变送器带隔膜； The pressure transmitter with a bottom ripple in PID requires the pressure transmitter to be equipped with a diaphragm； 3.Keith分享了建议的管道直径与保温厚度表格，直径10到25mm的管路，保温厚度为30-35mm。 Keith shared the recommended pipe diameter and insulation thickness table, with insulation thickness ranging from 30-35mm for pipes with diameters of 10 to 25mm. | YES | ShuangshuangFan
06/16 | SW | 会议确认：气液分离器为侧进，尺寸为DN200*600mm，下次例会前CFCT向SW提供气液分离器的设备图纸 Confirmed at the meeting: The gas-liquid separator adopts side inlet configuration with dimensions DN200 × 600 mm. CFCT shall submit the equipment drawing of the gas-liquid separator to SW prior to the next regular meeting. | 06/22设备图纸已提供。06/23Keith回复意见，见06/23讨论内容。 Equipment drawings were provided on 06/22. Keith's feedback was received on 06/23 — please refer to the discussion notes from 06/23. | YES | Ziliang Zhao
06/17 | SW | 根据最新工作进展并结合HAZOP分析所需文件内容，更新“Sandwich Hydrogenation Implementation Schedule” Update the Sandwich Hydrogenation Implementation Schedule based on the latest progress and document requirements for HAZOP study. |  | NO | All
06/17 | SW | 讨论操作规程：哪些部分需要顺控？开停车步骤等 Discuss operation procedures: identify sections requiring sequence control, including startup and shutdown steps, etc. | 06/23：开车步骤：公用工程确认/催化剂装填→氮气置换（R24-BT01、R24-BT04和剩余部分），氧含量<0.5vol%→氢气置换→原料系统备料→TCU系统调温→反应器进料（氢气先进料背压至反应压力，液相再进料）→气液分离→产品转移 停车步骤：停进料→产品缓冲罐物料转移→反应器卸压→R24-BT03卸压→反应系统降温→氮气置换→关闭氮气和TCU Startup Procedures： 1.Verification of utility systems & catalyst loading 2.Nitrogen purging (for R24-BT01, R24-BT04 and the rest of the system), oxygen content controlled below 0.5 vol% 3.Hydrogen purging 4.Raw material preparation for feed system 5.Temperature adjustment of TCU system 6.Reactor feeding: Introduce hydrogen first to build backpressure up to reaction pressure, then feed liquid phase material 7.Gas-liquid separation 8.Product transfer Shutdown Procedures： 1.Cut off feed supply 2.Transfer materials from product buffer tank 3.Depressurize reactor 4.Depressurize R24-BT03 5.Cool down reaction system 6.Nitrogen purging 7.Shut down nitrogen supply and TCU system Keith提供HAZOP时的开停车步骤，结合上述文件，整理开停车和清洗步骤 Compile the plant start-up, shutdown and cleaning procedures based on the above documents together with the start-up & shutdown sequences supplied by Keith for HAZOP assessment. | NO | All
06/17 | SW | 会后确认：安全阀的泄放温度超过设备的设计温度，是否需要提高设备的设计温度？ To be confirmed after the meeting：If the relief temperature of the safety valve exceeds its design temperature, is it necessary to increase the design temperature rating? | 设备和管线材质为316L，结合设备和管道的壁厚，计算得出：在泄放温度下，材料的许用应力满足其强度要求，不需提高设备的设计温度 The equipment and piping are fabricated from 316L stainless steel. Wall thickness calculations for the equipment and piping demonstrate that the allowable stress of the material satisfies the strength requirements at relief temperature; therefore, no increase to the equipment design temperature is required. | Yes | Ziliang Zhao/Chaoqun Hu
06/17 | SW | CFCT做撬块设计时，注意清洗过程中的低点排净 CFCT shall take full consideration of low-point draining during cleaning when designing the skid package. | 06/23：在撬块设计时，设置管道的低点排净阀 When designing the layout, install a drain valve at the low point of the pipeline 06/23会议方案：管道最低点设置排净阀，操作说明中明确排放时用容器收集排放液体。 Meeting Plant: Install drain valves at the lowest point of the pipeline, and specify in the operating instructions to collect the discharged liquid with a container during the drainage process. | NO | Shuangshuang Fan
06/17 | SW | CFCT提供放空缓冲罐T06是否放在撬内的方案 CFCT to provide a scheme on whether vent buffer tank T06 shall be installed inside the skid. | 06/23：按照现有空间的布置，T06放在撬块内的空间不足；撬块中间的操作维护通道宽度为300-350mm，能否将整体撬块宽度增加150-200mm？ According to the existing space arrangement, there is insufficient space for T06 to be placed inside the pry block; The width of the operation and maintenance channel in the middle of the pry block is 300-350mm. Can the overall pry block width be increased by 150-200mm? 06/23会议方案：T06不放在撬块内，放置在service area，同时反应柱/冷凝器的TCU出口管路上的温度变送器安装在近出口处，去掉手动球阀，安全阀可放到service area，并设置排净阀，进口管路手动球阀保持不变，温度变送器加套管，位置可前可后，低点设置排净阀，整体管路的高点设置排气阀。 Meeting Plant:: T06 is not placed inside the lever block but in the service area. The temperature transmitter on the TCU outlet pipeline of the reaction column/condenser is installed near the outlet. The manual ball valve is removed, and the safety valve can be placed in the service area. A drain valve is installed, while the manual ball valve on the inlet pipeline remains unchanged. The temperature transmitter is equipped with a protective sleeve, with its position adjustable forward or backward. A drain valve is set at the low point, and an air vent valve is installed at the high point of the entire pipeline. | NO | Shuangshuang Fan
06/23 | SW Cleaning Philosophy & Cleaning Sequence 清洗策略与清洗程序 | Keith意见： 基本设计：我们是否有经批准的分离器设计方案？我上次看到的摘录中，计算出的容器直径为3毫米，这表明计算或输入数据可能存在错误。 Basic design 1. Do we have an approved design for the separator. The last extract I saw had a calculated vessel diameter of 3mm, which suggests an error in the calculations or input data. | 06/23讨论： 基本设计：按最新设备数据表进行气液分离器设计。气液分离器的计算书已复核过，数据无误。 06/23Discussion—Basic Design: The gas-liquid separator shall be designed in accordance with the latest equipment data sheet. The calculation sheet for the gas-liquid separator has been reviewed and the data are confirmed to be correct. | NO | Ziliang Zhao/Chaoqun Hu
06/23 | SW Cleaning Philosophy & Cleaning Sequence 清洗策略与清洗程序 | Keith意见： 分离器内件 1、本设计中是否已考虑分离器内件，例如入口导流装置或入口旋风分离器、气相除雾器、液体出口处的防涡流挡板？ 2、喷淋球能否采用焊接固定方式，而非通过管接头引入容器内部？ 3、喷淋球是否必须为旋转式喷淋球？这会增加设备复杂度，并在工厂运行寿命期内带来检查与维护方面的问题。 4、喷淋球实际能否起到喷淋清洗作用，还是仅仅将容器注满清洗液直至触发高位液位开关？根据此前讨论，从空罐到高位跳闸点的时间不足25秒，这无法为分离器气相侧提供足够的机械清洗作用时间。 Separator internals 1. Have separator internals been considered for this design e.g. inlet diverters or inlet cyclones, demisting of the vapour stream, vortex breakers on the liquid outlet. 2. Can the spray ball be welded in position rather than introducing a tube fitting into the vessel. 3. Does the spray ball need to be a rotary spray ball. This adds complexity and inspection/maintenance issues during the life of the plant. 4. Will the spray ball actually work as a spray ball, or will it simply fill the vessel with cleaning fluid until the high-level switch is activated. Based on previous discussions this would be less than 25 seconds from empty to high-level trip point, which doesn’t allow much time for mechanical cleaning action in the gas side of the separator. | 06/23讨论： 分离器内件： 1、气液分离器设计采用重力式分离，无需额外的内件。 2、喷淋球相关事宜，CN团队内部结合喷淋球供应商商议方案。 06/23 Discussion — Separator Internals: 1.The gas-liquid separator is designed as a gravity-type separator; no additional internals are required. 2.Regarding the spray ball matters, the CN team will internally discuss and determine the solution in coordination with the spray ball supplier. | NO | Ziliang Zhao/Chaoqun Hu
06/23 | SW Cleaning Philosophy & Cleaning Sequence 清洗策略与清洗程序 | Keith意见： 设计参数 1、“流体性能”是否应定为“非致命性”？我推测此概念类似于PED容器设计中的流体分组，在英国规范中应属于Group 1气体（即可燃/爆炸/有毒），而非“非致命性”。 2、工作压力应为0至6MPaG。 3、设计温度应至少为150°C，并且我假设在泄压事故工况下，容器温度可能达到约300°C。 4、设计压力应为全真空至9MPaG。 5、规范是否要求进行焊后热处理（PWHT）？ 6、水压试验压力应为设计压力的1.5倍，即13.5MPaG，而非12MPaG。 7、对于该容器，S4应为DN32 Cl900 WN法兰。喷淋球接口是否应作为单独细节在本图纸上表示，还是另页图纸表示更为合适？ 8、充装系数（Fulling Factor）是多少？ Design Parameters 1. Should the ‘Fluid Performance’ be Non-Lethal? I assume this is similar to the fluid group for PED vessel design, which for the UK would be Group 1 gas i.e. flammable/explosive/toxic and not Non-Lethal. 2. The working pressure should be 0 to 6MPaG. 3. The design temperature should be at least 150 °C and I assume the vessel has the potential to reach circa 300°C during a relief event. 4. The design pressure should be FV to 9MPaG 5. Is PWHT required by the code. 6. Hydro test pressure should be 1.5x design pressure i.e. 13.5MPaG not 12 MPaG. 7. For the vessel, S4 should be a DN32 Cl900 WN Flange. Should the spray ball fitting be shown as a separate detail on this drawing or possibly shown on a separate drawing. 8. What is the Fulling Factor. | 06/23讨论： 设计参数 ： 1、介质调整为易爆。 2、CN团队结合URS，修正工作压力，更新设备数据表。 3、可以将泄压事故工况，纳入到常规设计考虑中，即可提高设计温度到300℃。 4、修正设计压力，更新设备数据表。 5、规范可不进行焊后热处理（PWHT）。 6、水压试验压力为设计压力的1.3倍，故试验压力可不做调整。 7、S4为喷淋口，口径为Φ10，DN32法兰接口结构为保证喷淋球可抽出，后续根据喷淋球整体方案做调整，判定是否需要可抽式。 8、充装系数是指物料实际容积与容器全容积之比。 06/23 Discussion — Design Parameters: 1.The medium classification is revised to "explosive." 2.The CN team will revise the working pressure based on the URS and update the equipment data sheet accordingly. 3.The relief event scenario can be incorporated into the normal design considerations — i.e., the design temperature can be raised to 300°C. 4.The design pressure will be revised and the equipment data sheet updated accordingly. 5.PWHT (post-weld heat treatment) is not required per the applicable code. 6.The hydrostatic test pressure is 1.3 × design pressure, so the test pressure does not need to be adjusted. 7.S4 is the spray ball connection, with a bore size of Φ10. The DN32 flange connection is designed to allow the spray ball to be withdrawable. This will be reviewed and adjusted as part of the overall spray ball solution, and a decision will be made on whether a withdrawable type is necessary. 8.The filling factor is defined as the ratio of the actual liquid volume to the total vessel volume. | NO | Ziliang Zhao/Chaoqun Hu
06/23 | SW | Keith意见： 通用事项 1、管口方位是否已考虑设备布置的最优化？ 2、在撬装高度限制范围内，容器能否通过重力自由排液至产品收集罐？ 3、在顶部法兰上开孔用于引出管，是否会损害其机械完整性并违反安全规范？是否已重新计算法兰厚度或进行有限元分析（FEA），以确保足够的金属厚度和结构完整性？ 4、液位变送器/液位开关的规格是否已确认？法兰尺寸及位置是否与仪表相匹配？ 5、请更新P&ID，以显示S4正确的管口尺寸。 6、是否有容器设计计算书？技术文件中需要包含设计计算书，并应在FAT（工厂验收测试）时进行核查。 General 1. Does the nozzle orientation allow for optimum equipment layout. 2. Can the vessel free drain into the product collection tank, within the skid height constraints. 3. Does boring a hole in the top flange for the outlet pipe compromise its mechanical integrity and violate safety codes. Have you recalculated the flange thickness/carried out FEA to ensure adequate metal thickness and structural integrity. 4. Has the level transmitter/level switches been agreed – does the flange size/position align with the instruments. 5. Update P&ID to show correct nozzle size for S4. 6. Do you have vessel design calculations. Design calculations will be required in the technical file and should be checked at FAT. | 06/23讨论： 通用事项 ： 1、管口方位已结合3D撬装布置给定。 2、3D撬装设计已考虑，待3D模型复核时，详细讨论。 3、重新计算法兰厚度，以满足结构强度要求。 4、仪表工程师已经确认复核。 5、P&ID，不需要更改S4管口尺寸。 6、设计计算书是设备完整技术文件中必不可少的一部分，后续会提供。 06/23 Discussion — General Items: 1.Nozzle orientation has been determined based on the 3D skid layout. 2.The 3D skid design has taken this into consideration; detailed discussion will be held during the 3D model review. 3.The flange thickness will be recalculated to meet structural strength requirements. 4.The instrumentation engineer has confirmed and verified this. 5.The P&ID does not require changes to the S4 nozzle size. 6.The design calculation sheet is an essential part of the complete technical documentation for the equipment and will be provided in due course. | NO | Ziliang Zhao/Chaoqun Hu

## 0616
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. 05/12：Keith建议用气液两相计算安全阀尺寸，不提供模板 05/12：Keith suggests using gas-liquid two-phase calculations for determining the size of the safety valve, but no template is provided. 05/20：根据API520的气液两相泄放时计算安全阀尺寸，部分已完成 05/20：Calculate the size of the safety valve based on the API520 standard for the two-phase gas-liquid discharge situation.Partially completed. 06/02：安全阀计算初版已完成（包含临界流体和气液两相），校审中。 06/02：Preliminary calculation of safety relief valve (covering critical fluid & gas-liquid two-phase flow) completed, under review. 06/09: General 1. What was the source/reference for the Specific Volumes stated in column D/D 列中比容数据的来源及参考依据是什么？ The Specific Volumes stated in column D are derived from Aspen Plus simulation results.比容数据来自Aspen模拟 2. There is no backpressure considered in the calculation. The emergency vent relief will create some backpressure which needs to be considered in the calculation./本次计算未考虑背压。紧急放空泄放过程会产生一定背压，该因素需纳入计算。 Backpressure consists of static backpressure and built-up backpressure. Given the wide total pressure range, backpressure effects shall be incorporated into the calculation.背压分为静背压和积聚背压，总压力范围大，将背压包含在其中 3. At the assumed relief pressure Ethyl Acetate will be a supercritical fluid, therefore the required relief mass flowrate will not be dependent on the latent heat of vapourisation, and the calculated ‘required discharge area’ will not be valid. Do you agree with this statement, or have you found a reference in the standard that allows for this? 在设定的泄放压力下，乙酸乙酯将处于超临界流体状态，因此所需泄放质量流量不再依赖汽化潜热，本次算出的所需泄放流通面积也不再适用。你是否认同该观点？或是你是否在相关标准中查到可支持该计算的依据？ Hold. Cooling Failure Calculations 4. For the cooling failure calculation, I would suggest using 550kJ/mol rather than 501.48. This is based on Sandwich PSL experience of heats of reaction. 针对冷却失效工况计算，建议将反应热取值由 501.48 kJ/mol 改为 550 kJ/mol。该取值参考了桑威奇工艺安全实验室（Sandwich PSL）过往反应热项目经验。 OK 5. Is the feed flowrate used in the calculation, based on the maximum metering pump capabilities? Do you assume a maximum concentration of reactant in the feed stream? 计算中采用的进料流量，是否按照计量泵最大额定流量取值？计算时是否假定进料流中反应物浓度为最大浓度？ The flow rate used in the calculation is set at the maximum rated capacity of the metering pump, and the maximum reactant concentration is adopted for the feed stream.计算时流量是按照计量泵最大额定流量取值，反应物浓度为最大浓度 06/16：根据文献“Relief Calculation for Supercritical Fluids”计算超临界流体的质量泄放流量，会后向Keith发计算书审核 06/16：Calculate the mass relief flow rate of supercritical fluids in accordance with the document Relief Calculation for Supercritical Fluids, and send the calculation sheet to Keith for review after the meeting. | NO | Chaoqun Hu/Keith
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun HU
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. 06/16：06/11已收到审核完成的URS。 06/16：Received the reviewed URS on 06/11. | YES | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith确认CV08也是故障关，可以使用DS6080型，该型号没有5 bar 差压限制。 Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith confirmed that CV08 is also a faulty-close type, the DS6080 model can be used. This model does not have a 5-bar differential pressure limit. Keith offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. 06/02 进展：Habonim厂家反馈了样本资料，反馈可以满足工艺参数需求，货期大概16~20周。可以作为开关阀的备选品牌。 06/02 Progress: "Habonim" manufacturer has provided sample materials that can meet the process parameter requirements. The delivery time is approximately 16 to 20 weeks. It can be an alternative brand for on-off valves. | YES | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. 06/02：关于气液分离器液相出口减压，电子压力阀和自力式减压阀都可以满足使用，首选自力式减压阀。 06/02：For pressure reduction at the liquid outlet of the gas-liquid separator，both electronic pressure valves and self-operated pressure reducing valves can meet the requirements, with self-operated pressure reducing valves being the preferred choice. | YES | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. 05/20：SW已更新完URS并发出。The SW has been updated and the URS has been sent out. | YES | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表条件表。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. | NO | Chaoqun Hu
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. 05/20：SW已更新完PFD并发出。The SW has been updated and the PFD has been sent out. | YES | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ 4/30：Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? | NO | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted?05/12Decided not to make any adjustments. 05/12确定不做调整。 05/12：It is determined that the height of the catalyst bed in the main reactor will not be adjusted. | YES | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. 06/16：会议澄清：待布局完成后，SW主导完成爆炸危险区域的划分 09/06：Meeting Clarification: SW shall take the lead in completing the classification of hazardous areas for explosion after layout design is finalized. | NO | All
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | YES | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements. | 05/20：与聂博沟通，小试使用的是进口是插底的分离器，生产使用的是侧进的分离器，按会议沟通的气体最大流量0.2Nm³/h，液体最大流量20L/h重新计算了分离器 05/20: Communicated with Nie Bo. The small-scale test used an imported bottom-insertion separator, while the production version used a side-inlet separator. Based on the maximum gas flow rate of 0.2 Nm³/h and the maximum liquid flow rate of 20 L/h for the communication at the meeting, the separator was recalculated.. | YES | Chaoqun Hu
06/02 | IEPE | 管道编号中的管线尺寸一般是指的公称直径，PID中尺寸为10mm的管道是Φ10mm，公称直径为6mm The line size in pipe line designations generally refers to the nominal diameter. In a P&ID, a pipe with a size of 10mm is specified as Φ10mm, corresponding to a nominal diameter of 6mm. | 06/02：会议澄清：DN15以下的管道，管道编号中的管径为外径，DN15及其以上的管道，管道编号中的管径为公称直径。 06/02：Clarification from meeting:For piping below DN15, the size specified in pipe tag number denotes outer diameter; for DN15 and above, the size in pipe tag refers to nominal diameter. | YES | Chaoqun Hu
06/02 | IEPE | 设备BT-01/03/04上的压力变送器不便于现场观察，是否可以考虑也选用WIKA的不带现场显示紧凑型的压力变送器？ The pressure transmitter on the equipment BT-01/03/04 is not convenient for on-site observation. Could it be considered to also choose WIKA's compact pressure transmitter without on-site display？ | 06/02：会上建议保留BT-01/04的现场显示，BT-03可不带现场显示。 06/02：It was suggested at the meeting that the on-site display of BT-01/04 be retained, while BT-03 may not have an on-site display. | YES | Yu Gao
06/02 | CFCT | 1-PID中V-9868，V-9965阀柄的含义？ What is the meaning of valve handles V-9868 and V-9965 in PID? 2-PID中压力变送器底部波纹含义是什么？ What does the corrugation at the bottom of the pressure transmitter signify? 3-与管道直径对应的保温厚度是多少？ What is the insulation thickness corresponding to the diameter of the pipeline? | 06/02： 1.PID中阀门V-9868，V-9965的阀柄为弹簧复位阀柄； In the PID,the valve handles of V-9868 and V-9965 are spring-reset handles； 2.PID中带底部波纹的压力变送器要求压力变送器带隔膜； The pressure transmitter with a bottom ripple in PID requires the pressure transmitter to be equipped with a diaphragm； 3.Keith分享了建议的管道直径与保温厚度表格，直径10到25mm的管路，保温厚度为30-35mm。 Keith shared the recommended pipe diameter and insulation thickness table, with insulation thickness ranging from 30-35mm for pipes with diameters of 10 to 25mm. | YES | ShuangshuangFan
06/16 | SW | 会议确认：气液分离器为侧进，尺寸为DN200*600mm，下次例会前CFCT向SW提供气液分离器的设备图纸 Confirmed at the meeting: The gas-liquid separator adopts side inlet configuration with dimensions DN200 × 600 mm. CFCT shall submit the equipment drawing of the gas-liquid separator to SW prior to the next regular meeting. |  | NO | Ziliang Zhao
06/17 | SW | 根据最新工作进展并结合HAZOP分析所需文件内容，更新“Sandwich Hydrogenation Implementation Schedule” Update the Sandwich Hydrogenation Implementation Schedule based on the latest progress and document requirements for HAZOP study. |  | NO | All
06/17 | SW | 讨论操作规程：哪些部分需要顺控？开停车步骤等 Discuss operation procedures: identify sections requiring sequence control, including startup and shutdown steps, etc. |  | NO | All
06/17 | SW | 会后确认：安全阀的泄放温度超过设备的设计温度，是否需要提高设备的设计温度？ To be confirmed after the meeting：If the relief temperature of the safety valve exceeds its design temperature, is it necessary to increase the design temperature rating? | 设备和管线材质为316L，结合设备和管道的壁厚，计算得出：在泄放温度下，材料的许用应力满足其强度要求，不需提高设备的设计温度 The equipment and piping are fabricated from 316L stainless steel. Wall thickness calculations for the equipment and piping demonstrate that the allowable stress of the material satisfies the strength requirements at relief temperature; therefore, no increase to the equipment design temperature is required. | Yes | Ziliang Zhao/Chaoqun Hu
06/17 | SW | CFCT做撬块设计时，注意清洗过程中的低点排净 CFCT shall take full consideration of low-point draining during cleaning when designing the skid package. |  | NO | Shuangshuang Fan
06/17 | SW | CFCT提供放空缓冲罐T06是否放在撬内的方案 CFCT to provide a scheme on whether vent buffer tank T06 shall be installed inside the skid. |  | NO | Shuangshuang Fan

## 0609
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. 05/12：Keith建议用气液两相计算安全阀尺寸，不提供模板 05/12：Keith suggests using gas-liquid two-phase calculations for determining the size of the safety valve, but no template is provided. 05/20：根据API520的气液两相泄放时计算安全阀尺寸，部分已完成 05/20：Calculate the size of the safety valve based on the API520 standard for the two-phase gas-liquid discharge situation.Partially completed. 06/02：安全阀计算初版已完成（包含临界流体和气液两相），校审中。 06/02：Preliminary calculation of safety relief valve (covering critical fluid & gas-liquid two-phase flow) completed, under review. 06/09: General 1. What was the source/reference for the Specific Volumes stated in column D/D 列中比容数据的来源及参考依据是什么？ The Specific Volumes stated in column D are derived from Aspen Plus simulation results.比容数据来自Aspen模拟 2. There is no backpressure considered in the calculation. The emergency vent relief will create some backpressure which needs to be considered in the calculation./本次计算未考虑背压。紧急放空泄放过程会产生一定背压，该因素需纳入计算。 Backpressure consists of static backpressure and built-up backpressure. Given the wide total pressure range, backpressure effects shall be incorporated into the calculation.背压分为静背压和积聚背压，总压力范围大，将背压包含在其中 3. At the assumed relief pressure Ethyl Acetate will be a supercritical fluid, therefore the required relief mass flowrate will not be dependent on the latent heat of vapourisation, and the calculated ‘required discharge area’ will not be valid. Do you agree with this statement, or have you found a reference in the standard that allows for this? 在设定的泄放压力下，乙酸乙酯将处于超临界流体状态，因此所需泄放质量流量不再依赖汽化潜热，本次算出的所需泄放流通面积也不再适用。你是否认同该观点？或是你是否在相关标准中查到可支持该计算的依据？ Hold. Cooling Failure Calculations 4. For the cooling failure calculation, I would suggest using 550kJ/mol rather than 501.48. This is based on Sandwich PSL experience of heats of reaction. 针对冷却失效工况计算，建议将反应热取值由 501.48 kJ/mol 改为 550 kJ/mol。该取值参考了桑威奇工艺安全实验室（Sandwich PSL）过往反应热项目经验。 OK 5. Is the feed flowrate used in the calculation, based on the maximum metering pump capabilities? Do you assume a maximum concentration of reactant in the feed stream? 计算中采用的进料流量，是否按照计量泵最大额定流量取值？计算时是否假定进料流中反应物浓度为最大浓度？ The flow rate used in the calculation is set at the maximum rated capacity of the metering pump, and the maximum reactant concentration is adopted for the feed stream.计算时流量是按照计量泵最大额定流量取值，反应物浓度为最大浓度 | NO | Chaoqun Hu/Keith
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun HU
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. | YES | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith确认CV08也是故障关，可以使用DS6080型，该型号没有5 bar 差压限制。 Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith confirmed that CV08 is also a faulty-close type, the DS6080 model can be used. This model does not have a 5-bar differential pressure limit. Keith offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. 06/02 进展：Habonim厂家反馈了样本资料，反馈可以满足工艺参数需求，货期大概16~20周。可以作为开关阀的备选品牌。 06/02 Progress: "Habonim" manufacturer has provided sample materials that can meet the process parameter requirements. The delivery time is approximately 16 to 20 weeks. It can be an alternative brand for on-off valves. | YES | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. 06/02：关于气液分离器液相出口减压，电子压力阀和自力式减压阀都可以满足使用，首选自力式减压阀。 06/02：For pressure reduction at the liquid outlet of the gas-liquid separator，both electronic pressure valves and self-operated pressure reducing valves can meet the requirements, with self-operated pressure reducing valves being the preferred choice. | YES | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. 05/20：SW已更新完URS并发出。The SW has been updated and the URS has been sent out. | YES | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表条件表。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. | NO | Chaoqun Hu
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. 05/20：SW已更新完PFD并发出。The SW has been updated and the PFD has been sent out. | YES | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ 4/30：Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? | NO | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted?05/12Decided not to make any adjustments. 05/12确定不做调整。 05/12：It is determined that the height of the catalyst bed in the main reactor will not be adjusted. | YES | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. | NO | ALL
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | YES | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements. | 05/20：与聂博沟通，小试使用的是进口是插底的分离器，生产使用的是侧进的分离器，按会议沟通的气体最大流量0.2Nm³/h，液体最大流量20L/h重新计算了分离器 05/20: Communicated with Nie Bo. The small-scale test used an imported bottom-insertion separator, while the production version used a side-inlet separator. Based on the maximum gas flow rate of 0.2 Nm³/h and the maximum liquid flow rate of 20 L/h for the communication at the meeting, the separator was recalculated.. | YES | Chaoqun Hu
06/02 | IEPE | 管道编号中的管线尺寸一般是指的公称直径，PID中尺寸为10mm的管道是Φ10mm，公称直径为6mm The line size in pipe line designations generally refers to the nominal diameter. In a P&ID, a pipe with a size of 10mm is specified as Φ10mm, corresponding to a nominal diameter of 6mm. | 06/02：会议澄清：DN15以下的管道，管道编号中的管径为外径，DN15及其以上的管道，管道编号中的管径为公称直径。 06/02：Clarification from meeting:For piping below DN15, the size specified in pipe tag number denotes outer diameter; for DN15 and above, the size in pipe tag refers to nominal diameter. | YES | Chaoqun Hu
06/02 | IEPE | 设备BT-01/03/04上的压力变送器不便于现场观察，是否可以考虑也选用WIKA的不带现场显示紧凑型的压力变送器？ The pressure transmitter on the equipment BT-01/03/04 is not convenient for on-site observation. Could it be considered to also choose WIKA's compact pressure transmitter without on-site display？ | 06/02：会上建议保留BT-01/04的现场显示，BT-03可不带现场显示。 06/02：It was suggested at the meeting that the on-site display of BT-01/04 be retained, while BT-03 may not have an on-site display. | YES | Yu Gao
06/02 | CFCT | 1-PID中V-9868，V-9965阀柄的含义？ What is the meaning of valve handles V-9868 and V-9965 in PID? 2-PID中压力变送器底部波纹含义是什么？ What does the corrugation at the bottom of the pressure transmitter signify? 3-与管道直径对应的保温厚度是多少？ What is the insulation thickness corresponding to the diameter of the pipeline? | 06/02： 1.PID中阀门V-9868，V-9965的阀柄为弹簧复位阀柄； In the PID,the valve handles of V-9868 and V-9965 are spring-reset handles； 2.PID中带底部波纹的压力变送器要求压力变送器带隔膜； The pressure transmitter with a bottom ripple in PID requires the pressure transmitter to be equipped with a diaphragm； 3.Keith分享了建议的管道直径与保温厚度表格，直径10到25mm的管路，保温厚度为30-35mm。 Keith shared the recommended pipe diameter and insulation thickness table, with insulation thickness ranging from 30-35mm for pipes with diameters of 10 to 25mm. | YES | ShuangshuangFan

## 0511
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. | NO | Chaoqun HU/Keith
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun HU
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. | NO | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：CV08需要故障开型，厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: CV08 requires a faulty-open type . The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. | NO | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. | NO | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. | NO | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表条件表。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. | NO | Chaoqun Hu
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. | NO | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ 4/30：Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? | NO | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. | NO | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. | NO | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted? | NO | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. | NO | ALL
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | NO | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements.

## 0602
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. 05/12：Keith建议用气液两相计算安全阀尺寸，不提供模板 05/12：Keith suggests using gas-liquid two-phase calculations for determining the size of the safety valve, but no template is provided. 05/20：根据API520的气液两相泄放时计算安全阀尺寸，部分已完成 05/20：Calculate the size of the safety valve based on the API520 standard for the two-phase gas-liquid discharge situation.Partially completed. 06/02：安全阀计算初版已完成（包含临界流体和气液两相），校审中。 06/02：Preliminary calculation of safety relief valve (covering critical fluid & gas-liquid two-phase flow) completed, under review. | NO | Chaoqun HU/Keith
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun HU
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. | NO | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith确认CV08也是故障关，可以使用DS6080型，该型号没有5 bar 差压限制。 Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith confirmed that CV08 is also a faulty-close type, the DS6080 model can be used. This model does not have a 5-bar differential pressure limit. Keith offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. 06/02 进展：Habonim厂家反馈了样本资料，反馈可以满足工艺参数需求，货期大概16~20周。可以作为开关阀的备选品牌。 06/02 Progress: "Habonim" manufacturer has provided sample materials that can meet the process parameter requirements. The delivery time is approximately 16 to 20 weeks. It can be an alternative brand for on-off valves. | YES | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. 06/02：关于气液分离器液相出口减压，电子压力阀和自力式减压阀都可以满足使用，首选自力式减压阀。 06/02：For pressure reduction at the liquid outlet of the gas-liquid separator，both electronic pressure valves and self-operated pressure reducing valves can meet the requirements, with self-operated pressure reducing valves being the preferred choice. | YES | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. 05/20：SW已更新完URS并发出。The SW has been updated and the URS has been sent out. | YES | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表条件表。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. | NO | Chaoqun Hu
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. 05/20：SW已更新完PFD并发出。The SW has been updated and the PFD has been sent out. | YES | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ 4/30：Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? | NO | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted?05/12Decided not to make any adjustments. 05/12确定不做调整。 05/12：It is determined that the height of the catalyst bed in the main reactor will not be adjusted. | YES | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. | NO | ALL
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | NO | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements. | 05/20：与聂博沟通，小试使用的是进口是插底的分离器，生产使用的是侧进的分离器，按会议沟通的气体最大流量0.2Nm³/h，液体最大流量20L/h重新计算了分离器 05/20: Communicated with Nie Bo. The small-scale test used an imported bottom-insertion separator, while the production version used a side-inlet separator. Based on the maximum gas flow rate of 0.2 Nm³/h and the maximum liquid flow rate of 20 L/h for the communication at the meeting, the separator was recalculated.. | YES | Chaoqun Hu
06/02 | IEPE | 管道编号中的管线尺寸一般是指的公称直径，PID中尺寸为10mm的管道是Φ10mm，公称直径为6mm The line size in pipe line designations generally refers to the nominal diameter. In a P&ID, a pipe with a size of 10mm is specified as Φ10mm, corresponding to a nominal diameter of 6mm. | 06/02：会议澄清：DN15以下的管道，管道编号中的管径为外径，DN15及其以上的管道，管道编号中的管径为公称直径。 06/02：Clarification from meeting:For piping below DN15, the size specified in pipe tag number denotes outer diameter; for DN15 and above, the size in pipe tag refers to nominal diameter. | YES | Chaoqun Hu
06/02 | IEPE | 设备BT-01/03/04上的压力变送器不便于现场观察，是否可以考虑也选用WIKA的不带现场显示紧凑型的压力变送器？ The pressure transmitter on the equipment BT-01/03/04 is not convenient for on-site observation. Could it be considered to also choose WIKA's compact pressure transmitter without on-site display？ | 06/02：会上建议保留BT-01/04的现场显示，BT-03可不带现场显示。 06/02：It was suggested at the meeting that the on-site display of BT-01/04 be retained, while BT-03 may not have an on-site display. | YES | Yu Gao
06/02 | CFCT | 1-PID中V-9868，V-9965阀柄的含义？ What is the meaning of valve handles V-9868 and V-9965 in PID? 2-PID中压力变送器底部波纹含义是什么？ What does the corrugation at the bottom of the pressure transmitter signify? 3-与管道直径对应的保温厚度是多少？ What is the insulation thickness corresponding to the diameter of the pipeline? | 06/02： 1.PID中阀门V-9868，V-9965的阀柄为弹簧复位阀柄； In the PID,the valve handles of V-9868 and V-9965 are spring-reset handles； 2.PID中带底部波纹的压力变送器要求压力变送器带隔膜； The pressure transmitter with a bottom ripple in PID requires the pressure transmitter to be equipped with a diaphragm； 3.Keith分享了建议的管道直径与保温厚度表格，直径10到25mm的管路，保温厚度为30-35mm。 Keith shared the recommended pipe diameter and insulation thickness table, with insulation thickness ranging from 30-35mm for pipes with diameters of 10 to 25mm. | YES | ShuangshuangFan

## 0519
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：安全阀已计算完成，待整理数据单 04/28 Progress:Relief valves have been calculated. Data sheets are pending review. 04/30会议确定：在Keith返回的Relief Design Study Template中补充安全泄放的各种工况，IEPE的安全阀数据单作为附件；确认溶剂为乙酸乙酯（IEPE与研发沟通，提供的危险溶剂为乙酸异丙酯，Keith建议溶剂使用乙酸乙酯） 04/30 Progress:Supplement all safety relief scenarios in the template returned by Keith, attach the IEPE safety valve data sheet as an appendix.The solvent is confirmed as ethyl acetate. IEPE communicated with the R&D department, which initially provided isopropyl acetate as the hazardous solvent; Keith recommended adopting ethyl acetate as the final solvent. 05/09进展：溶剂改为乙酸乙酯，安全阀已重新计算完毕，表Relief Design Study Template为空白表格，在补充数据时，有一定的难度，希望Keith提供个填好的模板作为参考，防止理解上的偏差 05/09：The solvent has been changed to ethyl acetate, and the safety valve recalculation has been completed.The Relief Design Study Template is currently blank. It is difficult to supplement the relevant data directly.We would appreciate it if Keith could provide a filled-out template for reference, to avoid any misunderstanding or deviation in interpretation. 05/12：Keith建议用气液两相计算安全阀尺寸，不提供模板 05/12：Keith suggests using gas-liquid two-phase calculations for determining the size of the safety valve, but no template is provided. 05/20：根据API520的气液两相泄放时计算安全阀尺寸，部分已完成 05/20：Calculate the size of the safety valve based on the API520 standard for the two-phase gas-liquid discharge situation.Partially completed. | NO | Chaoqun HU/Keith
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun HU
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. | NO | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 04/17：已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 04/17：The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，按照厂家的反馈，该型号为常闭电磁阀，不通电时关闭，通电打开，开启时压力至少需要5bar，关闭时没压力要求，断电就关了，属于故障关型。需讨论是否适用于CV03和CV08的工艺需求。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is about 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘, according to manufacturer's feedback, this model is a normally closed solenoid valve. It closes when not powered and opens when powered. At least 5 bar is required for opening, and there is no pressure requirement for closing. It closes when power is cut off,so it belongs to the fault-closed type.It is necessary to discuss whether it is applicable to the process requirements of CV03 and CV08. 04/30进展：CV08需要故障开型，正在与厂家沟通是否有故障开型，待回复。如果没有故障开型，CV08可以改为一般气动开关阀。Keith还提供了气动开关阀的备选品牌Habonim，正在与国内代理商进行咨询。 04/30 Progress: CV08 requires a faulty-open type . We are currently communicating with the manufacturer to see if there is a faulty-open type ,waiting for reply. If there is no faulty-open type, CV08 can be changed to a general pneumatic on-off valve. Keith also offers the alternative brand of pneumatic on-off valves,"Habonim", and is currently consulting with domestic agents. 05/12进展：厂家推荐DS6080型号电磁阀可以定制常开型(故障开型),常开型只能用在2区，常开型需要定制货期较长(会大于12周)。Keith确认CV08也是故障关，可以使用DS6080型，该型号没有5 bar 差压限制。 Keith提供的气动开关阀的备选品牌Habonim，代理商反馈与该品牌Habonim需要邮件沟通，过程比较慢，是否合适这两天应该会有结果。 05/12 Progress: The manufacturer recommends that the DS6080 model solenoid valve can be customized as a normally open type (fault-open type). The normally open type can only be used in Zone 2. The delivery time for customizing the normally open type is relatively long (it will be more than 12 weeks).Keith confirmed that CV08 is also a faulty-close type, the DS6080 model can be used. This model does not have a 5-bar differential pressure limit. Keith offers the alternative brand of pneumatic on-off valves,"Habonim", the agent has reported that communication with the brand of Habonim needs to be conducted via email, and the process is rather slow. Whether it is suitable or not should have a result within the next two days. 05/19进展：Habonim厂家反馈了样本资料，可以满足工艺参数需求，小尺寸阀门安装图片和防爆认证正在进一步沟通。 05/19 Progress: "Habonim" manufacturer has provided sample materials that can meet the process parameter requirements. The installation pictures for small-sized valves and explosion-proof certification are under further communication. | NO | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | 04/17：Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 04/17：Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. 04/28进展： PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.3barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.3barg。 04/28 Progress: The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.3barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.3barg. 04/30进展：关于气液分离器液相出口减压，考虑用电子压力阀(或FISEHER的MR95HP型自力式减压阀-尺寸不大更省成本）+调节阀串联减压，后面调节阀用液位串级流量控制器。 04/30：For pressure reduction at the liquid outlet of the gas-liquid separator, it is proposed to adopt a series pressure reducing scheme consisting of an electronic pressure valve (or Fisher MR95HP self-operated pressure reducing valve — compact in size and more cost-effective) plus a control valve. The downstream control valve shall adopt a liquid level cascade flow control strategy. 05/09：内部讨论认为气液分离器液位与出口流量控制器可组成PID控制回路，PID控制器根据液位设定值与检测值偏差，调节流量控制器的流量设定值，达到恒液位控制。 05/09：It is agreed that the liquid level of the gas-liquid separator can cascade the outlet flow controller within a PID loop. The PID controller adjusts the flow setpoint according to liquid level deviation between setpoint and process value to maintain constant level. | NO | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 04/21：工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ 04/21：The process and equipment has been reviewed. There might be a problem in one place.7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C 04/30：会议澄清温度为10~30℃，Keith修改URS对应的部分 04/30：It was clarified in the meeting that the temperature range is 10~30℃. Keith will revise the corresponding content in the URS 04/21：设备部分已审查完，有一处可能有问题，URS-6.12中R23模块置于危险区域，ATEX Zone 2 IIC T4 04/21：6.12“The R23 module is designated as a hazardous area. The default zone for the module is ATEX Zone 2 IIC T4 unless additional, specific bubble zoning requirements have been designated.” 05/11：待SW发出更新版URS。 Wait for SW to issue the updated URS. 05/20：SW已更新完URS并发出。The SW has been updated and the URS has been sent out. | YES | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表条件表。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 04/28进展：已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. | NO | Chaoqun Hu
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. 04/30会议澄清MP01的流量为2~20L/h，Keith修改PFD It was clarified in the 04/30 meeting that the flow rate range of MP01 is 2~20 L/h. Keith will revise the PFD accordingly. 05/11:待SW发出更新版PFD文件。 Wait for SW to issue the updated PFD. 05/20：SW已更新完PFD并发出。The SW has been updated and the PFD has been sent out. | YES | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved cable penetration hole in R23. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement | 4/30：当前设计需要穿线孔18~20个，可以改进设计缩减为14个，需要进一步确认；穿线孔是否可以32芯或以上的电缆？ 4/30：Originally design requires 18~20 cable holes; design might be optimized to reduce it to 14, to be confirmed later: Can the cable holes accommodate cables of 32 cores or more? | NO | Dezhi Meng
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve? | 04/30：BT01缓冲罐取消尾气管线手阀，取消安全阀，Keith修改PID 04/30：For buffer tank BT01, isolate the manual valve on the vent line and remove the safety valve, Keith to revise the PID drawing accordingly. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID，取消CR01/CR02/CR03的压差报警和联锁的意图？ What is the intention of removing the differential pressure alarms and interlocks for CR01/CR02/CR03 in the P&ID returned by email on 04/22? | 04/30：PLC系统中有CR01/CR02/CR03的压差报警和联锁，并未删除，Keith完善一下PID表达。 04/30：The differential pressure alarms and interlocks for CR01/CR02/CR03 in the PLC system are still retained and have not been removed. Keith shall optimize and refine the relevant representation on the PID drawing. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004. | 04/30：建议PID中不删除PRV030 04/30：It is recommended not to remove PRV030 in the PID. 05/11：待SW发出更新版PID文件。Wait for SW to issue the updated PID. 05/20：SW已更新完PID并发出。The SW has been updated and the PID has been sent out. | YES | Keith
04/28 | IEPE | 04/22邮件返回的“Pilot Plant Equipment List v0.1”，未找到本项目设备 The "Pilot Plant Equipment List v0.1" returned in the email on April 22nd did not include the equipment for this project. | 04/30：已找到 04/30：Found already. | YES | Chaoqun Hu
04/30 | SW | CFCT发SW最新版模型文件，用STP格式。 CFCT发SW反应器图纸PDF版。 CFCT sends the latest version of the SW model file in STP format. CFCT sends the SW reactor drawings in PDF | 05/06邮件发出。主反应器催化剂床高度是否调整？ 05/06The email has been sent. Has the catalyst bed height of the main reactor been adjusted?05/12Decided not to make any adjustments. 05/12确定不做调整。 05/12：It is determined that the height of the catalyst bed in the main reactor will not be adjusted. | YES | ZiliangZhao/ShuangshuangFan
04/30 | ALL | 各专业一起会审那个爆炸危险区域划分邮件，形成一致意见后再和SW沟通反馈。 All disciplines shall jointly review the email regarding the classification of explosive hazardous areas, reach a consensus, and then communicate and provide feedback to SW. | 05/09各专业经过讨论后达成共识，即该图需要结合SW当地规范进行绘制，故建议由SW主导完成。CN团队做支持，配合提供所需资料条件。 All relevant disciplines reached a consensus after discussion: this drawing shall be formulated in accordance with local SW standards and specifications. It is therefore proposed that the SW team takes the lead in completing the work, while the CN team will provide support and supply all required supporting documents and data. | NO | ALL
05/06 | SW | 1、橇块是否需要CE-LVD认证。 2、CE认证SGS能否提供认证资料需求清单，以及示例？ 1. Does the skid require CE-LVD certification? 2. For CE certification, can SGS provide a list of required documentation and an example? | 1、整机进行CE-MD认证，不需要单独再进行CE-LVD，可以理解为MD指令是一条综合性指令，会综合考虑各种风险，包括电气风险；也可以理解做了MD，就不需要做LVD，一个产品不可能同时是机械设备和电气设备。 1. For the whole machine to undergo CE-MD certification, a separate CE-LVD is not required. This can be understood as the MD directive being a comprehensive directive that takes various risks into account, including electrical risks. It can also be understood that once MD is done, LVD is not needed, as a product cannot be both a mechanical device and an electrical device at the same time. 2、已找SGS索要，其内部需整理需求清单，示例无法提供，清单已提供。 2. We have already requested this from SGS. They need to internally compile the required documentation list. An example cannot be provided, and list has been provided. | YES | ZiliangZhao
05/12 | IEPE | 分离器的设计依据：气体最大流量1.0Nm³/h，液体最大流量40L/h，分离器的操作压力为10~60barG。经估计10~24barG时，体系液相体积<气相体积，为气液体系，24~b0barG时，体系液相体积>气相体积，为液气体系； 但整体都属于小气量，小流量，优先选择立式分离器，选择的分离器直径大于计算直径，增大流通截面积，更容易满足气液分离要求。 Design basis of the separator: maximum gas flow rate is 1.0 Nm³/h, maximum liquid flow rate is 40 L/h, and the operating pressure of the separator ranges from 10 to 60 barG. It is estimated that at 10~24 barG, the liquid phase volume of the system is less than the gas phase volume, which is defined as a gas-liquid system; at 24~60 barG, the liquid phase volume exceeds the gas phase volume, belonging to a liquid-gas system. Overall, this is a working condition with low gas volume and low flow rate. A vertical separator is preferred. The selected separator diameter is larger than the calculated diameter to increase the flow cross-sectional area, which makes it easier to meet the gas-liquid separation requirements. | 05/20：与聂博沟通，小试使用的是进口是插底的分离器，生产使用的是侧进的分离器，按会议沟通的气体最大流量0.2Nm³/h，液体最大流量20L/h重新计算了分离器 05/20: Communicated with Nie Bo. The small-scale test used an imported bottom-insertion separator, while the production version used a side-inlet separator. Based on the maximum gas flow rate of 0.2 Nm³/h and the maximum liquid flow rate of 20 L/h for the communication at the meeting, the separator was recalculated.. | YES | Chaoqun Hu