## Slide 1
SANDWICH · CONTINUOUS HYDROGENATION
Technical discussion with Keith
Tracker close-out and one new instrument risk
8 September 2026
Internal working session · not a new HAZOP · close what we can online
01
Gasket
02
3D layout
03
PIC-028 vs 270 °C
04
PSV if DN50
05
Tracker close-out

## Slide 2
AGENDA
What we need to cover today
01
INFORM
High-pressure gasket
Vendor can supply a 316L metal-ring gasket if hardness limits are written into the spec.
02
DISCUSS
3D layout — three-cavity, height, control panel
A draft based on Keith’s three-cavity idea is ready. Close what we can before the site week.
03
DECIDE
Separator vapour-outlet valve vs 270 °C
Bronkhorst electronics may fail at 270 °C. No qualified alternative yet. This is the new risk.
04
CLARIFY
Relief-valve size if the reactor is DN50
DN80 and DN65 already share the same orifice. Confirm whether DN50 still can.
05
CONFIRM
Tracker lines already answered
Cleaning, operating manual and control description — please confirm which lines can close.
Asymchem · Sandwich continuous hydrogenation · Discussion with Keith
8 Sep 2026 02 / 7

## Slide 3
01 · INFORM / CONFIRM
High-pressure gasket — vendor result
Already agreed on 25 Aug
● Primary route: 316L octagonal metal-ring gasket.
● Tantalum remains the expensive fallback.
● PTFE spiral-wound is out — code does not allow PTFE at 270 °C.
● Keith accepts gasket damage after a 270 °C relief event.
● The gasket must still seal during relief. A leak into the module is an ignition risk.
Vendor position now
Gasket hardness
< 150 HB
Pipe-flange hardness
> 160 HB
Evidence
Hardness test report for gasket and flange
Check
Equipment vendor re-inspects before assembly
Scope
Vessel joints and piping gaskets from one supplier
ASK Please confirm SW accepts this hardness specification and single-vendor scope.
Asymchem · Sandwich continuous hydrogenation · Discussion with Keith
8 Sep 2026 03 / 7

## Slide 4
02 · DISCUSS
3D layout — close what we can online
Three-cavity draft
WHERE WE ARE
We have drawn a layout from Keith’s three-cavity / split-module idea.
TODAY
Walk the draft today. Agree what is acceptable so the site week is not used to rediscover the same points.
Overall height
WHERE WE ARE
The skid height has already been reduced on our side.
TODAY
Confirm the remaining height envelope with the split-module and goods-lift constraints.
Control panel
WHERE WE ARE
Still the hard item: shower clash, ATEX split, cabling, and whether the panel can hinge or ship loose.
TODAY
Need Keith’s instrument-to-module list before the cabinet can be frozen.
ASK Review the three-cavity draft now. Leave only items that truly need the Sandwich room.
Asymchem · Sandwich continuous hydrogenation · Discussion with Keith
8 Sep 2026 04 / 7

## Slide 5
03 · DECIDE
PIC-028 · vapour-outlet back-pressure vs 270 °C
New risk. Gas–liquid separator vapour outlet. Currently a Bronkhorst electronic back-pressure valve.
Duty
● Tag: PIC-028 / PCV-028 on the separator vapour line.
● Wide pressure range, low flow — this is why the electronic valve was chosen.
● System design temperature remains 270 °C after the 25 Aug discussion.
What we found
● Bronkhorst: electronics may fail instantly at 270 °C.
● Pneumatic substitutes checked so far cannot cover the ΔP and the low flow together.
● Only one vendor asked. Procurement is expanding the list before a formal enquiry.
Why this is not “replace the instrument”
● If the valve dies in the relief case it may lose back-pressure.
● Inventory then dumps downstream / to vent — not a leak into the module, but not a safe silent failure either.
● We will not leave this as an unstated hazard.
DECIDE Must this tag survive 270 °C? If no qualified valve exists, what architecture will SW accept?
Asymchem · Sandwich continuous hydrogenation · Discussion with Keith
8 Sep 2026 05 / 7

## Slide 6
04 · CLARIFY
Relief-valve size if the reactor moves to DN50
Working assumption
● Reactor path: DN80 is dropped. Working case is DN65. DN50 is the backup if the September trial requires it.
● R&D trial on a DN65 column is now expected from about 18 Sep, with data by end of September.
● The current relief-valve selection is already the same orifice for DN80 and DN65.
● A DN50 case would cut heat generation further. We would rather not re-open the PSV file unless SW requires it.
● PFD and mass balance stay unchanged — only equipment datasheets move if the bore changes.
Please confirm
1. If the reactor is DN65 — keep the current PSV.
2. If the reactor is DN50 — may we keep that same orifice?
3. Or must the relief case be re-run before HAZOP?
Asymchem · Sandwich continuous hydrogenation · Discussion with Keith
8 Sep 2026 06 / 7

## Slide 7
05 · CONFIRM
Tracker close-out, and the decisions we need today
Please confirm these can close
● Cleaning philosophy — our scheme is issued; remaining comments to be listed or closed.
● Operating manual — issued; SW review still outstanding.
● Control description — issued; SW review still outstanding.
● We will write the replies into the tracker and ask Keith to confirm line by line.
Decisions needed before we leave
1. Accept the 316L gasket hardness spec — or say what else QA needs.
2. Mark the three-cavity draft: accepted / change / leave for site.
3. State whether PIC-028 must be rated for 270 °C.
4. State whether the current PSV orifice still holds at DN50.
Not for this meeting
PFD and mass balance stay unchanged. Reactor size stays a September data decision (DN65 working case). HAZOP and the Sandwich week are a separate scheduling discussion — we are targeting mid-October, subject to Keith and Claire.
Please do not leave open technical points “to finish after we get home”. If a point cannot close today, write the remaining action and the owner in the tracker before we stop.
Asymchem · Sandwich continuous hydrogenation · Discussion with Keith
8 Sep 2026 07 / 7