## UK Visit Agenda
【SW】Agenda of the visit to Sandwich — 3D Layout & HAZOP
No. | Date | Time | Itinerary | Person in Charge | Detailed Topic | Objective 目标
Site Walkdown & 3D Model Review
1 | 2026.10.12 | 09:00-12:00 | 1. 现场勘察 Site Walkdown （0.5 天 / 0.5 day） | Keith / Clare / 李涛 / 范双双 / 胡超群 | 1, Skid boundary line, stairwell clearance and the faces actually available for access. 2, Emergency shower and eyewash — actual position and dimensions. 3, HTF wall-penetration position and the equipment-room interface. 4, Goods lift and delivery route dimensions. 现场：撬块边界线与楼梯井净空、可用操作面；紧急淋浴与洗眼器实际位置与尺寸；HTF 穿墙位置与设备间接口；货梯与进场路径尺寸。 | Measured constraints recorded and jointly confirmed on site, forming the fixed basis for every layout decision made this week. 现场实测，对作为本周全部布置决策的固定基准。
2 |  | 12:00-13:00 | Lunch
3 |  | 13:00-17:00 | 2.1 设备顺序调整 Equipment Sequence Re-arrangement （0.5 天 / 0.5 day） | Keith / 李涛 / 范双双 / 胡超群 | 1, The U-shape re-sequencing. 2, Positions of preheater, condenser, separator and product tank. 3, Pipe routing length and crossings after re-sequencing. 核算U形重排；预热器 / 冷凝器 / 分离器 / 产品罐位置；重排后管路长度与交叉情况。 | Equipment sequence agreed as a figure; model updated the same day. 设备顺序定案，双方认可，更新模型。
3D Model Review
4 | 2026.10.13 | 09:00-12:00 | 2.2 维修通道的变更 Maintenance Access Revision （0.5 天 / 0.5 day） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智(线上) | Maintenance access route decided, together with its stated impact on site disassembly workload and SAT scope. 维护可达性路线定案，并明确其对现场拆装工程量与 SAT 范围的影响。 | Maintenance access route decided, together with its stated impact on site disassembly workload and SAT scope. 维护可达性路线定案，并明确其对现场拆装工程量与 SAT 范围的影响。
5 |  | 12:00-13:00 | Lunch
6 |  | 13:00-17:00 | 2.3 控制柜布置（分体）调整方案 Control Panel Layout / Split Scheme （1 天 / 1 day — 第 1 段 Part 1） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智（线上） | 1, Split Control panel layout. 2, IS and non-IS panels must be split as separate enclosures. 控制柜分柜布置方案；本安柜与非本安柜须分别拆分。 | panel position decided. 控制柜位置方案确认。
3D Model Review
7 | 2026.10.14 | 09:00-12:00 | 2.3 控制柜布置（分体）调整方案 Control Panel Layout / Split Scheme （第 2 段 Part 2） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智（线上） | 1, Junction box split and cable count alignment. 2, Hinged panel so tested cabling need not be disconnected for shipping. 3, Panel sizes computed against the instrument allocation agreed in this session. 接线箱拆分方案与电缆数对齐；柜体铰接方案实现免拆已测电缆发运；按本段确定的仪表归属核算柜体尺寸。 | Panel quantity, size and mounting position fixed; cable count reconciled to a single agreed figure. 柜体数量、尺寸与安装位置定案，电缆数对齐为唯一双方认可的数值。
8 |  | 12:00-13:00 | Lunch
9 |  | 13:00-17:00 | 2.4 四个分体撬块分开方案 Four-Module Split Scheme （0.5 天 / 0.5 day） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智（线上） | 1, Split boundaries and the I/O belonging to each module. 2, Lifting lugs, skates handling and the re-assembly sequence on site. 3, Overall height for the goods lift — top section removal, HTF pipework shipped loose. 分体边界与各模块 I/O 归属；吊耳、skates 搬运方式与现场重组顺序；整撬高度适配货梯（去掉顶部一段、HTF 管道散件发运）。 | Split boundaries and per-module I/O frozen; the height solution for the goods lift confirmed feasible. 分体边界与各模块 I/O 冻结，进货梯的降高方案确认可行。
Operating Manual
10 | 2026.10.15 | 09:00-12:00 | 3.1 操作手册讨论 Operating Manual Review （1 天 / 1 day — 第 1 段 Part 1） | Keith / 李涛 / 范双双 / 胡超群 | 1, Walk through the manual section by section against the layout fixed earlier this week. 2, Catalyst charging and discharging, including the water-wet discharge sequence. 3, Cleaning operations — valve line-up and hose connections. 结合本周已定案的布置逐节走查操作手册；催化剂装料与卸料（含水润催化剂卸料顺序）；清洗操作的阀门开关与软管连接。 | Comments captured and dispositioned within the session; the manual revision scope is agreed. 意见当场记录并逐条给出处置，操作手册的修订范围达成一致。
11 |  | 12:00-13:00 | Lunch
12 |  | 13:00-17:00 | 3.1 操作手册讨论 Operating Manual Review （第 2 段 Part 2） | Keith / 李涛 / 范双双 / 胡超群 | 1, Start-up, normal operation, shutdown and emergency response. 2, Operator access to valves and sampling points, checked against the walkdown findings. 3, Remaining comments closed out one by one. 开车、正常操作、停车与应急处置；结合现场勘察结果确认阀门与取样点的操作可达性；剩余意见逐条关闭。 | Operating manual signed off, or every remaining comment carries an agreed resolution and owner. 操作手册签认，或每条未决意见均已有双方认可的处置方案与责任人。
Control Philosophy & Sequence Control
13 | 2026.10.16 | 09:00-12:00 | 3.2 控制说明讨论 Control Philosophy Review （0.5 天 / 0.5 day） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智(线上) | 1, Control loops, interlocks and fail positions. 2, Division between hardwired interlocks and remote I/O. 3, Instrument signal types 控制回路、联锁与故障位；硬联锁与远程 I/O 的划分；仪表信号形式 | Control philosophy agreed and the instrument selection items closed, so the I/O schedule can be issued. 控制说明达成一致，仪表选型条目关闭，I/O 表可据此发布。
14 |  | 12:00-13:00 | Lunch
15 |  | 13:00-17:00 | 3.3 顺控方案讨论 Sequence Control Review （0.5 天 / 0.5 day） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智(线上) | 1, Sequence steps, permissives and hold points. 2, Cleaning sequence including inerting, and the high-level interlock bypass in cleaning mode. 3, Operator interface and alarm handling. 顺控步骤、允许条件与保持点；清洗顺控（含惰化）及清洗模式下高液位联锁的旁通；操作界面与报警处理。 | Sequence scheme agreed as an input to HAZOP, with no sequence question left open going into the study. 顺控方案达成一致并作为 HAZOP 的输入，进入分析前不留未定的顺控问题。
HAZOP Study
16 | 2026.10.20 | 09:00-17:00 | 4. HAZOP 分析讨论 HAZOP Study （3 天 / 3 days — 第 1 天 Day 1） | Keith / 李涛 / 范双双 / 胡超群
HAZOP Study
19 | 2026.10.21 | 09:00-17:00 | 4. HAZOP 分析讨论 HAZOP Study （第 2 天 Day 2） | Keith / 李涛 / 范双双 / 胡超群
HAZOP Study
22 | 2026.10.22 | 09:00-12:00 | 4. HAZOP 分析讨论 HAZOP Study （第 3 天 Day 3） | Keith / 李涛 / 范双双 / 胡超群
Total 合计：7.5 days / 8 天 — Site walkdown 0.5 + 3D model 2.5 + Operating manual & control 2 + HAZOP 2.5 （现场勘察 0.5 + 3D 模型 2.5 + 操作手册与控制说明 2 + HAZOP 2.5）

## Dave schedule (hidden)
No. 序号 | Date 日期 | Time 时间 | Itinerary 行程安排 | Person in Charge 负责人 | Location 地点 | Preparation 筹备事项
24:00 | 1st-NOV Friday-周五 | 07:00-09:30 | Go to Capital International Airport 前往首都国际机场 |  |  | 1.送机车辆
48:00 |  | 09:30-12:45 | Check in 值机办理
72:00 |  | 12:45-15:55（+1） | back to UK 回到英国