## Slide 1
01
Overall Progress
整体推进
● Design package closing out — internal cross-review complete, issue to SW next Tuesday
设计文件收口，国内内部会审完成，下周二发出 SW
– Cleaning philosophy · 3D layout · control philosophy
清洗方案 · 3D 布置 · 控制说明
– Equipment datasheets reissued at 75 barg / CLASS 900
设备数据单按 75 barg / CLASS 900 升版
– Instrument datasheets 11 Aug · operating manual first issue
仪表数据表 8/11 · 操作手册初稿本周发出
● Weekly technical session with SW now running — items closed live in the meeting
与 SW 建立每周技术会，跟踪条目在会上直接判定关闭
● Tracker upgraded with a “Pending” state — resolved in China, awaiting SW confirmation
跟踪表新增 Pending 状态：国内已解决、待 SW 确认，进度可见性提升
● SW returning 3D tie-in points, mounting brackets and hydrogen detector locations
SW 将返回 3D 接入点、支架与氢气探测器位置
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-07-29 ~ 08-11 · 01 / 04

## Slide 2
02
Technical Progress & Open Item
关键技术进展与待解决事项
● Six tracker items closed with SW this period
本期与 SW 关闭六项跟踪条目
– Polishing filter blockage → bypass to separator, flushed during cleaning
精滤器堵塞泄压 → 增设旁通至分离器，清洗时一并冲洗
– Differential pressure monitoring accepted for blockage detection
差压监测精度用于堵塞判断可接受
– Hardwired interlocks confirmed independent of remote I/O
硬联锁确认独立于远程 I/O，直接进 PLC 柜
● SE01 cleanliness verification by residue sampling — method accepted, limits to be set by UK QA
SE01 清洁度改用取样残留分析，方法获认可，限值由 UK QA 确定
● Open — high-pressure sealing solution not yet found
待解决：高压密封方案尚未找到（技术问题，非决策事项）
270 °C relief duty with hydrogen rules out PTFE, copper, nickel and Monel; Hastelloy flange cost-prohibitive. Affects all high-pressure joints and sits on the critical path for vessel ordering. Specialist sealing suppliers being engaged on both sides.
270 ℃ 泄放工况且涉氢，排除 PTFE、铜、镍、蒙乃尔；哈氏合金法兰成本过高。影响全部高压法兰连接，处于设备下单关键路径。中英双方正在接触专业密封厂家。
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-07-29 ~ 08-11 · 02 / 04

## Slide 3
03
⚠ Decisions Needed from Leadership
需领导层决策
● Transport route — four-module split shipment vs whole-unit lift through the roof
运输方案：四撬块分体运输 vs 整橇经屋顶吊装
● Container internal height is 2.35–2.69 m against a 3.6–3.7 m skid — it cannot ship upright; an open flat-rack takes the whole skid but is unsealed and risks corrosion, and road height also limits
集装箱内高 2.35–2.69 m，撬块最高 3.6–3.7 m，立装装不下；框架箱可装整橇但不密封、暴露易腐蚀，陆运高度同样受限
● Modular route adds steelwork, disassembly, re-cabling and a repeat of IQ/OQ at Sandwich
分体方案增加钢结构支撑、拆装、重新布线，并需在 Sandwich 重做 IQ/OQ
● Whole skid reuses about 90% of the FAT testing, but a new roof costs approximately £250k
整橇可复用约 90% 的 FAT 测试成果，但换屋顶费用约 25 万英镑
● Reactor final size DN65 or DN50 — set on September R&D test data; URS 30 kg/day at stake
反应器最终定 DN65 或 DN50，依据 9 月研发实验数据 → 关系 URS 30 kg/day
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-07-29 ~ 08-11 · 03 / 04

## Slide 4
04
Next Steps
下一步
● Issue cleaning philosophy, 3D layout and control philosophy to SW — next Tuesday
下周二向 SW 发出清洗方案、3D 布置与控制说明
● Resolve 3D interface clashes with SW — extract duct, emergency shower, low-level control panel
与 SW 解决 3D 界面冲突：穿墙排风管、紧急淋浴、低位控制柜
● Import & export department to confirm oversized carrier options, then table the transport comparison
协调进出口部核实超尺寸海运方案，随后提交运输方案对比
● Engage specialist sealing suppliers on both sides to close the high-pressure gasket issue
中英双方接触专业密封厂家，闭合高压垫片问题
● FAT — adapt the existing IQ/OQ template and obtain UK QA pre-approval to offset site testing
FAT：沿用国内 IQ/OQ 模板改制，取得 UK QA 预批以抵扣现场测试
● HAZOP early September — 3D and control philosophy agreed with SW first, run once only
9 月初 HAZOP：先与 SW 谈定 3D 与控制说明，确保只做一次
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-07-29 ~ 08-11 · 04 / 04