## Slide 1
01
Overall Progress
整体推进
● Three technical sessions held with SW this period — items judged and closed live in the meeting
本期与 SW 召开三次技术会，跟踪条目在会上直接判定关闭
– 13 Aug — cleaning philosophy reviewed; four real gaps identified in our design rather than misunderstandings
8/13 清洗方案过审：识别出四项属于我方设计的实际缺口，而非理解偏差
– 18 Aug — cleaning items closed out; 3D layout and maintenance access opened up
8/18 清洗条目基本收口，3D 布置与维护可达性议题展开
– 25 Aug — both blue-flag tracker items closed: PFD and high-pressure gasket
8/25 跟踪表两个蓝标条目全部结论：PFD 与高压垫片
● Working method agreed — exchange drawings first, settle the mechanical layout before optimising instrumentation
确立工作方式：先交换图纸对齐理解，先定机械布置、再优化仪表
● Tracker closure mechanism agreed with SW — responses written into the tracker, confirmed line by line by email
与 SW 约定跟踪表关闭机制：答复写入表内、邮件逐条确认后标记关闭
● Cleaning philosophy, operating manual and control philosophy issued — SW review still outstanding
清洗方案、操作手册与控制说明已发出，SW 侧反馈仍未返回
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-08-13 ~ 08-26 · 01 / 04

## Slide 2
02
Technical Progress & Open Items
关键技术进展与待解决事项
● PFD and mass balance confirmed unchanged — the consequential re-work is avoided
PFD 与物料平衡确认不改，连带的配置调整全部免除
– Residence time is variable: smaller volume, but hourly feed flow holds — so heat load and TCU duty are unchanged
停留时间可变：容积变小但每小时进料流量可不降，热负荷与 TCU 负荷均不变
– Heat transfer, not volume, is the capacity bottleneck — a smaller bore may preserve or even raise throughput
限制产能的是传热而非容积，缩径可能保住甚至提高产量
● Cleaning philosophy substantially closed out with SW
清洗方案与 SW 基本收口
– Catalyst discharge resequenced to solvent → water → discharge water-wet catalyst — never discharge solvent-wet
催化剂卸料改为溶剂洗 → 水洗 → 卸水润催化剂，绝不卸载带溶剂的催化剂
– All three spray balls changed to fixed type; high/low pressure direct connection removed from the CIP route
三台喷淋球全部改固定式；CIP 路径取消高低压直连
● Open — high-pressure gasket route defined, not yet closed
待解决：高压垫片路线已定，但尚未闭合
Primary route is a 316L soft metal ring, with vendor evidence that hardness sits 20–30 HB below the flange; tantalum is the fallback. PTFE spiral wound is ruled out because code forbids PTFE at 270 °C. Keith accepts gasket damage during relief but requires sealing integrity throughout it — a leak into the module risks ignition.
主推 316L 软金属环，需厂家证明硬度比法兰低 20–30 HB；钽材为退路。PTFE 缠绕垫因规范不允许用于 270 ℃ 而排除。Keith 接受泄放后垫片损坏，但要求泄放全过程保持密封——漏入撬块房间即有点火风险。
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-08-13 ~ 08-26 · 02 / 04

## Slide 3
03
⚠ Decisions Needed from Leadership
需领导层决策
● Maintenance access — the skid cannot be widened, so the route to maintainability must be chosen
维护可达性：撬块无法加宽，实现可维护的路径需要定向
● Keith has ruled out widening — the skid abuts the stairwell and the second-floor stair carries fire escape requirements
Keith 明确不能加宽：撬块紧贴楼梯井，二层楼梯另有消防要求
● Two competing philosophies: keep the central walkway so people can get in, or drop it and rely on a removable module plus remote calibration — this sets the site disassembly workload and the SAT scope
两种路径对立：留中间通道让人进得去，或取消通道改为可移出模块 + 远程标定——直接决定现场拆装工程量与 SAT 范围
● Gasket cost escalation — if the 316L route fails, tantalum needs a budget application, and the scope covers instrument and short connections, not vessels alone
垫片成本上升风险：316L 方案走不通则需申请钽材预算，且范围不止设备本体，还含仪表接口与短接
● Reactor fixed at DN65 as the practical middle value — height limits rule out DN50; capacity risk against URS 30 kg/day is retained pending the September trial
反应器取 DN65 作为折中值——高度受限使 DN50 不可行；对 URS 30 kg/day 的产能风险保留，待 9 月试生产验证
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-08-13 ~ 08-26 · 03 / 04

## Slide 4
04
Next Steps
下一步
● Keith to issue the layout sketch and the instrument-to-module allocation list — the precondition for sizing the control panels
Keith 出布置草图与仪表模块分配清单——核算控制柜尺寸的前置条件
● Produce the two numbers that settle the layout debate — width released by the U-shape re-sequencing, and the man-days to remove the reactor module
算出定案所需的两个数：U 形重排能省多少宽度、反应器模块移出要多少工时
● Obtain the gasket hardness feasibility evidence from vendors and confirm 316L for instrument and short connections
取得垫片厂家硬度可行性证明，并确认仪表接口与短接可用 316L
● Close the remaining cleaning items — recirculation hydraulics, metering pump internal relief valve, and the inerting route for SE01
闭合清洗剩余条目：循环清洗水力计算、计量泵内置安全阀、SE01 惰化路径
● Evaluate the height reduction that would fit the goods lift — remove the top section, ship HTF pipework loose, hinge the control panel to avoid re-cabling
评估进货梯所需的降高方案：去掉顶部一段、HTF 管道散件发运、控制柜加铰链以免重新布线
● Send tracker responses to Keith for line-by-line closure this week; HAZOP early September with the 3D layout and control philosophy agreed first, run once only
本周将跟踪表答复发 Keith 逐条关闭；9 月初 HAZOP 前先谈定 3D 与控制说明，确保只做一次
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-08-13 ~ 08-26 · 04 / 04