## Slide 1
01
Overall Progress
整体推进
21 Sep — first 3D on the 8 Sep direction, issued by email. 22 Sep — reviewed live with Keith.
9 月 21 日发出按 9 月 8 日方向排的第一版 3D；9 月 22 日与 Keith 对照模型过完。
The maintenance principle is unchanged: pull the front module out. No central walkway. Shipping height stays 2.5 m.
维护原则未变：前撬拉出检修，不留中间通道，运输高度仍为 2.5 m。
Tracker: 62 closed, 44 pending, 29 open. Nothing moved to closed this fortnight.
跟踪表：已关闭 62，待定 44，未关闭 29。本双周没有新的关闭项。
– The movement is on the model and on three rules Keith set on 22 Sep — not on line-by-line closure.
本期推进在模型和 22 日 Keith 定下的三条规则上，不在逐条关项上。
Critical path has narrowed: nozzle direction and the HTF runs, then Keith can release the 18 Aug equipment drawings.
关键路径收窄为：先定管嘴朝向和 HTF 走向，Keith 才能放行 8 月 18 日的主设备图。
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-09-09 ~ 09-23 · 01 / 05

## Slide 2
02
What 22 Sep Settled
9 月 22 日已说清的技术规则
TCU — the wall penetration is fixed. Ten pipes may stack after the wall. The five TCU units follow our nozzles.
TCU：穿墙位置已定。10 根管过墙后可以叠成两层。5 台 TCU 跟着我方管口走。
– One vent on the SW side of the wall, not ten vents on the skid. Wall plate is flanged both sides — no site weld in the gap.
排气只留一个点，放在墙的 SW 侧，不在撬上放 10 个排气阀。穿墙板两侧法兰对接，窄处不现场焊接。
Layout — two options will be drawn and compared. Not a freeze yet.
布置先出两版对比，这次会上没有冻结。
– Fan’s option: swap SE01 / CU01 with the rear valves, so the valves stay in front when the module is pulled.
范双双的方案：SE01 / CU01 与后部阀门对调，前撬拉出后阀门仍在前面。
– Keith’s option: condenser slightly forward; separator turned to the wall so the level gauge withdraws from the end. The hole in the middle takes fully welded HTF.
Keith 的方案：冷凝器略向前；分离器靠墙转约 90°，液位计从端部抽出。中间空档走全焊接 HTF。
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-09-09 ~ 09-23 · 02 / 05

## Slide 3
03
Piping Rules from 22 Sep
9 月 22 日定下的管路规则
Reactor 3 HTF nozzle turns toward the wall riser. The pipe no longer runs out to the skid end and doubles back.
反应器 3 的 HTF 管嘴改朝穿墙立管。管子不再先跑到撬端再折回。
Drains and CIP — valve at the tee, hose at the front. PSV-025 and PSV-019 stay separate and move to the skid edge.
排净和 CIP：阀紧贴三通，软管接口在撬前。PSV-025 与 PSV-019 不合并，挪到撬边。
– Unreachable valves take a compact Habonim actuated ball valve, operated from the end. A 300–400 mm reach can stay manual.
够不到的阀用 Habonim 小型气动球阀，在撬端操作。伸手 300–400 mm 能到的可以保持手动。
Width cannot drop 100–200 mm — the limit is the pump and BT01. Cleaning-mode high-level bypass is written into the manual, and is not yet agreed with Keith.
宽度减不了 100–200 mm，限制在泵和 BT01。清洗模式旁路高液位联锁已写入手册，Keith 尚未认可。
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-09-09 ~ 09-23 · 03 / 05

## Slide 4
04
What Changes the Plan
相对 9 月 9 日计划的变化
Main-equipment enquiry now waits on nozzle orientation and the HTF runs — not on a full drawing sign-off, and not on the UK visit.
主设备询价改为等管嘴朝向和 HTF 走向。不等整套图纸签完，也不等赴英。
– 9 Sep allowed the enquiry once the reactor specification was confirmed. On 22 Sep Keith would not comment on the 18 Aug drawings until those nozzles are shown to fit.
9 月 9 日的口径是反应柱规格确认后即可询价。22 日 Keith 明确：管嘴方向和 HTF 没在模型里站住之前，他不审 8 月 18 日的图。
Charging stairs — SW supplies them in the UK, in stainless steel, separate from the main-equipment order.
加料梯由 SW 在英国供货，不锈钢，不并进主设备采购。
– A catalogue aluminium stair is not acceptable. China will not design or fabricate this item. Target height is under 1.4 m.
不用成品铝梯。中方不设计、不制造。高度目标低于 1.4 m。
12–22 October is still the proposed visit. It is not confirmed. An early-November window is being checked.
10 月 12–22 日仍是建议行程，尚未确认。11 月初的备选窗口正在核实。
– The model work this week does not wait for that confirmation.
本周的模型工作不等这个日期。
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-09-09 ~ 09-23 · 04 / 05

## Slide 5
05
Next Steps
下一步
Fan — both layouts; reactor-3 nozzle toward the wall riser; drain and CIP valves at the tee.
范双双：两版布置、反应器 3 管嘴朝向穿墙立管、排净和 CIP 阀放在三通处。
Gao Yu — Habonim valve and actuator envelope to Fan, and whether China can buy it.
高宇：Habonim 阀和气动头外形交给范双双，并确认国内能否采购。
Meng — which signals stay on the pull-out module. Cable count waits on the junction box.
孟德智：列出可拉出模块上留下的信号。电缆数量等接线箱尺寸。
Keith — send the NWD; junction-box size by 25 or 28 Sep; tidy valves when the layout is close.
Keith：发送 NWD；9 月 25 日或 28 日反馈接线箱；布置接近后精简阀门。
Zhao — hold the 18 Aug equipment issue until nozzles and HTF runs are accepted.
赵子亮：管嘴和 HTF 被接受之前，不按 8 月 18 日的图提采购。
Confirm the visit window with Keith. Next session is 23 Sep, on this model.
与 Keith 确认赴英窗口。9 月 23 日继续对着这版模型讨论。
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Bi-weekly Progress 2026-09-09 ~ 09-23 · 05 / 05