## Slide 1
01
Overall Progress
整体推进
● Technical session with Keith on 8 September — two tracker items closed in the meeting
9 月 8 日与 Keith 召开技术会，两项跟踪条目在会上关闭
– High-pressure gasket accepted as a 316L metallic ring; tantalum is withdrawn
高压垫片接受 316L 金属环方案，钽材路线取消
– PIC-028 stays Bronkhorst if the mechanical seal holds at 270 °C
PIC-028 继续用 Bronkhorst，前提是 270 ℃ 时机械密封不外漏
● 3D layout is not frozen — the next model follows the direction agreed on 8 September
3D 布置尚未冻结，下一版模型按 9 月 8 日商定的方向更新
– Compact split-skid, 2.5 m shipping height, withdrawable front module
紧凑分撬、运输高度 2.5 m、前撬可拉出，不留中间通道
● Working programme aligned on 9 September with the Sandwich visit — layout freeze and HAZOP sit in the same trip
9 月 9 日将工作计划与赴 Sandwich 行程对齐：布置冻结与 HAZOP 安排在同一次现场
● Draft visit agenda issued — four blocks, eight working days, proposed 12–22 October
现场议程草案已发出：四块内容、八个工作日，建议 10 月 12–22 日
– Walkdown, 3D, manuals / control / sequence, then HAZOP — dates for Keith and Claire to confirm
勘察、3D、手册 / 控制 / 顺控，然后 HAZOP——日期待 Keith、Claire 确认
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Progress 2026-08-27 ~ 09-09 · 01 / 05

## Slide 2
02
Technical Progress
关键技术进展
● Gasket — closed. 316L metallic ring; hardness written into the spec
垫片已关闭：316L 金属环，硬度要求写入规格
– Gasket < 150 HB, flange > 160 HB; mill certificates plus a vendor re-check before assembly
垫片 < 150 HB，法兰 > 160 HB；厂家硬度报告，组装前复验
● PIC-028 — closed. Electronics may fail at 270 °C; the seal must not
PIC-028 已关闭：270 ℃ 时电子件允许失效，密封不得外漏
– PSV takes the relief; valve is replaced afterwards. FFKM on the datasheet and the order; same check for FCV-004 if needed
泄放由安全阀承担，事后换阀。FFKM 写入数据单与合同；FCV-004 视情况同样处理
● Layout direction for the next 3D revision
下一版 3D 的布置方向
– Ten TCU pipes through a wall plate (China plate / UK slot); last elbow fitted on site
10 根 TCU 管经穿墙板（中方出板、英方开槽）；最后弯头现场安装
– Separator may be lowered after the CIP change; new height goes to process
清洗方案调整后分离器可降低，新高度交工艺核算减压后余压
– Cabinet set back and rectangular; vents over 2.5 m stripped for shipping
控制柜后移并改为长方形；超 2.5 m 放散管运输拆下、现场复原
● Still open — model being redrawn; one instrument item not reached on 8 September
仍开放：模型按新方向重排中；9 月 8 日未轮到一项仪表问题
Whether the PSV can stay at the DN65 size if the reactor is later confirmed as DN50. DN65 remains the working basis pending the September trial.
若反应器最终确认为 DN50，安全阀能否维持 DN65 口径。在 9 月试验数据到位前，工作基准仍为 DN65。
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Progress 2026-08-27 ~ 09-09 · 02 / 05

## Slide 3
03
Working Programme
工作计划
Near-term freeze points aligned on 9 September. Downstream work keeps the established sequence after the layout is frozen.
9 月 9 日对齐的近期冻结节点。布置冻结之后，后续仍按既定顺序推进。
End Sep 2026
9 月底
Draft FDS / SDS / HDS, control description and operating instructions as HAZOP input. Finals after FAT.
FDS / SDS / HDS、控制说明与操作手册出初稿，作为 HAZOP 输入；定稿在 FAT 之后。
End Sep 2026
9 月底
Reactor specification confirmed for enquiry. Main-equipment procurement can then start — it does not wait for 3D freeze.
反应柱规格确认后即可发起主设备采购，不必等待 3D 冻结。
12–16 Oct 2026
10/12–16
Sandwich: walkdown, 3D layout, operating manual, control philosophy and sequence. Proposed — for confirmation.
赴 Sandwich：现场勘察、3D、操作手册、控制说明与顺控。建议档期，待确认。
20–22 Oct 2026
10/20–22
Sandwich HAZOP on the layout frozen that week. Proposed — Keith and Claire to confirm.
在当周冻结的布置上做 HAZOP。建议档期，待 Keith、Claire 确认。
Oct W2 2026
10 月第 2 周
Main-equipment enquiry after the 1–7 October holiday in China, once the reactor specification is in hand.
中国 10 月 1–7 日假期之后，规格到位即可进入主设备询价。
~ Nov W3 2026
约 11 月第 3 周
Vendor information confirmation — after manufacturer selection, not before. About four weeks.
厂家信息确认：在选定厂家之后，而不是之前。约四周闭环。
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Progress 2026-08-27 ~ 09-09 · 03 / 05

## Slide 4
04
Sandwich Visit
赴 Sandwich 现场
Purpose — freeze the layout against the room, then run HAZOP once on that frozen basis.
目的：对照现场空间把布置冻结，再在该基准上只做一次 HAZOP。
1
Site walkdown 0.5 day
现场勘察
Skid boundary, stairwell, emergency shower, HTF wall penetration, goods-lift and delivery route — measured and jointly confirmed.
2
3D model 2.5 days
3D 模型
Equipment sequence, maintenance access, control-cabinet envelope, and the split-skid boundaries, including height for the goods lift.
3
Manuals & control 2 days
手册与控制
Operating manual, control philosophy and sequence walked against the layout fixed earlier in the week.
4
HAZOP 3 days
HAZOP
Study on the frozen P&ID and layout. Actions and owners recorded in the room; no node left for a follow-up study.
Proposed 12–16 Oct (walkdown / 3D / manuals) · 20–22 Oct (HAZOP)
Attendees Keith · Li Tao · Fan Shuangshuang · Hu Chaoqun · Meng Dezhi Agenda: Agenda of the visit to Sandwich (3D & HAZOP).xlsx
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Progress 2026-08-27 ~ 09-09 · 04 / 05

## Slide 5
05
Next Steps
下一步
● Fan — redraw the 3D model to the 8 September direction; pass the new separator height to process
范双双：按 9 月 8 日方向重排 3D，并将分离器新高度交给工艺
● Meng — send Keith the rectangular, reachable cabinet envelope for enquiry
孟德智：把长方形、够得到的控制柜目标尺寸发给 Keith 询价
● Zhao / Gao — write gasket hardness and PIC-028 FFKM into the datasheets (FCV-004 if needed)
赵子亮 / 高宇：垫片硬度与 PIC-028 的 FFKM 写入数据单（必要时含 FCV-004）
● Issue draft FDS, control description and operating instructions by the end of September, as HAZOP input
9 月底发出 FDS、控制说明与操作手册初稿，作为 HAZOP 输入
● Raise the main-equipment enquiry once the reactor specification is confirmed — do not wait for 3D freeze
反应柱规格确认后即发起主设备询价，不因 3D 未冻结而等待
● Confirm 12–22 October with Keith and Claire; start visa / travel once the dates are firm
与 Keith、Claire 确认 10 月 12–22 日，日期确定后启动签证与差旅
● Close remaining tracker lines — cleaning, manuals, control description — at the visit or the next session
剩余跟踪条目（清洗、手册、控制说明）在现场或下一次技术会上关闭
Asymchem · Sandwich Site | Continuous Hydrogenation Skid
Progress 2026-08-27 ~ 09-09 · 05 / 05