## UK Visit Agenda
【SW】Agenda of the visit to Sandwich — 3D Layout & HAZOP
No. | Date | Time | Itinerary | Person in Charge | Detailed Topic | Location | Objective 目标
Site Walkdown & 3D Model Review
1 | Day 1 | 09:00-12:00 | 1. 现场勘察 Site Walkdown （0.5 天 / 0.5 day） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | 1, Skid boundary line, stairwell clearance and the faces actually available for access. 2, Emergency shower and eyewash — actual position and dimensions. 3, HTF wall-penetration position and the equipment-room interface. 4, Goods lift and delivery route dimensions. 现场核对：撬块边界线与楼梯井净空、可用操作面；紧急淋浴与洗眼器实际位置与尺寸；HTF 穿墙位置与设备间接口；货梯与进场路径尺寸。 |  | Measured constraints recorded and jointly confirmed on site, forming the fixed basis for every layout decision made this week. 现场实测约束当场记录并双方确认，作为本周全部布置决策的固定基准。
2 |  | 12:00-13:00 | Lunch
3 |  | 14:00-17:00 | 2.1 设备顺序调整 Equipment Sequence Re-arrangement （0.5 天 / 0.5 day） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | 1, Whether the U-shape re-sequencing releases the estimated 500–600 mm. 2, Positions of preheater, condenser, separator and product tank. 3, Pipe routing length and crossings after re-sequencing. 核算 U 形重排实际可释放的宽度；预热器 / 冷凝器 / 分离器 / 产品罐位置；重排后管路长度与交叉情况。 |  | Equipment sequence fixed and the released width agreed as a figure; model updated the same day. 设备顺序定案，释放宽度以数值形式双方认可，当日更新模型。
3D Model Review
4 | Day 2 | 09:00-12:00 | 2.2 维修通道的变更 Maintenance Access Revision （0.5 天 / 0.5 day） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | 1, Central walkway versus removable module — one route to be chosen. 2, Manual handling of flanges at approx. 100 kg per item inside a confined space. 3, Flange-to-wall distance, reach-in depth and gasket replacement space. 中间通道与可拆卸模块二选一；单件约 100 kg 法兰在受限空间内的人工搬运；法兰离墙距离、探身深度与垫片更换所需空间。 |  | Maintenance access route decided, together with its stated impact on site disassembly workload and SAT scope. 维护可达性路线定案，并明确其对现场拆装工程量与 SAT 范围的影响。
5 |  | 12:00-13:00 | Lunch
6 |  | 14:00-17:00 | 2.3 控制柜布置（分体）调整方案 Control Panel Layout / Split Scheme （1 天 / 1 day — 第 1 段 Part 1） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | 1, Nature of the clash with the emergency shower — physical interference or water spray. 2, Whether the eyewash can be relocated to just outside the door. 3, IS and non-IS panels must be split as separate enclosures. 控制柜与紧急淋浴冲突的性质（物理干涉或淋浴溅水）；洗眼器能否移至门外；本安柜与非本安柜须分别拆分。 |  | Clash nature confirmed and the eyewash relocation answered, so the panel position ceases to be an open loop. 冲突性质确认、洗眼器能否外移给出明确答复，控制柜位置不再悬置。
3D Model Review
7 | Day 3 | 09:00-12:00 | 2.3 控制柜布置（分体）调整方案 Control Panel Layout / Split Scheme （第 2 段 Part 2） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | 1, Junction box split and cable count alignment — 16 against 21. 2, Hinged panel so tested cabling need not be disconnected for shipping. 3, Panel sizes computed against the instrument allocation agreed in this session. 接线箱拆分方案与电缆数对齐（16 根与 21 根的差异）；柜体铰接方案实现免拆已测电缆发运；按本段确定的仪表归属核算柜体尺寸。 |  | Panel quantity, size and mounting position fixed; cable count reconciled to a single agreed figure. 柜体数量、尺寸与安装位置定案，电缆数对齐为唯一双方认可的数值。
8 |  | 12:00-13:00 | Lunch
9 |  | 14:00-17:00 | 2.4 四个分体撬块分开方案 Four-Module Split Scheme （0.5 天 / 0.5 day） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | 1, Split boundaries and the I/O belonging to each module. 2, Lifting lugs, skates handling and the re-assembly sequence on site. 3, Overall height for the goods lift — top section removal, HTF pipework shipped loose. 分体边界与各模块 I/O 归属；吊耳、skates 搬运方式与现场重组顺序；整撬高度适配货梯（去掉顶部一段、HTF 管道散件发运）。 |  | Split boundaries and per-module I/O frozen; the height solution for the goods lift confirmed feasible. 分体边界与各模块 I/O 冻结，进货梯的降高方案确认可行。
Operating Manual
10 | Day 4 | 09:00-12:00 | 3.1 操作手册讨论 Operating Manual Review （1 天 / 1 day — 第 1 段 Part 1） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | 1, Walk through the manual section by section against the layout fixed earlier this week. 2, Catalyst charging and discharging, including the water-wet discharge sequence. 3, Cleaning operations — valve line-up and hose connections. 结合本周已定案的布置逐节走查操作手册；催化剂装料与卸料（含水润催化剂卸料顺序）；清洗操作的阀门开关与软管连接。 |  | Comments captured and dispositioned within the session; the manual revision scope is agreed. 意见当场记录并逐条给出处置，操作手册的修订范围达成一致。
11 |  | 12:00-13:00 | Lunch
12 |  | 14:00-17:00 | 3.1 操作手册讨论 Operating Manual Review （第 2 段 Part 2） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | 1, Start-up, normal operation, shutdown and emergency response. 2, Operator access to valves and sampling points, checked against the walkdown findings. 3, Remaining comments closed out one by one. 开车、正常操作、停车与应急处置；结合现场勘察结果确认阀门与取样点的操作可达性；剩余意见逐条关闭。 |  | Operating manual signed off, or every remaining comment carries an agreed resolution and owner. 操作手册签认，或每条未决意见均已有双方认可的处置方案与责任人。
Control Philosophy & Sequence Control
13 | Day 5 | 09:00-12:00 | 3.2 控制说明讨论 Control Philosophy Review （0.5 天 / 0.5 day） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | 1, Control loops, interlocks and fail positions. 2, Division between hardwired interlocks and remote I/O. 3, Instrument signal types — Modbus or 4–20 mA, IS or Ex d. 控制回路、联锁与故障位；硬联锁与远程 I/O 的划分；仪表信号形式（Modbus 或 4–20 mA、本安或隔爆）。 |  | Control philosophy agreed and the instrument selection items closed, so the I/O schedule can be issued. 控制说明达成一致，仪表选型条目关闭，I/O 表可据此发布。
14 |  | 12:00-13:00 | Lunch
15 |  | 14:00-17:00 | 3.3 顺控方案讨论 Sequence Control Review （0.5 天 / 0.5 day） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | 1, Sequence steps, permissives and hold points. 2, Cleaning sequence including inerting, and the high-level interlock bypass in cleaning mode. 3, Operator interface and alarm handling. 顺控步骤、允许条件与保持点；清洗顺控（含惰化）及清洗模式下高液位联锁的旁通；操作界面与报警处理。 |  | Sequence scheme agreed as an input to HAZOP, with no sequence question left open going into the study. 顺控方案达成一致并作为 HAZOP 的输入，进入分析前不留未定的顺控问题。
HAZOP Study
16 | Day 6 | 09:00-12:00 | 4. HAZOP 分析讨论 HAZOP Study （3 天 / 3 days — 第 1 天 Day 1） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | 1, Confirm scope, node split, and the P&ID and layout revision to be studied. 2, Nodes: feed, buffer tanks BT01 / BT04 and metering pumps. 确认分析范围、节点划分，以及所用 P&ID 与布置的版本；节点：进料、缓冲罐 BT01 / BT04 与计量泵。 |  | Study basis locked to the layout fixed this week; the day's nodes completed with actions and owners recorded in the meeting. 分析基准锁定为本周定案的布置；当日节点全部完成，行动项与责任人会上直接记录。
17 |  | 12:00-13:00 | Lunch
18 |  | 14:00-17:00 | 4. HAZOP 分析讨论 HAZOP Study （第 1 天 续 Day 1 cont.） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | Nodes: preheater and reactors CR01–CR03, covering cooling failure, hot spot and hydrogen supply. 节点：预热器与反应器 CR01–CR03，涵盖冷却失效、热点与氢气供给工况。 |  | Nodes closed out with recommendations agreed on the spot rather than deferred. 节点当场关闭，建议措施当场达成一致，不作延后处理。
HAZOP Study
19 | Day 7 | 09:00-12:00 | 4. HAZOP 分析讨论 HAZOP Study （第 2 天 Day 2） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | Nodes: condenser, gas-liquid separator SE01, relief and vent system. 节点：冷凝器、气液分离器 SE01、安全泄放与放空系统。 |  | Nodes closed out with recommendations and owners agreed in the session. 节点当场关闭，建议措施与责任人会上确定。
20 |  | 12:00-13:00 | Lunch
21 |  | 14:00-17:00 | 4. HAZOP 分析讨论 HAZOP Study （第 2 天 续 Day 2 cont.） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | Nodes: product buffer tank, polishing filter and product discharge; valve accessibility and sampling reviewed against the walkdown. 节点：产品缓冲罐、精滤器与产品出料；结合现场勘察复核阀门可达性与取样方式。 |  | Any layout or valve change arising is resolved against the physical space in the same session. 由此引出的布置或阀门变更，在同一时段内对照实体空间解决。
HAZOP Study
22 | Day 8 | 09:00-12:00 | 4. HAZOP 分析讨论 HAZOP Study （第 3 天 Day 3） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | Nodes: CIP and cleaning circuit, inerting, utilities, control and interlock functions. 节点：CIP 与清洗回路、惰化、公用工程、控制与联锁功能。 |  | All nodes completed; no node left for a follow-up study. 全部节点完成，不遗留需另行安排的节点。
23 |  | 12:00-13:00 | Lunch
24 |  | 14:00-17:00 | Close-out 结论汇总与签认 （第 3 天 续 Day 3 cont.） | Keith / 李涛 / 范双双 / 胡超群 / 孟德智 | 1, Review the full action list, assign owners and dates, and sign off both sides. 2, Confirm which documents require revision and the issue dates. 3, Record the decisions taken this week against the tracker items they close. 逐条复核行动项清单、确定责任人与时间并双方签认；确认需要升版的文件及发布日期；将本周形成的决策对应到其所关闭的跟踪表条目。 |  | Signed action list and revision list issued before departure, with every item of this agenda either closed or carrying an agreed resolution. 离场前形成经双方签认的行动项与文件升版清单，本议程各项均已关闭或已有双方认可的处置方案。
Total 合计：8 days / 8 天 — Site walkdown 0.5 + 3D model 2.5 + Operating manual & control 2 + HAZOP 3 （现场勘察 0.5 + 3D 模型 2.5 + 操作手册与控制说明 2 + HAZOP 3）

## Agenda
【SW】Agenda of the visit
No. | Date | Time | Itinerary | Person in Charge | Detailed Topic | Location
| 31st -Jan Saturday | TBD | Airport Pickup
2 | 1st -Feb Sunday | TBD | Airport Pickup
TJ4 Visit
| 2nd-Feb Monday | 08:30-09:00 | TJ4 site
|  | 09:00-10:30 | 902扩建：RFI（信息征询）评审与后续问题 | 刘凯/郑国喜/郭宏杰/张暴/林浩淦/李涛 |  | TJ4南区101
6 |  | 10:30-12:00 | 英国项目需求评审——由 Clare 和 Scott 准备汇报材料 | 刘凯/郑国喜/郭宏杰 |  | TJ4南区101
|  | 12:00-13:00 | Lunch （商务工作餐）
|  | 13:00-14:00 | Site Tour：参观HPLC及冻干机系统 | 魏鹏/李涛/刘凯 | 1, 参观 汉邦 的制备型 HPLC 系统。 2, 在 TJ4 进行制备型 HPLC 卸料/转运方式评审（现场参观） 3, 参观冻干机（Lyophilizer） 4, TJ4 制备型 HPLC 的 PFD 流程——逐步走查设备与工艺流程 就概念方案达成一致——起草 URS 或评审既有设施改造 | TJ4南区101
|  | 14:00-17:00 | 902扩建（包括改造）：与更大范围团队评审布局（layouts） | 杨道兴/魏鹏/刘亚男/郭宏杰/张暴/IEPE（？）/郑国喜 |  | TJ4南区101
|  | 18:30-20:30 | Dinner
TJ4 Visit
| 3th-Feb Tuesday | 08:30-09:00 | TJ4 site
|  | 09:00-12:00 | OEB5 Lab Site tour | 魏铮/龚成/王海妮/李涛/Martin | 1，按现状评审 Sandwich 的概念方案。 2，参观 OEB 5–6 区域 （拍照）。 3，了解固体分析在 OEB 测试中的处理方式（例如通常为开放式设备的 PXRD 粉末 X 射线衍射）。 4，分析人员 : 隔离器 配置比。 5，化学家 : 隔离器 配置比。 6, 现场查看隔离器设备 | TJ4南区101
|  | 12:00-13:00 | Lunch （商务工作餐x人）
|  | 14:00-17:00 | OEB5 Lab Discuss | 魏铮/龚成/王海妮/李涛/Martin/TJ6 | 1, 以隔离器 : 项目步骤的比例来规划实验室空间。 2, TJ6 能否向英国供应隔离器？如何满足 CE 标志并符合英国/欧标设计标准（ISO 10648，待确认）？ 3, 哪些固体类分析仪器不在 HIPO（高活性） 区域？ 4, 若用于粉末形态，如何清洁这些仪器？ 5, ROI（投资回报） 6, 对 OEB5 化合物如何评估与管理？ | TJ4南区101
TJ2 Visit
|  | 08:30-09:00 | TJ2 site
| 4rd-Feb Wednesday | 09:00-12:00 | EHS讨论 | 郑国喜/朱劲松/刘天元/刘美琪/张振华/赵轶/黄竹芸 | 工业卫生检测规划。 Sandwich 方案以及中国团队来访计划如何对其提供支持。 | 主楼一层105
|  | 12:00-13:00 | Lunch （商务工作餐） |  |  | 主楼一层105
|  | 14:00-15:30 | EHS讨论 | 郑国喜/朱劲松/侯英凤/马永林/刘金同/李香莲/郑苗苗/杨晓杰/姚志敏/曹振 | SBTI 及其他环境项目的进展更新、下一步与时间节点。 | 主楼一层105
|  | 15:30-17:00 | EHS讨论 | 郑国喜/朱劲松/侯英凤/刘天元 /Clare | 其他可能影响 Sandwich 路线的战略性 EHS 倡议更新如 PFAS | 主楼一层105
|  | 15:30-17:00 | HR讨论 | 刘倩/刘凯/Scott | 与 HR 的讨论议题
TJ2 Visit
| 5th-Feb Thursday | 08:30-09:00 | TJ2 site
|  | 09:00-12:00 | 待定/总结 |  |  | 主楼一层105
|  | 12:00-13:00 | Lunch （商务工作餐x人）
|  | 14:00-17:00 | 902扩建：可行性研究反馈讨论 | 刘凯/郑国喜/郭宏杰/张暴/林浩淦/李涛 | 1，就可行性研究的外部供应商达成一致，并审查可研资金渠道（funding stream）。 2, 制定信息管理策略及对可研工作的支持方案 3, 确认供应商是否会就现有占地（existing footprint）升级进行报价，并确定报价生成策略 | 主楼一层105

## Sheet1
【SW】Agenda of the visit
No. | Date | Time | Itinerary | Person in Charge | Location
| 15th -OCT Wednesday | 14:15-18:00 | Airport Pickup: Beijing-Tianjin
2 |  | 18:00-20:00 | Dinner
TJ2 Visit
| 16th-OCT Thursday | 08:30-09:00 | TJ2 site
|  | 09:00-12:00 | 902贴临扩建及未来小分子商业厂房设计与操作经验 | 杨道兴、TJ3生产 | 主楼一层105
|  | 12:00-13:00 | Lunch （商务工作餐6人） |  | 主楼一层105
|  | 14:00-16:00 | 工厂自动化系统 | 聂永广/(孟德志)/徐鹏程 | 主楼一层105
|  | 17:30-20:30 | Dinner
TJ4 Visit
8 | 17th-OCT Friday | 08:30-09:00 | To TJ4 site
9 |  | 09:30-12:00 | 多肽与小核酸厂房的设计与操作经验 | 杨道兴/史永钢/刘其琛 | TJ4大分子楼223
10 |  | 12:00-13:00 | Lunch （商务工作餐6人） |  | TJ4大分子楼223
|  | 13:00-15:00 | HiPo厂房设计/操作/ IH标准； | 杨道兴/魏鹏、刘天元/张振华 | TJ4大分子楼223
12 |  | 15:00-17:30 | CFCT与IEPE讨论连续PP氢化装置 | 周洪如/赵子亮/孙艳/郑淞元/聂永广/冯先涛 | TJ4大分子楼223
|  | 17:30-20:30 | Dinner
TJ2 Visit
| 20th-OCT Monday | 08:30-09:00 | TJ2 site
|  | 09:00-12:00 | 项目管理方法及全面项目定义（Holistic） | 暂定 | 主楼一层105
|  | 11:30-12:15 | Lunch （商务工作餐x人）
|  | 12:15-2:00 | 送机

## Dave schedule (hidden)
No. 序号 | Date 日期 | Time 时间 | Itinerary 行程安排 | Person in Charge 负责人 | Location 地点 | Preparation 筹备事项
24:00 | 1st-NOV Friday-周五 | 07:00-09:30 | Go to Capital International Airport 前往首都国际机场 |  |  | 1.送机车辆
48:00 |  | 09:30-12:45 | Check in 值机办理
72:00 |  | 12:45-15:55（+1） | back to UK 回到英国