## 0414
日期 Date | 议题提出方 Issue Originator | 会议主题内容 Meeting Theme and Content | 进展 Progress | 是否完成 Completed or not | 负责人 Person in charge
03/10 | SW | 3月10日邮件问题回复，涉及安全阀计算待进行。按照设计文件分工约定，需要SW提供模板文件。 Response to the email dated March 10: the relief valve calculation is yet to be performed. In accordance with the agreement on the division of design documents, SW is required to provide the template file. | 04/17Keith提供模板文件，04/21研发提供溶剂SDS，准备进行安全阀计算 04/17 Keith provided the template file. 04/21 The R&D department provided the solvent SDS and prepared to conduct the the relief valve calculation. 04/28进展：部分安全阀已计算完成，待整理数据单 04/28 Progress: Partial relief valves have been calculated. Data sheets are pending review. | NO | Chaoqun HU/Keith
|  | Confirmation of the minimum turndown for the hydrogen gas flow controller FICV003 and minimum metering pump flows (MP01/MP02) for scale up/process development. 放大试验/工艺开发需求，确认氢气流量控制器 FICV003 最小调节比及计量泵MP01/MP02 最小流量。 | 计量泵MP01/MP02最小流量为4l/h，FICV003调节比为1：50 The minimum flow rate of the metering pump MP01/MP02 is 4 liters per hour, and the range turndown of FICV003 is 1：50. | YES | Chaoqun HU
04/08 | IEPE | Current Document List – Confirmation of Document Responsibilities | 会上再次澄清，已达成一致。 It was clarified again in the meeting and an agreement has been reached. | YES | Shaofeng Gao
04/14 | IEPE | 周四讨论下各自设计文件的进度时间。 Let’s discuss the schedule and progress of each party’s design documents on Thursday. | 已完成 Completed. | YES | Peter/Shaofeng Gao
04/14 | SW | URS升版工作已完成初版，待评审后发出。 The initial draft of the URS revision has been completed and will be issued after review. | 初版已完成 The initial version has been completed. | NO | Keith
04/14 | IEPE | 咨询的ASCO电磁阀最大耐压9bar较低，请Keith协助下看是否可以咨询到合适高压的电磁阀厂家。 The maximum pressure resistance of the ASCO solenoid valve inquired about is 9bar, which is relatively low. Please ask Keith for assistance to see if a suitable high-pressure solenoid valve manufacturer can be consulted. | 已把Keith提供的Burkert样本发给代理商，代理商正在与当地厂家进行咨询 The Burkert samples provided by Keith have been sent to the agent, who is currently consulting with the local manufacturer. 04/28进展：中国代理商反馈该Burkert电磁阀可以买到，产品在德国生产制造，货期大约12周。需要注意的是资料里提示'阀门内需要至少5bar的最小压差来支持开启和关闭过程'，则说明在开车前期压力没升到5bar前该电磁阀不能正常工作。 04/28 Progress: The chinese agent reported that the Burkert solenoid valve can be purchased. The product is manufactured in Germany and the delivery time is approximately 12 weeks. It should be noted that the samples indicates that ‘A minimum differential pressure of at least 5 bar is required in the valve to support the opening and closing process‘ ,it means that the solenoid valve cannot work normally before the pressure rises to 5 bar in the early stage of startup. | NO | Keith/Yu Gao
04/14 | SW | PRV都考虑按Bronkhorst电子压力阀去选型，将根据最新工艺参数与厂家进行沟通 PRV is considering selecting the Bronkhorst electronic pressure valve and will communicate with the manufacturer based on the updated process data. | Bronkhorst厂家关于电子压力阀选型参数已反馈，有以下几个问题： 1.Bronkhorst电子压力阀最高耐温50℃，不满足工艺操作温度70℃的需求。 2.Bronkhorst电子压力阀的防爆等级为II 3 G Ex ec IIC T4 Gc，最高可用在2区。且电子压力阀没有本安防爆类型。 3.关于气液分离器气相出口背压，工艺需求背压3~60barg，厂家只能满足背压9~60barg可调。 4.关于气液分离器液相出口减压，工艺需求从3~60barg减压到2barg，厂家只能满足从3~40barg减压到2barg。 Bronkhorst manufacturer has provided feedback regarding the selection parameters of electronic pressure valves, with the following issues: 1.The Bronkhorst electronic pressure valve can withstand a maximum temperature of 50℃, which does not meet the process operation temperature requirement of 70℃. 2. The explosion-proof grade of the Bronkhorst electronic pressure valve is II 3 G Ex ec IIC T4 Gc, and it can be used in Zone 2 at most. Moreover, electronic pressure valves do not have intrinsically safe explosion-proof types. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, the process requires a back pressure range of 3~60 Barg. The manufacturer can only provide an adjustable back pressure range of 9~60 Barg. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, the process requirement ranges from 3~60 Barg to 2 Barg. The manufacturer can only meet the pressure reduction requirement from 3~40 Barg to 2 Barg. | YES | Yu Gao/Chaoqun Hu
04/14 | CFCT | 1.原料储罐接口对照PID少一个压力变送器接口，CFCT反馈给IEPE更新数据单。 The raw material storage tank interface lacks one pressure transmitter interface in the PID. CFCT has provided feedback to IEPE for updating the data sheet. 2.为完善3D模型设计，需计算确认安全阀的进出口尺寸，及确认流程中的开关阀选用气动阀还是电磁阀。 To improve the 3D model design, it is necessary to calculate and confirm the inlet and outlet dimensions of the safety valve, as well as determine whether pneumatic or solenoid valves should be used for the switching valve in the process. | 1.已更新设备数据单 Updated equipment data sheet 2.根据邮件及会议内容，8个开关阀中，2个选用电磁阀，6个选用带限位开关的气动阀 According to the email and meeting content, among the eight switching valves, two are selected as solenoid valves, and six are selected as pneumatic valves with limit switches | YES | Shuangshuang FAN/Chaoqun Hu
04/21 | IEPE | Keith和孟德志补充"0416-Sandwich Continuous Hydrogen Timeline" 中责任部门为SW和CIMT的时间进度 Keith and Dezhi Meng added the time schedule for the responsible departments of SW and CIMT in the "0416-Sandwich Continuous Hydrogen Timeline" |  | NO | Keith/Dezhi Meng
04/21 | SW | 各专业一起审查URS和QTM文件内容 All the departments review the contents of the URS and Quality Task Matrix | 工艺部分已审查完，有一处可能有问题。7.12冷凝器和分离器的温度应为10~30℃ The process has been reviewed. There might be a problem in one place. 7.12 “Equipment Functions: The temperature of the condenser and separator will be controlled within a temperature range of -20 to 130°C ± 2°C (based on jacket temperature).”The temperature of the condenser and separator should be controlled within a temperature range of 10 to 30°C ± 2°C | NO | All
04/21 | SW | 会上SW反馈并结合国内项目执行经验，澄清冷凝器后操作温度为30℃。梳理核实物流数据信息后升版设备数据单和仪表条件表。 At the meeting, SW feedback and based on domestic project implementation experience, clarified that the operating temperature after the condenser is 30℃. After reviewing and verifying the logistics data information, the equipment data sheet and the instrument conditions table were updated. | 已更新设备数据单，仪表数据单还未完成 The equipment data sheet has been updated, but the instrument data sheet is not yet completed. | NO | Chaoqun Hu
04/21 | SW | 梳理泵厂家返回资料，MP01/02的流量范围为4~40L/h。会上工艺需求确定为2~20L/h，需修改升版设备数据单 Reviewing the data from the pump manufacturer, the flow range of MP01/02 is 4 to 40 liters per hour. The process requirement at the meeting was determined to be 2 to 20 liters per hour. The equipment data sheet needs to be updated. | 04/22邮件返回的PFD中MP01的流量为4~40L/h，请确认工艺流量需求 In the PFD returned in the 04/22 email, the flow rate of MP01 is 4 - 40 liters per hour. Please confirm the process flow requirements. | NO | Chaoqun Hu
04/21 | SW | 会上SW提出当前供电缆穿墙的预留孔只有14个，需要CIMT根据当前方案计算电缆数量，确认能否满足需求 Thre are only 14 reserved holes for cables going through the wall. CIMT is to calculate the quantity of cables based on the current scheme and confirm whether it can meet requirement |  | NO | Dezhi Meng
04/21 | SW | PRV按Bronkhorst电子压力阀去选型后，不满足工艺需求问题讨论 After PRV selected the Bronkhorst electronic pressure valve, the issue of not meeting the process requirements was discussed. | PRV按Bronkhorst电子压力阀选型问题，最新核实结果如下： 1.根据最新工艺参数核实结果，介质操作温度为30℃，可以使用电子压力阀。 2.Keith回复现场有1区和2区，2区可以使用电子压力阀。 3.关于气液分离器气相出口背压，根据最新核实工艺需求背压10~60barg，厂家计算为背压9~60barg可调，可以满足需求。 4.关于气液分离器液相出口减压，根据最新核实工艺需求从10~60barg减压到0.1barg，厂家只能满足从10~60barg减压到1~20barg,不能满足需求。考虑先用电子压力阀减压到1.5~2barg左右，再利用后面的CV调节阀把压力从1.5~2barg减到0.1barg。 The new review results of PRV regarding the selection of Bronkhorst electronic pressure valves are as follows: 1.According to the latest process data recheck results, the medium operating temperature is 30℃, and an electronic pressure valve can be used. 2.Keith replied that there are Zone 1 and Zone 2 on site. Electronic pressure valves can be used in Zone 2. 3. Regarding the back pressure at the gas phase outlet of the gas-liquid separator, based on the latest rechecked process requirement of a back pressure of 10 to 60barg, the manufacturer has calculated that the back pressure is adjustable from 9 to 60barg, which can meet the requirement. 4. Regarding the pressure reduction at the liquid phase outlet of the gas-liquid separator, according to the latest recheck process requirements, the pressure reduction should be from 10~60barg to 0.1barg. However, the manufacturer can only meet the pressure reduction requirements from 10~60barg to 1~20barg, which cannot satisfy the requirement. Consider first reducing the pressure to around 1.5~2barg using an electronic pressure valve, and then use the CV control valve at the back to lower the pressure from 1.5~2barg to 0.1barg. | NO | Yu Gao
04/28 | IEPE | 04/22邮件返回的PID，BT01为常压罐，为什么用安全阀而不是呼吸阀 The PID returned in the 04/22 email. BT01 is a constant-pressure tank. Why was a safety valve used instead of a breathing valve?
04/28 | IEPE | 04/22邮件返回的PID，为什么取消CR01/CR02/CR03的压差报警和联锁？ Regarding the PID returned in the 04/22 email, why were the pressure difference alarms and interlocks for CR01/CR02/CR03 cancelled?
04/28 | IEPE | 04/22邮件返回的PID中删除PRV030，SE01的操作压力为10~60bar，BT04的操作压力为常压，删除PRV030,靠调节阀FCV004无法减压至常压 In the PID returned in the 04/22 email, PRV030 were removed. The operating pressure of SE01 was 10 to 60 bar, while BT04's operating pressure was at atmospheric pressure. Removing PRV030, it is impossible to reduce the pressure to atmospheric pressure by adjusting valve FCV004.